## Project Breakdown
PROJECT BREAKDOWN
Apartment - Refer to Tab
Building
| A | B | C | TownHouse
Level |  |  |  |  | Rough In | Statewide - Ventilation | Auscool- Refrigeration | AES - Electical
[5 empty] | Fit off | Statewide - Ventilation | Auscool- Refrigeration | AES - Electical
Commissoning

## Apartment Checklist
Apartments - Rough In Checklist
Statewide - Ventilation
1 | o PVC, flex duct & In-line Fan installed and correctly fixed
2 | o Cushion box installed to external louvers and duct connected & correctly sealed
3 | o Rangehood droppers installed
4 | o Access panels marked on floor
Auscool- Refrigeration
1 | o Ducted AC unit installed c/w isolation mounts & filters
2 | o Living & Bedroom cushion boxes & flex duct installed
3 | o Access panels marked on floor
4 | o Refrigeration pipes roughed in and installed to common riser
5 | o Drain pipes roughed in and Terminated internal tundish
6 | o Wall penetration Fire caulking completed and fire penetration labelled / documented.
7 | o Pressure testing of Refrigeration pipework complte
AES - Electical
1 | o Electrical cables roughed in and correctly clipped
2 | o Wall Controller cable roughed in
3 | o Wall penetration Fire caulking completed and fire penetration labelled / documented.
• Apartments Fit Off Checklist
Statewide - Ventilation
1 | o Grilles cut out complted
2 | o Grilles fit off and installed correctly
3 | o Fans fit off, powered and set to medium speed
4 | o Access panels installed at Fan
5 | o Rangehood installed / flex connected to Rangehood
Auscool- Refrigeration
1 | o Indoor unit fit off and installed correctly
2 | o Grilles cut out complted
3 | o Grilles fit off and installed correctly & B/fly dampers left open
4 | o Access panels installed
5 | o All drains fit off and tested
6 | o Condenser unit fit off, pipes and wires sealed and capped where required
7 | o Condenser labels Installed
8 | o Builders works complete
9 | o Clashes with other services
10 | o Ensure all rubbish and materials have been picked up and room is clean
AES - Electical
1 | o Equipment fitted off and tested
2 | o Wall Controller installed
checklist | Apartment Commissioning Checklist
section | Completion Status
checkpoint | Electrical Complete
checkpoint | Plumbing Complete
checkpoint | System Ready for Commissioning
section | Apartment Number
Text | Designated Apartment Number as written on Entry Door
section | System ID
Text | System identification as per Drawings
section | System ID
checkpoint | Wall controller installed correctly
checkpoint | Wall controller time and date set
checkpoint | Wall controller operating correctly
section | Drain
checkpoint | Tundish Installed (photo)
checkpoint | Tundish directional flow correct
checkpoint | Drain terminated at tundish correctly (photo)
checkpoint | Drain terminated at indoor unit correctly (photo)
checkpoint | Access to test drain
checkpoint | Drain tested
section | Indoor Unit
checkpoint | Take photo of model and seriel number
checkpoint | Unit installed correctly
checkpoint | Pipes fully insulated
checkpoint | Visible duct installed correctly and free of obstruction
checkpoint | Fan operating and free of vibration
section | Grilles
checkpoint | Grilles installed correctly
checkpoint | Grilles air-balnced to design aiflows
checkpoint | Strings removed from damper
section | System Operation
checkpoint | Correct Operating Temperatures and Pressures (provide 1 x temp read)
section | Additional Comments
checkpoint | Additional Comments and Notes
section | Summary
checkpoint | Apartment is Completed to ASC satisfaction and ready for handover.

## Apartment List
Bld | Floor | CU#
A | LG | 1
2
3
4
5
6
7
8
| G | 9
10
11
12
13
14
15
16
17
18
19
20
| L1 | 21
22
23
24
25
26
27
28
29
30
31
32
33
| L2 | 34
35
36
37
38
B | G | 39
40
41
42
43
44
45
46
47
48
49
50
| L1 | 51
52
53
54
55
56
57
58
59
60
61
62
| L2 | 63
64
65
66
67
68
69
70
71
C | G | 72
73
74
75
76
77
78
79
80
81
82
83
| L1 | 84
85
86
87
88
89
90
91
92
93
94
95
| L2 | 96
97
98
99
100
101
102
103
104
Townhouses |  | TH-105
TH-106
TH-107
TH-108
TH-109
TH-110
TH-111
TH-112
TH-113
TH-114
TH-115
TH-116