## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 3e274d90-8d44-4b1c-af20-70a5b7f786b6 |  | checklist | Apartments - Rough In Checklist |  |  |  |  | Yes | Apartments - Rough In Checklist | 47548cfb-c19d-4e72-8998-3e393a74275d
checkpoint-status | 743f97a4-83cc-4791-9e1b-c6e84b1cd1bd |  | checkpoint | PVC, flex duct, NRD & In-line Fan installed and correctly fixed
checkpoint-status | 01a89195-4124-43ed-aa94-091d4242ba8a |  | checkpoint | Make Air IFD installed c/w with acoustic flex
checkpoint-status | ea3b4dfb-1194-415e-8cb1-51e04bf81467 |  | checkpoint | Ducted AC unit in Living rm, levelled with isolation mounts, S/A & R/A ducted plenum installed
checkpoint-status | e73f7d85-1e89-41bb-bc46-8274d69ad201 |  | checkpoint | Ducted AC unit in Bedrm 1, levelled with isolation mounts, S/A & R/A ducted plenum installed
checkpoint-status | 404337eb-c9b2-4e19-89f4-409841fcb323 |  | checkpoint | Ducted AC unit in Bedrm 2, levelled with isolation mounts, S/A & R/A ducted plenum installed
checkpoint-status | ccd03e03-98eb-4048-b2c0-07b8dbdf1a42 |  | checkpoint | IF APPLICABLE - Ducted AC unit in Bedrm 3, levelled with isolation mounts, S/A & R/A ducted plenum installed
checkpoint-status | 60e20605-128e-438f-bc57-9a7cdac66c47 |  | checkpoint | S/A & R/A cushion boxes and flex duct installed
checkpoint-status | 03f945ad-a1c6-43d2-871d-229d9c36a88f |  | checkpoint | All Ducted AC unit that filters installed
checkpoint-status | 541d2559-ac9a-4ea7-a43a-590fa090fa8d |  | checkpoint | Branch Bx Installed
checkpoint-status | 774b08e1-3649-47d0-a4d8-55a13e3e6aa3 |  | checkpoint | Access panels marked n flr
checkpoint-status | 60acf66a-c191-493a-8fbf-1fd31ad5cd05 |  | checkpoint | Refrigeration pipes roughed in and connected ref nets and run back tBSB.
checkpoint-status | b1589ed4-6c35-4488-8f5f-8991edaac30d |  | checkpoint | Refrigeration pipes run from BSB, through corridor riser
checkpoint-status | 8a6af8dc-238b-4d61-8d1e-bf08271a59fa |  | checkpoint | Drain pipes roughed in TD at nominated sink
checkpoint-status | 1d6ae5d2-0c30-489c-863c-fc4d67861af5 |  | checkpoint | Electrical cables roughed in and correctly clipped including thermostat roughed in and located in wall
checkpoint-status | fac300b0-15e9-4a38-9568-d54eb6bf7afa |  | checkpoint | Wall penetration Fire caulking completed and fire penetration labelled / documented.
checkpoint-status | 454191e3-ae90-46c8-9ca8-e481b1ffe25c |  | checkpoint | Builders works complete
checkpoint-status | 392c112b-8cf8-4b78-a80d-21185ed7c2a4 |  | checkpoint | Pressure testing of Refrigeration pipework complete
checklist-flat | e61de44c-bac3-43d9-aa54-4d3be5f96acf |  | checklist | Apartments - Commissioning Checklist |  |  |  |  | Yes | Apartments - Commissioning Checklist | 53077b67-f757-41bb-90d8-b7f909d14018
checkpoint-status | af696d12-4232-4531-b841-2857a451704e |  | checkpoint | Test and record air flows and ensure crrect peratin
checkpoint-status | 040e40f3-bd58-4aa0-bae1-03f508e772da |  | checkpoint | Check and test for any noise, vibrations etc and rectify
checkpoint-status | 4a22aecc-6051-441a-ae67-183fcff9653e |  | checkpoint | A/C units pressure tested t3500Kpa
checkpoint-status | ae9b5433-6238-4a0f-923d-cc5f2420cc5c |  | checkpoint | A/C Refrigeration valves opened and A/C tested
checklist-flat | 86c854ad-46ee-4bdb-a3f6-35b3006bb1b6 |  | checklist | Apartments - Fit Off Checklist |  |  |  |  | Yes | Apartments - Fit Off Checklist | 8bb4e423-0c57-4230-b847-acca56c33f1d
checkpoint-status | f44b4ecf-08d7-4838-8b7e-a09d7e695368 |  | checkpoint | S/A & R/A Grilles fit off
checkpoint-status | 2d85e144-7382-4f39-9809-b99e3262589b |  | checkpoint | E/A Grilles fit off
checkpoint-status | 1d55df2d-5f07-46fc-baad-49d622142327 |  | checkpoint | Fans fit off, powered and set medium speed
checkpoint-status | fec89786-33cc-4759-ad3c-4e1f146bd429 |  | checkpoint | Access panels installed and equipment accessible
checkpoint-status | eda47b98-6936-4790-be76-41187d48d4d3 |  | checkpoint | Rangehood installed and flex connected
checkpoint-status | 5a883913-f05f-4df1-833a-5270e2396dda |  | checkpoint | Indoor A/C unit power fit off and addressed
checkpoint-status | 8b462be0-3ba9-4a97-8e4b-a4eb2b1bf08c |  | checkpoint | All drains fit off and tested
checkpoint-status | a41c2ebb-1f5b-4610-bc5f-ee4c3d3c550c |  | checkpoint | Condenser unit fit off, pipes and wires sealed and capped where required
checkpoint-status | 83b9d5cf-379d-4ccc-af7b-5817060c4c14 |  | checkpoint | Therstate installed and tested