## Nurse Call
Frances Hodgkins - ConQa Schedule
Building |  | Level |  | Area |  | Service |  | Location |  | Sign off (for each location)
Apartments Building | → | Level - Ground | → | Common Areas | → | Nurse Call | → | Side Entry/Gallery |  | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Garage 01 |  | Testing | (Test call-point)
Garage 02
Garage 03
Garage 04
Garage 05
Garage 06
Garage 07
Garage 08
Entry Foyer/Lifts
Stairs Landing
Hallway Passage
Garage 09 (comms room)
Garage 10
Garage 11
Garage 12
[5 empty] | → | CCTV | → | Side Entry/Gallery Cam |  | Fit-off | (Photo of wiring termination & photo of camera mounted)
[8 empty] | Garage 07 Cam |  | Testing | (Test/align camera)
Garage 08 Cam
Garages Corridor Entry Cam
Entry Foyer Cam
Apt Entry Door Cam
Garage 9 Cam (comms room)
[5 empty] | → | Access Control | → | Side Entry/Gallery |  | Fit-off | (Photo of wiring termination of card reader, rex, emrex, door lock & photo of devices mounted)
[8 empty] | Garages Corridor Entry |  | Testing | (Test all devices)
Apt Entry Left
Apt Entry Right
Foyer - Hallway Passage
Hallway Passage - Garage
Comms Room door
|  |  | → | Comms Room |  |  |  |  | → | Fit-off | (Photos of cabinet, patch panels, cables)
[10 empty] | Testing | (Test all cables)
| → | Level - One | → | Apartments | → | Nurse Call | → | Apartment 101 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Apartment 102 |  | Testing | (Test call-point)
Apartment 103
Apartment 104
Apartment 105
Apartment 106
Apartment 107
Apartment 108
Apartment 109
Apartment 110
Apartment 111
Apartment 112
Apartment 113
Apartment 114
Apartment 115
Apartment 116
[5 empty] | → | MATV | → | Apartment 101 | → | Fit-off | (Photo of connection & photo of TV-point on the wall)
[8 empty] | Apartment 102 |  | Testing | (Test signal strength)
Apartment 103
Apartment 104
Apartment 105
Apartment 106
Apartment 107
Apartment 108
Apartment 109
Apartment 110
Apartment 111
Apartment 112
Apartment 113
Apartment 114
Apartment 115
Apartment 116
[5 empty] | → | Data | → | Apartment 101 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Apartment 102 |  | Testing | (LAN pair test)
Apartment 103
Apartment 104
Apartment 105
Apartment 106
Apartment 107
Apartment 108
Apartment 109
Apartment 110
Apartment 111
Apartment 112
Apartment 113
Apartment 114
Apartment 115
Apartment 116
|  |  | → | Common Areas | → | Nurse Call | → | Side Entry/Gallery | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Lifts |  | Testing | (Test call-point)
Stairs Landing
Hallway Passage
Entry far right
[5 empty] | → | CCTV | → | Entry far right Cam | → | Fit-off | (Photo of wiring termination & photo of camera mounted)
[10 empty] | Testing | (Test/align camera)
[5 empty] | → | Access Control | → | Entry far right door | → | Fit-off | (Photo of wiring termination of card reader, rex, emrex, door lock & photo of devices mounted)
[10 empty] | Testing | (Test all devices)
| → | Level - Two | → | Apartments | → | Nurse Call | → | Apartment 201 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Apartment 202 |  | Testing | (Test call-point)
Apartment 203
Apartment 204
Apartment 205
Apartment 206
Apartment 207
Apartment 208
Apartment 209
Apartment 210
Apartment 211
Apartment 212
Apartment 213
Apartment 214
Apartment 215
Apartment 216
[5 empty] | → | MATV | → | Apartment 201 | → | Fit-off | (Photo of connection & photo of TV-point on the wall)
[8 empty] | Apartment 202 |  | Testing | (Test signal strength)
Apartment 203
Apartment 204
Apartment 205
Apartment 206
Apartment 207
Apartment 208
Apartment 209
Apartment 210
Apartment 211
Apartment 212
Apartment 213
Apartment 214
Apartment 215
Apartment 216
[5 empty] | → | Data | → | Apartment 201 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Apartment 202 |  | Testing | (LAN pair test)
Apartment 203
Apartment 204
Apartment 205
Apartment 206
Apartment 207
Apartment 208
Apartment 209
Apartment 210
Apartment 211
Apartment 212
Apartment 213
Apartment 214
Apartment 215
Apartment 216
|  |  | → | Common Areas | → | Nurse Call | → | Side Entry/Gallery | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Lifts |  | Testing | (Test call-point)
Stairs Landing
Hallway Passage
Entry far right
| → | Level - Three | → | Apartments | → | Nurse Call | → | Apartment 301 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Apartment 302 |  | Testing | (Test call-point)
Apartment 303
Apartment 304
Apartment 305
Apartment 306
Apartment 307
Apartment 308
[5 empty] | → | MATV | → | Apartment 301 | → | Fit-off | (Photo of connection & photo of TV-point on the wall)
[8 empty] | Apartment 302 |  | Testing | (Test signal strength)
Apartment 303
Apartment 304
Apartment 305
Apartment 306
Apartment 307
Apartment 308
[5 empty] | → | Data | → | Apartment 301 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Apartment 302 |  | Testing | (LAN pair test)
Apartment 303
Apartment 304
Apartment 305
Apartment 306
Apartment 307
Apartment 308
|  |  | → | Common Areas | → | Nurse Call | → | Gallery/Entry 1 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Lift Lobby/Lounge |  | Testing | (Test call-point)
Stairs Landing
Gallery/Entry 2
[5 empty] | → | Data | → | Lounge TV 1 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Lounge TV 2 |  | Testing | (LAN pair test)
| → | Level - Four | → | Apartments | → | Nurse Call | → | Apartment 401 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Apartment 402 |  | Testing | (Test call-point)
Apartment 403
Apartment 404
Apartment 405
Apartment 406
Apartment 407
Apartment 408
[5 empty] | → | MATV | → | Apartment 401 | → | Fit-off | (Photo of connection & photo of TV-point on the wall)
[8 empty] | Apartment 402 |  | Testing | (Test signal strength)
Apartment 403
Apartment 404
Apartment 405
Apartment 406
Apartment 407
Apartment 408
[5 empty] | → | Data | → | Apartment 401 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Apartment 402 |  | Testing | (LAN pair test)
Apartment 403
Apartment 404
Apartment 405
Apartment 406
Apartment 407
Apartment 408
|  |  | → | Common Areas | → | Nurse Call | → | Gallery/Entry 1 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Lift Lobby/Lounge |  | Testing | (Test call-point)
Stairs Landing
Gallery/Entry 2
[5 empty] | → | Data | → | Lounge TV 1 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Lounge TV 2 |  | Testing | (LAN pair test)
| → | Level - Five | → | Apartments | → | Nurse Call | → | Apartment 501 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Apartment 502 |  | Testing | (Test call-point)
Apartment 503
Apartment 504
Apartment 505
Apartment 506
Apartment 507
Apartment 508
[5 empty] | → | MATV | → | Apartment 501 | → | Fit-off | (Photo of connection & photo of TV-point on the wall)
[8 empty] | Apartment 502 |  | Testing | (Test signal strength)
Apartment 503
Apartment 504
Apartment 505
Apartment 506
Apartment 507
Apartment 508
[5 empty] | → | Data | → | Apartment 501 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Apartment 502 |  | Testing | (LAN pair test)
Apartment 503
Apartment 504
Apartment 505
Apartment 506
Apartment 507
Apartment 508
|  |  | → | Common Areas | → | Nurse Call | → | Gallery/Entry 1 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Lift Lobby/Lounge |  | Testing | (Test call-point)
Stairs Landing
Gallery/Entry 2
[5 empty] | → | Data | → | Lounge TV 1 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Lounge TV 2 |  | Testing | (LAN pair test)
| → | Level - Six | → | Apartments | → | Nurse Call | → | Apartment 601 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Apartment 602 |  | Testing | (Test call-point)
Apartment 603
Apartment 604
Apartment 605
Apartment 606
Apartment 607
Apartment 608
[5 empty] | → | MATV | → | Apartment 601 | → | Fit-off | (Photo of connection & photo of TV-point on the wall)
[8 empty] | Apartment 602 |  | Testing | (Test signal strength)
Apartment 603
Apartment 604
Apartment 605
Apartment 606
Apartment 607
Apartment 608
[5 empty] | → | Data | → | Apartment 601 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Apartment 602 |  | Testing | (LAN pair test)
Apartment 603
Apartment 604
Apartment 605
Apartment 606
Apartment 607
Apartment 608
|  |  | → | Common Areas | → | Nurse Call | → | Gallery/Entry 1 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Lift Lobby/Lounge |  | Testing | (Test call-point)
Stairs Landing
Gallery/Entry 2
[5 empty] | → | Data | → | Library PC/Printer | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[10 empty] | Testing | (LAN pair test)
| → | Level - Seven | → | Apartments | → | Nurse Call | → | Apartment 701 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Apartment 702 |  | Testing | (Test call-point)
Apartment 703
Apartment 704
Apartment 705
Apartment 706
[5 empty] | → | MATV | → | Apartment 701 | → | Fit-off | (Photo of connection & photo of TV-point on the wall)
[8 empty] | Apartment 702 |  | Testing | (Test signal strength)
Apartment 703
Apartment 704
Apartment 705
Apartment 706
[5 empty] | → | Data | → | Apartment 701 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Apartment 702 |  | Testing | (LAN pair test)
Apartment 703
Apartment 704
Apartment 705
Apartment 706
|  |  | → | Common Areas | → | Nurse Call | → | Gallery/Entry 1 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Lift Lobby/Lounge |  | Testing | (Test call-point)
Stairs Landing
| → | Level - Eight | → | Apartments | → | Nurse Call | → | Apartment 801 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Apartment 802 |  | Testing | (Test call-point)
Apartment 803
Apartment 804
[5 empty] | → | MATV | → | Apartment 801 | → | Fit-off | (Photo of connection & photo of TV-point on the wall)
[8 empty] | Apartment 802 |  | Testing | (Test signal strength)
Apartment 803
Apartment 804
[5 empty] | → | Data | → | Apartment 801 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Apartment 802 |  | Testing | (LAN pair test)
Apartment 803
Apartment 804
|  |  | → | Common Areas | → | Nurse Call | → | Gallery/Entry 1 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Lift Lobby/Lounge |  | Testing | (Test call-point)
Stairs Landing
Apartment Sign-off | → | Separate cables (add signature)
Separate security cables (add signature)
Complete cable risers (add signature)
Build patch panels (attach photo's)
Build nurse call system (attach photo's)
Build MATV system (attach photo's)
Build security panels (attach photo's)
Program nurse call system (add signature)
Commission nurse call system (attach photo's)
Commission Security system (attach photo's)
Commission Fire interface (attach photo's)
Resthome Building | → | Level - Ground | → | Rooms | → | Nurse Call |  | Room 1 | → | Fit-off | (Photo of wiring termination & photo of call-point on the wall)
[8 empty] | Room 2 |  | Testing | (Test call-point)
Room 3
Room 4
Room 5
Room 6
Room 7
Room 8
Room 9
Room 10
Room 11
Room 12
Room 13
Room 14
Room 15
Room 16
Room 17
Room 18
Room 19
Room 20
Room 21
Room 22
Room 23
Room 24
Room 25
Room 26
Room 27
Room 28
Room 29
Room 30
Room 31
Room 32
Room 33
Room 34
Room 35
Room 36
Room 37
Room 38
Room 39
Room 40
Room 41
Room 42
Room 43
Room 44
Room 45
Room 46
Room 47
Room 48
Room 49
Room 50
Room 51
[5 empty] | → | MATV | → | Room 1 | → | Fit-off | (Photo of connection & photo of TV-point on the wall)
[8 empty] | Room 2 |  | Testing | (Test signal strength)
Room 3
Room 4
Room 5
Room 6
Room 7
Room 8
Room 9
Room 10
Room 11
Room 12
Room 13
Room 14
Room 15
Room 16
Room 17
Room 18
Room 19
Room 20
Room 21
Room 22
Room 23
Room 24
Room 25
Room 26
Room 27
Room 28
Room 29
Room 30
Room 31
Room 32
Room 33
Room 34
Room 35
Room 36
Room 37
Room 38
Room 39
Room 40
Room 41
Room 42
Room 43
Room 44
Room 45
Room 46
Room 47
Room 48
Room 49
Room 50
Room 51
[5 empty] | → | Data | → | Room 1 | → | Fit-off | (Photo of wiring connection & photo of data outlet on the wall)
[8 empty] | Room 2 |  | Testing | (LAN pair test)
Room 3
Room 4
Room 5
Room 6
Room 7
Room 8
Room 9
Room 10
Room 11
Room 12
Room 13
Room 14
Room 15
Room 16
Room 17
Room 18
Room 19
Room 20
Room 21
Room 22
Room 23
Room 24
Room 25
Room 26
Room 27
Room 28
Room 29
Room 30
Room 31
Room 32
Room 33
Room 34
Room 35
Room 36
Room 37
Room 38
Room 39
Room 40
Room 41
Room 42
Room 43
Room 44
Room 45
Room 46
Room 47
Room 48
Room 49
Room 50
Room 51
|  |  | → | Common Areas | → | Nurse Call | → | Shower Room 1
Shower Room 2
Shower Room 3
Toilet 1
Lounge
Dining
Hairdresser
Theatre
Toilet 2
Shower Room 4
Shower Room 5
Spa Bath
[5 empty] | → | CCTV | → | Driveway Cam |  | Fit-off | (Photo of wiring termination & photo of camera mounted)
[8 empty] | Side entry Cam (by Linen) |  | Testing | (Test/align camera)
Main Entry Cam
Wind Lobby Cam
Reception Cam
Care Hub Cam
Kitchen Cam
Service Yard Area Cam
Far Entry Cam
[5 empty] | → | Access Control | → | Top entry door |  | Fit-off | (Photo of wiring termination of card reader, rex, emrex, door lock & photo of devices mounted)
[8 empty] | Side entry door (by Linen) |  | Testing | (Test all devices)
Main Entry door
Care Hub door
Comms Room door
Staff WC door
Staff WC 2 door
Storeroom door
Sluice room door
Exit door (to Apartments)
Far right door
|  |  | → | Comms Room |  |  |  |  | → | Fit-off | (Photos of cabinet, patch panels, cables)
[10 empty] | Testing | (Test all cables)
Resthome Sign-off | → | Separate cables (add signature)
Separate security cables (add signature)
Complete cable risers (add signature)
Build patch panels (attach photo's)
Build nurse call system (attach photo's)
Build MATV system (attach photo's)
Build security panels (attach photo's)
Program nurse call system (add signature)
Commission nurse call system (attach photo's)
Commission Security system (attach photo's)
Commission Fire interface (attach photo's)