## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITC 04 - R53 Concrete for Roadworks Rev 1 | itp |  |  |  |  | ITC 04 - R53 Concrete for Roadworks Rev 1 | 7401c29c-c66a-4c8a-bf14-31cb6824269a
section | Lot Information
checkpoint | Lot Information complete
textbox | Lot Opened On
textbox | Date of Works
textbox | Lot Type
textbox | Start Chainage
textbox | End Chainage
textbox | Offset
textbox | Control Line
section | 1. Material Compliance
checkpoint | 1.1 - Submission of Nominated Mixes
label | Document Reference / Applicable Standard - R53 Cl 2.4.3
label | Acceptance Criteria - Where the nominated mix(es) has had production assessment carried out in accordance with AS 1379 Clause 6.3, submit the production assessment report complying with AS 1379 Clause 6.4.2. Include a statement from each material supplier certifying that the constituent materials meet the requirement of this Specification.
label | Frequency/ Process Held - Once / 5 working days prior to commencement of production of mix
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Mix Design Report
holdpoint | AUTHORITY HOLDPOINT
section | 2. Construction
checkpoint | 2.1 - Notification of Concrete Placing and Finishing
label | Document Reference / Applicable Standard - R53 Cl 3.3.1
label | Acceptance Criteria - At least 2 working days prior to the placing of concrete, provide notice of:
label | – Expected completion time of fixing of the formwork and reinforcement (if applicable) and;
label | – Expected commencement date and time of placement of concrete
label | Frequency/ Process Held - Once / At least 2 working days prior to each placement
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - HP Submission
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Concrete and Air Temperature / Rain
label | Document Reference / Applicable Standard - R53 Cl 3.3.2, R53 Cl 3.3.3
label | Acceptance Criteria - Do not place concrete in the works if its temperature at the point of discharge is less than 10C and more than 32C.
label | Do not place concrete of the measured air temperature is below 5C or above 35C. Do not place concrete during rain or when rain appears imminent.
label | Frequency/ Process Held - Once / prior to concrete placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Project Quality Plan Pour Record Sheet
checkpoint | 2.3 - Placing and Compacting
label | Document Reference / Applicable Standard - R53 Cl 3.3.4
label | Acceptance Criteria - Place concrete in such manner that:
label | (a) limit segregation or loss of materials;
label | (b) limit premature stiffening;
label | (c) produce a dense homogeneous product which is monolithic between joints and edges;
label | (d) provide the specified thickness and surface finish.
label | Carry out vibration in a regular and systematic manner to ensure that all the concrete is thoroughly compacted.
label | Where internal vibrators are used, they must have a minimum diameter of 50 mm with an operating frequency between 130 Hz and 200 Hz.
label | Frequency/ Process Held - During Placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
checkpoint | 2.4 - Unformed Surface Finish
label | Document Reference / Applicable Standard - R53 Cl 3.3.6
label | Acceptance Criteria - Finish unformed concrete surfaces in such manner that:
label | (a) achieve the specified dimensions, grade and surface texture;
label | (b) avoid plastic or drying shrinkage cracks.
label | Frequency/ Process Held - During Construction
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
checkpoint | 2.5 - Joints
label | Document Reference / Applicable Standard - R53 Cl 3.3.9
label | Acceptance Criteria - Roughen the surface of concrete at construction joints to expose the coarse aggregate. Wash clean the roughened surfaces and projecting reinforcement, and remove all excess water and loose material prior to placing the adjoining concrete.
label | Frequency/ Process Held - During Construction
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
checkpoint | 2.6 - Curing
label | Document Reference / Applicable Standard - R53 Cl 3.4
label | Acceptance Criteria - Apply curing compound to unform surfaces immediately after the surface is firm and free of bleed water
label | Apply curing compound at the rate specified by the manufacturer
label | Apply two coats hen necessary to ensure complete and uniform coverage. The time between the first and second coat must be in accordance with the manufacturer’s recommendation.
label | During application, implement measures to prevent the curing compound drifting away from the target concrete surface and deposited on adjacent surfaces.
label | Maintain the curing membrane intact until at least seven days have elapsed after concrete placement
label | Frequency/ Process Held - During Construction
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Project Quality Plan
checkpoint | 2.7 - Mortar, Grout and Sprayed Concrete
label | Document Reference / Applicable Standard - R53 Cl 3.6
label | Acceptance Criteria - Notify principal prior to placing of mortar, grout and sprayed concrete.
label | Frequency/ Process Held - Prior to placing Mortar, grout or sprayed concrete
label | Inspection - ACPL - W
label | Inspection - Client - W
label | Verifying Records - Visual Inspection
section | 3. Conformity
checkpoint | 3.1 - Sampling and Testing (Concrete)
label | Document Reference / Applicable Standard - R53 Cl 4.1.1
label | Acceptance Criteria - Slump:
label | ○ Perform slump tests on each strength sample
label | Strength:
label | ○ Each grade at a plant shall be sampled at a frequency of at least one sample per 100 m3 of that grade produced except that, for Grade 20 concrete when 15 or more samples per month are obtained, the frequency may be reduced.
label | Frequency/ Process Held - Prior to Placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Slump Results Strength Results
checkpoint | 3.2 - Cracking
label | Document Reference / Applicable Standard - R53 Cl 4.2
label | Acceptance Criteria - At the end of the curing period, the concrete surface must have no unplanned cracks of width greater than 0.2 mm, measured at the concrete surface after completion of 21 days drying. Where such cracks exist, identify them as nonconformities.
label | Frequency/ Process Held - Once / Prior to Lot Closure
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Crack Map
checkpoint | 3.3 - Dimensions and Levels
label | Document Reference / Applicable Standard - R53 Cl 4.3
label | Acceptance Criteria - Dimensions and levels of surfaces constructed using fixed forms must be as shown on the Drawings or in the relevant Specification, and within the tolerances stated in AS 3610.1, unless specified otherwise on the Drawings or in the relevant Specification.
label | Dimensions and levels of unformed exposed surfaces, and surfaces constructed by slipforming or extrusion, must be as shown on the Drawings, and within the tolerances specified in the relevant Specification.
label | Frequency/ Process Held - Once / Prior to Lot Closure
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Survey Report
section | Review by Project Manager
checkpoint-no-value | Review by Project Manager
button | Any non-conformances? | YES, NO
textbox | No's:
button | Closed Out | YES, NO
button | All work has been satisfactorily completed. | YES, NO
textbox | Name:
signoff | Add signature
section | Lot Verification
checkpoint | Lot Verification complete
textbox | Lot Verified By:
textbox | Lot Closed Date:
button | Submitted to Client | Yes, No, N/A
button | Reviewed by Client | Yes, No, N/A
textbox | Submission Comments:
section-nested-checklists | NCR
checklist | ITC 07 - R15 Kerb and Gutters Rev 1 | itp |  |  |  |  | ITC 07 - R15 Kerb and Gutters Rev 1 | c9461529-4844-4043-b2b6-6e3734d33f85
section | Lot Information
checkpoint | Lot Information complete
textbox | Lot Opened On
textbox | Date of Works
textbox | Lot Type
textbox | Start Chainage
textbox | End Chainage
textbox | Offset
textbox | Control Line
section | 1. Preliminary Works
checkpoint | 1.1 - IFC Drawings are Current
label | Document Reference / Applicable Standard - Pavement IFC Drawings
label | Acceptance Criteria - Use of latest revision of approved Issued for Construction (IFC) Drawings. Any changes in design, RFI was raised and approved:
textbox | RFI
label | Frequency/ Process Held - Once / Prior to Construction
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Pavements IFC Drawing
checkpoint | 1.2 - Underlying lot conforming
label | Document Reference / Applicable Standard - Survey Report
label | Acceptance Criteria - Underlying/Preceding lot is conforming prior to commencement including survey levels of underlying lot and K&C Subgrade
label | Frequency/ Process Held - Once / Prior to Construction
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Test Results / Survey Report
checkpoint | 1.3 - Concrete Mix Design
label | Document Reference / Applicable Standard - R53 Cl 2.4.1, R53 Annexure, R53/E, R15 Cl 2.2
label | Acceptance Criteria - Concrete Mix Design approved by client
label | 25mpa – 15 – 25mm slump – max. nom aggregate 10mm
label | Frequency/ Process Held - Once / prior to construction
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Concrete Mix Design
holdpoint | AUTHORITY HOLDPOINT
section | 2. Construction
checkpoint | 2.1 - Survey Set out
label | Document Reference / Applicable Standard - QMP
label | Acceptance Criteria - Survey set out as per design drawings
label | Frequency/ Process Held - Once / Prior to Placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Set out Report
checkpoint | 2.2 - Placement of Concrete
label | Document Reference / Applicable Standard - R53 Cl 3.3.1
label | Acceptance Criteria - Provide 2 working days’ notice to client of expected completion of preparation and expected commencement date and time of concrete placement
label | Frequency/ Process Held - Once / Prior to Placement
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - HP Submission
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Concrete Sampling
label | Document Reference / Applicable Standard - R53 Cl 4.1 AS1379
label | Acceptance Criteria - Slump:
label | ○ Perform slump tests on each strength sample
label | Strength:
label | ○ Each grade at a plant shall be sampled at a frequency of at least one sample per 100 m3 of that grade produced except that, for Grade 20 concrete when 15 or more samples per month are obtained, the frequency may be reduced.
label | Frequency/ Process Held - Prior to Placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Slump Results Strength Results
checkpoint | 2.4 - Concrete and Air Temp
label | Document Reference / Applicable Standard - R53 Cl 3.3.2
label | Acceptance Criteria - Do not place concrete during rain or when air temperature in the shade is below 5oC or above 35oC
label | Frequency/ Process Held - Prior to pouring each load
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Pour Record
checkpoint | 2.5 - Joints
label | Document Reference / Applicable Standard - R15 Cl 2.6, R15 cl 3.8
label | Acceptance Criteria - Joint sealant must be silicone sealant conforming to Specification TfNSW R83. Form and prepare joints in conformity to AS 2876.
label | Shrinkage Control Joints: Spaced every 2.3 to 3m. Constructed by guillotining extruded work. Min 50% of the area of the section shall be cut. Resultant slot to be tooled to a depth of not less than 20mm to provide a groove of not less than 5mm in width.
label | Construction Joints: For Machine placed concrete, the last section of poorly formed or compacted concrete is to be removed while still plastic. Approx. 300mm. Leave suitable square face. Immediately prior to placing further concrete, the contact face shall be covered by a thin coat of cement water paste of creamy consistency. A Construction joint shall not be used to replace a shrinkage control joint.
label | Frequency/ Process Held - Once / prior to placement of concrete
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Checklist
checkpoint | 2.6 - Curing
label | Document Reference / Applicable Standard - R53 Cl 3.4.3
label | Acceptance Criteria - Apply curing compound to unform surfaces immediately after the surface is firm and free of bleed water
label | Apply curing compound at the rate specified by the manufacturer
label | Apply two coats when necessary to ensure complete and uniform coverage. The time between the first and second coat must be in accordance with the manufacturer’s recommendation.
label | During application, implement measures to prevent the curing compound drifting away from the target concrete surface and deposited on adjacent surfaces.
label | Maintain the curing membrane intact until at least seven days have elapsed after concrete placement
label | Frequency/ Process Held - Once / prior to placement of concrete
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Concrete Finish
label | Document Reference / Applicable Standard - R15 Cl 3.9
label | Acceptance Criteria - Unless otherwise shown in the drawings, provide a steel float finish to channel inverts and faces of kerb and broomed finish to vehicular crossing and ramps. Brooming must be transverse to the direction of travel.
label | Protect the concrete surface from rain during and after surface finishing and until final set.
label | Frequency/ Process Held - Once / Prior to Survey
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection Project Quality Plan
section | 3. Conformity
checkpoint | 3.1 - Conformity
label | Document Reference / Applicable Standard - R15 Cl 4
label | Acceptance Criteria - All finished surfaces must conform to the lines, levels, grades, thicknesses and cross sections shown on the Drawings within the specified tolerances.
label | The tolerances stated in AS 2876 for irregularities in the bedding layer, level of the bedding layer, horizontal alignment, level, deviation from a 3 m straightedge, deviation on vertical curves, and profile dimensions also apply, except that the level of the constructed channel lip must not vary by more than 0 mm above or 10 mm below the adjoining pavement surface at any point.
label | Frequency of conformity testing as per Annexure R15/L:
label | Frequency/ Process Held - During concrete delivery
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Concrete Docket Survey Report, Concrete Pour Record
section | Review by Project Manager
checkpoint-no-value | Review by Project Manager
button | Any non-conformances? | YES, NO
textbox | No's:
button | Closed Out | YES, NO
button | All work has been satisfactorily completed. | YES, NO
textbox | Name:
signoff | Add signature
section | Lot Verification
checkpoint | Lot Verification complete
textbox | Lot Verified By:
textbox | Lot Closed Date:
button | Submitted to Client | Yes, No, N/A
button | Reviewed by Client | Yes, No, N/A
textbox | Submission Comments:
section-nested-checklists | NCR
checklist | ITC 09 - R33 Trench Drains Rev 1 | itp |  |  |  |  | ITC 09 - R33 Trench Drains Rev 1 | 4f846bfc-a0ff-447a-bc01-fbce28393591
section | Lot Information
checkpoint | Lot Information complete
textbox | Lot Opened On
textbox | Date of Works
textbox | Lot Type
textbox | Start Chainage
textbox | End Chainage
textbox | Offset
textbox | Control Line
section | 1. Preliminary Works
checkpoint | 1.1 - IFC Drawings are Current
label | Document Reference / Applicable Standard - Pavement IFC Drawings
label | Acceptance Criteria - Use of latest revision of approved Issued for Construction (IFC) Drawings. Any changes in design, RFI was raised and approved:
textbox | RFI
label | Frequency/ Process Held - Once / Prior to Construction
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Pavements IFC Drawing
checkpoint | 1.2 - Underlying lot conforming
label | Document Reference / Applicable Standard - Survey Report
label | Acceptance Criteria - Underlying/Preceding lot is conforming prior to commencement including survey levels of underlying lot
label | Frequency/ Process Held - Once / Prior to Construction
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Test Results / Survey Report
section | 2. Material Compliance
checkpoint | 2.1 - Corrugated Drainage Pipe and Rigid Strip Filter Drain
label | Document Reference / Applicable Standard - R33 Cl 2.1
label | Acceptance Criteria - Corrugated plastic drainage pipe (both perforated and non-perforated) must comply with Specification TfNSW 3552. Caps and other fittings must be in accordance with the manufacturer’s recommendations.
label | Seamless tubular filter fabric for use with corrugated perforated plastic drainage pipe must comply with Specification TfNSW 3553.
label | Rigid strip filter drain must comply with Specification TfNSW 3556.
label | Frequency/ Process Held - Once / Submitted to principal 7 prior to use
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Compliance Records
checkpoint | 2.2 - Geotextile
label | Document Reference / Applicable Standard - R33 Cl 2.2
label | Acceptance Criteria - Geotextile must comply with specification TfNSW R63.
label | Geotextile for wrapping around rigid strip filter drain must be non-woven geotextile of Strength Class A
label | Frequency/ Process Held - Once / Submitted to principal 7 prior to use
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Compliance Records
checkpoint | 2.3 - No Fines Concrete and Aggregate Filter Material
label | Document Reference / Applicable Standard - R33 Cl 2.3, TfNSW 3580, D&C 3222 Cl 6
label | Acceptance Criteria - No fines concrete must be Grade NFC SD complying with Specification TfNSW 3222
label | Aggregate filter material must comply with Specification TfNSW 3580 and the Drawings for the aggregate type.
label | Detail the mixing plant and delivery vehicles
label | Frequency/ Process Held - Once / Submitted to principal 7 prior to use
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Mix Design & delivery methodology / Compliance Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Selected Material
label | Document Reference / Applicable Standard - R33 Cl2.4
label | Acceptance Criteria - Select Material must meet the requirements of Specification TfNSW R44. Select material at batter outlet and at the transverse outlets of pavements interface drains must, in addition, have a maximum particle size not exceeding 50mm.
label | Selected fill material for the plug used in staged construction must have a maximum particle size not exceeding 20mm and PI not exceeding 12.
label | Frequency/ Process Held - Once / Submitted to principal 7 prior to use
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Compliance Records
section | 3. Construction
checkpoint | 3.1 - Order of Construction
label | Document Reference / Applicable Standard - R33 Cl 3.1
label | Acceptance Criteria - Where trench drains are to be installed in embankment foundations, construct the trench drains after completion of clearing, stripping and general excavation operations, but preceding the commencement of embankment construction adjacent to the trench drain.
label | If trench drains are required in cuttings, construct the trench drains as soon as practicable following completion of earthworks.
label | Where the top of earthworks is to be stabilised, construct the trench drains after completion of stabilisation.
label | Where excessive ground water is encountered, trench drains may be installed prior to stabilisation if approved by the principal.
label | Frequency/ Process Held - During construction
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - N/A
checkpoint | 3.2 - Excavation
label | Document Reference / Applicable Standard - R33 Cl 3.2
label | Acceptance Criteria - Unless otherwise specified, the bottom of the trench must be at the same grade as the roadway. Where the grade of the roadway is less than 0.5%, provide minimum grade of 0.5% by increasing the depth of the trench.
label | Excavated material must either be stockpile or incorporated in the works or disposed of in accordance with R44.
label | Frequency/ Process Held - During construction
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Survey Report
checkpoint | 3.3 - Geotextile Installation
label | Document Reference / Applicable Standard - R33 Cl 3.3
label | Acceptance Criteria - When installing geotextile, do not allow loose material from the trench walls or outside the trench to enter the excavation.
label | Keep all geotextiles clean and secure the geotextile to ensure that they are located as shown on the drawings on completion of backfill.
label | Frequency/ Process Held - During construction
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
checkpoint | 3.4 - Laying of Pipe
label | Document Reference / Applicable Standard - R33 Cl 3.4
label | Acceptance Criteria - Lay the pipe in the centre of the trench on a bed of filter material 100mm thick to the required line and grade as shown on the drawing.
label | Keep the number of joints in the pipeline to the minimum and connect the pipes using coupling complying with the manufacturers recommendations.
label | Where an inlet into the trench drain is provided at a stormwater pit, the invert level of the inlet must be above the hydraulic grade line of the pit and as close to the underside of the pavement layer as possible.
label | Cap the upstream end of buried pipes where the upstream end of the pipe is enclosed within filter material and is not connected to a stormwater pit.
label | Where the filter material around the pipe is Grade F5 or F7 aggregate filter material (refer TfNSW 3580),
label | (a) for corrugated perforated plastic drainage pipe, install a seamless tubular filter fabric around the pipe;
label | (b) for rigid strip filter drain, wrap the strip filter drain with non-woven geotextile of Strength Class A. The geotextile must encapsulate the rigid strip filter and be joined by heat or an electrically generated welding process.
label | Frequency/ Process Held - During Construction
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
checkpoint | 3.5 - Backfilling
label | Document Reference / Applicable Standard - R33 Cl 3.5, TfNSW 3222 Cl 7.1
label | Acceptance Criteria - Compact the filter material to its full depth to avoid post-construction consolidation and to provide an even surface at the same level as the adjacent material.
label | Verification that pipe laying, jointing and bedding are complete and conforming.
label | At the end of each days production, total up the individual masses of cement and aggregates using in the days production of no fines concrete, and provide these details to the principal
label | Frequency/ Process Held - Backfilling
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Visual Inspection
holdpoint | AUTHORITY HOLDPOINT
section | 4. Outlets and Marking
checkpoint | 4.1 - Outlets at Stormwater Drainage Structures
label | Document Reference / Applicable Standard - R33 Cl 4.2
label | Acceptance Criteria - Where the outlet of the trench drain is at a stormwater pit or other stormwater drainage structure, the height of the pipe invert above the base of the trench drain must taper from 100 mm to zero within the end 5 metres from the outlet.
label | Where a trench drain is one without a pipe, provide 10 m of corrugated perforated plastic pipe immediately upstream of the outlet and taper the height of the pipe invert as described above to facilitate discharge of water. Fit the upstream end of the pipe with a suitable cap to prevent entry of material.
label | Frequency/ Process Held - Installation of Outlets at Stormwater Drainage Structures
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
checkpoint | 4.2 - Outlets at Batters
label | Document Reference / Applicable Standard - R33 Cl 4.3
label | Acceptance Criteria - Where it is not possible to connect the trench drain to a stormwater pit or other stormwater drainage structure, construct an outlet at the batter to discharge water beyond the edge of the road shoulder.
label | The outlet pipe must be of the same type and size as those in the trench drain but must be non- perforated for the length extending beyond the edge of the pavement.
label | Lay the non-perforated section of pipe at the base of the trench. Taper the height above the base of the trench of the connecting section of perforated pipe, from zero to 100 mm, over a 2 m length.
label | Backfill the trench along this section of pipe with Selected Material of maximum particle size of 50 mm, and compacted to a relative compaction of 95% as determined by Test Method TfNSW T166.
label | Construct a batter outlet structure at the discharge end in accordance with the Drawings. Locate the outlet so that erosion of the adjacent area does not occur or protect the outlet by placing selected stone in the splash zone.
label | Frequency/ Process Held - Installation of Outlets at Batters
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
checkpoint | 4.3 - Marking
label | Document Reference / Applicable Standard - R33 Cl 6
label | Acceptance Criteria - During construction, physically mark out on site the inlets and outlets of the subsurface drains, to avoid damage to them during construction.
label | Frequency/ Process Held - Marking of Outlets and Inlets
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Project Quality Plan
section | Review by Project Manager
checkpoint-no-value | Review by Project Manager
button | Any non-conformances? | YES, NO
textbox | No's:
button | Closed Out | YES, NO
button | All work has been satisfactorily completed. | YES, NO
textbox | Name:
signoff | Add signature
section | Lot Verification
checkpoint | Lot Verification complete
textbox | Lot Verified By:
textbox | Lot Closed Date:
button | Submitted to Client | Yes, No, N/A
button | Reviewed by Client | Yes, No, N/A
textbox | Submission Comments:
section-nested-checklists | NCR
checklist | ITC 15 - R63 Geotextiles Rev1 | itp |  |  |  |  | ITC 15 - R63 Geotextiles Rev1
section | Lot Information
checkpoint | Lot Information complete
textbox | Lot Opened On
textbox | Date of Works
textbox | Lot Type
textbox | Start Chainage
textbox | End Chainage
textbox | Offset
textbox | Control Line
section | 1. Material Requirements
checkpoint | 1.1 - General Material Requirements
label | Document Reference / Applicable Standard - R63 Cl 2.1
label | Acceptance Criteria - The fibres of the geotextile and thread used in joining lengths must consist of long chain synthetic polymers composed of at least 95% by mass of polyolefins or polyesters.
label | Geotextiles must be free of any flaws which may have an adverse effect on the physical and mechanical properties of the geotextile.
label | Geotextiles may be manufactured under controlled conditions from recycled materials. Geotextiles manufactured from recycled materials must conform to the requirements of this Specification, be identified as such on the Certificate of Compliance
label | Frequency/ Process Held - Once / Prior to procurement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Material Data Sheet
checkpoint | 1.2 - Strength and Filtration Class Requirements
label | Document Reference / Applicable Standard - R63 Cl 2.2
label | Acceptance Criteria - Geotextiles for the applications of separation and/or filtration must meet the relevant Strength Class requirements of Table R63/E.2 to ensure survivability.
label | Geotextiles must meet the relevant filtration requirements of Table R63/E.1 for each application.
label | Frequency/ Process Held - Once / Prior to procurement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Material Data Sheet
section | 2. Site Sampling and Testing
checkpoint | 2.1 - Certificate of Compliance
label | Document Reference / Applicable Standard - R63 Cl 2.5
label | Acceptance Criteria - Provide a Certificate of Compliance that the geotextile complies with all the requirements of this specification for its specified usage together with tests results reported on NATA endorsed test documents. The certificate must not be more than twelve months old.
label | Frequency/ Process Held - Once / Prior to delivery of geotextiles
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Certificate of Compliance
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Site Sampling and Testing
label | Document Reference / Applicable Standard - R63 Cl 2.4
label | Acceptance Criteria - Location, date and time of sampling and person sampling to be witnessed by the client. Frequency of sampling and testing must be in accordance with Table R63.1.
label | A representative sample, covering approximately 15 m2 of geotextile (e.g. 3 m by 5 m), is cut from each sampled roll but not within 2 m of the start or end of the roll. Where directed, provide samples to the principal.
label | Clearly mark, for example by means of a large arrow, the longitudinal direction of the geotextile on each sample.
label | Test the geotextile samples at an approved NATA registered laboratory accredited for the range of tests given in Table R63/E.1 and Table R63/E.2.
label | Frequency/ Process Held - As specified / Prior to Lot Closure
label | Inspection - ACPL - W
label | Inspection - Client - W
label | Verifying Records - Test Results
checkpoint | 2.3 - Sampling Test Results Submission
label | Document Reference / Applicable Standard - R63 Cl 4.1
label | Acceptance Criteria - Site sampling test results referred to in Clause 2.4 at least 14 days prior to placement of geotextile.
label | Frequency/ Process Held - Once / 14 days prior to placement of geotextile
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Test Results
holdpoint | AUTHORITY HOLDPOINT
section | 3. Storage, Identification and Delivery
checkpoint | 3.1 - Storage, Packing, Identification and Delivery
label | Document Reference / Applicable Standard - R63 Cl 3
label | Acceptance Criteria - Geotextiles must be stored under protective cover or wrapped with a waterproof, opaque UV protective sheeting to avoid any damage prior to installation.
label | Geotextiles must not be stored directly on the ground or in any way they may be affected adversely by heat, dirt or damage.
label | The protected geotextile rolls must be clearly labelled showing manufacturer, type of geotextile and batch number identification number.
label | Geotextile must be delivered to the site at least 14 days prior to commencement of installation.
label | Frequency/ Process Held - Delivery to site
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
section | 4. Construction
checkpoint | 4.1 - Placement
label | Document Reference / Applicable Standard - R63 Cl 4.3, R63 Cl 4.5, R63 Cl 4.6.3
label | Acceptance Criteria - Cover the placed geotextile with either the fill material or a suitable protective sheeting within 48 hours of being placed.
label | Unless specified otherwise on the Drawings, the overlap must be 500 mm or greater where large ground deformations are expected.
label | Provide in your PROJECT QUALITY PLAN how you would ensure that your construction process and compaction method does not damage the geotextile.
label | The principal may require a site trial to evaluate your construction process and compaction method.
label | Frequency/ Process Held - Once / Prior to Placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Project Quality Plan
section | Review by Project Manager
checkpoint-no-value | Review by Project Manager
button | Any non-conformances? | YES, NO
textbox | No's:
button | Closed Out | YES, NO
button | All work has been satisfactorily completed. | YES, NO
textbox | Name:
signoff | Add signature
section | Lot Verification
checkpoint | Lot Verification complete
textbox | Lot Verified By:
textbox | Lot Closed Date:
button | Submitted to Client | Yes, No, N/A
button | Reviewed by Client | Yes, No, N/A
textbox | Submission Comments:
section-nested-checklists | NCR
checklist | ITC 16 - R116 Heavy Duty Dense Graded Asphalt Rev1 | itp |  |  |  |  | ITC 16 - R116 Heavy Duty Dense Graded Asphalt Rev1
section | Lot Information
checkpoint | Lot Information complete
textbox | Lot Opened On
textbox | Date of Works
textbox | Lot Type
textbox | Start Chainage
textbox | End Chainage
textbox | Offset
textbox | Control Line
section | 1. Material Requirements
checkpoint | 1.1 - Production Trial
label | Document Reference / Applicable Standard - R116 Cl 2.3.2
label | Acceptance Criteria - As part of your nominated mix design submission process, conduct a production trial to demonstrate conformity of the nominated mix.
label | All production trial tests on each nominated mix must be from one trial batch. The tests on the constituent materials must represent the materials used in this trial batch.
label | Frequency/ Process Held - Once / Prior to placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Conformity Statement
checkpoint | 1.2 - Nominated Mix Designs
label | Document Reference / Applicable Standard - R116 Cl 2.3.5
label | Acceptance Criteria - Submit to the principal documents referenced in Clause 2.3.3 (Nominated Mix Design Submission Details) at least 7 working days before the nominated mixes are proposed to be placed.
label | Frequency/ Process Held - Once / Prior to placement
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Mix Design Submission
holdpoint | AUTHORITY HOLDPOINT
section | 2. Placing Asphalt
checkpoint | 2.1 - General Placement
label | Document Reference / Applicable Standard - R116 Cl 3.1
label | Acceptance Criteria - Provide for traffic in accordance with the requirements of Specification TfNSW G10 when carrying out asphalt paving.
label | Prepare the surface to be paved in accordance with AS 2150, including removal of raised extruded thermoplastic road markings and raised pavement markers.
label | Frequency/ Process Held - Once / Prior to placing Asphalt
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
checkpoint | 2.2 - Application of Tackcoat
label | Document Reference / Applicable Standard - R116 Cl 3.2
label | Acceptance Criteria - The existing surface must be clean, dry and free from loose material, prior to application of the tackcoat.
label | Apply the tackcoat evenly at a rate of between 0.15 and 0.30 litres of residual bitumen per square metre, ensuring that it is effectively bonded to the surface. For joints and chases, double the application rate.
label | Nominate in writing to the principal your proposed tackcoat application rate prior to applying the tackcoat.
label | Provide to the Principal a signed daily record of the average tackcoat application rate applied to each Lot.
label | Report the tackcoat application rate in terms of residual bitumen and state the percentage dilution of the tackcoat used during spraying.
label | Frequency/ Process Held - Once / Prior to applying tackcoat
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Application Rate Statement, Daily Records
checkpoint | 2.3 - Temperature and Weather Conditions for Asphalt Placement
label | Document Reference / Applicable Standard - R116 Cl 3.3
label | Acceptance Criteria - Measure and record the temperature of the surface to be paved, and wind velocity at the point of asphalt placing.
label | Do not commence or continue placing asphalt containing binder complying with TfNSW 3253 if the temperature of the surface to be paved over, measured at existing surface level, is less than 8°C where the nominal size of asphalt is less than 20 mm, or less than 5°C where the nominal size of asphalt is 20 mm or greater, for a zero-wind speed.
label | These minimum temperatures are increased by 5°C for asphalt containing binder complying with TfNSW 3252.
label | These minimum temperatures are increased by a further 5°C for each 5 kph of wind speed above zero; however the minimum temperatures must not exceed 30°C.
label | Do not place tackcoat and/or asphalt when the surface is wet, and/or when wet weather appears imminent.
label | Frequency/ Process Held - Once / Prior to each asphalt placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
checkpoint | 2.4 - Paving and Compaction Temperatures
label | Document Reference / Applicable Standard - R116 Cl 3.5
label | Acceptance Criteria - Submit the following details prior to commencement of paving using nominated mixes:
label | (a) minimum temperature at which asphalt will be delivered to the paver;
label | (b) minimum temperature at which initial compaction of the asphalt can still commence;
label | (c) method of temperature measurement.
label | Frequency/ Process Held - Once / Prior to commencement of paving
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Paving Temperatures Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Course and Layer Thickness
label | Document Reference / Applicable Standard - R116 Cl 3.6
label | Acceptance Criteria - Control the course thickness by maintaining the design levels during placing and the surface shape requirements specified in Clause 5.6.
label | Where a course comprises more than one layer, and the layer thicknesses have not been specified on the Drawings, nominate the thickness of each layer in your PROJECT QUALITY PLAN.
label | The nominated thickness of a layer of asphalt must be between 3.0 to 5.0 times the nominal mix size.
label | Frequency/ Process Held - Once / Prior to commencement of Paving
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Project Quality Plan
checkpoint | 2.6 - Nonconforming Layer Thicknesses
label | Document Reference / Applicable Standard - R116 Cl 3.6.3
label | Acceptance Criteria - For corrective courses and tie-ins to an existing pavement, you may propose for approval by the Principal to place layers in thicknesses that does not conform to the specified thickness requirements.
label | Prior to placing asphalt in layer thickness not conforming to specifried layer thicknesses, submit o the principal the following:
label | (a) nominated layer thicknesses which does not conform to specified thicknesses;
label | (b) work methods capable of producing a dense homogeneous layer at these thicknesses;
label | (c) areas affected, and evidence that these areas are the absolute minimum necessary.
label | Frequency/ Process Held - Once / Continuation of works in Lot
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Non-Conformance Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Joints
label | Document Reference / Applicable Standard - R116 Cl 3.7
label | Acceptance Criteria - Longitudinal joints must be:
label | (a) offset by 150 mm from the joint in the underlying layers;
label | (b) located within 150 mm of the line of change in crossfall;
label | (c) coincident with final traffic markings, unless otherwise approved by the Principal.
label | Transverse joints must be:
label | (i) located at a minimum of 25 m apart;
label | (ii) offset by a minimum of 1 m from the joint in the underlying layer;
label | (iii) formed at the commencement of each paving run;
label | (iv) formed when a delay in paving causes asphalt temperature to fall below the initial compaction temperature nominated in Clause 3.5.
label | Include in your PROJECT QUALITY PLAN the procedure for the construction of joints including a jointing plan showing widths and include temporary and final lane line configurations.
label | Frequency/ Process Held - Once / Prior to Paving
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Project Quality Plan
checkpoint | 2.8 - Trial Section
label | Document Reference / Applicable Standard - R116 Cl 3.8
label | Acceptance Criteria - Prior to commencement of paving of the Works, construct a separate trial section using the plant and personnel proposed for the work for each nominated mix.
label | Each trial section must be located remote from the Works, unless otherwise approved by the Principal. Demonstrate conformity with the Specification in respect of:
label | (a) homogeneity;
label | (b) insitu air voids;
label | (c) course thickness;
label | (d) course position;
label | (e) surface shape;
label | (f) joint quality, widths and layout;
label | (g) ride quality, where specified.
label | Submit to the principal details of:
label | Verification checklist and all relevant test results from the trial section demonstrating conformity to the specified requirements, at least 3 working days prior to commencing of paving at locations other than trial sections.
label | Frequency/ Process Held - Once / at least 3 working days prior to Commencement of paving at locations other than trial section
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Verification Checklist
holdpoint | AUTHORITY HOLDPOINT
section | 3. Sampling and Testing of Placed Asphalt
checkpoint | 3.1 - Frequency of sampling and Testing
label | Document Reference / Applicable Standard - R116 Cl 4.1.1
label | Acceptance Criteria - Frequency of sampling and testing of placed asphalt must be in accordance with Annexure R116/L.
label | Frequency/ Process Held - Once / At least 14 working days prior to each placement
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Test Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Determination of Bulk Density
label | Document Reference / Applicable Standard - R116 Cl 4.2.2
label | Acceptance Criteria - Do not test asphalt layers less than or equal to 30 mm thickness for insitu air voids. Calculate the characteristic values of insitu air voids in accordance with Annexure R116/K1. Determine Bulk Density by either of the below methods
label | Cores:
label | ○ Take cores in accordance with AS 2891.1.2.
label | ○ When trimming, do not reduce the core layer thickness by more than 5 mm. Determine the bulk density of cores taken in accordance with AS/NZS 2891.9.2.
label | Nuclear density gauge:
label | ○ Take measurements in accordance with AS/NZS 2891.14.2 and AS/NZS 2891.14.3.
label | ○ Determine the bulk density of cores taken for density offset calculations in accordance with AS/NZS 2891.9.2.
label | ○ Determine the density offset separately for every change in nominated mix and specified layer thickness. Verify that the applied density offset is still valid wherever there is a change in site characteristics, such as underlying surface roughness, composition of underlying layer and density of underlying layer.
label | ○ Report the density offset on all test reports.
label | Frequency/ Process Held - Once / Prior to Lot Closure
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Test Results
checkpoint | 3.3 - Determination of Course Thickness
label | Document Reference / Applicable Standard - R116 Cl 4.3
label | Acceptance Criteria - From Cores:
label | ○ Determine the characteristic values and average value of thickness of the Lot using statistical techniques as specified in TfNSW Q from cores taken in accordance with AS 2891.1.2.The cores may be the same as those taken for determination of air voids (refer Clause 4.2), but the core layer thickness is determined prior to trimming of the core.
label | ○ Where the asphalt is placed in one or more layers to form a single course, determine the course thickness by adding the average thickness from cores of the lower and upper layers.
label | ○ For the purpose of determining the course thickness from cores, the core diameter can be less than 95 mm and the test specimen may comprise more than one layer.
label | ○ Calculate the maximum and minimum characteristic values of thickness for the Lot in accordance with Annexure R116/K2.
label | By Survey:
label | ○ Carry out surveys for product conformity in accordance with Specification TfNSW G71 Clause 5.3.3.
label | ○ The average compacted course thickness of each Lot calculated from surveys must be consistent with the average compacted course thickness of the respective Lot determined from cores.
label | Frequency/ Process Held - Once / Prior to Lot Closure
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Test Results
checkpoint | 3.4 - Determination of Course Position
label | Document Reference / Applicable Standard - R116 Cl 4.4
label | Acceptance Criteria - Where finished surface levels are not specified, determine the course position of each Lot by reference to existing pavement surface and road fixtures.
label | Where finished surface levels are specified, measure the course position of each Lot by survey in accordance with TfNSW Q and TfNSW G71 Clause 5.3.3.
label | The survey location of any point on the surface of a course for level determination must be located within 25mm from the corresponding point determined from the Drawings.
label | Frequency/ Process Held - Once / Prior to lot closure
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Survey Report
checkpoint | 3.5 - Determination of Surface Shape
label | Document Reference / Applicable Standard - R116 Cl 4.5
label | Acceptance Criteria - Determine and report the surface shape in accordance with Test Method TfNSW T183.
label | The maximum Lot size must be in accordance with TfNSW Q but extended to include the adjacent longitudinal joints, transverse joints and tie-ins.
label | Prior to placing the next overlying course, determine the surface shape in accordance with Clause 4.5.1. Deal with any conformities in accordance with Clause 5.8.1.
label | Frequency/ Process Held - Once / Prior to lot closure
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Shape Report
checkpoint | 3.6 - Determination of Ride Quality
label | Document Reference / Applicable Standard - R116 Cl 4.6
label | Acceptance Criteria - See subcontractor ITP
label | Frequency/ Process Held - Once / Prior to lot Closure
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - ITP
section | 4. Conformity
checkpoint | 4.1 - Rectification of Non-Conforming Lots
label | Document Reference / Applicable Standard - R116 Cl 5.8.5
label | Acceptance Criteria - Submit to the principle the non-conformity report and details of your proposal to rectify or replace the lot prior to undertaking rectification works or replacement of a non-conforming lot.
label | Frequency/ Process Held - Once / Prior to lot Closure
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - NCR
holdpoint | AUTHORITY HOLDPOINT
section | Review by Project Manager
checkpoint-no-value | Review by Project Manager
button | Any non-conformances? | YES, NO
textbox | No's:
button | Closed Out | YES, NO
button | All work has been satisfactorily completed. | YES, NO
textbox | Name:
signoff | Add signature
section | Lot Verification
checkpoint | Lot Verification complete
textbox | Lot Verified By:
textbox | Lot Closed Date:
button | Submitted to Client | Yes, No, N/A
button | Reviewed by Client | Yes, No, N/A
textbox | Submission Comments:
section-nested-checklists | NCR
checklist | ITC 17 - R106 Sprayed Bituminous Surfacing (with Cutback Bitumen) Rev1 | itp |  |  |  |  | ITC 17 - R106 Sprayed Bituminous Surfacing (with Cutback Bitumen) Rev1
section | Lot Information
checkpoint | Lot Information complete
textbox | Lot Opened On
textbox | Date of Works
textbox | Lot Type
textbox | Start Chainage
textbox | End Chainage
textbox | Offset
textbox | Control Line
section | 1. Material Requirements
checkpoint | 1.1 - Bituminous Materials
label | Document Reference / Applicable Standard - R106 Cl 2.1
label | Acceptance Criteria - Provide documentary evidence of the binder conformity for each delivery used in the work. Also sample at the point of delivery and provide a representative sample of the delivered binder to the Principal.
label | Do not heat binder above 190oC or the manufacturer’s written recommendations, whichever is the lesser.
label | Implement procedures for storage and handling of binder that ensure prevention of segregation and contamination of the binder by flushing liquids or other materials.
label | Frequency/ Process Held - Once / Prior to supply of Bituminous Materials
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Evidence of Conformity
checkpoint | 1.2 - Aggregate Precoating Agent and Bitumen Adhesion Agent
label | Document Reference / Applicable Standard - R106 Cl 2.2, TfNSW 3258, TfNSW 3259
label | Acceptance Criteria - Aggregate precoating agents must conform to Specification TfNSW 3258. Bitumen adhesion agents must conform to Specification TfNSW 3259.
label | Frequency/ Process Held - Once / Prior to supply of aggregate precoating agent and bitumen adhesion agent
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Certificate of Conformity
checkpoint | 1.3 - Aggregate
label | Document Reference / Applicable Standard - R106 Cl 2.4, TfNSW 3151
label | Acceptance Criteria - Obtain test results for each Lot of aggregate, in accordance with TfNSW 3151, before aggregate from the Lot is incorporated in the Works.
label | When requested, provide a sample to the Principal from the same Lot by riffling or quartering your own samples. The amount of material obtained for each sample must be in accordance with the nominal size of the aggregate as per AS 1141.3.
label | Frequency/ Process Held - Once / Prior to supply of aggregates
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Test Results
checkpoint | 1.4 - General Materials and Design of Bituminous Surfacing
label | Document Reference / Applicable Standard - R106 Cl 3
label | Acceptance Criteria - Carry out the design of bituminous surfacing in accordance with TfNSW Form 395A or TfNSW Form 395K as appropriate and submit the design details including all results from texture testing for reseals and ball embedment tests for seals. Design application rates are the "nominated application rates" and materials used for the design are the "nominated materials".
label | Frequency/ Process Held - Once / Prior to placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - TfNSW Form 395A/K
checkpoint | 1.5 - Submission of Nominated Design
label | Document Reference / Applicable Standard - R106 Cl 3.3
label | Acceptance Criteria - Submit to the Principal the nominated design together with certification for the nominated materials at least seven days prior to the commencement of sprayed bituminous surfacing works.
label | Include the following details in the submission:
label | (a) Each constituent material;
label | (b) Verification of conformity of the nominated materials;
label | (c) Endorsement.
label | Frequency/ Process Held - Once / Prior to placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Design Certificate
checkpoint | 1.6 - Sealing Operations using Proposed Design
label | Document Reference / Applicable Standard - R106 Cl 3.3.3
label | Acceptance Criteria - Submit to the principal Documents referred to in Clause 1.2.4 (Project Quality Plan) and the proposed bituminous surfacing design together with certification for the nominated materials and design verification documentation at least seven days prior to the commencement of sprayed bituminous surfacing work.
label | Frequency/ Process Held - Once / 7 working days prior to commencement of sprayed bitumous surfacing work
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Project Quality Plan, Design Verification Documents
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Review of Nominated Application Rates
label | Document Reference / Applicable Standard - R106 Cl 3.4
label | Acceptance Criteria - Submit to the principal the below prior to spray sealing works for each work location: Select the locations where each Lot of aggregate is to be incorporated in the Works.
label | Review the bituminous surfacing design at each location based on the actual ALD test result for the actual aggregate to be used instead of the ALD value of the nominated aggregate and using the appropriate TfNSW 395 design form. The revised application rates are “target application rates”.
label | Frequency/ Process Held - Once / Prior to spray sealing works
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Aggregate Lot Details, Target Application Rates
holdpoint | AUTHORITY HOLDPOINT
section | 2. Process Control
checkpoint | 2.1 - Application of Sprayed Bituminous Surfacing
label | Document Reference / Applicable Standard - R106 Cl 4.2
label | Acceptance Criteria - Carry out sprayed bituminous surfacing so as to:
label | (a) provide a uniform application of binder with adequate adhesion to the underlying surface;
label | (b) provide a uniform cover of aggregate particles (except for primes); and
label | (c) achieve effective bond between binder and aggregate (except for primes).
label | Frequency/ Process Held - Once / Prior to Application
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Project Quality Plan
checkpoint | 2.2 - Process Control Chart
label | Document Reference / Applicable Standard - R106 Cl 4.3
label | Acceptance Criteria - Use process control charts, as shown in Annexure R106/E, for binder application rate for work where 10 or more sprayer runs greater than 1,000 litres are required. You may develop additional process control charts for the purpose of managing job specific risk(s) to quality. The process control charts must show the specified tolerances and plot the differences of individual results from the target value.
label | Take corrective action if any point is between 2% and 5% (inclusive) above or below the target over 5 successive runs.
label | Frequency/ Process Held - Once / Prior to Lot Closure
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Process Control Chart
checkpoint | 2.3 - Work Records
label | Document Reference / Applicable Standard - R106 Cl 4.4
label | Acceptance Criteria - Record the particulars of the work performed on TfNSW Form 500A or 500C (as appropriate).
label | Record details of primer, primerbinder, binder and aggregate applied immediately after every sprayer run. Each form must be signed by your representative as a true record of the work performed. Supply the principal with a copy of each completed form.
label | Frequency/ Process Held - Once / Prior to Lot Closure
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - TfNSW Form 500A/C
section | 3. Conditions for Commencement
checkpoint | 3.1 - Preparation of Pavement Surface
label | Document Reference / Applicable Standard - R106 Cl 5.2
label | Acceptance Criteria - Before the application of primer, primerbinder or binder, sweep the pavement surface using a rotary road broom or suction broom to provide a uniformly clean surface. If necessary, carry out additional sweeping by hand, using stiff bass or similar brooms. Sweeping must extend at least 300 mm beyond each edge of the area to be sprayed.
label | Where sealing work is carried out on localised areas and/or half pavement widths, remove any remaining loose material from the pavement surface immediately adjacent to the swept areas.
label | Remove adherent patches of foreign material from the surface of the pavement. Mask or remove raised pavement markers.
label | Measure and record pavement temperatures at regular intervals during work.
label | Place a spirit or mercury-in-glass thermometer or other suitable type of thermometer in direct contact with the pavement.
label | Undertake the spraying of primers, primerbinders and binders only if the pavement temperature has been at or above 10ºC for at least one hour before commencement of spraying and does not fall below the specified minimum pavement temperature for spraying during the period of spraying.
label | Do not spray wet pavement or while rain appears imminent or during strong winds or dust storms.
label | Frequency/ Process Held - Once / Prior to application
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
section | 4. Application of Sprayed Sealing, Binder and Aggregates
checkpoint | 4.1 - Application of Sprayed Bituminous Surfacing
label | Document Reference / Applicable Standard - R106 Cl 6
label | Acceptance Criteria - Apply primer, primerbinder and binder by using a sprayer. The sprayer must have a current Sprayer Certificate (TfNSW Form 354) issued or accepted by Transport for NSW.
label | Bitumen must be within the temperature range shown in Table R106.2 when cutter oil is incorporated.
label | Cutback bitumen must be within the temperature range shown in Table R106.3 at the time of spraying.
label | Frequency/ Process Held - Once / Prior to Application of Spray Seal
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - TfNSW Form 354
checkpoint | 4.2 - Incorporation of Cutter Oil, Flux Oil and Bitumen Adhesion Agent
label | Document Reference / Applicable Standard - R106 Cl 6.7
label | Acceptance Criteria - Determine and record the proportion of cutter oil required for each sprayer load, using TfNSW Form 382 for seals and reseals and TfNSW Form 395A for primes and primerseals.
label | Where flux oil is to be included, add it to the bitumen in the sprayer and circulate the mixture at a rate of at least 700 litres per minute for fifteen minutes before spraying.
label | Where bitumen adhesion agent is to be included, add it to the bitumen in the sprayer and circulate the mixture at a rate of at least 700 litres per minute for fifteen minutes before spraying.
label | Frequency/ Process Held - Once / Prior to incorporation of cutter oil, flux oil and adhesion agent
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - TfNSW Form 382 TfNSW Form 395A
checkpoint | 4.3 - Application of Primer, Primerbinder and Binder
label | Document Reference / Applicable Standard - R106 Cl 7
label | Acceptance Criteria - Limit the area to be sprayed with primerbinder or binder to the area that can be covered with aggregate at the target application rate within fifteen minutes of spraying bitumen or cutback bitumen.
label | The class and grade of primer and primerbinder must be as specified in Annexure R106/A.
label | Apply nominated and target application rates and quantities of primer and primerbinder to the whole material, including cutter oil, measured at 15ºC.
label | After application of a primer, a period of at least 48 hours, or such longer period as determined to be necessary for the primer to become completely dry, must elapse before the binder for a seal is applied. Keep all traffic off the primed surface.
label | Where bitumen adhesion agent and/or cutter oil have been added to the binder, adjust the application rate of the total binder at 15ºC, using TfNSW Form 500A,
label | The class of bitumen or grade of cutback bitumen must be as specified in Annexure R106/A.
label | Base nominated and target application rates and quantities of binder on the volumes of bitumen measured at a temperature of 15ºC and do not include any bitumen adhesion agent and/or cutter oil. If flux oil has been added to the bitumen, include the quantity of flux oil as part of the binder.
label | Where bitumen adhesion agent and/or cutter oil have been added to the binder, adjust the application rate of the total binder at 15ºC to allow for the quantities of bitumen adhesion agent and/or cutter oil in the mixture.
label | Determine the hot application rate of total binder, including bitumen adhesion agent and/or cutter oil, using TfNSW Form 382.
label | Where refinery cutback bitumen is used as the binder, increase the target application rate of binder to allow for the cutter oil in the mixture in accordance with Table R106.4.
label | Frequency/ Process Held - Once / Prior to application of primer, primerbinder and binder
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - TfNSW Form 500A / TfNSW Form 382
checkpoint | 4.4 - Application and Incorporation of Aggregate
label | Document Reference / Applicable Standard - R106 Cl 8
label | Acceptance Criteria - Use only precoated aggregate for seals and primerseals.
label | Apply the aggregate of the specified nominal size and at the target aggregate application rate.
label | The method to determine the actual aggregate spread rate must conform to Test Method TfNSW T274 or a method approved by the Principal and detailed in the PROJECT QUALITY PLAN.
label | Report the aggregate spread rate as actual rate using TfNSW Form 500C.
label | After the aggregate has been applied to each section of the work, carry out initial rolling with two or more dual axle smooth pneumatic tyred multi-wheel rollers of mass greater than 7 tonnes without ballast and minimum tyre pressure of 550 kPa. Continue initial rolling until the aggregate is firmly embedded in the primerbinder or binder.
label | Roll the cover aggregate with pneumatic tyred multi-wheel rollers at not less than eight passes within one hour of spraying at every point on the surface.
label | Frequency/ Process Held - Once / Prior to incorporation of aggregate
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - TfNSW Form 500C Project Quality Plan
checkpoint | 4.5 - Sweeping and Loose Aggregate Removal (10mm and 14mm Seals / Reseals Only)
label | Document Reference / Applicable Standard - R106 Cl 9
label | Acceptance Criteria - After final sweeping and prior to the work being opened to traffic at the pre-existing signposted speed, the number of loose aggregate particles (per m2) not including aggregate particles from any scatter coat, determined in accordance with Test Method TfNSW T277 must not exceed the values shown in Table R106.5:
label | Areas where speed limits exceed 60 km/h and that are opened to traffic prior to final sweeping must have temporary speed zone ‘loose stones’ and ‘slippery’ warning signs and temporary 60 km/h speed zoning in place until the maximum allowable loose aggregate requirement is met.
label | Notify the principle of the time and location prior to commencement of final sweeping and loose aggregate measurements prior to opening to traffic.
label | Frequency/ Process Held - Once / Prior to Lot Closure
label | Inspection - ACPL - W
label | Inspection - Client - W
label | Verifying Records - Visual Inspection
section | Review by Project Manager
checkpoint-no-value | Review by Project Manager
button | Any non-conformances? | YES, NO
textbox | No's:
button | Closed Out | YES, NO
button | All work has been satisfactorily completed. | YES, NO
textbox | Name:
signoff | Add signature
section | Lot Verification
checkpoint | Lot Verification complete
textbox | Lot Verified By:
textbox | Lot Closed Date:
button | Submitted to Client | Yes, No, N/A
button | Reviewed by Client | Yes, No, N/A
textbox | Submission Comments:
section-nested-checklists | NCR
checklist | ITC 18 - R107 Sprayed Bituminous Surfacing (with Polymer Modified Binder) Rev1 | itp |  |  |  |  | ITC 18 - R107 Sprayed Bituminous Surfacing (with Polymer Modified Binder) Rev1
section | Lot Information
checkpoint | Lot Information complete
textbox | Lot Opened On
textbox | Date of Works
textbox | Lot Type
textbox | Start Chainage
textbox | End Chainage
textbox | Offset
textbox | Control Line
section | 1. Material Requirements
checkpoint | 1.1 - Bituminous Materials and Polymer Modified Binder
label | Document Reference / Applicable Standard - R107 Cl 2.1
label | Acceptance Criteria - Provide documentary evidence of the binder conformity for each delivery used in the work. Also sample at the point of delivery and provide a representative sample of the delivered binder to the Principal.
label | The binder for seals and reseals must be in accordance with Annexure R107/A1 and must conform to Specification TfNSW 3252.
label | Torsional recovery and softening point must also conform to the requirements of Annexure R107/A1.2 at the point of delivery.
label | Do not heat binder above 190oC or the manufacturer’s written recommendations, whichever is the lesser.
label | Implement procedures for storage and handling of binder that ensure prevention of segregation and contamination of the binder by flushing liquids or other materials.
label | Frequency/ Process Held - Once / Prior to supply of Bituminous Materials
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Evidence of Conformity
checkpoint | 1.2 - Aggregate Precoating Agent and Bitumen Adhesion Agent
label | Document Reference / Applicable Standard - R107 Cl 2.2, TfNSW 3268, TfNSW 3269
label | Acceptance Criteria - Aggregate precoating agents must conform to Specification TfNSW 3268 for the grade of polymer modified binder specified in Annexure R107/A.
label | Bitumen adhesion agents must conform to Specification TfNSW 3269 for the grade of polymer modified binder specified in Annexure R107/A.
label | Frequency/ Process Held - Once / Prior to supply of aggregate precoating agent and bitumen adhesion agent
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Certificate of Conformity
checkpoint | 1.3 - Aggregate
label | Document Reference / Applicable Standard - R107 Cl 2.4, TfNSW 3151
label | Acceptance Criteria - Obtain test results for each Lot of aggregate, in accordance with TfNSW 3151, before aggregate from the Lot is incorporated in the Works.
label | When requested, provide a sample to the Principal from the same Lot by riffling or quartering your own samples. The amount of material obtained for each sample must be in accordance with the nominal size of the aggregate as per AS 1141.3.
label | Frequency/ Process Held - Once / Prior to supply of aggregates
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Test Results
checkpoint | 1.4 - General Materials and Design of Bituminous Surfacing
label | Document Reference / Applicable Standard - R107 Cl 3
label | Acceptance Criteria - Carry out the design of bituminous surfacing in accordance with TfNSW Form 395K as appropriate and submit the design details including all results from texture testing for reseals and ball embedment tests for seals. Design application rates are the "nominated application rates" and materials used for the design are the "nominated materials".
label | Frequency/ Process Held - Once / Prior to placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - TfNSW Form 395K
checkpoint | 1.5 - Submission of Nominated Design
label | Document Reference / Applicable Standard - R107 Cl 3.3
label | Acceptance Criteria - Submit to the Principal the nominated design together with certification for the nominated materials at least seven days prior to the commencement of sprayed bituminous surfacing works.
label | Include the following details in the submission:
label | (a) Each constituent material;
label | (b) Verification of conformity of the nominated materials;
label | (c) Endorsement.
label | Frequency/ Process Held - Once / Prior to placement
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Design Certificate
checkpoint | 1.6 - Sealing Operations using Proposed Design
label | Document Reference / Applicable Standard - R107 cl 3.2.3
label | Acceptance Criteria - Submit to the principal Documents referred to in Clause 1.2.4 (Project Quality Plan) and the proposed bituminous surfacing design together with certification for the nominated materials and design verification documentation at least seven days prior to the commencement of sprayed bituminous surfacing work.
label | Frequency/ Process Held - Once / 7 working days prior to commencement of sprayed bitumous surfacing work
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Project Quality Plan, Design Verification Documentation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Review of Nominated Application Rates
label | Document Reference / Applicable Standard - R107 Cl 3.3
label | Acceptance Criteria - Submit to the principal the below prior to spray sealing works for each work location: Select the locations where each Lot of aggregate is to be incorporated in the Works.
label | Review the bituminous surfacing design at each location based on the actual ALD test result for the actual aggregate to be used instead of the ALD value of the nominated aggregate and using the appropriate TfNSW 395 design form. The revised application rates are “target application rates”.
label | Frequency/ Process Held - Once / Prior to spray sealing works
label | Inspection - ACPL - H
label | Inspection - Client - H
label | Verifying Records - Aggregate Lot Details, Target Application Rates
holdpoint | AUTHORITY HOLDPOINT
section | 2. Process Control
checkpoint | 2.1 - Application of Sprayed Bituminous Surfacing
label | Document Reference / Applicable Standard - R107 Cl 4.2
label | Acceptance Criteria - Carry out sprayed bituminous surfacing so as to:
label | (a) provide a uniform application of binder with adequate adhesion to the underlying surface;
label | (b) provide a uniform cover of aggregate particles (except for primes); and
label | (c) achieve effective bond between binder and aggregate (except for primes).
label | Frequency/ Process Held - Once / Prior to Application
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Project Quality Plan
checkpoint | 2.2 - Work Records
label | Document Reference / Applicable Standard - R107 Cl 4.4
label | Acceptance Criteria - Record the particulars of the work performed on TfNSW Form 500E.
label | Record details of primer, primerbinder, binder and aggregate applied immediately after every sprayer run. Each form must be signed by your representative as a true record of the work performed. Supply the principal with a copy of each completed form.
label | Frequency/ Process Held - Once / Prior to Lot Closure
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - TfNSW Form 500E
section | 3. Conditions for Commencement
checkpoint | 3.1 - Preparation of Pavement Surface
label | Document Reference / Applicable Standard - R107 Cl 5.2
label | Acceptance Criteria - Before the application of primer, primerbinder or binder, sweep the pavement surface using a rotary road broom or suction broom to provide a uniformly clean surface. If necessary, carry out additional sweeping by hand, using stiff bass or similar brooms. Sweeping must extend at least 300 mm beyond each edge of the area to be sprayed.
label | Where sealing work is carried out on localised areas and/or half pavement widths, remove any remaining loose material from the pavement surface immediately adjacent to the swept areas.
label | Remove adherent patches of foreign material from the surface of the pavement. Mask or remove raised pavement markers.
label | Measure and record pavement temperatures at regular intervals during work.
label | Place a spirit or mercury-in-glass thermometer or other suitable type of thermometer in direct contact with the pavement.
label | Undertake spraying of polymer modified binders only if the pavement temperature has been at or above 20oC for at least one hour before commencement of spraying and does not fall below the specified minimum pavement temperature for spraying during the period of spraying.
label | Do not spray wet pavement or while rain appears imminent or during strong winds or dust storms.
label | Frequency/ Process Held - Once / Prior to application
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - Visual Inspection
section | 4. Application of Spray Sealing, Binder and Aggregates
checkpoint | 4.1 - Application of Sprayed Bituminous Surfacing
label | Document Reference / Applicable Standard - R107 Cl 6
label | Acceptance Criteria - Apply the binder by using a sprayer. The sprayer must have a current Sprayer Certificate (TfNSW Form 354) issued or accepted by Transport for NSW.
label | Measure and record the temperature of the polymer modified binder using a thermometer or other suitable means, accurate to within 2.5% over the range 100-240C. If the temperature of the binder is below the minimum temperature recommended by the manufacturer of the polymer modified binder, the binder may be heated providing safe heating practices are adopted. Do not use burners unless the level of the material in the heating tank is at least 250 mm above the tops of the heating tubes.
label | Where bitumen adhesion agent, cutter oil or flux oil is to be included, add it to the polymer modified binder in the sprayer and circulate the mixture at a rate of at least 700 litres per minute for fifteen minutes before spraying.
label | Frequency/ Process Held - Once / Prior to Application of Spray Seal
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - TfNSW Form 354
checkpoint | 4.2 - Application of Polymer Modified Binder
label | Document Reference / Applicable Standard - R107 Cl 7
label | Acceptance Criteria - Limit the area to be sprayed to the area that can be covered with aggregate at the target application rate and rolled initially within five minutes of spraying polymer modified binder.
label | Do not spray polymer modified binder over a prime until at least 48 hours after spraying the primer or such longer period as required for the primer to become completely dry.
label | Do not spray polymer modified binder over a primerseal until at least twelve months after spraying the primerbinder unless the hardness of the primerseal measured using Test Method TfNSW T271 is less than 2.5 mm.
label | The type of polymer modified binder must be as specified in Annexure R107/A1.
label | Base nominated and target application rates and quantities of polymer modified binder on the volumes of polymer modified binder measured at a temperature of 15C and do not include any bitumen adhesion agent or added oils.
label | Where bitumen adhesion agent and/or cutter oil has been added to the polymer modified binder, adjust the application rate of the total binder at 15C to allow for the quantity of additives in the mixture.
label | Determine the hot application rate of total polymer modified binder, including bitumen adhesion agent and cutter oil, using the appropriate multiplier from TfNSW Form 500E.
label | Frequency/ Process Held - Once / Prior to application of Polymer Modified Binder
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - TfNSW Form 500E
checkpoint | 4.3 - Application and Incorporation of Aggregate
label | Document Reference / Applicable Standard - R107 Cl 8
label | Acceptance Criteria - Use only precoated aggregate.
label | The application of aggregate must proceed after spraying is commenced and must be completed and rolled initially within five minutes of spraying the binder.
label | Apply the aggregate of the specified nominal size and at the target aggregate application rate.
label | The method to determine the actual aggregate spread rate must conform to Test Method TfNSW T274 or a method approved by the principal and detailed in the PROJECT QUALITY PLAN.
label | Report the aggregate spread rate as actual rate using TfNSW Form 500E.
label | After the aggregate has been applied to each section of the work, carry out initial rolling with two or more dual axle smooth pneumatic tyred multi-wheel rollers of mass greater than 7 tonnes without ballast and minimum tyre pressure of 550 kPa. Continue initial rolling until the aggregate is firmly embedded in the binder
label | Roll the cover aggregate with pneumatic tyred multi-wheel rollers at not less than eight passes within one hour of spraying at every point on the surface.
label | Frequency/ Process Held - Once / Prior to incorporation of aggregate
label | Inspection - ACPL - S
label | Inspection - Client - S
label | Verifying Records - TfNSW Form 500E Project Quality Plan
checkpoint | 4.4 - Sweeping and Loose Aggregate Removal (10mm and 14mm Seals / Reseals Only)
label | Document Reference / Applicable Standard - R107 Cl 9
label | Acceptance Criteria - After final sweeping and prior to the work being opened to traffic at the pre-existing signposted speed, the number of loose aggregate particles (per m2) not including aggregate particles from any scatter coat, determined in accordance with Test Method TfNSW T277 must not exceed the values shown in Table R107.1:
label | Areas where speed limits exceed 60 km/h and that are opened to traffic prior to final sweeping must have temporary speed zone ‘loose stones’ and ‘slippery’ warning signs and temporary 60 km/h speed zoning in place until the maximum allowable loose aggregate requirement is met.
label | Notify the principle of the time and location prior to commencement of final sweeping and loose aggregate measurements prior to opening to traffic.
label | Frequency/ Process Held - Once / Prior to Lot Closure
label | Inspection - ACPL - W
label | Inspection - Client - W
label | Verifying Records - Visual Inspection
section | Review by Project Manager
checkpoint-no-value | Review by Project Manager
button | Any non-conformances? | YES, NO
textbox | No's:
button | Closed Out | YES, NO
button | All work has been satisfactorily completed. | YES, NO
textbox | Name:
signoff | Add signature
section | Lot Verification
checkpoint | Lot Verification complete
textbox | Lot Verified By:
textbox | Lot Closed Date:
button | Submitted to Client | Yes, No, N/A
button | Reviewed by Client | Yes, No, N/A
textbox | Submission Comments:
section-nested-checklists | NCR