## ITP Cover Page
Sub-Soil Inspection and Test Plan
Project: Wellesley St Bus Interchange - WSBI
Number and Revision: DN1211 - 007 - Rev 00
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Wellesley St Bus Interchange - WSBI |  |  |  |  | ITP Number: |  |  | 007
Project Number: |  |  | DN1211 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Subsoil Drainage |  |  |  |  | Revision: | 1000 |  | 00
Contract Number: |  |  | WSBI - DN1211 |  |  |  |  | Drawing Sets: |  |  | Stormwater and Kerbing
Customer: |  |  | Auckland Transport |  |  |  |  | Specification: |  |  | WSBI Technical Specification, Ref: 522356-W00001-SPE-MC-0001
Quality Specified:
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
IFC | Draft for Review | 2024-09-17 |  | R.Collier |  | Sub-Soil ITP |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | DES | Designer
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Glen Maria |  |  | Glen Maria |  | 2024-07-17 | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP
Sub-Soil Inspection and Test Plan
Project: Wellesley St Bus Interchange - WSBI
Number and Revision: DN1211 - 007 - Rev 00
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity |  | Downer Conformance of Compliance Signoff
[6 empty] | Activity | By | Downer Signature | Date | MSQA signature (Blank as Req.) | Engineer Rep Signature (Blank as req.) | Comments / Closeout Details
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements | [11 empty] | IFC
3.01.01 | Construction Pack | Submit a Construction Pack including a Methodology and JSEA to the Engineer before works | Downer | Construction Pack | Submit 5 days prior to commencement of works | H | PE | H |  |  | R |  | 0
3.02.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV | H
3.01.02 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE | H
3.02.03 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE | H
3.01.03 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE | H |  |  | R
3.02.04 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE | H
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
IFC | General Material Approval
4.01.01 | Material Properties | Filter Aggregate, pipes and filter fabric shall comply with TNZ F/2 for non‐wrapped drains and TNZ F/6 for fabric wrapped drains. Filter aggregates specified in TNZ F/5 shall not be used. Pipes supplied and installed as specified in drawings | Aurecon Civil Spec Section 16.5 TNZ F/2, F/6 ATCoP | Supplier Records | Prior to use Checked on Delivery | H | PE | H |  | R | R
4.01.02 | Drainage Aggregate | Shall be NZTA F/2 or F/6 Drainage Aggregate chip (20/7mm) DN1211-DOW-RFI - 0048 | Aurecon Civil Spec Section 16.6.3 RFI-0048 | MAR record | Pior to Use Delivery Dockets | H | PE | H |  | R
4.01.03 | No-Fines Concrete | As per TfNSW 3222, for aggregate size distribution to be 26.5 mm @ 100 % 19 mm @ 95 - 100% 9.5 mm @ 0 - 5% | Aurecon Civil Spec Section 14,17.11.7 | Supplier Records Concrete Dockets | As required | H | PE | H |  | R
SECTION 5 – CONSTRUCTION ACTIVITY – DRAINAGE INSTALLATION
5.01 | Excavation
5.01.01 | Subsoil trenching | Construct subsoil trenches as per TNZ F/2 or Approved 20/7 drainage chip, falling towards drainage outlet. Install Geotextile filter fabric at base of trench where specified. Drainage aggregate bedding installed at trench base; 75mm thick for Ø=75mm pipe and 100mm thick for Ø=100mm pipe. Suvey Set-out position as per deign unless design clash changes required | Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP | QA Checksheet | Inspect on regular intervals | I | SE | I
5.01.02 | Subsoil installation | In absence of subsoil depths in drawings: Install subsoils at 600mm below FL forsealed roads and traffickable areas, and at 450mm for non‐trafficked areas. Subsoils laid straight, falling towards drainage outlet as per TNZ F/2 and drawing | Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP | QA Checksheet | Inspect on regular intervals | W | SE | W |  | R | I
5.01.03 | Trench Dimensions | Excavate trench to lines, levels, width and gradients shown on drawings. Trench of sufficient width to permit installation of all materials and fittings. Pipes minimum 100mm from trench wall. | Aurecon Civil Spec Section 16.6.2 | QA Checksheet | Inspect on regular intervals | W | SE | W
5.01.04 | Backfill Placement | Backfill with 150mm + 150mm depth of drainage filter material above pipe, hand tamped Backfill and plate compact remainder to FL as specified in drawing | Aurecon Civil Spec 18.6.3 TNZ F/2 ATCoP | QA Checksheet | Inspect on regular intervals | I | SE | I
5.01.05 | Flow Test | Visual inspection of water flow. | Visual Inspection | ITP Sign off | Once per Zone | H | SE | H |  | R | R
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | Site Post Construction Activities
6.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE | H |  | R | H
6.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting. Asbuilts to include type, size, quantity, location and level of subsoil laid. | Downer | Records | Post construction | H | SV | H |  | R | H
6.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Relevant change correspondence to be included. | Downer | Redlines | Post construction | H | PE | H |  | R | H
6.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE | H |  | R | H