## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1211-007 ITP Subsoil Drainage Rev 0 | itp |  |  |  |  | DN1211-007 ITP Subsoil Drainage Rev 0
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
label | Acceptance/Conformance criteria - Submit a Construction Pack including a Methodology and JSEA to the Engineer before works
label | Standard/Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 5 days prior to commencement of works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | MSQA Signature -
label | Engineer Rep Signature - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.02.02 - Survey Setout
label | Acceptance/Conformance criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard/Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
label | Downer Signature - H
label | MSQA Signature -
label | Engineer Rep Signature -
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.02 - Service Location
label | Acceptance/Conformance criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard/Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Downer Signature - H
label | MSQA Signature -
label | Engineer Rep Signature -
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.02.03 - Internal Permits
label | Acceptance/Conformance criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard/Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Downer Signature - H
label | MSQA Signature -
label | Engineer Rep Signature -
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.03 - External Permits
label | Acceptance/Conformance criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard/Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | MSQA Signature -
label | Engineer Rep Signature - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.02.04 - Approved Construction Drawings
label | Acceptance/Conformance criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard/Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | MSQA Signature -
label | Engineer Rep Signature -
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Material Properties
label | Acceptance/Conformance criteria - Filter Aggregate, pipes and filter fabric shall comply with TNZ F/2 for non‐wrapped drains and TNZ F/6 for fabric wrapped drains.
label | ○ Filter aggregates specified in TNZ F/5 shall not be used.
label | ○ Pipes supplied and installed as specified in drawings
label | Standard/Specification - Aurecon Civil Spec Section 16.5 TNZ F/2, F/6 ATCoP
label | Verifying Document - Supplier Records
label | Frequency - Prior to use, Checked on Delivery
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | MSQA Signature - R
label | Engineer Rep Signature - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.02 - Drainage Aggregate
label | Acceptance/Conformance criteria - Shall be NZTA F/2 or F/6
label | ○ Drainage Aggregate chip (20/7mm) DN1211-DOW-RFI - 0048
label | Standard/Specification - Aurecon Civil Spec Section 16.6.3 RFI-0048
label | Verifying Document - MAR record
label | Frequency - Pior to Use, Delivery Dockets
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | MSQA Signature - R
label | Engineer Rep Signature -
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.03 - No-Fines Concrete
label | Acceptance/Conformance criteria - As per TfNSW 3222, for aggregate size distribution to be
label | ○ 26.5 mm @ 100 %
label | ○ 19 mm @ 95 - 100%
label | ○ 9.5 mm @ 0 - 5%
label | Standard/Specification - Aurecon Civil Spec Section 14,17.11.7
label | Verifying Document - Supplier Records, Concrete Dockets
label | Frequency - As required
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | MSQA Signature - R
label | Engineer Rep Signature -
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 5 – CONSTRUCTION ACTIVITY – DRAINAGE INSTALLATION
checkpoint | 5.01.01 - Subsoil trenching
label | Acceptance/Conformance criteria - Construct subsoil trenches as per TNZ F/2 or Approved 20/7 drainage chip, falling towards drainage outlet. Install Geotextile filter fabric at base of trench where specified.
label | ○ Drainage aggregate bedding installed at trench base; 75mm thick for Ø=75mm pipe and 100mm thick for Ø=100mm pipe.
label | ○ Suvey Set-out position as per deign unless design clash changes required
label | Standard/Specification - Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP
label | Verifying Document - QA Checksheet
label | Frequency - Inspect on regular intervals
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
label | Downer Signature - I
label | MSQA Signature -
label | Engineer Rep Signature -
checkpoint | 5.01.02 - Subsoil installation
label | Acceptance/Conformance criteria - In absence of subsoil depths in drawings: Install subsoils at 600mm below FL forsealed roads and traffickable areas, and at 450mm for non‐trafficked areas.
label | ○ Subsoils laid straight, falling towards drainage outlet as per TNZ F/2 and drawing
label | Standard/Specification - Aurecon Civil Spec Section 16.6 TNZ F/2 ATCoP
label | Verifying Document - QA Checksheet
label | Frequency - Inspect on regular intervals
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
label | Downer Signature - W
label | MSQA Signature - R
label | Engineer Rep Signature - I
checkpoint | 5.01.03 - Trench Dimensions
label | Acceptance/Conformance criteria - Excavate trench to lines, levels, width and gradients shown on drawings.
label | ○ Trench of sufficient width to permit installation of all materials and fittings.
label | ○ Pipes minimum 100mm from trench wall.
label | Standard/Specification - Aurecon Civil Spec Section 16.6.2
label | Verifying Document - QA Checksheet
label | Frequency - Inspect on regular intervals
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
label | Downer Signature - W
label | MSQA Signature -
label | Engineer Rep Signature -
checkpoint | 5.01.04 - Backfill Placement
label | Acceptance/Conformance criteria - Backfill with 150mm + 150mm depth of drainage filter material above pipe, hand tamped
label | ○ Backfill and plate compact remainder to FL as specified in drawing
label | Standard/Specification - Aurecon Civil Spec 18.6.3 TNZ F/2 ATCoP
label | Verifying Document - QA Checksheet
label | Frequency - Inspect on regular intervals
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
label | Downer Signature - I
label | MSQA Signature -
label | Engineer Rep Signature -
checkpoint | 5.01.05 - Flow Test
label | Acceptance/Conformance criteria - Visual inspection of water flow.
label | Standard/Specification - Visual Inspection
label | Verifying Document - ITP Sign off
label | Frequency - Once per Zone
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Downer Signature - H
label | MSQA Signature - R
label | Engineer Rep Signature - R
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Construction Record Compilation
label | Acceptance/Conformance criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard/Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
label | Downer Signature - H
label | MSQA Signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.02 - Survey Records
label | Acceptance/Conformance criteria - Ensure all items have been surveyed and records are assembled for asbuilting. Asbuilts to include type, size, quantity, location and level of subsoil laid.
label | Standard/Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
label | Downer Signature - H
label | MSQA Signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.03 - Redline Drawings
label | Acceptance/Conformance criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Relevant change correspondence to be included.
label | Standard/Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | MSQA Signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.04 - Defect, Snag and Punch List
label | Acceptance/Conformance criteria - Update the project Defect, Snag and Punch List Register
label | Standard/Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
label | Downer Signature - H
label | MSQA Signature - R
label | Engineer Rep Signature - H
holdpoint | AUTHORITY HOLDPOINT