## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Concrete Pre-pour Inspection |  | Concrete Pre-pour Inspection | 29f4e71f-35f0-4034-a2e5-ded8ecbaf6dd
| section | Preliminary
| checkpoint | Engineer notified of pour
98ffea72-4951-5484-a1cb-4a448e1233c5 | textbox | Date
7006f770-0251-5e19-ad15-3a83db9ada77 | textbox | Drawing Number and Revision
| section | Formwork
| checkpoint | Installed as per formwork design
| checkpoint | Permit to load issued
| checkpoint | Dimensions correct
| checkpoint | Position and orientation correct
| checkpoint | Forms vertical, plumb and true
| checkpoint | Forms coated with release agent
| checkpoint | Forms clean and clear of debris
| checkpoint | Joints sealed
| checkpoint | Pour level marks
| section | Reinforcement
| checkpoint | Correct grade reinforcement
| checkpoint | Correct bar size
| checkpoint | Correct number of bars
| checkpoint | Correct spacing
| checkpoint | Starters bars included
| checkpoint | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
| checkpoint | Correct weld lengths (min 10 x bar diameter)
| checkpoint | Correct lap length (min 50 x bar diamenter or as per drawing)
| checkpoint | Correct lap position (staggered appropriately)
| checkpoint | Longitudinal bars terminate with 90 or 180 deg hook)
| checkpoint | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
| checkpoint | Reinforcing adequately tied
| checkpoint | Chairs or spacers fixed in place
| section | Embedded items
| checkpoint | Block-outs, ducts & cast in items installed
| checkpoint | Correct position, level & alignment
| checkpoint | Securely fixed in place
| section | Construction Joints
| checkpoint | Correct location
| checkpoint | Adequately prepped
| checkpoint | Joint board installed
| checklist | ITP - 107 - Pavement Drains |  | ITP - 107 - Pavement Drains | 6a922d6e-460a-401f-a8b8-39505e8a4626
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
eef00716-4e5d-5b03-b172-716ad54d042a | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
765b1048-c088-5b6f-9623-8c5346ff99e7 | note | Standard / Specification - Downer
397a1e6d-4464-5f66-b1bb-bdf001298e8b | note | Verifying Document - Construction Pack
05d4a935-0ef3-5cde-80aa-4d1301943a80 | note | Frequency - Submit 10 days prior to commencement of works
eac0916a-6ddb-5a54-949e-98cefbbc2210 | note | Activity - H
806a65ec-353e-5e0d-935c-204f576001c3 | note | By - PE
| checkpoint | 3.01.02 - Survey Setout
180417cf-f085-5ace-9953-f519ccf1706c | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
96347aea-037b-5640-95a4-1d4dfc132a6e | note | Standard / Specification - Downer
16eacf5e-a788-546e-a0cd-1aedc5ee8570 | note | Verifying Document - Survey Records
be32c357-44f6-529a-8363-67b4f3529304 | note | Frequency - Prior to Works
c4af63f6-c85f-59f1-809e-59bc586c641c | note | Activity - H
f104ef54-18ca-50f8-b622-564b36e5dd3e | note | By - SV
| checkpoint | 3.01.03 - Approved Construction Drawings
c494c038-e47d-5ce7-b618-58b9f20e4c67 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
c6ecdd42-653b-5c87-9072-43a0eadf906c | note | Standard / Specification - Downer
4e3ba869-ecd5-51a9-8e80-40f8a3e0199e | note | Verifying Document - IFC Drawings
988c6302-1576-5fe0-ad37-e6e63e58da1e | note | Frequency - Prior to works start
4d176dba-b452-553e-a533-5a82796a3ab1 | note | Activity - H
526d4aa1-d98f-5698-8a92-deeccd5de232 | note | By - PE
| checkpoint | 3.01.04 - Topographic surveys for measurement
f927db23-c857-5010-bccb-337cc5a5dab9 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
91b1b8ba-eb23-5cb1-89e8-90e6c32ba274 | note | Standard / Specification - PS 2.2.12
795d7fbf-075a-5c81-8f14-b524bc83a870 | note | Verifying Document - As-built
8e12b724-0f78-51b2-bdef-fa392fd5d083 | note | Frequency - Prior to works and Post Works
46002215-7271-508f-b388-aa1c2f73fb15 | note | Activity - H
a41ac510-4c8f-5101-a059-58a692208e38 | note | By - PE
| checkpoint | 3.01.05 - Permits
22e6ad25-092d-5548-a2d8-51e8a1593b0a | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
409b7359-80e8-5acc-9198-5d34ac52ec2d | note | Standard / Specification - ITP Register
1f3e89f2-4480-5fe8-b063-4a578a27d691 | note | Verifying Document - ITP Sign Off
ad52a87c-f310-5834-bdc5-abb31ce9ac1e | note | Frequency - Prior to commencement of construction activity
5eb73539-c018-532f-b744-52ab274ca51f | note | Activity - R
a7fc22a5-8f14-5766-918d-63b3cecf0195 | note | By - SE
| checkpoint | 3.01.06 - Stakeholder Management
6772a3a5-74ae-5849-b0e0-b36ea6baf81f | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
435660c9-5625-5888-837f-0a6f88ce611a | note | Standard / Specification - Project Stakeholder Management Plan
58ea1067-5df3-58c6-9b10-edbf2c8e408c | note | Verifying Document - ITP Sign Off
74cc34a4-f0aa-5202-9a03-dd52ea46867e | note | Frequency - Prior to Construction with continue updates throughout the works
89dcf2fb-9078-588c-aaa1-bf271fd79ee4 | note | Activity - R
96a554b1-43eb-5bc7-8a17-143409cfd62e | note | By - SE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 4.01.01 - Subsoil Pipes
6d376193-63a5-5f57-8e40-316e71973266 | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 100mm diameter complying with NZTA F/5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
34ad6500-373e-5051-9826-4a1d20223e96 | note | Standard / Specification - GWS 3.2.1
bc934418-5005-5ef9-bd0e-73582085601a | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
84cc8e48-b25d-50dd-b493-0872459f881f | note | Frequency - Every Delivery to Site
4d7be173-4c31-5cd2-8ec4-6235ebf15736 | note | Activity - C
c58e9fbc-5f93-5b00-8e1c-6ccd13b803d9 | note | By - SE
| checkpoint | 4.01.02 - Subsoil Drainage Aggregate
fcc12b20-cca2-512b-a937-1f951a99ded4 | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1: App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification: Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate) Test Sieve Aperture (mm) Percentage Passing (%) 53 100 13.2 10 (max)
fa485186-b96a-52c9-9058-24ec2e833fe9 | note | Standard / Specification - GWS 3.2.2 & 3.4
061ef45c-ffd4-58e4-87df-e8fd7f8adeb1 | note | Verifying Document - PSD, CR
b8c5182b-9ee9-5d26-aedc-1ebac092ca1b | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
c09d35b2-6d0a-5e65-8a73-0442d1581335 | note | Activity - C
8aeb1063-a1e3-53e1-bd84-41c3848cad13 | note | By - SE
| checkpoint | 4.01.03 - Filter Cloth
4d00d963-e5b2-5ec4-bdbe-7b83a09ad16d | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
3dbf25b6-cae4-5c3a-8e05-2898bf99e521 | note | Standard / Specification - GWS 3.2.3
c126941f-b768-5b30-ae2e-6798b6457186 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
4c219803-133a-5171-bab3-8ae8749045f5 | note | Frequency - Every Delivery to Site
54eaf21a-b3ea-5116-b8f4-0d0045c266e9 | note | Activity - C
b5976aef-6260-5629-816e-6e4bacaedafe | note | By - SE
| checkpoint | 4.01.04 - Securing Pins
d845c3e0-ef7e-5b4e-838b-d83b5a360f76 | note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and at least 400mm in length
8521468b-b01b-5e26-93aa-3e63694682c7 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
24f277e3-b638-5d86-91c5-3dd99a8884dd | note | Frequency - Every Delivery to Site
335ffb25-ee69-51f3-a9b7-28e2ed59402a | note | Activity - C
9c92a1d5-c2c7-544b-8af9-16d4f18d2241 | note | By - SE
| section | SECTION 5 – CONSTRUCTION ACTIVITY
| checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
6811ea07-5a89-50d9-81a0-240052de7a0d | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line.
ec53cdb7-cc25-54c6-b78e-5e162d0a5055 | note | Standard / Specification - GWS 3.2.2
4fcd2436-ca61-55b6-9fe5-fe0251ec6f08 | note | Verifying Document - Every line
5b1a35ef-fdc0-5fab-867b-ab02e3ba5f75 | note | Frequency - Photos of trench prior to backfill
e8addc07-99ec-5073-b4b5-509d0438c645 | note | Activity - HP
36b45a2b-5f18-58e7-9e19-1aeca008b0c0 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.02 - Trench Backfill
5a6ef704-1262-5cee-8cd3-1ca88e235869 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
3948db19-ece7-585a-af0f-11b4d7488df2 | note | Standard / Specification - GWS 3.3
d255d60e-c712-5220-9d3c-cb1bb86d98e7 | note | Verifying Document - Site Record
facea8de-cba0-5eaa-81b6-121bf1de9fe3 | note | Frequency - Each trench
cfd6590f-8894-55b7-86ae-a17a69dd2407 | note | Activity - I
7c6101e5-bd07-56fa-a1d6-fc30d486d76a | note | By - SE
| checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
e0e0dfdd-c152-5d0c-9412-91a6bd87c0fb | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
bc1e3839-cba4-575f-a42b-a8f7f6333d04 | note | Standard / Specification - GWS 3.6
af9a4333-12f2-5026-b386-959aed450a8a | note | Verifying Document - Site Records
f4c8e8e7-af68-5172-8727-d91b9dd9213b | note | Frequency - Each Subsoil Line
d5c01f6c-5dd3-57ae-a617-02ae9b57ca57 | note | Activity - I
aaed1beb-c26a-539c-a9dd-5c85e83ad979 | note | By - SE
| checkpoint | 5.01.04 - Subsoil Flushing
8d739b34-85cd-547a-8247-18cc3b18c86b | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
1d5f0a20-d2df-5e6f-b48a-0e7cdb078918 | note | Standard / Specification - GWS 3.6
4beb6424-e2fd-57df-a7c9-4d3712506bf3 | note | Verifying Document - Site Records
5719ebbd-4e3f-5c51-a425-06bc997661d4 | note | Frequency - On completion of earthworks
f9a6100d-206f-59c5-b591-faca25ca1a54 | note | Activity - HP
41c18113-5b1c-5d8e-8d40-7bff82d6cc82 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.05 - Survey
73f805ec-1be1-5740-aa84-faa7472fe6ac | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
719cc0d7-da0b-50cf-b857-21dac2d03368 | note | Standard / Specification - Downer
80ec50c7-3501-5099-aad9-d3107d575a5b | note | Verifying Document - Records
38279792-2520-5b5f-ad7e-c1d3dde7b3a6 | note | Frequency - Post construction
9dcc6c76-d7ee-5853-8a71-9bc96d68aa03 | note | Activity - H
0123bb12-7443-55a7-be46-bb5296d14b9d | note | By - SV
| checkpoint | 5.01.06 - Excavation
4f174c16-c79f-5a5f-bc71-b199753d4ed3 | note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate pavement drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
c2c9c1ae-73f5-5d4c-8575-26ff0a4b5f5a | note | Standard / Specification - Downer
6cf18612-24aa-5169-8377-5ee893f5aafa | note | Verifying Document - Records
050f8690-1a18-59af-a187-0ae929cb0cd6 | note | Frequency - Prior to laying filter cloth
59222acb-af43-5e0d-a2a8-9d1ecc17b8de | note | Activity - I
f93a0bce-6383-52de-b82c-c023bba5a452 | note | By - SE
| checkpoint | 5.01.07 - Bedding
2876f6cf-4450-58ef-a4e2-7e7506c0a1eb | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
8da47c77-5900-5d5c-939a-24a45d93b9c8 | note | Standard / Specification - Downer
e1e57d95-3cfa-5486-9252-177719884e87 | note | Verifying Document - Records
99282874-7427-5646-80c4-cf2d5c909736 | note | Frequency - Prior to laying Novacoil
1cde5baa-6f9e-594b-a1a1-92fe408db88b | note | Activity - I
dec6f213-96b0-5480-b5d3-821cf0ca163b | note | By - SE
| checkpoint | 5.01.08 - Joining Pipes
0ef64d31-9581-5189-b3ad-fac7edb017e9 | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
def28e6a-7bc3-51ba-a899-fd9dc500b9c1 | note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
260824f4-3576-52b7-a7c0-82ca028678f3 | note | Frequency - Every join
d30d276f-a5c3-59dc-887d-a339a38e82d2 | note | Activity - I
532c1d45-176c-5ea0-83bb-5e82f111d571 | note | By - SE
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 6.01.01 - Construction Record Compilation
41282f40-d6cb-5103-bf6e-958dd729ff05 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
dd7a487e-b81d-579c-a71f-0077755339d5 | note | Standard / Specification - Downer
1b01aacd-4fa9-5e67-bcee-f13a4f84057c | note | Verifying Document - Records
93c49c84-ab62-5d90-b6fe-8220b0513eb4 | note | Frequency - Post construction
443d80b3-29dc-5bc2-9371-f8aa81bb76cb | note | Activity - H
24d1b142-e483-53ee-b2e7-c01e05550ac7 | note | By - SE
| checkpoint | 6.01.02 - Survey Records
3989569f-afea-526f-b341-32ff9a57d0a2 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
efdca4bd-743a-5bae-a775-15a6dc53a42e | note | Standard / Specification - Downer
13d9852a-104e-5ddd-a414-a0b3c8436476 | note | Verifying Document - Records
0fddb792-cd96-5f76-99a6-ec5d92f65f44 | note | Frequency - As-builts taken every 10m prior to backfill
bd9d5d94-7a2f-5dc0-b4ab-68c25b7e617c | note | Activity - H
03d57b79-a84e-5ad6-8f79-e3d9e35c407c | note | By - SV
| checkpoint | 6.01.03 - Redline Drawings
09d83736-3d59-5664-876d-9b1e1a8010df | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
183aab9b-8a98-55b8-a516-5e4f702ae200 | note | Standard / Specification - Downer
f64d0f7d-04c7-5770-8bad-bc787444a8e3 | note | Verifying Document - Redlines
fa0c06a6-38af-5efd-adbf-da3e7ed08767 | note | Frequency - Post construction
62ca144a-fde4-5465-929a-b048f4828032 | note | Activity - H
e5945e0b-7d3d-5ef9-a8bf-da45d937a369 | note | By - PE
| checkpoint | 6.01.04 - Defect, Snag and Punch List
368f63a3-db77-5204-aaa7-aa01669bfbc1 | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
33ffc0bb-b4aa-5232-bf57-e66ad40668fe | note | Standard / Specification - Downer
33c668aa-88b6-5645-b971-30a3df4321e2 | note | Verifying Document - Register
2de9d500-3a86-5f99-a7fc-4eefa15fef75 | note | Frequency - Post construction
398eada4-e6f2-55aa-a516-2137af9b8da7 | note | Activity - H
82ab9b6a-b5a4-5adb-9c72-1b795d84926e | note | By - PE
| checkpoint | 6.01.05 - Photos
36a80c93-c9dc-55ff-b483-5aa242fff911 | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
01466be1-a2c6-517a-8f95-3cd5e3a2c397 | note | Standard / Specification - Downer
05d2b333-6235-5b98-a18f-eaa87e514051 | note | Verifying Document - Photo Records
4b223c81-de6d-5f09-96b9-2a7a39248c1b | note | Frequency - Post construction
66ef3d51-81b5-513d-9327-50fbd4284aae | note | Activity - H
ddc4612f-097a-5490-aa75-735a94bdffde | note | By - SE
| checklist | ITP - 112 - Subsoil Drains Rev D | itp | ITP - 112 - Subsoil Drains Rev D | b5778c46-874b-41bd-b3e5-d876f5f0dff7
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
6d2cb710-72cd-5df2-b3e9-73a49140a940 | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
91f28c74-e362-5849-8002-f4ae9c4468f0 | note | Standard / Specification - Downer
fd3e92cd-56d8-53bf-9ee1-0f157b79b9f5 | note | Verifying Document - Construction Pack
0ce126c2-ee88-5685-b03b-927c031c9060 | note | Frequency - Submit 10 days prior to commencement of works
b7b8c36d-a69c-55c2-b0fe-b116e8062c86 | note | Verification Activity: Activity - H
b4d48579-5db8-5887-bbd5-9af55cd14e81 | note | Verification Activity: By - PE
| checkpoint | 3.01.02 - Survey Setout
8514ab2c-cfe0-55fb-8786-674ddb1be46e | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
cc237e96-8ba8-5dfb-8137-6f250cacafb7 | note | Standard / Specification - Downer
dc52ec28-8f2e-5d5b-b028-32615db95ba8 | note | Verifying Document - Survey Records
2b88c3e5-8b7d-5041-bc40-8a64a72a2744 | note | Frequency - Prior to Works
7e8c8d26-e01c-5535-8524-f0f4fab0ae07 | note | Verification Activity: Activity - H
bdd9c68e-427f-5877-9c5f-536bad321990 | note | Verification Activity: By - SV
| checkpoint | 3.01.03 - Approved Construction Drawings
089c71b2-78a0-5832-8f98-0f4b65eda720 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
73ee12db-c958-5022-ae01-e60aa9b1e726 | note | Standard / Specification - Downer
bf3db28b-0b3d-59c4-8154-a5c95e7e27ac | note | Verifying Document - IFC Drawings
dbbc866e-098f-5006-a899-21bccd35999a | note | Frequency - Prior to works start
3b36a6be-0b05-5256-884a-d7343a017833 | note | Verification Activity: Activity - H
61ce0c6c-56ef-5f9e-901b-bc4ea60796cc | note | Verification Activity: By - PE
| checkpoint | 3.01.04 - Topographic surveys for measurement
95040f2e-bcb8-522e-a629-ace59946039e | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
ee453a3b-3438-59ca-8f57-a55b1e8319c1 | note | Standard / Specification - PS 2.2.12
3cdbdc0f-ef12-571e-85a5-9e3cfa7b0c51 | note | Verifying Document - As-built
22735181-5cd1-5969-9fa8-c6f847bc8d3b | note | Frequency - Prior to works and Post Works
bf316beb-d352-5434-a2e2-60d4d4e09e9c | note | Verification Activity: Activity - H
690358d1-9707-5026-98c8-3ddef963b02b | note | Verification Activity: By - PE
| checkpoint | 3.01.05 - Permits
8860f217-92be-5652-9437-05b98c40158f | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
9eb1e80f-921a-5448-999b-be5f51d1c52a | note | Standard / Specification - ITP Register
b587299c-4645-5da3-8880-0bc0f7d40862 | note | Verifying Document - ITP Sign Off
fa201e1f-08ca-5309-be48-8c7a6da0890c | note | Frequency - Prior to commencement of construction activity
fa017440-57f4-55f3-b3ad-4cac130943a3 | note | Verification Activity: Activity - R
eea69e6b-019e-5144-a2da-6bdd1088d3b4 | note | Verification Activity: By - SE
| checkpoint | 3.01.06 - Stakeholder Management
356df781-caef-5fbc-b34b-b0e863194f23 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works
1967110f-ee03-505a-9b98-288ab8cb6a44 | note | ○ Agree plans for maintaining access to properties during construction with landowners
4e253cc6-5278-5d95-aa37-c3932340657a | note | Standard / Specification - Project Stakeholder Management Plan
b57b533d-7d88-5858-a56d-e7d05f12ee86 | note | Verifying Document - ITP Sign Off
757e1648-e739-590f-a6b5-59fb76adf3f0 | note | Frequency - Prior to Construction with continue updates throughout the works
b0a6dadb-0e1a-5aa1-8e35-8a846a9c6f28 | note | Verification Activity: Activity - R
a8bfe4f5-0656-5a4e-80a7-603b24b96f1a | note | Verification Activity: By - SE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 4.01.01 - Subsoil Pipes
da810d94-d7cb-5284-a869-520fef6574be | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
570eddb5-7f95-5e84-b667-19b65668f688 | note | Standard / Specification - GWS 3.2.1
c1a97014-5e0c-54ea-bb13-7987af2a3d77 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
a4ed756c-0bf9-5819-9d29-492b79f5d417 | note | Frequency - Every Delievery to Site
e4f8e7f4-7a7b-532b-8cc5-29bfa4522d33 | note | Verification Activity: Activity - C
44c9bfc2-61ea-5fcb-8b39-4318245eb6d0 | note | Verification Activity: By - SE
| checkpoint | 4.01.02 - Subsoil Drainage Aggregate
16c3e251-e06b-5881-8040-a4785d91fc7a | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
9077a9e0-af21-56b5-bb8b-6640f9316153 | note | ○ App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
6aa6d767-ebfb-5f1a-a293-78b8b87511f7 | note | ○ Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
af7435e5-9b63-553a-8100-37d7591450b8 | note | ○ Test Sieve Aperture (mm) Percentage Passing (%)
0c045990-07b1-5cbb-bb4b-59c879115bc2 | note | ○ 53 100
bdaf19f5-b80e-5600-8556-9fe599a16cae | note | ○ 13.2 10 (max)
958cdcac-1d33-598c-bdee-1145e42dcdba | note | Standard / Specification - GWS 3.2.2 & 3.4
2ffb94b1-f5d7-58fe-9c7b-ff8b26e5a3c4 | note | Verifying Document - PSD, CR
27a7f7e5-ad5d-5fa8-885d-2633efadc0ad | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
ccb00f54-e4e5-5a74-9dba-af026a8bbc2c | note | Verification Activity: Activity - C
1b2bd01b-af2e-5c13-8f6e-bf74643d9f61 | note | Verification Activity: By - SE
| checkpoint | 4.01.03 - Filter Cloth
29f7d05c-7477-58ab-92dd-52027ff1d229 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
b87a2879-3a9d-5cf5-9f28-e6a5ef163ac6 | note | Standard / Specification - GWS 3.2.3
67d13fa6-77d2-57d5-a269-72c095e8dd1f | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
6bbc0e7b-9d7f-5805-b694-7f6935c9d64d | note | Frequency - Every Delievery to Site
af3aeb56-d2da-58ae-a8e2-58806563e24d | note | Verification Activity: Activity - C
9b0b06e6-c8c1-5a40-9fba-db1da3b970ee | note | Verification Activity: By - SE
| checkpoint | 4.01.04 - Securing Pins
9bed9f26-3e9b-5d86-abd9-5966575ce24c | note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and atleast 400mm in length
8c019ab4-a71e-5407-803a-b2367729bde5 | note | Standard / Specification -
ac82b453-0f01-51ce-aab4-98edd9c052e9 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
f6635755-eaad-51a5-a971-c9fa250ea516 | note | Frequency - Every Delievery to Site
16c20365-cfc1-5be6-b5ee-7db34c83884b | note | Verification Activity: Activity - C
92bb85c2-4712-55d6-9e59-814032360d7e | note | Verification Activity: By - SE
| section | SECTION 5 – CONSTRUCTION ACTIVITY
| checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
f2c7305f-d10e-5f6f-95c7-3590c0c8f7c3 | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line.
c8c23375-c309-5565-9b16-d0f323b1cc22 | note | Standard / Specification - GWS 3.2.2
a9f54cf3-45a4-5695-8eea-b6c069a55f18 | note | Verifying Document - Every line
7f69537e-373e-5123-ba29-a117205054ab | note | Frequency - Photos of trench prior to backfill
119275bc-f375-58a7-96c3-286420509ebb | note | Verification Activity: Activity - HP
b8731aaf-6c65-5b11-8439-574ad828f5d2 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.02 - Trench Backfill
041155eb-b426-59e1-9bc3-22bcd3e9bd5d | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
aee77156-3bb9-58f5-8c3a-a8a48b9ad021 | note | Standard / Specification - GWS 3.3
1202ad48-2ebe-526f-94d1-51b98d82bda2 | note | Verifying Document - Site Record
666e2a3b-fe29-56cb-a856-3a72bb07d7e1 | note | Frequency - Each trench
ec31424d-e07d-55de-9ff2-df6294bfbd7c | note | Verification Activity: Activity - I
17517802-e38b-53cd-9336-c3e2d2e5de9e | note | Verification Activity: By - SE
| checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
5b6474e9-a18a-5e30-9244-a51c96cc8e50 | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
90ee52cd-8c64-5a3d-a82f-6d0dc6276d4a | note | Standard / Specification - GWS 3.6
db88c4cc-0ee9-5b56-ba4e-6e434385382d | note | Verifying Document - Site Records
78353753-065d-50b7-9b3a-49b982808ffe | note | Frequency - Each Subsoil Line
cb1084a7-3a16-52c0-a25d-b3bf32880b2d | note | Verification Activity: Activity - I
f84a8ca7-9317-56a6-bc98-67bc52c17bb4 | note | Verification Activity: By - SE
| checkpoint | 5.01.04 - Subsoil Flushing
9b567b98-281a-5352-bb76-69632d74996c | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
2160f3eb-da5a-5752-ba5f-7256119bd2b4 | note | Standard / Specification - GWS 3.6
a527da54-fb01-5e84-a5c2-01c613ab943a | note | Verifying Document - Site Records
f0d1caa8-1b26-5978-ae07-c4c74268de4a | note | Frequency - On completion of earthworks
1abae4a6-5f93-572a-b376-b1603f97ad79 | note | Verification Activity: Activity - HP
5f111d56-e431-5fdb-96f7-ac290d94bd02 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.05 - Survey
445d3448-6846-52fb-8849-fd2441d881f1 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
c238e955-ca60-5db8-8693-f1fccefffe3c | note | Standard / Specification - Downer
8a8e5e7b-1f8e-5362-92e9-4561fbd69bde | note | Verifying Document - Records
c198bea4-1c96-5cf5-882f-9160c8421b12 | note | Frequency - Post construction
62170eaf-ad41-5763-aaa2-27d21853303d | note | Verification Activity: Activity - H
45f29599-e0a4-5440-9c7b-71c11a4a70e7 | note | Verification Activity: By - SV
| checkpoint | 5.01.06 - Excavation
09196edd-397f-50f9-ae5e-61c69e7f0fbc | note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate subsoil drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
6ca0d273-002c-5ba0-8ad1-333c6b66b8ae | note | Standard / Specification - Downer
4b1c8736-bbd3-58f0-932f-e05dd46a91c9 | note | Verifying Document - Records
8679490c-754d-5963-8f57-6c67c9b491fc | note | Frequency - Prior to laying filter cloth
3d94d594-7523-5e78-b39b-c16997211ef3 | note | Verification Activity: Activity - I
1784a8b8-56be-5a8b-a4b5-3bbf807dad17 | note | Verification Activity: By - SE
| checkpoint | 5.01.07 - Bedding
17015693-0f2e-5640-bfc9-600a6d931188 | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
7c4d64dd-9bcf-5044-ac7a-6e8db34b88b8 | note | Standard / Specification - TNZ F/5
4d7ee658-537d-5020-a93d-8fdae26c5fcd | note | Verifying Document - Records
aa4e887a-3065-5968-9410-246174a62493 | note | Frequency - Prior to laying Novacoil
847176d3-115c-5665-92f1-e0751c00537c | note | Verification Activity: Activity - I
5117ddec-08b9-577c-a4fe-bb33e6123328 | note | Verification Activity: By - SE
| checkpoint | 5.01.08 - Joining Pipes
3d53585f-ff18-58f7-9a3e-96a1c110f9fc | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
b3a3edec-fc50-55fd-8611-c33ebbf02f81 | note | Standard / Specification - TNZ F/5
d8816b27-5e6f-5c07-8363-6868a38e5070 | note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
5f443a7d-6e1d-5e18-b9cf-19eee81b4589 | note | Frequency - Every join
0c99cbdf-fb62-550b-b635-cd2f10346ebd | note | Verification Activity: Activity - I
6195fdff-e7c6-5f02-b8cd-dc5cca5bb6fb | note | Verification Activity: By - SE
| checkpoint | 5.01.09 - Pipe Grade
79bed3cb-f761-5926-937a-c0f089bab383 | note | Acceptance / Conformance Criteria - Grade of subsoils must be falling in the correct direction based on the IFC Drawings and at the correct grade (greater than 1% based on TNZ F/5)
9709ef60-5f90-5e83-bcae-327ee5cbad42 | note | Standard / Specification - TNZ F/5
c046403a-2e19-5d38-9fb1-31ec5335fa24 | note | Verifying Document - AsBuilt
a7003428-7741-524c-94bc-4b7acfbeff6a | note | Frequency - Every 10m
240970bf-3541-54a0-bdf1-46ef34967832 | note | Verification Activity: Activity - H
c900571e-45bc-592d-9733-928edae0bc34 | note | Verification Activity: By - SV
| checkpoint | 5.01.10 - Pipe Cover
f8323c79-4b2f-5a26-a1ea-92ecbbb426c8 | note | Acceptance / Conformance Criteria - Drainage aggregate must be placed till -0.1m from Top of SIL and verified by surveyor
5fc8ad30-3755-5b29-b2c7-a263f7277b93 | note | Standard / Specification - N/A
a67f5dd0-1db3-5005-b548-307e442ab690 | note | Verifying Document - Site Record
aca1bb03-105b-56fc-a4e1-f5644c5a8dec | note | Frequency - Every 10m
b43d1077-0a18-52cb-a528-fa62ca673b06 | note | Verification Activity: Activity - H
9dd087ae-d52d-5a40-b248-3279347d6fa2 | note | Verification Activity: By - SV
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 6.01.01 - Construction Record Compilation
28a769aa-0457-5acf-9c1d-116bd515da84 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
53f7704f-2829-5f85-b2cf-5e62ca432920 | note | Standard / Specification - Downer
673656b1-000a-52bd-b675-883d1305e243 | note | Verifying Document - Records
7ef7e0a4-077e-5ad1-bbe0-e993c7ad6fce | note | Frequency - Post construction
a99883c3-9a96-5029-877e-a1fe86a64ec6 | note | Verification Activity: Activity - H
efe21c4e-3c41-506c-a0f9-adba5ccb8342 | note | Verification Activity: By - SE
| checkpoint | 6.01.02 - Survey Records
46468559-3558-5778-b664-91a2b2a281c9 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
9764471b-4138-5b4f-9fab-5c485580c3a5 | note | Standard / Specification - Downer
d9f2516c-6067-5706-b00c-40d87acf823e | note | Verifying Document - Records
be9f4742-33f4-55e8-b397-155d38d20b25 | note | Frequency - As-builts taken every 10m prior to backfill
cb96a695-ff99-58e4-ae72-255b4a607666 | note | Verification Activity: Activity - H
b5a6f2be-4687-58bb-a88e-bce7b256ed88 | note | Verification Activity: By - SV
| checkpoint | 6.01.03 - Redline Drawings
5c05f607-e492-5a6c-a941-2fbad4887232 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
f5bb4a75-89ca-554d-bb31-994884288c00 | note | Standard / Specification - Downer
7e74c2ff-0bf1-552b-91c8-e1db69862690 | note | Verifying Document - Redlines
f3b498cb-c385-513c-992a-3fe107f4e101 | note | Frequency - Post construction
97b95796-6abc-58cf-aaa9-03013a7d9fa5 | note | Verification Activity: Activity - H
886f22f1-84bd-55a2-b3a2-3fb552224e98 | note | Verification Activity: By - PE
| checkpoint | 6.01.04 - Defect, Snag and Punch List
973dbf69-190a-53b3-8d04-5696e73cdb03 | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
67c1c603-8620-58a7-a1cc-b88d98fb2d8b | note | Standard / Specification - Downer
527b4620-0e6f-5e57-a777-b13acced914b | note | Verifying Document - Register
49d38632-5f0d-52ea-8a4d-a04a1609d0e8 | note | Frequency - Post construction
77db538b-ddc8-50f6-b82d-ee68dfe51f7e | note | Verification Activity: Activity - H
ecf9ffa4-8a36-545e-a195-5f1c550fc5f9 | note | Verification Activity: By - PE
| checkpoint | 6.01.05 - Photos
748bdeb6-facb-54a1-b9bf-64af40990b0c | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
5cef6e8e-5830-5084-b687-83fcb4424e3c | note | Standard / Specification - Downer
3bb98567-73f2-50c6-8ad0-8c9da2d40eeb | note | Verifying Document - Photo Records
2f16b406-d193-5c86-bd9a-9e5493c8c1e7 | note | Frequency - Post construction
ebaa79bf-e4bf-5ced-b043-5fa934182c2b | note | Verification Activity: Activity - H
264ce5d5-3d13-5e9a-b5d1-7827956470f9 | note | Verification Activity: By - SE
| checklist | ITP - 113 - Pavement Drains Rev D | itp | ITP - 113 - Pavement Drains Rev D | 8bd46e8d-d436-4de8-9834-a133113573c2
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
129692ca-cf9e-50b9-af21-0c2b34571c32 | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JSEA to the Engineer before works
b6344e20-bd3a-582a-bce6-3e7c10ed76da | note | Standard / Specification - Downer
69b7f7e4-cecf-5785-9742-0c0af2af33dd | note | Verifying Document - Construction Pack
cc5bf1b4-eb6d-53bd-bc4e-914a50e1fc9f | note | Frequency - Submit 10 days prior to commencement of works
a8aff456-8946-57d4-93b4-fa78942a7531 | note | Verification Activity: Activity - H
c62b2621-fb70-5afb-ae77-5632968e80e7 | note | Verification Activity: By - PE
| checkpoint | 3.01.02 - Survey Setout
35384116-3ec2-50c1-8458-9ac359c18590 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
09c0bd6f-614c-5497-9f12-20fb846f6bdb | note | Standard / Specification - Downer
33151928-f942-57c3-af0f-0a90afc76750 | note | Verifying Document - Survey Records
7946d4d2-2dbd-5ef0-a458-303264c36a35 | note | Frequency - Prior to Works
821d29ef-0dab-5a77-8289-ab5abd9b77d7 | note | Verification Activity: Activity - H
55fe4916-25de-59b5-a91f-1daf9916502c | note | Verification Activity: By - SV
| checkpoint | 3.01.03 - Approved Construction Drawings
329abf24-47ee-5be0-88ac-7bc504bec6c8 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
f6441f94-7842-5987-b483-15c7c99dc726 | note | Standard / Specification - Downer
5017ef42-81d7-5c8e-8fcb-a11cc652703a | note | Verifying Document - IFC Drawings
674221b0-b39b-5e22-a63d-8df46eaeb05d | note | Frequency - Prior to works start
bd74208d-e5cb-5a94-9468-2c1fa7c359ab | note | Verification Activity: Activity - H
983d6148-8cdd-50a9-8c05-4af3928ac7c0 | note | Verification Activity: By - PE
| checkpoint | 3.01.04 - Topographic surveys for measurement
4bba2dad-9dac-5e7d-bed9-b3a23d1ff945 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
b6eb4df6-4ae9-5a66-a229-caab84a97a28 | note | Standard / Specification - PS 2.2.12
5fff2221-99f3-5d5a-af52-3ec12ceb8295 | note | Verifying Document - As-built
0d85a8fc-ad0e-5f7c-9f26-88554e8553ba | note | Frequency - Prior to works and Post Works
4db64b9f-d952-5bbd-9082-e9766dbeef4c | note | Verification Activity: Activity - H
591e153a-7413-5f5e-a1b1-e5358215424d | note | Verification Activity: By - PE
| checkpoint | 3.01.05 - Permits
1d34652c-effb-5dd3-822b-dca5687f6b26 | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
84a74d0a-ca71-515f-81a8-42b8107801fb | note | Standard / Specification - ITP Register
1a2fe970-d7d5-5edc-9045-dbfd5f9c250c | note | Verifying Document - ITP Sign Off
b79d8486-eb9f-57cc-98e3-6f9149480fd4 | note | Frequency - Prior to commencement of construction activity
85182a0a-c00d-5626-9d2a-8780fb0224aa | note | Verification Activity: Activity - R
fb535253-3e9c-5921-b453-981b418a8747 | note | Verification Activity: By - SE
| checkpoint | 3.01.06 - Stakeholder Management
fba96e04-b4fe-555e-b6b0-867d3f091e01 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works
59ee5232-ca96-5533-bc46-ce09045aa410 | note | ○ Agree plans for maintaining access to properties during construction with landowners
fe76c5aa-7971-5c7b-8f86-ad8d25d353d0 | note | Standard / Specification - Project Stakeholder Management Plan
77e94b34-6eff-5197-8286-2c2716260add | note | Verifying Document - ITP Sign Off
1bbe9402-ca3a-5a68-81f1-7539d480bbca | note | Frequency - Prior to Construction with continue updates throughout the works
cced4a7e-547f-58e3-8045-09f4b6e00aa4 | note | Verification Activity: Activity - R
ef845f35-4e39-5599-95e7-7312cd4bc049 | note | Verification Activity: By - SE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 4.01.01 - Pavement Pipes
5c1b00b1-1108-5697-9ddf-94c0defd2680 | note | Acceptance / Conformance Criteria - Drainage pipes used in Pavement drainage shall be smooth bore perforated corrugated 110mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
c315dc98-de06-514a-bbe2-fb6e76959206 | note | Standard / Specification - GWS 3.2.1
6ddc05a8-243a-583b-aae3-6faaf39b590f | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
46e31382-14ea-55ce-88c5-8149071fa687 | note | Frequency - Every Delievery to Site
eba14c63-29f3-58ad-8d43-7675029a87f1 | note | Verification Activity: Activity - C
56182f11-7fcd-5808-a487-6a1afd0d3414 | note | Verification Activity: By - SE
| checkpoint | 4.01.02 - Pavement Drainage Aggregate
5036878c-b80c-585a-a650-22b620c53f30 | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
a54c52d1-82ca-58cd-96ca-3e727119c60f | note | ○ App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
c46d8dab-f59d-5d75-8375-b9d91d152f33 | note | ○ Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
b48908bc-9c13-598a-b80f-fe840384e770 | note | ○ Test Sieve Aperture (mm) Percentage Passing (%)
62540440-4f8a-514e-ad58-f952271044b3 | note | ○ 53 100
ff4297a3-e0f0-5f6d-9d2d-6df78fec5137 | note | ○ 13.2 10 (max)
dae2326e-918a-57ea-839b-b2390c9c0d1c | note | Standard / Specification - GWS 3.2.2 & 3.4
e01bab2d-ec09-548b-9126-8de8ab29ab42 | note | Verifying Document - PSD, CR
35e3fa41-f23c-57a5-bc17-eea7660d143b | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
e436ab8e-3431-5b24-9161-19fe6eea1e2a | note | Verification Activity: Activity - C
af2fdaee-5bc6-5ec4-8de0-a43353cc195b | note | Verification Activity: By - SE
| checkpoint | 4.01.03 - Filter Cloth
e97c31e2-2703-5531-921c-968367ba4426 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
395aaa72-f8cb-5ff7-b833-f83d51597c1a | note | Standard / Specification - GWS 3.2.3
38145b06-8215-5d7a-bae9-05b22b031c53 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
11a34487-579d-556d-af28-87ebd931137c | note | Frequency - Every Delievery to Site
b9984d57-5fc5-53e7-ba3b-88d1338b4713 | note | Verification Activity: Activity - C
98c3f6bf-f2fa-58c0-8ce4-6945531cc81b | note | Verification Activity: By - SE
| checkpoint | 4.01.04 - Securing Pins
81765145-212d-5f11-9a15-bafd43dd3bf0 | note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and atleast 400mm in length
21e825c9-801a-5e5e-bf23-4dd7f89f00f3 | note | Standard / Specification -
9be1bb75-2395-5f77-936f-8fcf090b165d | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
b3bb8c10-32fe-544f-bb14-522fab494c96 | note | Frequency - Every Delievery to Site
dd593997-acbf-5308-9281-0c1d7a16e204 | note | Verification Activity: Activity - C
15b0e4ac-c302-5b64-b5e7-6e9c227ba4ce | note | Verification Activity: By - SE
| section | SECTION 5 – CONSTRUCTION ACTIVITY
| checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
2b6be960-71f1-57f0-8ea6-cdd1f2b1c8b1 | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line.
3ccf6b76-bbde-5e3b-ada6-b881ad83c9cd | note | Standard / Specification - GWS 3.2.2
1c0f6feb-de39-5114-a92f-e7f1a3b4dd6e | note | Verifying Document - Every line
b146b93c-e1e5-56f9-a2ef-ba3e5b5dce18 | note | Frequency - Photos of trench prior to backfill
84575761-6d3e-56a4-9329-95ee7877851e | note | Verification Activity: Activity - HP
bfce74a7-b98e-5bdc-9b8c-50e844e85dda | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.02 - Trench Backfill
505a6f94-4bd2-511d-9d0d-4e9fc5090197 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
d3140e35-3242-5933-b0d3-e38b8270c5db | note | Standard / Specification - GWS 3.3
1643d9aa-6eb2-5bec-a464-c029437b564b | note | Verifying Document - Site Record
bf422bec-d466-536c-b03b-f48e37c6ce0c | note | Frequency - Each trench
72d01061-88af-57bb-98c9-a754ad8fd732 | note | Verification Activity: Activity - I
7bfeb181-fb01-5a8c-9926-d1a8ffda4332 | note | Verification Activity: By - SE
| checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
5bdc6d42-db0a-5adb-8215-e7029a66611e | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each Pavement drainage system to enable flushing of the system once the earthworks are complete.
f60bd95e-fa1e-57ff-ad7d-1d00b83a57e6 | note | Standard / Specification - GWS 3.6
9c05594f-ed7d-5015-8b52-ab70ea3b8b4f | note | Verifying Document - Site Records
1a731b27-0ebd-5947-bba9-e73dccf04e65 | note | Frequency - Each Pavement Line
6dc43e98-625a-5520-8135-b8ab0d998cb8 | note | Verification Activity: Activity - I
c5c3f257-ffd9-52ab-a23e-b095eebb1d83 | note | Verification Activity: By - SE
| checkpoint | 5.01.04 - Pavement Flushing
adceec4b-08d7-5638-9590-d083ff51f7a4 | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the Pavement drainage system. This must be witnessed by the Engineer.
6271ec30-4afb-5969-944b-54e344866ae4 | note | Standard / Specification - GWS 3.6
859164a6-ad96-5ddb-a88b-f7dc359ca8d1 | note | Verifying Document - Site Records
d94d9e49-9eca-5320-9322-f5ac86bfabb0 | note | Frequency - On completion of earthworks
3d2160ea-f1b9-5cc0-8c43-c58506bd329d | note | Verification Activity: Activity - HP
5e792c4e-c7f1-5e32-a1aa-a0dd2ddc9e8a | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.02 - Trench Backfill
654bb316-ddbe-5e42-adcf-fa72dcf5342c | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
bfa0fb89-2f4f-558d-94aa-9a0fc9c58dac | note | Standard / Specification - Downer
44090232-a2d0-5a5c-925e-210050b08237 | note | Verifying Document - Records
5903e67c-03f6-519d-810c-7603000c443c | note | Frequency - Post construction
d0c0e5fe-1a5f-55a4-a056-388fa3a0e8ed | note | Verification Activity: Activity - H
961a6fd6-7d50-5b8a-ae3f-b3d4f2411d05 | note | Verification Activity: By - SV
| checkpoint | 5.01.06 - Excavation
65235ddd-45ef-583c-9df0-645df14c76ae | note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate Pavement drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
f9dae494-0842-5564-ab25-737d3d617ea5 | note | Standard / Specification - Downer
d4a598a7-d37b-56f9-8ce9-67208fb05dd5 | note | Verifying Document - Records
0a7b899f-5027-5cb6-a0e9-a5ed108ab2ce | note | Frequency - Prior to laying filter cloth
438046f7-12c2-521d-aaa4-41f5f76802eb | note | Verification Activity: Activity - I
83a78f40-a888-5f4c-89a9-bd9440268d42 | note | Verification Activity: By - SE
| checkpoint | 5.01.07 - Bedding
7defa5f5-31a9-5944-bcb3-df1f2cb77270 | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
de0db94e-b9cd-53b9-9a58-96aee795766f | note | Standard / Specification - TNZ F/5
16380dc3-53bd-56ae-b6f1-ca7d1dccf9e8 | note | Verifying Document - Records
67ef690e-499e-5013-b665-03d557586e57 | note | Frequency - Prior to laying Novacoil
71587158-cc12-533d-be39-764eeb56c7d0 | note | Verification Activity: Activity - I
1c0c27fb-2fa3-52d5-a59b-7678fbc81896 | note | Verification Activity: By - SE
| checkpoint | 5.01.08 - Joining Pipes
6d762c48-d2c5-5a4f-8b0d-20269983f5db | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
14ec8209-5172-5617-8da3-66ff73a76429 | note | Standard / Specification - TNZ F/5
b51a876e-13f1-5da3-8d29-6f2653edc9a7 | note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
4aac0cbc-893d-5825-8ae9-efd4c84ff11e | note | Frequency - Every join
f2dba296-9eea-5252-bb45-28f8334067fb | note | Verification Activity: Activity - I
0ded4b4c-eb4e-5102-b7aa-2338e66e9e01 | note | Verification Activity: By - SE
| checkpoint | 5.01.09 - Pipe Grade
b30ea0e5-d151-5ae2-a76c-d0f209e2b822 | note | Acceptance / Conformance Criteria - Grade of Pavements must be falling in the correct direction based on the IFC Drawings and at the correct grade (greater than 1% based on TNZ F/5)
63039763-9cac-5a8a-82fd-88c60cde71a6 | note | Standard / Specification - TNZ F/5
00b39255-fb56-5c6f-b73b-88ada0db74b9 | note | Verifying Document - AsBuilt
d4915a18-e3c3-52f5-8b03-4ac44b80bfcd | note | Frequency - Every 10m
20684865-8b5e-5fa2-bea4-d8964508f516 | note | Verification Activity: Activity - H
a8033010-40dd-5cb5-bbfc-6ac5743b153c | note | Verification Activity: By - SV
| checkpoint | 5.01.10 - Pipe Cover
22d863dc-6e49-5dff-a947-5a01f9b659a1 | note | Acceptance / Conformance Criteria - Drainage aggregate must be placed till -0.1m from Top of SIL and verified by surveyor
6b94c535-a97c-5da0-b72b-0459c4888852 | note | Standard / Specification - N/A
0561413a-e201-5274-9a04-3d47ff05754b | note | Verifying Document - Site Record
4e96a172-c3c8-59a9-8933-b309679d8348 | note | Frequency - Every 10m
4362392e-14ca-58d1-a7cd-46709fe887b6 | note | Verification Activity: Activity - H
fe6beaab-16d5-5f53-8a82-fa7aca0b22b5 | note | Verification Activity: By - SV
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 6.01.01 - Construction Record Compilation
ec823516-bdd5-50a9-b19d-0c3a2a890c4a | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
c789a8ba-9ae4-5fcd-971c-d94eacbb7e96 | note | Standard / Specification - Downer
887591a5-e4a2-56a0-8ff0-fff1c3ecbebe | note | Verifying Document - Records
ac08efe8-cdc3-5215-9ec6-ef1a076d8edc | note | Frequency - Post construction
8e6372b4-32c9-54be-a4df-4309442031d4 | note | Verification Activity: Activity - H
9aed564b-0b6f-51c5-b80d-d7e7cee237d0 | note | Verification Activity: By - SE
| checkpoint | 6.01.02 - Survey Records
dacff708-5a7b-5bdb-818d-06785b006c3d | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
f9496bff-7d38-5f43-9604-5d3ddc94e14e | note | Standard / Specification - Downer
6301abb6-46f8-5ab5-bfb4-f6c2ea4cd66d | note | Verifying Document - Records
b76aa70a-d9b1-5fd6-aea0-05079cba5f17 | note | Frequency - As-builts taken every 10m prior to backfill
8d10078b-0b46-5819-b7f6-692b2a161728 | note | Verification Activity: Activity - H
e83977fd-a3ae-555a-b87c-f0e49bc8f226 | note | Verification Activity: By - SV
| checkpoint | 6.01.03 - Redline Drawings
676ab5f0-362b-5671-a809-c49e1d6e0f7e | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all Pavements, including temporary Pavements that become part of the permanent works, to show all outlet locations
9e1f7f3a-2c37-5fdd-a24f-5b8e82b68f19 | note | Standard / Specification - Downer
1eea1431-ee7d-565e-8cd5-fe08bbaad33b | note | Verifying Document - Redlines
a62b2ffc-c6f7-53ea-b940-0159e3c38201 | note | Frequency - Post construction
710695e1-3d61-574b-be99-ad7c35a6975f | note | Verification Activity: Activity - H
9a4e76da-1a27-5e3e-a545-b057814cd788 | note | Verification Activity: By - PE
| checkpoint | 6.01.04 - Defect, Snag and Punch List
c2d4f392-8493-57ae-b999-cd0197f51275 | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
19143ea5-5338-5575-a6d6-f69cb65a66f4 | note | Standard / Specification - Downer
640858d8-59b6-5e62-ae70-83f4483fd3ce | note | Verifying Document - Register
64fb3d89-59ff-54c8-9575-0e29ab7a6686 | note | Frequency - Post construction
6296a3c9-a0d5-5967-8342-ef78390459e0 | note | Verification Activity: Activity - H
e544e806-6156-5cc5-91d7-78e47d3d322f | note | Verification Activity: By - PE
| checkpoint | 6.01.05 - Photos
2f113112-8c0a-57e4-a8bb-b15e40b4ad6f | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
e549179f-e214-57e2-b20e-3f497a9de829 | note | Standard / Specification - Downer
33188f4a-b1e0-530f-847a-921a7672124c | note | Verifying Document - Photo Records
58d981ea-285b-53a4-bfe5-ab9042ca61e8 | note | Frequency - Post construction
7735807e-b533-5ed5-a222-be1ab2e9c1d2 | note | Verification Activity: Activity - H
2944ca66-a734-51d6-9a0c-c47379b2b0b0 | note | Verification Activity: By - SE
| checklist | ITP - 114 - Footpath Construction Rev B | itp | ITP - 114 - Footpath Construction Rev B | 670305c0-583f-4333-98b7-bec1651ba9bd
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 - Site Requirements
| checkpoint | 3.01.01 - Construction Pack
ce5284c7-af2d-529e-9acd-6ec3ffb48e55 | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
351562d1-6be9-57f5-a2a1-90f7a1de99c7 | note | Standard / Specification - Downer
5a6d6486-ffec-5112-abc7-f47263382980 | note | Verifying Document - Construction Pack
db83dee9-c593-52bc-a602-a6cadf51d587 | note | Frequency - Submit 10 days prior to commencement of works
f1eb0f48-6a23-52f4-98e0-e3236e6e8124 | note | Activity - HP
9c8b9328-ba74-5759-9146-307748f2deae | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.01.02 - Survey Setout
4f71c412-f4d9-5424-be4a-38cecbf3a2ae | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
ecd7cf5c-246e-5523-9530-b5ac0afce4c3 | note | Standard / Specification - Downer
23415da0-6c29-58f4-91e9-27f1db880189 | note | Verifying Document - Survey Records
367bc75c-07f2-54c5-82ef-82ebac414fca | note | Frequency - Prior to Works
3f9d6745-524d-5c0f-9f9e-e00336e8723a | note | Activity - H
06f3dcac-1bec-5cc5-bb25-44064608dba7 | note | By - SV
| checkpoint | 3.01.03 - Service Location
af821ed1-3204-55d2-ba32-4e8fd4b8731f | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
019d9f89-86ac-56b9-b69e-c6689f37786a | note | Standard / Specification - Downer
e9f13907-7099-5fc0-93b3-9e29f29ca377 | note | Verifying Document - Excavation Permit
4e839873-9cd7-5043-9740-f050b3a36d73 | note | Frequency - Prior to Excavation
f6ce9bea-ef92-543d-8768-b0cf3de2e03b | note | Activity - H
65bb7491-2f5d-5b9d-9714-5edf55aa18a3 | note | By - SE
| checkpoint | 3.01.04 - Internal Permits
d96df4ad-67ee-567c-b3e6-cbe90d1e2e84 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
c790c451-26c9-50f7-a4c9-d677f961b25b | note | Standard / Specification - Downer
57e06db8-d314-5a24-996f-9ca6d49aaeee | note | Verifying Document - Internal Permits
c8cb4af0-690d-5c60-a2ac-f11d47ce54c7 | note | Frequency - Prior to Excavation
0c71dc81-2b73-5fb6-9d2e-8ea5f544d523 | note | Activity - H
6ea247ce-2e7e-59b3-ae88-b640f7987ec7 | note | By - SE
| checkpoint | 3.01.05 - External Permits
8f833f4b-5061-5ae6-a522-f5f7164954d7 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
48e6ca0e-685c-5a45-9bec-86009bdb3e80 | note | Standard / Specification - Downer
be490c86-2175-553f-9801-0d1b5d5e5690 | note | Verifying Document - External Permits
f90cf7da-aa05-56ba-88d5-f09dd8f19558 | note | Frequency - Prior to Excavation
0aa33499-6971-597d-b391-87306aa055e1 | note | Activity - H
52769e5d-c5ad-540a-8f47-f78f8bba2793 | note | By - PE
| checkpoint | 3.01.06 - Approved Construction Drawings
2fef669d-2fa1-5fe9-9686-0b9e5a3adf42 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
98d59d68-4988-5e46-a739-d42e96b5479e | note | Standard / Specification - Downer
76a8fc04-ad6c-53b7-96fd-1db1d14ae33f | note | Verifying Document - IFC Drawings
a27455cf-46c0-5643-be87-e2c99e316aaf | note | Frequency - Prior to works start
ff94ef36-92ec-5834-82bc-4454151210f4 | note | Activity - H
7c42344c-de3d-5823-87a1-fac75afdf675 | note | By - PE
| checkpoint | 3.01.07 - Previous Completed Work Packs
da7166a4-431d-55a0-ae99-d8950516c21a | note | Acceptance / Conformance Criteria - Review previously completed workpacks to ensure work completed meets the contract requirements
8d486b5e-27ae-5c1e-9584-8249cf992fb6 | note | Standard / Specification - Downer
d0b5cd3e-3506-522b-b6dd-ac02ad557d85 | note | Verifying Document - CONQA
24b235fb-91b1-55c5-b134-b0d11fbb7d2a | note | Frequency - Prior to works start
7c5220b5-f554-5315-8e16-be315e901353 | note | Activity - H
1b2d4d84-9278-5b0f-a62e-6c709860ee28 | note | By - PE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 4.01 Sub Activity
| checkpoint | 4.01.01 - Bedding Sand
e1226926-429c-594f-962e-99cb82b9bdaa | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
1f48d203-bdad-5681-853d-4716eac5a361 | note | Standard / Specification - BBO
01ecc247-fb68-54b5-91a3-f911bd3bf5b5 | note | Verifying Document - Source Test/Site Notes
c3a5a8fe-74db-53b6-aa5e-56199009a08d | note | Frequency - 1 source test per material type
3cdc5de5-8449-591b-81d2-37302573b3e2 | note | Activity - R
52244458-0278-561b-bb96-4e1b8ad41ffc | note | By - SE
| checkpoint | 4.01.01 - Undercut Backfill
1ada175c-0e6c-5bef-8cf2-e274ce0d201e | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
388d2ba7-1567-5ba8-80bd-ad1403a1fb90 | note | Standard / Specification - BBO
50497f66-815a-5188-b1fc-3a7a56cff965 | note | Verifying Document - Source Test/Site Notes
1b33edc8-73da-5d3f-b973-824077cb9694 | note | Frequency - 1 source test per material type
59430bc5-bbc0-509d-a9cf-799c20b1e24f | note | Activity - R
6d730eae-f596-57a2-95d1-b5297c57238c | note | By - SE
| section | SECTION 5 – CONSTRUCTION ACTIVITY - 5.01 - Footpath Construction
| checkpoint | 5.01.1 - Footpath
87df6cff-9150-52f4-8f4e-b460bb53e57f | note | Acceptance / Conformance Criteria - After set-out and prior to installation of footpaths
045ed956-718d-59ca-a233-0cb4ff073a44 | note | Standard / Specification - PS - 2.2.16
73268c21-979d-5072-879a-2c1e760517d6 | note | Verifying Document - Hold Point Release
24f26b00-03b9-52b9-ac50-90aee9287b65 | note | Frequency - Min 48h Notice
73b646fc-b543-5076-a666-1efda5849508 | note | Activity - HP
66332c55-8d87-5db6-99f8-f5ae783b95ea | note | By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.2 - Subgrade Preparation
bb9313c5-53ef-59ac-bc5a-c524c2b15c64 | note | Acceptance / Conformance Criteria - The exposed subgrade (excavated to trial subgrade level or pavement depth) shall be tested by using a Scala Penetrometer for compliance with a CBR value >10 (4 blows per 100mm)
a0c62e94-6b18-59cd-945e-60dd7363dd8e | note | Standard / Specification - RITS - 3.4.9.4
6a55b29c-ef44-5495-92f7-38cabf543236 | note | Verifying Document - Scala Results
f4f9195d-bb3b-5220-ad16-effb38497ecd | note | Frequency - Every 15m
da7f1d8b-983c-5ba7-8ba9-658d90e76999 | note | Activity - I
da6e6413-b571-5c5a-9533-d24f66bed276 | note | By - SE
| checkpoint | 5.01.3 - Subgrade Undercut and Subgrade Backfill
1b9bb59b-f2bc-5821-89f1-1829e8f9f3ca | note | Acceptance / Conformance Criteria - If subgrade does not meet the requirements of a CBR > 10 (4 blows per 100mm), and undercut and backfill of the CBR will be required. Backfill material will either be GAP or sand material and will be instructed by the engineer.
40aaf3d2-a6e2-5325-af34-6072b05658bc | note | Standard / Specification - RITS - D3.3.5
11fb04f6-fd2d-5fbe-9928-99afb580c869 | note | Verifying Document - Hold Point Release
5bc9ff8c-7d6d-5f14-b2ae-5e927b65d288 | note | Frequency - Every 15m
4bf00c67-c95a-534e-beb5-dce6b1084b20 | note | Activity - HP
922dce0a-f6d6-509d-93c9-84e6132b2a85 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.4 - Subgrade Backfill Fill Compaction Testing - Aggregate Subgrade
5e1c8060-3239-517f-b79e-d796aaa1f784 | note | Acceptance / Conformance Criteria - Aggregate Subgrade Fill shall be compacted to Clegg Impact Value (CIV) 15
5b19ab62-ede7-57e1-b588-ff92f513f966 | note | Standard / Specification - RITS - 3.4.6.5
d5196ad3-c7a3-5031-befd-092d0bad6076 | note | Verifying Document - Clegg Results
5421eec4-6911-5b15-b886-70a328b74561 | note | Frequency - Every 15m
b1c9f53a-a48b-5415-a1c1-0ffbad81cd92 | note | Activity - I
712e3587-fd40-5f4e-a449-a464158d0c59 | note | By - SE
| checkpoint | 5.01.5 - Bediding Sand
898b9b6e-5251-5e27-b84d-e7ef46583e4e | note | Acceptance / Conformance Criteria - Bedding Sand to be placed at a consistent thickness of 75mm free of foreign materials, bedding surface must be level and free of any peaks or troughs
0907a616-cae8-5b56-b766-b2bb240362dc | note | Standard / Specification - RITS - 3.8.3.3
73139c0a-8565-59f2-b8a2-4f396af58e13 | note | Verifying Document - Site Notes / Photos
8ec36ad8-2eee-5081-8f9a-583ec83f48b8 | note | Frequency - Every 15m
1db253e7-1fc2-5821-9b36-b520e490e789 | note | Activity - I
1f149fc6-c2fd-50a0-a6a8-3af067210be4 | note | By - SE
| checkpoint | 5.01.6 - Concrete Pre-Pour
eeac9f18-9036-5812-9937-730b30252219 | note | Acceptance / Conformance Criteria - The Contractor shall give due notice to the Engineer of the time it is intended to place any concrete and no concrete shall be placed until approval has been obtained from Council.
4afd2489-822f-5cae-b486-590641667334 | note | Standard / Specification - RITS - 3.4.5.3
50189b59-5091-5422-b9bd-798a5f0a8e5f | note | Verifying Document - Hold Point Release, Pre-Pour Check
f92e6219-d0cc-5ddb-b96e-323df356d3b1 | note | Frequency - Min 48h Notice
886439f7-e505-5825-ac09-3872edf1a489 | note | Activity - HP
0287aadd-6648-5077-a2d9-59647c8f3134 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.7 - Ground Preparation
955dea00-b2e9-5c44-9ef2-78a9e100eedf | note | Acceptance / Conformance Criteria - Immediately before placing the concrete, the foundations shall be lightly dampened, and formwork shall be cleaned out. In all cases surplus water shall be removed before concrete is placed.Any foreign or organic material shall be cleaned out.
2be0f46a-270b-5441-9f78-b88fa06c1712 | note | Standard / Specification - RITS - 3.4.5.3
f5f979be-859b-56ed-8ad4-6046e3ee6887 | note | Verifying Document - Pre-Pour Check
072374df-ff13-5c27-9d2a-279c6526a4ed | note | Frequency - Each Pour
8d443340-6a04-5d9a-9b45-97cda6f3a4a1 | note | Activity - H
e2f2916f-bfa5-5092-8d73-252243305eaa | note | By - SE
| checkpoint | 5.01.8 - Frozen Ground & Unfavourable Conditions
240798d5-5645-5742-8a9f-607fbe3971cf | note | Acceptance / Conformance Criteria - Concrete shall not be placed on frozen ground nor shall it be placed in unfavourable conditions, which may be detrimental to the quality and finish of the concrete (i.e rainfall)
43bd83ac-2572-5183-8894-44f3d96d21b4 | note | Standard / Specification - RITS - 3.4.5.3
68549b75-f80c-5fee-a15a-605038807a6d | note | Verifying Document - Pre-Pour Check
94ed8cd1-303b-5b11-bc17-589e7e799173 | note | Frequency - Each Pour
8e2024b6-338d-573d-96da-f21e306e7138 | note | Activity - I
8f41a3a1-e13f-5b3e-9557-e2dc960d3548 | note | By - SE
| checkpoint | 5.01.9 - Curing Of Concrete
7b0506c4-fbea-51f1-bf28-698579515344 | note | Acceptance / Conformance Criteria - Immediately after placement, concrete shall be protected from premature drying, excessively high or low temperatures and mechanical damage and shall be maintained with minimal moisture loss for the necessary curing period and hardening of the concrete. In hot dry weather sprinklers or damp covers will need to be used.
df50fab9-c0f7-513a-bbb5-de0ced2b1bc9 | note | Standard / Specification - RITS - 3.4.5.5
e6298ec8-a5e6-5088-a5da-f5bba4a20c56 | note | Verifying Document - Post Pour Check
e17b0b60-f439-5ea9-9585-d5130438d714 | note | Frequency - Each Pour
785fced2-0338-59f7-80e0-5eb43b95a71e | note | Activity - I
a1248d1f-1114-546e-a761-9f98704a38c0 | note | By - SE
| checkpoint | 5.01.10 - Concrete Compressive Strength
126f30a0-7173-5dca-9c71-6aa5392eab45 | note | Acceptance / Conformance Criteria - Concrete to meet a placed 28-day compressive strength of 20-Mpa
a6647773-4132-5272-909c-c1ab1add4a52 | note | Standard / Specification - RITS - D3.3.5
8f725eda-f28c-575a-bcde-30dcbcd20f3c | note | Verifying Document - Concrete Dockets
60ef0079-98be-594d-a669-f4be24fd41dc | note | Frequency - Each pour
08ec14ed-9ebd-5d0d-9f4f-7fc9502ea89c | note | Activity - R
1e9d039b-480d-5127-a51e-fff86c8bed4c | note | By - SE
| checkpoint | 5.01.11 - Finished Work
fe6f5a11-c908-52a1-938f-460cd9c0f8b0 | note | Acceptance / Conformance Criteria - Methods shall be used that will provide a smooth, clean and even surface on the exposed faces of all concrete work.
b7a68477-03d7-58b2-8f02-66ff8f6d634a | note | Standard / Specification - RITS - 3.4.5.7
313b25bc-ad5e-5784-baee-c15211ff8daf | note | Verifying Document - Post Pour
6c43aed2-8f84-56de-9028-ac3910f744f6 | note | Frequency - Each Pour
f75df3ca-2395-52b1-8d71-9487a9b7eedf | note | Activity - I
44cf6397-57b4-568b-b8bd-b3b9ef22d565 | note | By - SE
| checkpoint | 5.01.12 - Contraction/Expansion Joints
6a775d3b-5758-5070-ace9-f3d5ec9cc1eb | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m. The slot shall penetrate the concrete by not less than 50mm and the mortar dressed over the cut face. The contractor shall ensure that cold joints are accurately marked and set out via total station so that the subsequent saw cut is in the cold joint. Should cracking occur adjacent to the saw cut a minimum section of 1.5 metres of the footpath shall be removed and re-cast.
29c98797-12b0-51d9-8fe5-c8ab27c292d8 | note | Standard / Specification - RITS - 3.4.5.8
5f655169-cd8e-51bb-bb0a-69de9d3fe1c5 | note | Verifying Document - Post Pour
51a01500-016f-5bd2-b2c5-8c6a7a8c9b9a | note | Frequency - Each Pour
abe05d06-8549-5dc0-bab9-aa27230a6fb5 | note | Activity - I
8ecfac3a-ec12-58e4-8bd9-29473e9601a8 | note | By - SE
| checkpoint | 5.01.13 - Backfilling against Concrete Work
d11f5586-c5c9-5f71-beae-1c199d6008bf | note | Acceptance / Conformance Criteria - Backfilling against the poured footpath shall take place as soon as practicable after the concrete has reached sufficient strength, with particular emphasis at curves, corners, intersections and pedestrian kerb crossings but not prior to 36 hours after pouring.
0d10d705-4ed7-5c84-a8f3-b833192f4aa1 | note | Standard / Specification - RITS - 3.4.5.9
6e141db8-3130-53a5-9895-f0cc0b7aad57 | note | Verifying Document - Site Notes
d72556a9-a38b-5ba4-b2e5-0e31285af35d | note | Frequency - Not prior to 36 hours after pouring
3cf19196-701c-5e5d-a4ee-764329620ffa | note | Activity - I
a876d563-56d1-519c-8ce8-6663eb4b3538 | note | By - SE
| checkpoint | 5.01.14 - Finished Concrete (Surface Finish & Final Levels)
39e9b9c1-18ef-5983-a0e8-b7b4a0a8149d | note | Acceptance / Conformance Criteria - All final path and vehicle crossing surfaces shall be true to the lines and levels Specified and ‘broom’ finished.
9d8f96e1-9bd2-59b3-90bb-8afb5feab005 | note | Design considerations aside, the final surface shall not vary by more than 5mm when checked with a 3m straight edge. No finished surface shall hold water.
0e6bcd81-9749-528e-b559-18cd42691988 | note | Standard / Specification - RITS - 3.4.5.10
3e7a0871-1eb2-5dcc-8917-e55de59f1c0d | note | Verifying Document - Post Pour Check
35efb868-bd76-5de2-9bd7-d2d38d750fca | note | Frequency - Each Pour
e3174e0b-e036-5c55-ac66-9bb138488758 | note | Activity - I
9bbe291a-4b09-5e2c-9140-235b645b6509 | note | By - SE
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 6.01 - General
| checkpoint | 7.01.01 - Construction Record Compilation
66a905ef-67fd-5577-9a07-1c6eb5d9f84f | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
7ef3391f-aa1d-567a-99c4-7a2f909a6923 | note | Standard / Specification - Downer
3f9c50f8-ae85-5327-baaf-0e91dfaa5081 | note | Verifying Document - Records
c8332514-2bd9-507e-a938-7e75a58cb1c2 | note | Frequency - Post construction
fadad837-b793-5499-958f-6bbb5fcd9bde | note | Activity - H
3295bdaf-8b72-5cb5-8139-990564ce17d7 | note | By - SE
| checkpoint | 7.01.02 - Survey Records
7a4f52a0-cd0b-5fa0-bf31-4f8b7d021a0a | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
f18df727-6fa5-5726-a49e-bd8f7e5e4b75 | note | Standard / Specification - Downer
d80c503c-1987-5ae1-b647-6fdb82cec402 | note | Verifying Document - Records
fe6e2180-4efc-5918-bf4c-63501e87e517 | note | Frequency - Post construction
139ecf52-71c9-5073-b035-35a7e1477ce4 | note | Activity - H
cd75a03c-9c8c-5818-a845-e1e9531da55b | note | By - SV
| checkpoint | 7.01.03 - Redline Drawings
4c6290cf-839f-5763-9a5c-7804fdab4b5c | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
d0eece7e-d556-5eb0-958f-e221547ec3fc | note | Standard / Specification - Downer
da045d72-d79a-5ac7-afb9-a36da44bd43a | note | Verifying Document - Redlines
b76c2f29-b580-5d90-a029-494d807f2995 | note | Frequency - Post construction
6387ecfa-7d2c-5d4a-8330-3e6f14310148 | note | Activity - H
b615ee2a-9ea1-5aa9-bd0f-90ff5d3526e3 | note | By - PE
| checkpoint | 7.01.04 - Defect, Snag and Punch List
67ccddcc-a441-5a00-9e8b-0a8be75384b9 | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
4415ff06-d7c8-5fcd-bef1-c2884ed83a47 | note | Standard / Specification - Downer
ed5f01e7-9815-5abb-8b01-1f10e8d18694 | note | Verifying Document - Register
cbf60885-6788-5f0c-83d5-f2e33d34ae14 | note | Frequency - Post construction
32a5d262-0d30-57f3-b2dc-f5fcb00addb2 | note | Activity - H
0b6639fc-aad3-5a9e-b281-d0385eee7f91 | note | By - PE
| checklist | ITP - 114 - Footpath Construction Rev C | itp | ITP - 114 - Footpath Construction Rev C | 14cbdc72-0408-4a26-a596-0acab476dea8
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
da4e31d1-91b7-5dfc-9883-d750aa73968b | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
22c2e398-038b-5ebe-9fd3-97d089f1f84e | note | Standard / Specification - Downer
51f28ae6-76b5-5476-b8a7-1e3c160ea9ff | note | Verifying Document - Construction Pack
14df887a-86c4-52a0-9263-c022d237cfe3 | note | Frequency - Submit 10 days prior to commencement of works
2c95298d-1a7a-584c-9129-0c8cc596a1e0 | note | Verification Activity: Activity - HP
0f2f83b5-5565-53f1-8eb1-64909c315acc | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.01.02 - Survey Setout
7adfd0da-6cb1-514a-8414-93fb86ec0a65 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
8371c1de-3285-5475-ab9a-1feeaf3c3dbe | note | Standard / Specification - Downer
b7eb301e-1f39-5f6a-8ec4-ba779724ad10 | note | Verifying Document - Survey Records
4e4cda27-c986-5197-8d59-e672f6d2c4eb | note | Frequency - Prior to Works
572e42bb-3e75-5329-84f6-9783775f2c15 | note | Verification Activity: Activity - H
b2fb77bc-7151-5657-9f90-196e757dbb8a | note | Verification Activity: By - SV
| checkpoint | 3.01.03 - Service Location
4a0a6b5c-4770-53e2-b27a-9b0bacbfb96e | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
f7a295d9-642c-5025-aff9-1e73964b4a78 | note | Standard / Specification - Downer
407fd6ef-6569-55e5-b04d-562e29d04133 | note | Verifying Document - Excavation Permit
88a68e61-5089-5738-8236-98dcf5de001b | note | Frequency - Prior to Excavation
e9c1e5af-04bd-50d3-8d54-365b51c53d26 | note | Verification Activity: Activity - H
889e2f29-22e6-55fe-b8cd-1a1cd1331ec2 | note | Verification Activity: By - SE
| checkpoint | 3.01.04 - Internal Permits
a7770878-b7b1-5e3c-80ba-e63f45ef37c9 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
77f4ae8c-c18a-543c-92d7-f14b76fdbf61 | note | Standard / Specification - Downer
3961ecde-cae0-5507-909c-616cab971954 | note | Verifying Document - Internal Permits
67543f22-4f4a-5e56-8ca5-87ac396de934 | note | Frequency - Prior to Excavation
1cfad12f-661d-5229-87a9-89b650cfd0ca | note | Verification Activity: Activity - H
592e8229-6b47-518d-8d6d-738fed132ae7 | note | Verification Activity: By - SE
| checkpoint | 3.01.05 - External Permits
76e16d14-b834-51ab-b28e-585c1a480860 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
2ab1457d-e577-5737-a9c8-d3cdf83698d2 | note | Standard / Specification - Downer
d92182ce-ac5b-580a-9ad7-74def00bfce7 | note | Verifying Document - External Permits
9e6b7642-cb72-5c3e-a7f0-07e84aa76c99 | note | Frequency - Prior to Excavation
fd47d71f-c009-5fa8-aa4e-2478702576d7 | note | Verification Activity: Activity - H
2d37fb9f-5ee1-5eea-a6b6-ecc52f598c31 | note | Verification Activity: By - PE
| checkpoint | 3.01.06 - Approved Construction Drawings
0cc6560a-b5db-5ca6-8395-cd60465052e4 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
6075603e-6ff5-5fcb-bcf9-1763b369b130 | note | Standard / Specification - Downer
c9699d70-adf3-5f19-b815-e1725a5c6077 | note | Verifying Document - IFC Drawings
c228c584-be3f-520c-9416-fadd9c318b1b | note | Frequency - Prior to works start
f529d555-ae4f-58ee-9b6f-630181516742 | note | Verification Activity: Activity - H
8f356468-5773-580d-832c-9ba5de3f9894 | note | Verification Activity: By - PE
| checkpoint | 3.01.07 - Previous Completed Work Packs
a1fd307e-05b8-5bd4-879b-6290667bc562 | note | Acceptance / Conformance Criteria - Review previously completed workpacks to ensure work completed meets the contract requirements
473cb92d-a42e-5fa1-9d01-5cb6f9b4cf5d | note | Standard / Specification - Downer
fe316d62-99a5-556c-82fb-53fd79b60f8d | note | Verifying Document - CONQA
4333b296-f902-5a91-9ccb-11d0c7721897 | note | Frequency - Prior to works start
3ebb18de-cd32-5a6a-8755-3ad4a4fb8ab2 | note | Verification Activity: Activity - H
d585416b-64a6-5191-b9a0-fdbc224fb3c0 | note | Verification Activity: By - PE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 4.01.01 - Bedding Sand
28e31cdd-c9bf-5e1c-b484-a209f941bcd3 | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
28a63c63-6b64-5f92-b0c8-c60919142920 | note | Standard / Specification - BBO
1b21c5b6-0401-55a6-9aa5-0dce895b7ca4 | note | Verifying Document - Source Test/Site Notes
5539197d-bf3c-5be0-ae91-48ea7400aa98 | note | Frequency - 1 source test per material type
1d0f6a19-310b-52a7-85ed-349ef693f717 | note | Verification Activity: Activity - R
e20fb7af-0946-58e5-8d81-fe9512a864ba | note | Verification Activity: By - SE
| checkpoint | 4.01.02 - Undercut Backfill
7c1c82c7-fb69-5c99-9c1d-6258a5a549e4 | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
1e48974b-1904-5d12-b299-a169e4391ed0 | note | Standard / Specification - BBO
9135086a-ae39-5a1c-89ad-86a584ee315e | note | Verifying Document - Source Test/Site Notes
b6c9ed36-56c5-5172-8a70-e14af499a132 | note | Frequency - 1 source test per material type
e826c202-a533-5dac-abf1-9342b557327a | note | Verification Activity: Activity - R
5502c201-cd67-5fdb-80ab-204090226978 | note | Verification Activity: By - SE
| checkpoint | 4.01.03 - Uniaxial, Biaxial and Triaxial Geogrid
6c485a36-1e5b-5ff2-9e67-03168a57970c | note | Acceptance / Conformance Criteria - All uniaxial, biaxial and triaxial geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001 and shall submit to the Engineer for approval.
e51309fb-8d25-5c69-a8af-ecf080c6c783 | note | Standard / Specification - GWS 4.2
dc54e220-2348-55d3-a447-9411a7ec607d | note | Verifying Document - Datasheet
7f729b1e-67ed-5fc8-acdb-e99025a8dfbf | note | Frequency - At least two weeks prior to works.
635de2f3-94ed-53ba-a288-1f709d14d989 | note | Verification Activity: Activity - HP
f9674768-a1f6-59c7-a1df-c55aad859451 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 5 – CONSTRUCTION ACTIVITY
| checkpoint | 5.01.1 - Footpath
908777f8-13d9-54cd-a057-cb00c27fbfe9 | note | Acceptance / Conformance Criteria - After set-out and prior to installation of footpaths
c3f7b93f-20ff-5f13-b287-1eb2d4049659 | note | Standard / Specification - PS - 2.2.16
21c7480e-6335-5273-adfc-74bb9705be94 | note | Verifying Document - Hold Point Release
0887ec57-80c8-5d4c-9820-2117ddf31976 | note | Frequency - Min 48h Notice
c8bc5408-9d80-5790-813d-4dc74448b00c | note | Verification Activity: Activity - HP
bfdd6fa3-b890-5373-b207-b1124b461033 | note | Verification Activity: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.2 - Subgrade Preparation
89e10954-615f-536e-b273-95e4bb40e1e8 | note | Acceptance / Conformance Criteria - The exposed subgrade (excavated to trial subgrade level or pavement depth) shall be tested by using a Scala Penetrometer for compliance with a CBR value >10 (4 blows per 100mm). For subgrade of CBR value <10 (4 blows per 100mm), refer to 5.01.3.
28cf4ce2-cd56-531c-9e47-ff8e15d54928 | note | Standard / Specification - RITS - 3.4.9.4
507e480b-cafc-5ecd-a5aa-6bdd78c26921 | note | Verifying Document - Scala Results
b9b44e33-fd4a-5a4d-91b4-c3df9442117e | note | Frequency - Every 15m
760dcc7d-ccf8-5c6e-8ad2-5eac300c26dd | note | Verification Activity: Activity - I
3e152a2e-e61b-52aa-886e-8e2b920d32af | note | Verification Activity: By - SE
| checkpoint | 5.01.3 - Subgrade Undercut and Subgrade Backfill
ddaf608f-44a3-509f-be78-c4ab1de783fe | note | Acceptance / Conformance Criteria - Subgrade CBR <10 but > 7 (3 blows per 100mm) 75mm GAP20, CBR <7 (2 blows per 100mm) 100mm undercut & 175mm GAP20, CBR < 3 100mm Undercut, grid (standard biaxial or triaxial equivalent) & 175mm GAP20.
7853bfa5-025c-55c6-8475-68e65376a1c3 | note | Standard / Specification - RITS - D3.3.5 BBO
c93e8f11-a494-5c2d-83fa-ed4c47c0e295 | note | Verifying Document - Hold Point Release
a9ba145a-104f-572b-b833-053579b5c130 | note | Frequency - Every 15m
7f703640-1047-5691-927a-c509139171d3 | note | Verification Activity: Activity - HP
c27ef9e5-5a36-5fe8-9a7c-8448e3762911 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.4 - Undercut Geogrid Placement
94eb9090-a5b4-502e-af61-59c8afb3e86b | note | Acceptance / Conformance Criteria - Geogrid to be placed flat on subgrade. For areas that require lapping, lapping to be 500mm.
f1a2a709-2242-57eb-b842-74d62f45cf2a | note | Standard / Specification - GWS 4.1
994c46b4-6c14-5700-bcc3-85ad8cfcfbf6 | note | Verifying Document - Records
47b10ca8-9381-55ba-b356-3ad1e10d92be | note | Frequency - Each undercut
6ef10fb6-3aab-5516-93e3-b765e462fb84 | note | Verification Activity: Activity - V
2c0378ff-131f-56c5-bc1d-aa2543c28728 | note | Verification Activity: By - SE
| checkpoint | 5.01.5 - Subgrade Backfill Fill Compaction Testing - Aggregate Subgrade
30326775-e281-5ca4-b482-75b27b5cc8f8 | note | Acceptance / Conformance Criteria - Aggregate Subgrade Fill shall be compacted to Clegg Impact Value (CIV) 10 for footpaths upto 3m wide, and CIV20 for footpath greater than 3m wide.
e6622324-792e-5f27-8957-d4da4f9aac92 | note | Standard / Specification - RITS - 3.4.6.5
85fc9129-4950-52c6-bbc6-45ac0b7acc91 | note | Verifying Document - Clegg Results
1df7924b-a1bf-5ce3-a4ce-868badad09e1 | note | Frequency - Every 15m
da0c3aea-2fd1-58c2-bae0-641ac6da5657 | note | Verification Activity: Activity - I
97fab05e-d8cb-5b6f-b077-f3c5f29014e9 | note | Verification Activity: By - SE
| checkpoint | 5.01.6 - Bedding Sand
4d42bc40-457f-54e4-b9d3-13501fb17694 | note | Acceptance / Conformance Criteria - (For CBR > 10% or 4 blows per 100mm) - Bedding Sand to be replaced at a consistent thickness of 75mm free of foreign materials, bedding surface must be level and free of any peaks or troughs
880dec4d-57e7-5e36-b3af-3e3f6278c441 | note | Standard / Specification - RITS - 3.8.3.3
b46e2e91-0db7-55f3-957f-17688ad49168 | note | Verifying Document - Site Notes / Photos
699a0042-76ca-5c90-8aa7-6ac19c487242 | note | Frequency - Every 15m
a32dd790-e1ab-585e-a45b-a8c29746f68b | note | Verification Activity: Activity - I
c655a22f-2cc5-5052-b66f-db24cff2a8c6 | note | Verification Activity: By - SE
| checkpoint | 5.01.7 - Concrete Reinforcing
09052192-4b7d-5423-aa0c-c683ec8589c6 | note | Acceptance / Conformance Criteria - In instances where rain gardens are to be installed, adjacent footpaths consist of a reinforced footing and a mesh section (Pavement Type 4). 2 x D12 Longitudinal bars with a min lap length of 384mm & R10 Stirrups @ 600 CRS. Pavement Type 4 found in DWG3152 - 150mm Concrete with 665 Mesh on 100mm GAP20. Minimum cover of 50mm.
14efbad6-affe-5f6c-b11c-97f5da93f60c | note | Standard / Specification - RITS - 3.4.5.4
3ee560cf-9f51-550c-ba3a-a2dd2eb663fc | note | Verifying Document - Site Notes / Photos
74a69f01-4738-5166-85a4-30e2337f7b90 | note | Frequency - Min 24h Notice
fc70243d-988b-5b9d-baaf-b14d71384863 | note | Verification Activity: Activity - I
60871f4e-9ad7-5b52-a9af-a96d549ecdc0 | note | Verification Activity: By - SE
| checkpoint | 5.01.8 - Concrete Pre-Pour
5a81f1a8-fd2e-5e37-a8c2-a9103ad5f466 | note | Acceptance / Conformance Criteria - The Contractor shall give due notice to the Engineer of the time it is intended to place any concrete and no concrete shall be placed until approval has been obtained from Council.
98b8f422-f39c-577a-aa54-9065195c3790 | note | Standard / Specification - RITS - 3.4.5.3
10fc23c7-1766-520d-b207-1884c1546dad | note | Verifying Document - Hold Point Release, Pre-Pour Check
11d8dcaa-2d9c-5400-8d25-49f06ea34d9b | note | Frequency - Min 48h Notice
2415e9a8-ac9e-5126-88e5-99b476a6fd64 | note | Verification Activity: Activity - HP
3a86b9e5-8421-5f37-b168-8149b16cb411 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.9 - Ground Preparation
24b744e8-9641-5b2a-af8d-f37ee0badcc1 | note | Acceptance / Conformance Criteria - Immediately before placing the concrete, the foundations shall be lightly dampened, and formwork shall be cleaned out. In all cases surplus water shall be removed before concrete is placed.Any foreign or organic material hall be cleaned out.
c20186d3-ca4a-53e8-a9ea-e48f83ea6d0a | note | Standard / Specification - RITS - 3.4.5.3
50019442-d430-5090-a550-116eecd6eee8 | note | Verifying Document - Pre-Pour Check
9564bcc3-35a1-5668-9aff-b876f559b263 | note | Frequency - Each Pour
6ff546c8-7d26-5574-8e5e-b32ba34ad643 | note | Verification Activity: Activity - H
1e3a0a52-8a7e-581a-8201-12f0a6a36852 | note | Verification Activity: By - SE
| checkpoint | 5.01.10 - Frozen Ground & Unfavourable Conditions
8baae2ed-c68e-55e0-aecd-8aaeb381fc2a | note | Acceptance / Conformance Criteria - Concrete shall not be placed on frozen ground nor shall it be placed in unfavourable conditions, which may be detrimental to the quality and finish of the concrete (i.e rainfall)
c32ac166-e93f-5aca-81af-d3b9d7c52355 | note | Standard / Specification - RITS - 3.4.5.3
4e939bbc-43e5-5b44-9c22-82a83a43b731 | note | Verifying Document - Pre-Pour Check
89aa9783-1364-5cd6-8151-dbc82cc210ef | note | Frequency - Each Pour
ab3c9297-cb63-5e05-a586-ea9f2a82f303 | note | Verification Activity: Activity - I
436f59ea-8706-56dd-b335-434ec313839d | note | Verification Activity: By - SE
| checkpoint | 5.01.11 - Curing Of Concrete
5694b9f5-52cf-5ca7-a599-4ef7c2e3c8b4 | note | Acceptance / Conformance Criteria - Immediately after placement, concrete shall be protected from premature drying, excessively high or low temperatures and mechanical damage and shall be maintained with minimal moisture loss for the necessary curing period and hardening of the concrete. In hot dry weather sprinklers or damp covers will need to be used.
3c3cec70-d8f6-5473-ab94-99c3096e6f41 | note | Standard / Specification - RITS - 3.4.5.5
da67b0d9-bf8e-5a4e-8dbe-3bdae2aefb46 | note | Verifying Document - Post Pour Check
a37ffe17-cc43-5a15-9b87-1bd96eb66468 | note | Frequency - Each Pour
5d565167-84aa-5918-aac0-250f7dbe8db9 | note | Verification Activity: Activity - I
3f8bfc2e-22a7-5591-bdc8-3dfb2cd621ae | note | Verification Activity: By - SE
| checkpoint | 5.01.12 - Concrete Compressive Strength
13fc6a02-f751-5a8a-b0ad-ea573b03e838 | note | Acceptance / Conformance Criteria - Concrete to meet a placed 28-day compressive strength of 20-Mpa
42b8d0d1-ecf8-541d-b5b6-155c20ac194a | note | Standard / Specification - RITS - D3.3.5
e6f2d538-223e-5478-b172-e2bdc9c73bbd | note | Verifying Document - Concrete Dockets
f48bf4b1-1652-5a21-aeed-abe0e3b935aa | note | Frequency - Each pour
c6dca3c8-92a9-5068-9cc9-0532bf247072 | note | Verification Activity: Activity - R
b5bc0b4c-3c57-5520-b2b4-d3891e06e110 | note | Verification Activity: By - SE
| checkpoint | 5.01.13 - Finished Work
a09d24a5-7606-5230-8ea2-3745590c5d03 | note | Acceptance / Conformance Criteria - Methods shall be used that will provide a smooth, clean and even surface on the exposed faces of all concrete work.
4d408ab1-0198-52b8-b320-5acaf4871702 | note | Standard / Specification - RITS - 3.4.5.7
5a67833f-67db-5837-8fe9-9a31d40d5806 | note | Verifying Document - Post Pour
dddbd0aa-fce6-5663-9d5c-c2ce631be1d6 | note | Frequency - Each Pour
1bde09a7-e8d9-5268-accf-9503cc7e39c9 | note | Verification Activity: Activity - I
391e97e9-e992-5a05-99dc-f944a3fdf702 | note | Verification Activity: By - SE
| checkpoint | 5.01.14 - Contraction/Expansion Joints
3aaeef3d-83b0-57f0-9ccc-7bcf5eade92b | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m. The slot shall penetrate the concrete by not less than 50mm and the mortar dressed over the cut face. The contractor shall ensure that cold joints are accurately marked and setout via total station so that the subsequent saw cut is in the cold joint. Should cracking occur adjacent to the saw cut a minimum section of 1.5 metres of the footpath shall be removed and re-cast. For reinforced Concrete, Cuts to be 30mm depth to avoid contact with steel reinforcing.
a8119bfe-92e8-528e-b157-d1e467b081f3 | note | Standard / Specification - RITS - 3.4.5.8
1ae26c56-d637-52a9-b983-277465c75fb1 | note | Verifying Document - Post Pour
e88895bf-ade1-5921-8816-b0fa6995dc2e | note | Frequency - Each Pour
4b3b25d2-dca0-542d-a938-b8c621c92edd | note | Verification Activity: Activity - I
63d951df-76a5-5649-a7a4-889bec116c8b | note | Verification Activity: By - SE
| checkpoint | 5.01.15 - Backfilling against Concrete Work
32bb1c33-9eff-5723-a138-fe71e52b0d5a | note | Acceptance / Conformance Criteria - Backfilling against the poured footpath shall take place as soon as practicable after the concrete has reached sufficient strength, with particular emphasis at curves, corners, intersections and pedestrian kerb crossings but not prior to 36 hours after pouring.
a1904119-c4c9-59d6-a24d-3225e9757905 | note | Standard / Specification - RITS - 3.4.5.9
92dad5ff-c4a6-5e9a-bc45-5300b867b569 | note | Verifying Document - Site Notes
ef46bd31-a031-50e1-8fb6-c000b2e71734 | note | Frequency - Not prior to 36 hours after pouring
c6049b82-49e8-5274-8fa3-36d92c9b9b40 | note | Verification Activity: Activity - I
c36dc286-68c0-5bde-84af-70d018be772e | note | Verification Activity: By - SE
| checkpoint | 5.01.16 - Finished Concrete (Surface Finish & Final Levels)
e9b1467d-25a3-5b45-b67d-05538f51d33b | note | Acceptance / Conformance Criteria - All final path and vehicle crossing surfaces shall be true to the lines and levels. Specified and ‘broom’ finished. Design considerations aside, the final surface shall not vary by more than 5mm when checked with a 3m straight edge. No finished surface shall hold water.
78bfc4c1-9545-5fdf-a395-8735c81cb9b8 | note | Standard / Specification - RITS - 3.4.5.10
93875082-830f-5035-b361-2f291c475bfd | note | Verifying Document - Post Pour Check
539b0dd4-d8b9-55a9-852f-bbbcc1eefc1d | note | Frequency - Each Pour
8c8c983e-3eeb-5c68-825f-98aadd284836 | note | Verification Activity: Activity - I
dd4f3d49-14ea-5e1d-a0b9-3ec2b9950058 | note | Verification Activity: By - SE
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 7.01.01 - Construction Record Compilation
6c58462b-a30c-57c5-85b3-ed6b02f4429d | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
0f4077a8-c09d-5eb1-a55b-a5ea479892ef | note | Standard / Specification - Downer
529aa3d2-e2c8-5ce5-8e1c-dd92a372e279 | note | Verifying Document - Records
fcca9f71-5bcb-5211-9bef-dc0c1e2ea35d | note | Frequency - Post construction
febf01f9-93b7-5623-a920-8aa5c90d4f4f | note | Verification Activity: Activity - H
392c4756-11b1-592f-902e-e738e419a4ab | note | Verification Activity: By - SE
| checkpoint | 7.01.02 - Survey Records
1baba57d-00b1-5734-8924-b6a1bc3c85dc | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
2553cb8b-26ec-5173-b4dd-3a00f846ca2d | note | Standard / Specification - Downer
60510461-c115-524c-88f8-23576b77f146 | note | Verifying Document - Records
d9f69550-8a85-5856-b38e-0d4ecc83ac19 | note | Frequency - Post construction
8f39c29c-f15b-55d4-a510-7de084814854 | note | Verification Activity: Activity - H
a21c9379-e2d3-50af-afcc-1e629edeba8d | note | Verification Activity: By - SV
| checkpoint | 7.01.03 - Redline Drawings
2a5c3d60-6956-58dc-ac97-4da7689fa3f1 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
12fe14e8-8e13-5203-b3c8-44efd6ac622e | note | Standard / Specification - Downer
04bb6fd3-e6f5-5237-9235-1e81056413d8 | note | Verifying Document - Redlines
dcceb05c-acb1-5fd5-a989-8852621b6b1d | note | Frequency - Post construction
d6e2ca6f-aec7-563c-80b5-65af2c147304 | note | Verification Activity: Activity - H
4dd40fb8-f599-5701-8cc9-9b7b4b0d7ce6 | note | Verification Activity: By - PE
| checkpoint | 7.01.04 - Defect, Snag and Punch List
a69ae53b-c45d-5d7c-8966-18c5d311894d | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
26b00a9c-48a0-5071-b048-8a88b760b5c0 | note | Standard / Specification - Downer
c9e22ef3-25c1-5c3d-a744-c7b16693a236 | note | Verifying Document - Register
8a50cd04-56b1-54a0-9896-5cc9464fce35 | note | Frequency - Post construction
b1407f79-60c6-5483-b103-a1357d32762c | note | Verification Activity: Activity - H
054841be-e546-55a3-97c9-d2b5f72fb757 | note | Verification Activity: By - PE
| checklist | ITP - 116 - Pavement SIL Rev C | itp | ITP - 116 - Pavement SIL Rev C | c3f531d9-5122-43ea-a472-3c0dcbf7df54
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
c40fa04e-13bc-52d2-96ab-64f63b73c062 | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
6c6fb38c-6a48-589d-9f32-48e709e1cd2f | note | Standard / Specification - Downer
6639788b-38a1-5bb3-b19c-caf2d3e2300a | note | Verifying Document - Construction Pack
58a3cb4c-245f-5b89-8450-acb58a784745 | note | Frequency - Prior to Works
25464d71-aea9-51a6-a729-7bfbfbdfed60 | note | Verification Activity: Activity - H
4f0adf16-abb4-5f29-9a52-fd242a9f2a38 | note | Verification Activity: By - PE
| checkpoint | 3.01.02 - Survey Setout
64b55ec4-42f2-5ebc-9905-6c26ed810702 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
46049ddb-5425-5a76-b44e-feb4e1999006 | note | Standard / Specification - Downer
a3806e12-3999-5074-843a-c47d1b7e1cd4 | note | Verifying Document - Survey Records
b60098de-3ee2-54e3-b42d-4751a0263f1f | note | Frequency - Prior to Works
3688549a-eb1f-5beb-9832-647ec65b5a74 | note | Verification Activity: Activity - H
973b7e09-3aab-5043-8be7-072efe7e38f0 | note | Verification Activity: By - SV
| checkpoint | 3.01.03 - Service Location
6e787462-9a97-553d-801b-a7dccdfafbc8 | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
ed0f280f-f8ac-5a09-9672-3cf33faa605e | note | Standard / Specification - Downer
0fc81a14-3e98-5427-88cd-2b78e1881ed4 | note | Verifying Document - Excavation Permit
c0038974-f486-5d5d-a8b1-aaa88a400346 | note | Frequency - Prior to Excavation
68f531aa-2f97-591c-9e4d-5b67241e5bf1 | note | Verification Activity: Activity - H
f8d27db9-1694-5c4d-bd5a-6ac182673484 | note | Verification Activity: By - SE
| checkpoint | 3.01.04 - Internal Permits
d986341e-82f8-58a9-8582-b70fa39800f7 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
f8306c64-b4fc-5e67-94fd-8bfdb3117a3f | note | Standard / Specification - Downer
d8105282-76f0-5cc9-bcf4-b31fc99670e2 | note | Verifying Document - Internal Permits
42494a2f-4ac2-534c-89c7-f1ed3902d88b | note | Frequency - Prior to activity being undertaken
d3331e29-8c2e-5d36-a606-e1919a129e64 | note | Verification Activity: Activity - H
d63e15fc-e8ec-5cfd-ac4c-69e191340406 | note | Verification Activity: By - SE
| checkpoint | 3.01.05 - External Permits
493daff9-55ff-5ab5-b341-27e318fb18fc | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
7fc1af21-d3b9-5816-a9b0-7c975d068572 | note | Standard / Specification - Downer
08dd5f42-099a-5358-892c-f8e48ff540ce | note | Verifying Document - External Permits
3c2e104c-6d7e-5993-95cb-d49ce71ca53d | note | Frequency - Prior to commencment of activity
b6491fa9-f1bd-5a41-8d23-9c3979a6a3b6 | note | Verification Activity: Activity - H
88684cca-8136-5f3e-a94b-4bb63dc6b478 | note | Verification Activity: By - PE
| checkpoint | 3.01.06 - Approved Construction Drawings
2d8bed13-a256-5820-93c3-239f8fd05c54 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
08f89712-8651-5fe9-ab4b-d6e51a041502 | note | Standard / Specification - Downer
12ecd9d4-c68e-5a6b-8a34-d753ab18f30b | note | Verifying Document - IFC Drawings
de366472-6407-528d-9f65-88e2328d5c60 | note | Frequency - Prior to works start
4cfc74e4-63bf-520b-8f1d-d6d828782ec6 | note | Verification Activity: Activity - H
c302bdfe-c0b4-5e2b-ae14-f939b3a66f60 | note | Verification Activity: By - PE
| checkpoint | 3.01.07 - Previous Layer QA Sign Off
759644f3-c189-510e-9984-ffbbf9a4457c | note | Acceptance / Conformance Criteria - All Previous layers signed off, QA complete. Including subgrade, SW, WW, WM. Ensuring everything up to the bottom of SIL is compliant.
5d3b8915-ce59-5d36-82db-db17194583ce | note | Standard / Specification - Downer
f7ea8c9b-a684-5cfc-a407-4c595ce13634 | note | Verifying Document - QA Records
96ee17ba-5921-56cd-b22e-a1ce63b618dd | note | Frequency - Prior to works start
1970ad1c-eb9e-51bb-a5e5-10207f8738ae | note | Verification Activity: Activity - H
3f580ecb-eb69-5f18-aa68-7ee9ba5be9dc | note | Verification Activity: By - PE
| section | SECTION 4 – ENGINEERS HOLD POINTS
| checkpoint | 4.01.01 - SIL Inspection
ace7915d-b335-5044-bf9b-510395667093 | note | Acceptance / Conformance Criteria - Prior to placing of sub-base pavement, to include proof roll, inspection of extents of works, general shape, and tidiness, free of organic or contaminated material, review of Benkelman Beaming of the SIL and final levels.
bf3713ae-0c11-5951-882e-cd868286d53e | note | Standard / Specification - PS - 2.2.16
14c91a0d-1f8e-5153-9477-647a932eba34 | note | Verifying Document - Hold Point Release
234ef8f6-58bd-5f2d-a62f-b92075854b98 | note | Frequency - Min 48h Notice
072768c5-b408-56af-b8e2-d9fc9f83ca86 | note | Verification Activity: Activity - HP
cde2bf39-8343-5cc7-80f5-87c657e7f791 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.01.02 - Subgrade Inspection
98f56f2f-a2fc-5db0-92f7-96515cfce501 | note | Acceptance / Conformance Criteria - Proof roll, Scalar penetrometers, and shear vanes prior to SIL fill commencing
e45574da-a763-5f81-b355-413c0d29cd55 | note | Standard / Specification - PS - 2.2.16
5394684b-f36b-5ed9-b144-97b893e708da | note | Verifying Document - Hold Point Release
dfd76a41-a6a3-5e32-8fcd-8ef042ee2f19 | note | Frequency - Min 48h Notice
ace9466a-e662-518c-8004-b429923c70ae | note | Verification Activity: Activity - HP
5b4f32fd-698a-531a-b091-3c418830b074 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
| checkpoint | 5.01.01 - Pavement Subgrade CBR
e235899c-1101-58e9-adf3-8bd9aadc8f7d | note | Acceptance / Conformance Criteria - CBR testing of the subgrade shall be carried out by the contractor prior to final trimming. The pavement design requires a soaked CBR of not less than 10 within 1.0m of the bottom of the SIL layer. Subgrade CBRs testing includes 4x DCP's at subgrade level to a depth of 1m in a 1m grid around the CBR test location and 4x NDM's DT -0.1m subgrade level with a probe depth of 300mm in a grid. CBR testing is then completed (For Subgrades in cut or fill 1 x In-situ CBR test (truck mounted CBR), Push tube CBR for subgrades in cut and remoulded CBR sample for subgrades in fill). Another 400mm material is then cut, 4 x NDMs are completed around the test location and CBR testing is completed. If the soaked CBR is less than 10 the Engineer may instruct changes to the pavement design. Invitation for engineer to witness CBR testing. To be accurate representation of site materials.
ecdab66f-f43c-594a-b89d-ddcacf94456f | note | Standard / Specification - PS 7.1
4a5a1f49-499f-55cc-b553-091f83b9217a | note | Verifying Document - IANZ Lab Reports
698cf41c-3cb1-57fe-b1e4-8bc069990d26 | note | Frequency - One test per 2,000m2, with a minimum of three tests per material type.
5552604d-44fa-536a-9995-e2684135d758 | note | Verification Activity: Activity - HP
7c10cef9-9ecd-55fc-8c30-b2bc8dbee054 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.01 - SIL Conformance
01dedcf8-53dd-5801-bf4c-85d7078dabc3 | note | Acceptance / Conformance Criteria - AP200 from Taotaoroa Quarry will need Gradation (PSD envelopes, set limits for the SE and CI. (recommend SE>25 and CI<10), set crushing resistance (<10% at 130kN), WQI (AA,AB,BA,BB) and MDD/OMC test results.
0ac72aa9-a6cc-5cb5-ac17-743f2f9af6e3 | note | Standard / Specification - BBO
fbfba3c4-9265-593a-a902-33cf676e3dc3 | note | Verifying Document - Lab Reports
a3dcb2c7-c221-5093-bc8b-448af6c40ddf | note | Frequency - All testing shall be completed at the rate of 1 test per 2,500m3, and being no less than 1 test every 3,000m2 (placed).
65ac43da-eeda-5d04-b76d-4ff0736bb03b | note | Verification Activity: Activity - HP
965386b3-d89e-5be2-9b22-1a1d438b848e | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
c244761f-570b-5268-aec2-b925831e8ab8 | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density & Optimum Moisture Content
c98f5384-794e-5d3e-bce0-e9d516934bdd | note | Standard / Specification - PS - 7.2.1
2cb005e1-9bf6-5c65-95b6-a01ab3b39b63 | note | Verifying Document - Lab Reports
d5195d6c-0837-5bc2-a127-59c598119d4c | note | Frequency - 1 test per material type and no less than 1 test every 5,000m³ (in place)
2b86371a-ca46-5d15-a45f-6bc5114324c2 | note | Verification Activity: Activity - HP
3d9bc47d-919b-5fb1-a426-02f53544201c | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.03 - Plateau Density Test
d74c9e5d-6e08-56db-8233-b761a40f4a24 | note | Acceptance / Conformance Criteria - Compaction shall be undertaken using the higher of the two density targets. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
652f5d09-22e3-5ad9-b3d2-69c02a82fea0 | note | Standard / Specification - BBO
b9591980-3522-55e3-8e1c-cd0fe43598e8 | note | Verifying Document - IANZ Lab Reports
4d21c09d-1072-5f9f-97b3-8462f41b15e5 | note | Frequency - 5 tests per 10,000m2
50a9463e-98ed-51cb-88a5-43d06bb14a96 | note | Verification Activity: Activity - I
f783f559-3ec6-51b8-8833-b0b15d300d88 | note | Verification Activity: By - ENG
| section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
| checkpoint | 6.01.01 - Subgrade Prep
958c8338-5b33-51ce-8659-d282d5eb34a5 | note | Acceptance / Conformance Criteria - The subgrade shall be prepared in accordance with the requirements of the Geotechnical Works Specification in Appendix B, including proof rolling, Scala penetrometer and NDM testing at the specified frequencies.
1c1d25c3-1c0c-5119-94ac-3bb6d4bb68dd | note | Standard / Specification - PS 7.1 GWW
335a7fc5-352c-57ba-9bb3-3c7bff749696 | note | Verifying Document - Completed Earthworks ITP
d9e82ec7-9807-5637-b51a-fbbe61b0f902 | note | Frequency - Prior to Pavement Works
36c5a72d-b0fa-5959-811d-774112aef47e | note | Verification Activity: Activity - HP
ee1691c5-9e43-520a-b738-6b90b6530c8f | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.02.01 - Layer thickness
7b7395fe-8190-5681-b681-d4eca93de0bd | note | Acceptance / Conformance Criteria - Each layer shall be checked to ensure the required layer thickness is achieved which is a minimum of 250mm of AP200.
7d347154-06df-5db4-893e-adae1e00f98a | note | Standard / Specification - BBO
4d98a622-0994-57a0-9608-0d7413eb3ca3 | note | Verifying Document - Site Notes
f40e52dd-2b7b-51fa-9e2d-e1ed4b3a1699 | note | Frequency - Check every 20m
8ff8da8a-140d-547e-9822-9d5a7f92ec4f | note | Verification Activity: Activity - I
7c4f62be-ea24-57dd-b298-073e72488a7b | note | Verification Activity: By - SV
| checkpoint | 6.02.02 - Services Protection
18a79a9e-329e-5360-807b-4a37752c162d | note | Acceptance / Conformance Criteria - In instaces where there are services, a minimum of 400mm cover of bedding sand is required prior to AP200 being placed to protect and avoid piercing.
61f852a2-b3bf-5523-a04e-d6a41712ecb1 | note | Standard / Specification - BBO
80b01301-0ed7-587f-a585-2ddfc802886e | note | Verifying Document - Site photos/ records
151db57e-af12-5370-8719-5d8c8a235f3e | note | Frequency - Every services
4b417c25-0138-5339-bdec-1e7dae8e09a7 | note | Verification Activity: Activity - I
04678288-81cf-592d-9b2b-24ee6a863cba | note | Verification Activity: By - SE
| checkpoint | 6.02.03 - Plateau Density Test
01696134-52fd-5b4b-b347-cac5edb38264 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
68b3ecce-8f03-5060-a480-467a519f97df | note | Standard / Specification - PS - Table 7.2 - 2.2
6396dfa4-48da-5f9d-888a-66e56d9e47e3 | note | Verifying Document - Plateau Density Report
bde06433-7507-597b-8b66-2bf38cce2fc1 | note | Frequency - 5 tests per 10,000m2
593a01b6-bc47-5e64-a8dc-07f9e3bdc755 | note | Verification Activity: Activity - I
2bf421ad-0e46-5280-8082-197e172dedea | note | Verification Activity: By - PE
| checkpoint | 6.02.04 - AP200 SIL layer compaction
d840ee6b-3f3f-54c1-9e52-ec4c52f07504 | note | Acceptance / Conformance Criteria - Further to Figure 2 of NZTA B/2, the acceptance criteria for compaction of the AP200 SIL layer shall be a Mean Value ≥ 98, and Minimum Value ≥ 95.
6e96ba7a-b57b-570a-b3b6-d8aa5312ca0f | note | Standard / Specification - PS - 7.3.1
da698b73-9b4d-5489-bc13-6c323384730d | note | Verifying Document - IANZ NDMS
6498eb4b-b819-5cb0-a6fd-306efe87a66d | note | Frequency - 5 tests 1,000m2, 1 test halfway (250mm layer thickness) and 1 test on top of SIL (500mm layer thickness). 10 Tests total per 1,000m2.
0981876e-f991-5fdb-9d7e-8f9fd3f950ae | note | Verification Activity: Activity - I
8e766ca7-76cd-5c96-9bca-6688761eeec0 | note | Verification Activity: By - PE
| checkpoint | 6.02.05 - Proof roll
ca8b507d-b30e-5b0c-927b-5b0eceda46cd | note | Acceptance / Conformance Criteria - The SIL shall be tested via Proof roll prior to Benkelman Beam testing. Proof roll to be under supervision of engineer and verifying document to be signed off by engineer.
ef4fc51e-0eab-58e6-be7d-843037d9324f | note | Standard / Specification - PS - Table 7.2 - 2.2
961871e0-1d7f-5952-a0e0-5b1d0f54c568 | note | Verifying Document - Site Notes
08c46cf8-7010-593b-bc20-514dc63f602a | note | Frequency - 100% of layer
a1721636-5d7c-5825-a375-27f7a3a2968b | note | Verification Activity: Activity - HP
fada9282-d505-5ef1-8b80-18e8d8bb2e38 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.02.06 - SIL Benkelman Beam test
78f988c9-a17e-56f3-8239-9d9d93f3ca19 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be carried out on the top of the SIL layer at the rate specified in PS Clause 7.4 and reported to the Engineer. Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm. Performance verification of these target deflections shall be confirmed by the Engineer on review of results from within the pavement Stabilisation trial (PS Clause 7.3.3).
4202d00b-497e-5e0d-a724-4178a060f8bd | note | Standard / Specification - PS - 7.3.1, PS - 2.2.16
2bd96a39-ce74-5995-863c-36c42778e94d | note | Verifying Document - Benkelman Beam Report
96228506-0732-56f8-98c7-b52e167ea5c2 | note | Frequency - every 10m of each lane – staggered between left and right wheel path. Min 48h Notice.
4f088441-bfaf-5fdd-a434-da9fbc7df354 | note | Verification Activity: Activity - HP
624f9233-1786-564f-929d-482eaf69643e | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.02.07 - SIL Inspection
47e80799-51b1-5c6a-bf2f-cc22a1ead256 | note | Acceptance / Conformance Criteria - Before laying of any pavement SIL and metal courses. SIL inspection to be carried out under supervision of engineer, verifying document to be signed off by engineer.
b70014cb-3981-5575-99b1-f78bd13b5599 | note | Standard / Specification - PS - 2.2.16
2524d696-5c6c-50ee-ac58-ae9b63a0062d | note | Verifying Document - Hold Point Release
53ba4b1d-5715-5388-b0a7-db5d0271dc42 | note | Frequency - Min 48h Notice
3a79f8c1-45d6-57b9-8381-0ff3a57d6316 | note | Verification Activity: Activity - HP
7a76cac5-6b1e-5ed3-ad08-272e9ae3e1de | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.02.08 - Topography
52d9391d-24c7-5f70-b1b0-5db5f76a5bbc | note | Acceptance / Conformance Criteria - Carry out level check on trimmed SIL. Survey conformance with Total Station. Tolerance = -30mm +0mm (NZTA F/2).
50fefc58-87dd-5c21-9973-e4146aff6fe1 | note | Standard / Specification - NZTA F/2
715a071e-2e75-5886-bd5f-377aaf0676cb | note | Verifying Document - Survey PDF against IFC or similar
8c663fad-9b5b-5f8e-889f-47f48a28a394 | note | Frequency - every 1m across the road (avoiding islands) at 20m intervals
1ebdd31b-775d-5cc7-ac53-4f493563334e | note | Verification Activity: Activity - R
3ea56599-c9e1-58cf-baf5-370d39ccc7af | note | Verification Activity: By - ENG
| section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 7.01.01 - Construction Record Compilation
f464ae83-eb06-538a-bb1a-4ad7d0d1a9e2 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
69bb90df-4780-50c6-8e22-7ff538f201ea | note | Standard / Specification - Downer
91dd33e1-2376-59ff-af17-91c40bb075d2 | note | Verifying Document - Records
e6f4cdbd-f1c0-558b-b462-cfe7c77babb4 | note | Frequency - Post construction
3c061ce3-a053-513f-9871-c93507432463 | note | Verification Activity: Activity - H
84dac486-bdde-5968-bb8a-ae515d5122ea | note | Verification Activity: By - SE
| checkpoint | 7.01.02 - Survey Records
0ac1e123-4f48-505c-a410-d4a5c73c5b1f | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
fc7875d2-1020-5abe-838d-047371bcd10d | note | Standard / Specification - Downer
e79e64fc-93d8-5e8d-b06e-69f33f888e4f | note | Verifying Document - Records
d351c1a1-4a72-5d10-b94f-108b68b24ace | note | Frequency - Post construction
17ffbb98-dd3d-5541-89b2-f9730258be9c | note | Verification Activity: Activity - H
2b244de3-d7ed-58c6-9d6f-c99b39b092c9 | note | Verification Activity: By - SV
| checkpoint | 7.01.03 - Redline Drawings
52e0efca-22b1-5f73-ba83-8c6eba817c67 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any increase in SIL depth.
bea7c94f-2a21-5e8d-af76-2797f07c3a10 | note | Standard / Specification - Downer
a804c94e-909f-5111-9f6d-8c9f89d44605 | note | Verifying Document - Redlines
729664ad-6783-5794-8bcc-16e8f378c377 | note | Frequency - Post construction
053cc7f0-16a2-501d-9e34-5610eab1e4f1 | note | Verification Activity: Activity - H
e8c8730a-2448-5ae8-b052-b0ce0c88b6b1 | note | Verification Activity: By - PE
| checkpoint | 7.01.04 - Defect, Snag and Punch List
01988b67-6605-5403-aa7c-d06f8f3c9e1a | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
9aaa54ae-b937-50d5-9999-5c573fd2468b | note | Standard / Specification - Downer
1ecb29ea-cb19-54fa-9e34-8bc77a6bb434 | note | Verifying Document - Register
01a55ec6-cfdf-5a89-9a6e-edf7a036d625 | note | Frequency - Post construction
d971d27d-4d49-53df-853a-b00c7c93d858 | note | Verification Activity: Activity - H
993911c6-7004-5dbf-916b-ec66812d5844 | note | Verification Activity: By - PE
| checklist | ITP - 119 - Rain Garden Rev B | itp | ITP - 119 - Rain Garden Rev B | f036e760-124e-4d4f-9a50-a151df1e41b2
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
9def2e52-5a00-5c71-bb5d-a5731d79f771 | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
f8918e32-072c-5e4f-bdbe-4ee0debe3d06 | note | Standard / Specification - Downer
5451e42e-e56c-531a-a32e-217f393d85b2 | note | Verifying Document - Construction Pack
06620205-379c-56fe-a968-1c3bfd8e297f | note | Frequency - Submit 10 days prior to commencement of works
6193f489-f3fb-5464-8890-95381175b697 | note | Verification Activity: Activity - HP
5d1e4cea-dbe8-52d7-8f42-0afb29cdaaea | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.01.02 - Survey Setout
8e6e2633-9699-515c-842d-4ad5617b6756 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
cdc1a5de-c649-51dc-af72-655bddf75dfb | note | Standard / Specification - Downer
32599dcb-6c95-5d61-be91-fe7c780cccf0 | note | Verifying Document - Survey Records
beca2a2d-0fe7-5424-a8a6-dea170b05ba9 | note | Frequency - Prior to Works
70978d11-faf9-5157-955a-a0eab665e53d | note | Verification Activity: Activity - H
18003291-8496-5c14-bde9-4671827d2c56 | note | Verification Activity: By - SV
| checkpoint | 3.01.03 - Service Location
a145cd98-5afd-5c76-84f3-b630dcbbf24a | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
2b61464f-60ec-58a0-9716-ee55082b8e9e | note | Standard / Specification - Downer
afdc609c-3532-51db-8de0-aac2fa4fa5c5 | note | Verifying Document - Excavation Permit
69afc0c4-55c4-52e5-a629-603a532a29c9 | note | Frequency - Prior to Excavation
f5e4d1aa-ae87-5b76-9e5e-137ed9d5de0f | note | Verification Activity: Activity - H
f45161a3-251a-5e3d-b14f-eb4c283c4b70 | note | Verification Activity: By - SE
| checkpoint | 3.01.04 - Internal Permits
2ffc1661-38e8-5a7c-8801-d480405b411a | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
200ea0a8-50f6-5fcd-9745-13b0c3e5ce01 | note | Standard / Specification - Downer
025caee4-663d-51f2-90ba-87349e939820 | note | Verifying Document - Internal Permits
47643a11-8feb-5416-9bc2-be5ef37187c0 | note | Frequency - Prior to Excavation
e2cc506b-6fb3-5e3a-94b8-8b294a73074e | note | Verification Activity: Activity - H
d288e985-0f3e-5c63-8716-900de1dd6c53 | note | Verification Activity: By - SE
| checkpoint | 3.01.05 - External Permits
619e42e2-93c1-59c0-9895-735c939e1265 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
a162d817-c75f-5509-a0cc-d8ca1f32a42b | note | Standard / Specification - Downer
27c3b5a5-7f3f-5634-8c5c-c4180b4cae27 | note | Verifying Document - External Permits
e0768b2d-0d3c-5d2b-9ecf-ddec27426721 | note | Frequency - Prior to Excavation
7a307292-5710-5039-96f2-f1782db0fa01 | note | Verification Activity: Activity - H
a369be10-0c78-5535-b298-29afb02fef13 | note | Verification Activity: By - PE
| checkpoint | 3.01.06 - Approved Construction Drawings
a1181f9e-eedb-5625-9694-c5f40918b168 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
9e9fcaa7-d74f-52ed-87b2-01625a59b5be | note | Standard / Specification - Downer
6e7fc801-b160-5175-947b-6ad87f2064cb | note | Verifying Document - IFC Drawings
7feebb4e-a7a9-5202-9378-9d919a1e5fea | note | Frequency - Prior to works start
9f7c0492-f0f4-5792-a4fa-78e04f916fbd | note | Verification Activity: Activity - H
e861a933-1d19-5714-b642-a3cdb2f583e9 | note | Verification Activity: By - PE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 4.01.01 - GCL Liner
0b26c487-731b-5581-98f1-6e89fd3c5f6f | note | Acceptance / Conformance Criteria - GCL to be meet or exceed the test values of Bentosure NW4000.
0d5bf86a-1738-53e8-95ea-b9314c30530b | note | Standard / Specification - Project Sechedule
d72dfea0-ab18-5c7e-9ad7-41e8baa600fb | note | Verifying Document - Technical Datasheet
9d35c253-0e9c-50a7-82fc-39331e638b26 | note | Frequency - Atleast 2 days prior to placement
30c5dac6-202c-5aad-b037-ba83f190ae1e | note | Verification Activity: Activity - HP
b71da0d6-6e42-5ac0-b642-21a082e6f083 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.01.02 - Geotextile
6b191de0-f149-52fe-884e-76a9998ce5fb | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used to wrap 20/40 drainage aggregate. Confirm before placement
9fcef079-bab8-58fb-ad7b-48743881ea91 | note | Standard / Specification - GWS 3.2.3
2263df06-b649-5e02-80a6-f7d66da36dcb | note | Verifying Document - Technical Datasheet Delivery Dockets or photos
4f066066-135c-50df-a0e9-6b45679625fd | note | Frequency - Before placement
c1755163-cd66-5f75-a7cc-31ac3c2e097d | note | Verification Activity: Activity - C
585a4b69-728e-5cee-9769-5b85dc9dc005 | note | Verification Activity: By - SE
| checkpoint | 4.01.03 - Drainage Aggregate
221b297f-110c-5871-9743-1ea092d461e1 | note | Acceptance / Conformance Criteria - Drainage aggregate should be deep washed and in accordance with TNZ F/6 including gradings (40/20 aggregate). Open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991
a6d31f75-39f4-59cb-94bf-d848199b4a10 | note | Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
aa9e6105-cb0e-5190-9303-97000a09132e | note | App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
c936dee8-4a12-5e54-aabf-9d2288dc4d1e | note | Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
01b12554-1f83-5157-80c7-42795d9468be | note | Test Sieve Aperture (mm) Percentage Passing (%)
491fd46f-234a-50a1-9d89-3523102db8f3 | note | ○ 53 100
20d7a798-62d4-56bd-9024-4acc977e81c0 | note | ○ 13.2 10 (max)
26861176-ba6c-507e-b8eb-f046ed92d7b5 | note | Standard / Specification - GWS 3.2.2 & 3.4
82aa571a-6752-5d5a-a562-d79114ac0d37 | note | Verifying Document - PSD, CR
e71e9084-b5d1-5a76-b2de-73316ce0b3ea | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
4d8826a0-b967-5d79-81c4-5f7e7dc4fe2c | note | Verification Activity: Activity - C
3891c4cc-4d13-5d8e-b96a-7d14f6f4a329 | note | Verification Activity: By - SE
| checkpoint | 4.01.04 - Pipes and fittings
384ab256-614e-5e0c-b042-d330884b61cc | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 110 mm diameter Class 200 complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
b1c32c74-89c8-5700-9514-461ee4a6b3d4 | note | Standard / Specification - GWS 3.2.1
021e83e3-92b5-54cf-be9b-225bf97036d3 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
9f479e02-87de-5a0b-b98a-058141438c1d | note | Frequency - Before placement
61f334cd-3da0-573c-99d5-b67239121813 | note | Verification Activity: Activity - C
159be186-33a6-56c8-903a-8e8c4d123e3a | note | Verification Activity: By - SE
| checkpoint | 4.01.05 - Graded Sand
2c159e7f-e667-5167-ae10-55eccd67b11b | note | Acceptance / Conformance Criteria - (2A SAND) 10mm clean well graded sand transition layer with minimal fines, void ratio 0.3.
4e8c8953-6ba4-5a6e-9728-f9466b773cf5 | note | Standard / Specification - DWG 2195 REV1
bfa66001-aa81-56fc-8d67-72c583598df5 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of sand onsite
fe17e41b-e7b7-5fa3-9c30-f02aa4f4c570 | note | Frequency - Every Delivery to Site
20af0589-2876-558d-93c3-e3ed86adf40a | note | Verification Activity: Activity - C
20d5e767-0a1e-591a-a02d-229e6e5ebf59 | note | Verification Activity: By - SE
| checkpoint | 4.01.06 - Filter Media
c5d062f0-ab98-5419-b038-ae7aefda4472 | note | Acceptance / Conformance Criteria - Filter/ Planting Media must follow the specification as per RITS 4.2.19. Seen below.
2d7b6ed3-c522-577d-b20c-727b72991c08 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
5d006976-72ff-5405-a583-184daabab4ce | note | Planting media is to be as per RITS 4.2.19.
8de8009b-5ef5-5cac-8abe-2a1c3ddb846d | note | Planting Media
ef0e71dd-58b5-5977-9b20-a4d728414836 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
ec5acb6c-fcef-5c7b-9fb5-000d2fce3e13 | note | Raingarden media should meet the following specifications:
349ec037-1c73-57fa-aee7-011f242e188e | note | ○ Minimum depth 500mm.
ae4b69fb-db03-5d6b-9846-d3ab2934f7b0 | note | ○ Saturated Hydraulic Conductivity: 50 to 300 mm hr^-1.
66cb35fd-e9b7-5b59-979a-aea2b3046d5b | note | ○ Plant available water: 100 mm
7f23d222-671a-5f13-8be0-f5dcaba1ddb0 | note | ○ Organic matter: 10% – 30% by volume
45e23989-4308-5ac6-ab37-3858f269d53e | note | ○ pH range: 6.5 – 7.5+
af0681bf-ced5-55cf-961a-1f52f478bbcd | note | ○ Electrical Conductivity: < 2.5 dS m^-1
a09595b1-8671-5baf-a85c-2bab48a0fcf4 | note | ○ Total Nitrogen: < 1,000 mg kg-1
452909c0-4ce3-5e73-9071-ea5c9645fe02 | note | ○ Total phosphorus: Leachate testing required if > 100mg kg^-1
c065957c-2851-569e-b8f2-4d69ad64bde5 | note | ○ Total Copper: ≤ 80 mg kg^-1
59e189fe-40f3-5950-9bc5-088da18ed886 | note | ○ Total Zinc: ≤ 200 mg kg^-1
b6d417fd-4337-5efb-8f7e-b592a9b3e2d8 | note | ○ Media sources: From a clean source (no waste products)
1c64159f-72bc-5b8b-9623-6baea1bf0878 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
3d5cbaf1-a62c-5001-893e-962490d391f5 | note | Standard / Specification - RITS 4.2.19
600675f4-47b9-51d2-9772-cd66bf2cb451 | note | Verifying Document - Verifying documents Dockets
8866c5e8-3842-5ccd-9b45-69daf7185d1c | note | Frequency - Every Delivery to Site
ea81d774-536d-5184-b97e-089b1de790b0 | note | Verification Activity: Activity - C
114ffbcf-cd8b-5dd6-b69f-ed29bdb9ceef | note | Verification Activity: By - SE
| checkpoint | 4.01.07 - Scour Protection GAP 65 Rip Rap
2e2f339d-3f91-56fd-8577-bde9f9b05083 | note | Acceptance / Conformance Criteria - Clean GAP65 to be used as Rip Rap. For soil filled scour protection a ratio of 30% topsoil, 70% GAP65.
7eb9b777-f572-5c94-85f8-4b5ac7d3c348 | note | Standard / Specification - BBO
f69eb349-24e4-5224-b102-c11f69a02e54 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of mix
6ee203d5-4402-553b-9e7e-47f4ba7cbbe3 | note | Frequency - Every Rain Garden
605bfe48-7198-58ff-9fad-ec8a176bd576 | note | Verification Activity: Activity - C
307a0731-98f3-5b73-ad12-73bb724f239e | note | Verification Activity: By - SE
| checkpoint | 4.01.08 - Coconut (Coir) Matting
b2149d44-c2c0-5ac7-9f23-e68e78f6f815 | note | Acceptance / Conformance Criteria - Biodegradable Erosion
ea308e43-ecf5-5f65-b7e5-28c8654bc6f6 | note | ○ Mat (Coir Mat). Biodegradable mulching fabric 450 gsm
5d071044-7ba5-5cda-be9e-315e9adf188c | note | Standard / Specification - DWG 2195 REV1. Schedule SP2 4.3.7
cdfa223d-c4f4-58a3-be1f-fe5d0a75a973 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of mat onsite
e9f1e6e3-856f-5b65-9c7c-93bbe37ad83a | note | Frequency - Every Delievery to Site
ff7e18fe-40d0-5df1-9789-39211dadab87 | note | Verification Activity: Activity - C
a380baee-ac44-5f56-b581-48c0f2cf96fa | note | Verification Activity: By - SE
| section | SECTION 5 – CONSTRUCTION ACTIVITY
| checkpoint | 5.01.01 - Set-out
600f05d5-cd60-5a54-b4f3-2746d702ac26 | note | Acceptance / Conformance Criteria - Check set-out prior to excavation of Rain Garden.
4493c0d8-0bc6-5b9b-9727-0623d648a1e6 | note | Standard / Specification - PS - 2.2.12
cee83049-a5b9-512b-ae6c-d75b343325cc | note | Verifying Document - Hold Point Release
f36a231e-d26f-57b2-859d-d1e72bdf2998 | note | Frequency - Min 48h Notice
1d930587-40d8-5f7c-8e59-576f65ded1bb | note | Verification Activity: Activity - H
55190d5e-4025-5a63-b39a-ff7f394c4771 | note | Verification Activity: By - SUP
| checkpoint | 5.01.02 - Excavation
4a27e751-010c-5453-88dc-0e8767489641 | note | Acceptance / Conformance Criteria - Excavations shall be completed in such manner that it is true to the drawings will allow novacoil to be laid true to the depths, grades and lines.
59d30fcb-b799-5c41-b903-9463f1a2acc8 | note | Standard / Specification - Downer
f4fa8486-f648-5d56-a446-e39e7c3fcd69 | note | Verifying Document - Survey Data, Photos
815aa440-231f-51d6-b6d4-041fd2de20a9 | note | Frequency - Prior to laying filter cloth
5629bd6d-6da9-5095-ade7-bac1103dce26 | note | Verification Activity: Activity - H
1080d04e-7ae6-591a-ac8a-93028cef5cd2 | note | Verification Activity: By - SV
| checkpoint | 5.01.03 - GCL Liner Fixing to Kerb
5cd2247f-913c-5193-b633-30ebcf20b4da | note | Acceptance / Conformance Criteria - GCL Liner to be fixed to kerb as per manufacturers guidelines (Bentofix GCL 18.2, figure 14). Mechanical fasteners with stainless steel batten (connection bar) to be used to fix the liner to the kerb. Mechanical fasteners to be fixed 5 times ever meter of along the connection bar.
4c1f2594-00c0-5cb4-b283-270f41f3f716 | note | Standard / Specification - Manufacturers Guidelines 18.2
60ef2f84-00c4-54b4-a9ff-5fc8cd8012d5 | note | Verifying Document - Site Photos
fb8d44b4-9b70-5121-a5a5-fb84a118abe8 | note | Frequency - Prior to backfill
10d47998-5f5b-5baa-b21d-17ac73bdb5e2 | note | Verification Activity: Activity - I
926dcbb4-ecc0-5621-b441-bb0f962cb374 | note | Verification Activity: By - SE
| checkpoint | 5.01.04 - GCL Sealing (Pipes)
a1b6b76a-586d-5295-b07d-7a199bfc1d7a | note | Acceptance / Conformance Criteria - GCL Liner to be sealed around pavement drains and stormwater lines which connect into rain garden. Sealing shall be completed as per manufacturers guidelines (Bentofix GCL 18.3 & 18.4 Figuire 15). GCL shall be cut with a sharp utility knife. For horizontal pipes, vertical laps of min 1m are required. Inside the rain garden a clamp shall be used anchor the GCL lap to the pipe. Bentonite paste shall be be used in the void between the main GCL and GCL lap to ensure a water tight seal.
667d5700-5b1a-5c50-9b96-e7dc61aedb0e | note | Standard / Specification - Manufacturers Guidelines 18.3 & 18.4
909e44a4-da81-51e7-a4a4-62e5b4f0640c | note | Verifying Document - Site Photos
4bffd81b-50ac-5aac-a8a0-ec538efcc69c | note | Frequency - Prior to backfill
c7d9b028-9831-57e7-bf77-8a4e9c71b44e | note | Verification Activity: Activity - I
7c4a97d2-10a0-5a7b-bb34-1bfe52d32963 | note | Verification Activity: By - SE
| checkpoint | 5.01.05 - GCL Repair
1b1258e3-9755-5f6e-9172-c7e48ee5dcef | note | Acceptance / Conformance Criteria - GCL to be repaired as per manufacture's guidelnes (Bentofix PVB5100c). GCL becomes damaged, torn or punctured during installation, the affected area should be repaired. For damaged areas, a separate piece of GCL shall be used and extend past the comprimised section by 500mm in every direction. Bentonite shall be used to connect the seperate GCL to the main liner.
83b9ad06-5588-58d7-9d75-46a86a271b3f | note | Standard / Specification - Manufacturers Guidelines 21
3eb9fe2a-43a3-5a97-8958-25889e12c7a6 | note | Verifying Document - Site Photos
8cb2aa44-5657-5ed3-9e0c-1a004d9d5685 | note | Frequency - Prior to backfill
1dde0c36-378e-5da4-abd1-af3d767a5e64 | note | Verification Activity: Activity - I
06d19e04-674c-52fb-b0c6-f26fea2cea48 | note | Verification Activity: By - SE
| checkpoint | 5.01.06 - GCL Inspection
f68ab60e-2892-5e0d-b81b-ba30fd0d67fd | note | Acceptance / Conformance Criteria - GCL to be installed as per manufacturers guide and true to the drawings.The inspection should include overlaps, alignments, penetrations, connections, detections of any defects, including installation damage.
44c1fa93-473b-5b99-8da5-1d39bc90a737 | note | ○ Detected falsely installed areas shall be marked, repaired and the repairs shall be inspected and approved engineer.
6d8921ad-6f4a-533a-b456-792ec29c7d0c | note | Standard / Specification - Manufacturers Guidelines 22.2
ffe309d9-a9be-5376-bf41-bc762cea8a81 | note | Verifying Document - Site Photos
dcae8388-5132-5ced-8c26-518881685a51 | note | Frequency - Prior to backfill
1d1a34d5-8d49-57ef-b8fa-5326f02f2d1a | note | Verification Activity: Activity - HP
942e0f00-fc57-59f7-8192-02b5d3a225da | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.07 - Geotextile Installation
a29735f9-34eb-5a9c-a394-c3bc94154550 | note | Acceptance / Conformance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
d6869b93-3017-51ce-964f-159a3b47048e | note | Standard / Specification - GWS 3.2.3
6ffb215c-94e6-5854-b098-3e6eb31dfc2b | note | Verifying Document - Site Photos
4d9f8add-0e77-5722-baab-9e5e5766d4f0 | note | Frequency - Prior to aggregate placement
ffcc9995-ac25-5f61-95d2-41588d654df9 | note | Verification Activity: Activity - I
2070edc2-cb6c-5037-b67e-f39f11a7ec1d | note | Verification Activity: By - SE
| checkpoint | 5.01.08 - Bedding
44edf9b1-5f71-5fa1-ad4c-0a9d944929b0 | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
13e34238-b4ca-56ac-a4de-5bc5716b5d63 | note | Standard / Specification - TNZ F/5
da7f24f9-3732-500b-888d-2d2144d17cce | note | Verifying Document - Photos, Sruvey Data
a3a98082-d942-5028-9afe-2b1040219ee6 | note | Frequency - Prior to laying Novacoil
e065347c-a0dd-5d45-840f-f3bff790f901 | note | Verification Activity: Activity - I
a394516c-2836-5ca3-9fc0-75035d15247c | note | Verification Activity: By - SE
| checkpoint | 5.01.09 - Joining Pipes
182f1c45-9999-59ba-b4b3-1f830467bb15 | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
86540013-2f92-5552-826d-5b7bf226eae6 | note | Standard / Specification - TNZ F/5
96de2e5e-1bd4-5bfb-86ea-ab510f833971 | note | Verifying Document - Copy of delivery dockets, photos of joins onsite with tag showing class
21a889e4-6cf2-548b-8830-fda70e6424b2 | note | Frequency - Every join
ebab9131-d025-539d-9379-126751b0a827 | note | Verification Activity: Activity - I
6d1363a4-ba95-5a8b-b91a-72f47b42c1e6 | note | Verification Activity: By - SE
| checkpoint | 5.01.10 - Pipe Grade
5ce789c6-6ee6-5be9-b07a-73a23d6afd19 | note | Acceptance / Conformance Criteria - Grade of subsoils must be falling in the correct direction based on the IFC Drawings and at the correct grade (greater than 1% based on TNZ F/5)
308913a1-b89b-5266-8230-723fd382cbc2 | note | Standard / Specification - TNZ F/5
8bee89d9-8267-5038-af59-eb0b8a14320d | note | Verifying Document - AsBuilt
b5937b6d-dee4-5863-a7e9-fe84d6368bfd | note | Frequency - Every 10m
99ae9c11-dab5-5e11-88e4-5e62e5760cb6 | note | Verification Activity: Activity - H
f3b63dcc-8c18-5779-bb93-65d3a75ca474 | note | Verification Activity: By - SV
| checkpoint | 5.01.11 - Pipe Cover
45f6b39b-faef-5d70-83a8-96fbb3919e86 | note | Acceptance / Conformance Criteria - Pipe to have 100mm of drainage aggregate as top cover for pipe.
b2f4089d-485a-5329-bebb-33c600709fd7 | note | Standard / Specification - N/A
6243c14d-2fd7-58e1-af45-9ea75de8ed78 | note | Verifying Document - Site Photos
fb4ecb70-d7d8-5353-8528-e5366b4f1ef5 | note | Frequency - Every 10m
3eba3e8b-6bd9-51eb-9f13-65c91c42ced7 | note | Verification Activity: Activity - H
8e10125f-9c86-5eb8-b4c6-c8d35c42af68 | note | Verification Activity: By - SV
| checkpoint | 5.01.12 - Sand Placement
39c4cca1-9cf9-5fcb-9d92-14c46d00df2d | note | Acceptance / Conformance Criteria - Sand to be placed at a constant thickness of 100mm. Sand should be free of peaks and troughs.
12559d02-92db-5d69-922d-d36d03b735c2 | note | Standard / Specification - N/A
83f0147f-7607-5108-9dd6-e7e33a01c13a | note | Verifying Document - Site Photos
a4f2c54c-4dd2-5e5e-8c93-141232aa35a6 | note | Frequency - Every Rain Garden
79130b52-d4cf-5bd5-a1b7-64d5cbf8292a | note | Verification Activity: Activity - I
d1a9f347-148a-529d-9e40-6c028f31167b | note | Verification Activity: By - SE
| checkpoint | 5.01.13 - Filter Media
89017aa0-48c4-538e-9a49-394f4a9415bf | note | Acceptance / Conformance Criteria - Filter media to be placed at a constant average thickness of 600mm, refer to drawing for detail. Filter media should be free of peaks and troughs.
fec33b6a-952e-59b4-bbdb-e728f3c2c2cb | note | Standard / Specification - N/A
31082cfa-3a10-5cb8-8367-0f1a29afca37 | note | Verifying Document - Site Photos
50160857-86c6-590c-b455-ea9a3457241d | note | Frequency - Every Rain Garden
4820cfd2-6c04-5db0-b627-e12d02994a3a | note | Verification Activity: Activity - I
d400e801-9172-54c9-a25d-656c4f6779bf | note | Verification Activity: By - SE
| checkpoint | 5.01.14 - Coconut Matting
d314f001-d64e-5690-984b-d6f0f417c538 | note | Acceptance / Conformance Criteria - Mat shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
21594c11-04a8-56e4-8267-7b263e7a0a70 | note | Standard / Specification - GWS 3.2.3
a093a406-d1f3-558a-89f1-58230e400337 | note | Verifying Document - Site Photos
348ffcaf-297f-5053-9328-330398f1b4c1 | note | Frequency - Every Rain Garden
f341404c-5bca-5784-9fa9-233677b37665 | note | Verification Activity: Activity - I
738700f5-6608-5a5f-9f4d-4448e1f52b53 | note | Verification Activity: By - SE
| checkpoint | 5.01.15 - Scour Protection GAP 65 Rip Rap
a153e58b-fe5a-52f4-a40c-413447caaee1 | note | Acceptance / Conformance Criteria - Scour protection shall be installed as per drawings around let downs, scruffy dome and the flush point end.
842ef001-1887-5763-9452-83ad19265168 | note | Standard / Specification - GWS 3.6 & BBO
16b96443-9310-5c47-9c54-c3900d0c4ea7 | note | Verifying Document - Site Photos/ Survey Data
1371382c-d043-5dc7-8622-93265a43e5c3 | note | Frequency - Every Rain Garden
fc74b2fe-916c-51da-87ba-f437eebd4b06 | note | Verification Activity: Activity - I
047d71c0-11bf-5ac7-a1f5-ab47bf21e5f8 | note | Verification Activity: By - SE
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 6.01.01 - Construction Record Compilation
305b604d-63af-5a53-a11c-ad86f47fc8e6 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
34ad28d5-f430-523d-82bb-725cf094c681 | note | Standard / Specification - Downer
54b8020c-b526-5e03-9b88-ee358fc56a95 | note | Verifying Document - Records
82931b34-5b61-5522-b03f-750a4a203559 | note | Frequency - Post construction
34e75775-ad54-5544-aafd-710aee05a3b0 | note | Verification Activity: Activity - H
9fab602f-4544-58af-9146-3e170b4b9e7f | note | Verification Activity: By - SE
| checkpoint | 6.01.02 - Survey Records
75612203-35cc-50ca-99af-d6940a3d4b1b | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
62ce2c95-23d7-5e9f-9eb5-873f8570dc4d | note | Standard / Specification - Downer
69be40fe-abd1-5235-8a5d-1deeee39adab | note | Verifying Document - Records
6f33c896-49e0-55bc-b5f5-fd20510fe684 | note | Frequency - As-builts taken every 10m prior to backfill
67c35579-6e93-5cab-9af8-6507322f38e6 | note | Verification Activity: Activity - H
42089a71-816d-5dbe-a2cd-6d348fe31e36 | note | Verification Activity: By - SV
| checkpoint | 6.01.03 - Redline Drawings
d102114c-c9a7-57ea-a50b-c97676639cbb | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
d1b26aec-3938-56d4-bfd2-b63867827f5f | note | Standard / Specification - Downer
c68c40c9-67a0-53b1-9e59-e46c6be6c9c7 | note | Verifying Document - Redlines
f6c46ea3-f969-56a4-b139-1b3cd17269c3 | note | Frequency - Post construction
e50a5760-26e3-5920-8abf-6644c9d59ceb | note | Verification Activity: Activity - H
afd1a16d-47c6-512f-8f51-d27376473de7 | note | Verification Activity: By - PE
| checkpoint | 6.01.04 - Defect, Snag and Punch List
b5af6412-179f-542c-8cdf-cc6533e91c5e | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
de65548a-b3e4-582d-b55f-b0dcaa214093 | note | Standard / Specification - Downer
bfe471c2-4587-52fb-a949-719e33696257 | note | Verifying Document - Register
9779e2b9-a1fe-520a-be31-ecc6bbc102b6 | note | Frequency - Post construction
2288330e-eea2-5250-aaa8-68a85fb03d02 | note | Verification Activity: Activity - H
9faa3bc2-9c9e-5b0e-ac99-e5ef487319f1 | note | Verification Activity: By - PE
| checkpoint | 6.01.05 - Photos
ab1da870-da7a-5fb9-8982-88c1abf53033 | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
57e29fcf-0a48-5d29-b1aa-653496a43e32 | note | Standard / Specification - Downer
6b4aef35-4b9a-5854-9860-bf464cbaba90 | note | Verifying Document - Photo Records
8dd7e61e-c163-5706-8b5a-7e8441532e31 | note | Frequency - Post construction
834d8cc4-474d-518b-ac3d-c9bbe7a931f1 | note | Verification Activity: Activity - H
c67803bd-73f2-5315-8a9f-2e8b104e1fe1 | note | Verification Activity: By - SE
| checklist | ITP - 131 - SWD04 Eastern Gully Works Rev E | itp | ITP - 131 - SWD04 Eastern Gully Works Rev E | 9ee30323-c995-4b61-90d1-e4e6987a8340
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
17053592-32f5-5964-84d1-bfea17c64d15 | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
80553e45-1f94-584d-8d6c-8178552abd7e | note | Standard / Specification - Downer
340370a0-d3ee-51d6-8764-a6acc65e4d31 | note | Verifying Document - Construction Pack
b61c2550-a291-585d-b778-21cdd0e147e5 | note | Frequency - Submit 10 days prior to commencement of works
458dd144-001a-5c09-afc1-f89fc47a9415 | note | Verification Activity: Activity - HP
a328997a-80d0-587a-92c1-e33597cee564 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.01.02 - Survey Setout
de0209dc-910e-5370-85ed-9de131b9dc73 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
f591bd3f-9ccf-503f-9aa7-ed87a951a6c8 | note | Standard / Specification - Downer
92088bb0-3b45-5e46-a8ad-d66f647402e1 | note | Verifying Document - Survey Records
37c006b8-6c13-5399-b4a1-c7c1ac78e6c2 | note | Frequency - Prior to Works
54579433-b13b-549c-a7f8-31b3b6986df7 | note | Verification Activity: Activity - H
f54aa70b-fdf0-5135-ada5-eba098a81493 | note | Verification Activity: By - SV
| checkpoint | 3.01.03 - Service Location
dbae9da8-ed02-5f01-b8cd-3888ebc18c9b | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
a287c49f-12f1-5f16-a218-f8305b0226b2 | note | Standard / Specification - Downer
fae85e2d-319b-515b-bcda-801ff483d7bf | note | Verifying Document - Excavation Permit
2bb9f676-6ec3-5eb9-9962-4c520480a7f7 | note | Frequency - Prior to Excavation
99c64542-048c-51a3-adeb-69ccf8543cd8 | note | Verification Activity: Activity - H
a46cb02c-9bd8-5c51-a29b-eef5aa72e75f | note | Verification Activity: By - SE
| checkpoint | 3.01.04 - Internal Permits
eefac666-e679-5fa9-98d4-725e56d9ca6b | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
a7336049-1dc9-5bd5-a778-15cc2961a9d6 | note | Standard / Specification - Downer
417c04fc-f5ee-5081-8a81-d15401e4000f | note | Verifying Document - Internal Permits
acfd012d-7bb5-533c-bf2a-52c5454ebd3a | note | Frequency - Prior to Excavation
f6d6554d-e80b-51e8-8f10-56e1ccd59d1b | note | Verification Activity: Activity - H
2a8b1cb6-0942-5af7-9789-c2fbd8664608 | note | Verification Activity: By - SE
| checkpoint | 3.01.05 - External Permits
179271ab-fcfc-5718-a548-075031a6f706 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
39714b05-7f05-58ba-aaf5-ab942adf357f | note | Standard / Specification - Downer
51bad531-352d-5a1d-bedf-29a6332b94e6 | note | Verifying Document - External Permits
fc84a512-59d4-5146-ae31-1510948aeffb | note | Frequency - Prior to Excavation
515f7fe9-5dde-516a-9291-c0f4cf5ae3d1 | note | Verification Activity: Activity - H
9e28b133-9ba4-54ee-b473-4ffccb0ec7b5 | note | Verification Activity: By - PE
| checkpoint | 3.01.06 - Approved Construction Drawings
7988cb2f-0e53-5528-88a2-adc46d9e766e | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
118e6f3e-0649-5c67-8339-1215aeaf582f | note | Standard / Specification - Downer
2ef056cf-ba4d-59a7-8bc9-68873aa644f3 | note | Verifying Document - IFC Drawings
2f5caa0d-2161-5849-a203-e1e49530983d | note | Frequency - Prior to works start
b8e3a7cc-b20e-5011-8bba-bdf3b1f4a3cc | note | Verification Activity: Activity - H
99f31c97-3036-550a-ae61-fc2c45fdc826 | note | Verification Activity: By - PE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 4.01.01 - Fish Relocation
7a31ab84-0a36-595b-8812-5362424c114b | note | Acceptance / Conformance Criteria - In-Streams works to be carried out between Jan to April. Fish relocation to be carried out by Ecology NZ as per FMP requirements.
cadc9f43-d95b-501f-8d01-944c225af3e7 | note | Standard / Specification - Fish Management Plan
fc7ba2b1-121a-5451-a39a-780650172bf1 | note | Verifying Document - Ecologist Memo
86f8823c-38e6-526f-8f32-20734f0587c3 | note | Frequency - Prior to in-stream works
32191ef6-9e57-5f9f-becf-e5a2e42ea1df | note | Verification Activity: Activity - H
e466b861-03d3-5401-91ab-f72a1c752641 | note | Verification Activity: By - SE
| checkpoint | 4.01.02 - Tree Clearance
5139519a-80ab-5512-bb6b-3c71fdbf4e37 | note | Acceptance / Conformance Criteria - EcologyNZ to inspect trees for fauna prior to removal.
f785ff5e-3874-5965-80f9-4121552723ff | note | Standard / Specification - Bat Management Plan, Lizard Management Plan
b9aa0be2-c271-522a-8631-7fa5d03ae257 | note | Verifying Document - Ecologist Memo
c790dd7a-199a-5f22-bc77-0220f05ebe93 | note | Frequency - Within 24hrs of tree felling
1c70fe35-09e1-50c1-9c4a-ce8fa7d36ab1 | note | Verification Activity: Activity - H
2be4ee2e-07f9-51f6-bc6a-842b17cae378 | note | Verification Activity: By - SE
| checkpoint | 4.01.03 - Weir Clay Fill Material Testing
2bf512e2-5b5f-5663-85b5-3c6a5f3c2722 | note | Acceptance / Conformance Criteria - Standard Compaction
978a2bcb-a9ca-5350-be0a-eca7c130f120 | note | ○ Minimum 30% fines content.
943d2135-a08c-5752-9a07-b2fc817ba251 | note | ○ Plasticity Index 16-30, Liquid Limit 30%-60%.
f0204c93-8d04-55a6-af94-83750f5ef3bd | note | Standard / Specification - GWS Table 1
5717fc90-de7e-59f0-8ec8-fd6a49ad8992 | note | Verifying Document - Test Results
d78f81a4-43ef-5ad4-ba84-0f94507b40ac | note | Frequency - 3 initial tests per source of fill
b48b4773-ed5f-5042-a486-2b62142981a7 | note | Verification Activity: Activity - HP
34d6fb86-d54a-56f8-b44d-937a37e76b77 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.01.04 - Grouted Boulders
58eccf7c-fd9f-53c6-84c1-7be60c8b55eb | note | Acceptance / Conformance Criteria - Boulders to have specific gravity >2.1, be clean and crack-free.
8b66f255-4bb6-5a92-826a-63ef763d5fa9 | note | ○ The grout shall meet NZS 3109 and be kept wet 12 hours post pour.
d21ca87a-7407-5d3e-b0f6-249ac2cce010 | note | ○ Grout should be recessed 1/3 the diameter of the boulders' side facing the channel.
e8992f9b-eadf-542d-8f50-98bcbb23b069 | note | ○ 48 hrs before grouting, placement must be inspeted by Engineer.
6c6fab36-dc7e-5e93-8d02-a5c47f8ac03a | note | ○ 20MPa concrete.
22cdb040-c28a-5ce9-a355-f4c41f8dc952 | note | Standard / Specification - Project Specification 4.7.6
4c79d79f-1cc7-5689-b0c8-f484a2f87fc5 | note | Verifying Document - Material Certs, Concrete Docket
51e959f3-0e82-516a-b662-a3f981c6b52c | note | Frequency - Before Delivery to Site
9a0d8e75-881f-5a43-9a6a-1a7cbeb9eb81 | note | Verification Activity: Activity - HP
2ec5613f-7915-5025-8739-2e15b00530b4 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.01.05 - Riprap Material
a4b4fba3-fd23-5c20-a846-c814587f1dbe | note | Acceptance / Conformance Criteria - Density - Greater than 2.40t/m3
0b6d42f5-c833-542e-92d9-3b0c4b7caefc | note | ○ Crushing Resistance - Not less than 150kN
ffbfb70e-4b3b-5326-8f17-be7296ddcc70 | note | ○ Weathering Classification - AA, BA, AB or BB
557610b7-6a1e-53e1-b788-e7412b3f5574 | note | ○ Abrasion Resistance - Not more than 26%
8c242084-b004-5efb-bd21-cf8aff3227ef | note | ○ Calcite intrusions - Rock shall be free of calcite intrusions
99d917eb-cff1-5ada-b18f-f6cb3c681d41 | note | ○ Grading - Rock for riprap shall be the nominal D50 size shown on the drawings and shall be well graded.
8c16c804-0135-5bc1-b1b3-0cdd834027c4 | note | ○ If riprap product is unavailable, alternative material to be approved by designer.
ee9c06e1-d8f5-59de-a60a-390ceb60df45 | note | Standard / Specification - Project Specification 4.7.1
749cb8ff-6c1f-5602-b3bf-db757d14e772 | note | Verifying Document - Delivery Dockets, Lab Reports
a4e3f4a8-d5ab-5057-a9d4-52ee80ecb9ab | note | Frequency - Per Truck
60b5ae32-41fc-5ec5-b5b4-65c4ccc2439c | note | Verification Activity: Activity - HP
3f47884e-6e2f-5c00-a96c-9cc6212ddd75 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.01.06 - Bulk Fill below Clay Fill
01f01445-6adf-5fc4-9408-093779ebfc3a | note | Acceptance / Conformance Criteria - Maximum 10% fines
b25282f8-bd05-549b-986a-c9c3d053bb43 | note | ○ Blue/brown run of pit material (not too weathered)
ed0a1e31-74a5-5af3-a12f-6df660a88bf1 | note | ○ Wrapped in a geotextile (strength class determined by the clast size of aggregate)
e1051fe8-a4e2-5a6f-a613-cf1ad87ea962 | note | ○ Maximum clast size 200mm. All larger blasts to be broken up.
d58762b7-a7b9-581a-9c03-5fef9e31d19d | note | Standard / Specification - Desiger
d08dbe47-03eb-55b9-b640-bc02e1016c72 | note | Verifying Document - Delivery Dockets, Proof Roll Testing
027be3b0-62f9-5fe2-89a1-77a65e312297 | note | Frequency - Per Truck
8afc855e-ebfb-5b4b-af9a-bc076ddcd0ad | note | Verification Activity: Activity - HP
4ba781a9-dc8b-5136-bd80-d9e7946f12a2 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.01.07 - Grout
d317f3c7-d6ff-5297-a732-3357f201e412 | note | Acceptance / Conformance Criteria - 20MPa Grout mix design to be deemed suitable by designer.
67e76c51-bbb8-5cf8-a2dc-fdde6222f50c | note | Standard / Specification - Designer
f9f54fe0-2d28-54c0-9034-4afd79a46d00 | note | Verifying Document - Record of Approval
4abda46c-3e01-5826-9c05-5e4c9ae40faa | note | Frequency - Prior to use.
5539174c-badd-5536-a805-d425c766986b | note | Verification Activity: Activity - HP
545f8d72-9a74-5500-bb77-330462258c88 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.01.08 - Geotextile (Base of Undercut)
ad2e936b-0d4b-52fa-857c-c7790cbe3908 | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C geotextile installed at the base of undercut.
b3ec8265-9e3c-58f6-b6f9-7e24607ecce6 | note | Standard / Specification - Designer
e00cb19c-2430-512f-8f35-c6139e63ec25 | note | Verifying Document - Dockets
6fa8b98b-b539-5685-b1eb-a4feee44adbc | note | Frequency - Per Delivery
03ec3c61-27e0-5be3-8454-0399610f8aac | note | Verification Activity: Activity - C
25799180-cabb-5948-a273-13f3e0a3c043 | note | Verification Activity: By - PE
| checkpoint | 4.01.09 - Geotextile (Top of Rockfill)
1484735a-c95b-51a5-bf33-47377b74e5ed | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class E geotextile installed on top of finished rockfill surface. Only required if GCL is installed.
254eec6c-1835-5ac9-a1c3-4c12d9399ed3 | note | Standard / Specification - Designer
bf98bbb7-6468-5bc7-ae61-f8c422796f39 | note | Verifying Document - Dockets
7cfd4bfc-73d8-5091-be9c-9dfde21c41d6 | note | Frequency - Per Delivery
c4aa5d90-a132-574f-ad0a-4e9f87b5a37f | note | Verification Activity: Activity - HP
14e1a407-806c-599f-a125-215a0da03bc1 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.01.10 - Geosynthetic Clay Liner
f798af58-e4d5-5ba3-87a9-883cb185261e | note | Acceptance / Conformance Criteria - Elcoseal GCL to be deemed suitable by designer. X800 grade to be used unless otherwise advised by designer.
ae08dbb7-fe74-55a6-8c9c-acc48c0c6898 | note | Standard / Specification - Designer
22194dc5-267c-5dde-b3f8-a947c37bd048 | note | Verifying Document - RFI
3590c85f-23d8-5b81-9eb7-e39bafec12fd | note | Frequency - Prior to use.
1b7d15cb-f69d-5082-8f21-da9825d313b6 | note | Verification Activity: Activity - HP
00ad5173-b4d7-56d8-b698-107ac2682867 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.02.01 - Pipes, Fittings and Pre-cast Structures
5694908b-a763-5386-bbfc-e869190d9908 | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes/catchpits are correct and in good condition and compliant.
9667d322-e54e-58d8-bf8e-890f350518b3 | note | Standard / Specification - As per design
483b1bed-131c-5a70-ba89-4a84d2c1fe85 | note | Verifying Document - Delivery Dockets
920d35f7-38d2-5003-be20-f7d4b0026d4b | note | Frequency - Per Deliver
34722adf-8440-5111-a249-25ca9d27fc05 | note | Verification Activity: Activity - S
0b042295-333b-5a2b-ab64-a1277ad5c8b9 | note | Verification Activity: By - SE
| checkpoint | 4.02.02 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
4e2afbec-77ce-5ff4-8940-052d8ebbd4de | note | Acceptance / Conformance Criteria - Pit sand, PAP 5 or an equivalent material approved by Engineer.
284a5bae-1a8c-5c46-a7ba-c40a016e7d31 | note | Standard / Specification - Project Specification
a2a5892e-284b-5a27-a452-b0113afba679 | note | Verifying Document - IANZ Lab Test Report
c04e6e94-1d0a-5b48-a0ac-ab01db1c0d18 | note | Frequency - 1 Test per 1000m3
27d9c726-f8fa-53fb-8e80-d96a1be49381 | note | Verification Activity: Activity - H
d046acea-3a80-59ee-90f9-f397a9b31f72 | note | Verification Activity: By - SE
| checkpoint | 4.02.03 - Quick Mix Concrete (Haunching)
fc3e01ce-01ef-5844-8f70-d7da1298aa08 | note | Acceptance / Conformance Criteria - Mixed as per manufacturer's requirements
a8af5beb-bb93-5159-aff7-59df9dedfa3b | note | Standard / Specification - Minimum 20MPa concrete mix
9b15bb09-058c-5d4f-948a-cc5eee3223b4 | note | Verifying Document - Photographs
69cd3e5e-99da-533d-9ac8-29ad708dd47a | note | Frequency - Per Application
5a475ae9-4645-5524-830f-947eab89cc93 | note | Verification Activity: Activity - C
f27f1980-86fc-519a-8185-23f3cd4efb88 | note | Verification Activity: By - PE
| section | SECTION 5 – CONSTRUCTION ACTIVITY
| checkpoint | 5.01.01 - Erosion and Sediment Control
f11b4a19-70d8-5132-9b72-76475c93370e | note | Acceptance / Conformance Criteria - Super Silt Fencing and Silt Fencing in place as per ESCP Silt Buster to provide sediment control for weir.
c63ec11a-068d-5925-8eef-8b26bcdde96e | note | Standard / Specification - ESCP WRC TR0902
3bf5ab1c-d45f-5e3f-86ee-c66e26eef8e8 | note | Verifying Document - Enviro As-Built
0c76fa4f-c4f0-50a7-a993-f8b3b3c8db55 | note | Frequency - Prior
a23355b8-d70b-595e-bdd0-e9dec7d46533 | note | Verification Activity: Activity - H
6af6abb0-de5e-5576-894c-47af67b651cd | note | Verification Activity: By - SE
| checkpoint | 5.01.02 - Upstream and Downstream Bunds
54acba75-8db2-5cce-8b2f-bc3ed58af3f7 | note | Acceptance / Conformance Criteria - Temporary dam constructed via 1m sand bags, stacked up to max 2m height. 600mm rigid pipe at stream level to connect to 600mm flexible flume.
f3f06d3c-e123-5971-b3b2-3a175f2c10bf | note | Standard / Specification - ESCP
34926255-14e2-5e92-b995-8b915ec1abe1 | note | Verifying Document - Enviro As-Built
1e7d39ef-7cb2-50d9-a407-b9b86775bfd3 | note | Frequency - Prior
073b8feb-68a1-5c9b-b303-c76ecf526001 | note | Verification Activity: Activity - H
d4b50985-804e-5aa6-b796-661d2722d29e | note | Verification Activity: By - SE
| checkpoint | 5.01.03 - Dewatering
f058a380-8e7a-5019-8f1d-4645f78c7c34 | note | Acceptance / Conformance Criteria - Water from downstream bund to be pumped to Lamella Clarifier and discharged under into the stream further down.
29a44ca8-7729-5464-9319-e725072da56f | note | ○ Treated discharge into stream to be between pH 5.5-8.5. TSS limit 150mg/l. Turbidity limit 50NTU or 100mm clarity. Non-compliant discharge notified to WRC within 24 hours.
51660c33-51fc-58c8-b474-890b7e9833c1 | note | Standard / Specification - ESCP / DMP
6a94940e-a469-598e-84be-1e8e4fe2870e | note | Verifying Document - Enviro As-Built
b0d79beb-315c-58fd-9a82-75df05093b9f | note | Frequency - As required
0afcb97c-4cd6-5f80-8cbd-f35f32b1d983 | note | Verification Activity: Activity - M
f706d808-605c-584e-a138-e3dfc323310f | note | Verification Activity: By - SE
| checkpoint | 5.02.01 - Preparation for Filling
b51c54e2-b0a5-57af-bcf5-a96598d301a0 | note | Acceptance / Conformance Criteria - Preparation of the firm to stiff / medium dense subgrade beneath the proposed fill areas should comprise stripping of all vegetation, topsoil, any pre-existing fill materials or weak alluvium followed by benching of the exposed subgrade where natural slopes beneath the fill exceed gradients of nominally 1:5 (vertical to horizontal). CMW to inspect subgrade prior to placement of rockfill.
2e20430c-ea4c-5b22-8709-f8fdfdfe94e1 | note | ○ Benching in accordance with CMW sketch detail.
6f350a60-686a-5957-aee5-69957402de00 | note | Standard / Specification - GWS 2.9.2
0ea6e42b-57a1-55b0-ad32-f73daac24a3d | note | Verifying Document - Subgrade Inspection
b94816b3-e34e-5b19-bd0d-4fc4741fac49 | note | Frequency - Prior to placement and compaction of fill
89ef02a6-b38f-5b6f-a3c7-53d8df05b291 | note | Verification Activity: Activity - HP
7a9d41f0-1285-5b82-96ee-d2afb82f1552 | note | Verification Activity: By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.06 - Rockfill Installation
50d9325e-eb95-5fb6-99f3-9e427df1617f | note | Acceptance / Conformance Criteria - Proof rolls at 500mm lifts, to be observed by CMW.
ed71057a-9a00-589c-b7b3-66e2e01e8208 | note | ○ Rockfill to be fully wrapped in geotextile filter fabric, strength class c.
a410a494-1160-5ca5-8684-479a2147c3f4 | note | ○ Wrapping to be inspected by CMW.
1bbd5637-ad77-5c13-a5e4-9a97f9e71366 | note | ○ Upon completion of rock fill instalation, inspection by CMW.
865aff46-7bb1-538a-ac2f-59379a322c1f | note | ○ Sharp edges of rock (protrusions) to be minimised.
afab0fda-af66-561d-94c6-0f7d81172440 | note | Standard / Specification - Designer
dd8c4447-ec3d-57c6-81d2-fffa25453893 | note | Verifying Document - Proof Roll Record
d7ca839a-03f5-5550-b6fd-35d4f7b855e1 | note | Frequency - per 500mm lift
2bea75db-55e6-52c6-a011-804154480285 | note | Verification Activity: Activity - HP
4dce9bb9-f93d-5d7e-a9ba-d591af3dea14 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.07 - Geotextile (Base of Undercut)
63e95285-c783-55e6-ba38-fbbf0ca475c2 | note | Acceptance / Conformance Criteria - Class C Geotextile to cover the entire base of excavation and be fully wrapped around the rockfill material. Minimum 500mm overlap required.
c8331358-7126-5054-aca2-eb6e6a050945 | note | Standard / Specification - Designer
ae1033ab-5c52-58d4-bba0-3bc48274274c | note | Verifying Document - Photographs
cf6aced6-cc9e-581d-866c-e1461fc1ddcc | note | Frequency - every overlap
e4a05fc4-212d-53e7-92ee-0efe140b2bbf | note | Verification Activity: Activity - HP
4d48ab13-388f-503e-8e1e-8c1122cf2747 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.08 - Geotextile (Top of Rockfill)
7ba1d97c-9ca2-5db1-a8e7-7d3321039b44 | note | Acceptance / Conformance Criteria - Class E Geotextile to cover the entire surface of rockfill material between rockfill – GCL interface.
3142aa81-6172-5edc-ba25-6c0a5c0f7e4d | note | ○ CMW to inspect prior once installed.
d4d9617e-2c0b-59a0-8f94-d55f45d69fbe | note | Standard / Specification - Designer
5b67ce8e-2de3-5c1e-bd81-5375da872b74 | note | Verifying Document - Photographs
2d8953c8-99b5-546a-a9e4-cc7a8c7d891f | note | Frequency - upon installation
3f190c29-4f5a-5a9e-9541-1feaf505299e | note | Verification Activity: Activity - HP
e1cb2d67-f5e1-5684-8987-b56669fd7e62 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.09 - GCL
2acea702-e75f-576d-b392-eb8a75855d71 | note | Acceptance / Conformance Criteria - GCL to cover entire surface of rockfill material.
a853246d-aede-506c-a3f1-4c3f12de78f6 | note | ○ Installed as per manufacturer's requirements.
2e9e603c-abb6-5cad-a886-f8970fd6463e | note | ○ CMW to inspect once installed.
8a81350b-f176-5c49-a21e-3e289d9ca00f | note | Standard / Specification - Designer
d80b413f-dccf-5628-9854-163145872118 | note | Verifying Document - Photographs
0618005a-b774-5664-923f-e3bdeb795cae | note | Frequency - upon installation
5a258718-5ba4-5b36-8423-d15427813142 | note | Verification Activity: Activity - HP
31a0991b-bbd6-5559-ae41-4e571f69e0fa | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.10 - Topsoil
a6075a6f-1f76-50ee-8f44-0504ee590e83 | note | Acceptance / Conformance Criteria - Topsoil to cover entire surface of GCL. Minimum 300mm of coverage.
3382de70-34e6-5ba1-8f4e-d7bcb55a8885 | note | Standard / Specification - Designer
4a28bc8c-6123-5318-a28d-28ba4011c6ef | note | Verifying Document - Photographs
3b9b2f42-6f5d-5550-8f8c-972f548b0c97 | note | Frequency - upon installation
c239aaac-a412-5a17-99b1-392b4cb3f7a7 | note | Verification Activity: Activity - HP
720cd90e-415b-52e1-993a-42c05a901f63 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.03.01 - Foundation Compliance
b55ee95d-14d1-5650-9a65-a85b0438fd20 | note | Acceptance / Conformance Criteria - Clegg Testing to be carried out on pipe foundation.
60fc9774-3084-5bb2-a852-1b14c959dd04 | note | ○ Clegg Test to correlate to minimum CBR of 15.
cfab5ed2-96a6-568e-911d-193ecefcc720 | note | ○ Foundation for Manholes/structures to only be measured with Clegg CIV of where there is a rockfill foundation.
10ec5f8d-d064-5bea-a915-e8db5bb7314b | note | ○ Other MH's and impact basin structures are to meet the foundation requirement.
ce4e78a2-c8f3-5bcc-aedf-efa7cb08736e | note | ○ Granular Material: Scala 3 blows/100mm
f7a3018a-6e64-5b27-b3fd-683756608177 | note | ○ Cohesive Material: Vane Shear Strength 70kPa
1f1a0f08-4750-54a6-88a8-bbc7754b28a1 | note | Standard / Specification - Project Specification 4.3
b072b2ee-7b46-5da9-a951-0d9213bd0d91 | note | Verifying Document - Test Results
18646c9f-0410-5b79-b9c3-e0c87476e1ed | note | Frequency - 0-5m: 2 Tests
32773128-569d-5670-b036-6b68866eb2a7 | note | ○ 5m-10m: 3 Tests
c2c4bb2e-071a-57f2-8950-a6e3cefc4cd0 | note | ○ 10m-40m: 4 Tests
cadcbb97-8e16-57ac-b602-c0e31884f96e | note | ○ 40m-100m: 5 Tests
3fa32cbd-90df-5c0e-b615-b7d873f1f277 | note | ○ 100m: 1 test per 20m
ff2b2980-7d85-572b-8e8c-7fe9498da924 | note | Verification Activity: Activity - H
4a26bd66-f010-5521-bbd2-be2c3b2b41fe | note | Verification Activity: By - SE
| checkpoint | 5.03.03 - Bedding Compaction Testing
dc3a2255-a6d2-5ed7-abd1-bb346710260e | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement
a9da3725-1fac-5295-867a-87de4cfd3e80 | note | ○ H2 Bedding outside pavement
6abde6b9-1765-543c-8681-fce07700fdcf | note | ○ NDM Back Scatter
2f5ca1b4-d6b5-5aac-a3f7-14c3ba763551 | note | ○ Minimum Compaction 95%(Average98%) of MDD
dfbad3e7-4dc6-55cb-8f21-d1192edcb638 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD, AS/NZS 2566.2/2002
8e48f539-29c2-5f44-99a2-04efc63bc220 | note | Verifying Document - IANZ Lab Test Report
c47a15ec-bfa9-54e1-86d5-a46d9c885bcb | note | Frequency - 0-5m: 2 Tests
6ec5cfb0-7b3a-5a4b-b555-d5e13e2fce23 | note | ○ 5m-10m: 3 Tests
0f194002-52ac-5e1f-95af-8c3806469a31 | note | ○ 10m-40m: 4 Tests
95bc8d3c-4fcb-5e2a-9de1-a2b51ea42c26 | note | ○ 40m-100m: 5 Tests
dad51fd2-4980-5291-904d-c3da0e068299 | note | ○ 100m: 1 test per 20m
3d88fd0a-5c89-5723-9f19-33d051e2fa64 | note | Verification Activity: Activity - H
43bc6622-1ba0-54c5-a7c6-c46ff4469ea1 | note | Verification Activity: By - QE
| checkpoint | 5.03.04 - Haunch Zone Compaction Testing - Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
724d04b3-1b92-5cb2-88d8-463afe2f742b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 92% of MDD
f0859c49-ea0f-50c8-996e-0f2479497200 | note | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD, AS/NZS 3725:2007
9038c9e5-610d-59b3-8312-a2923c9d8ef9 | note | Verifying Document - IANZ Lab Test Report
4d28df91-1f42-5c4f-935c-c2adfe8fd29d | note | Frequency - 0-5m: 2 Tests
d02767d9-a864-5475-9f2a-5274910df8ca | note | ○ 5m-10m: 3 Tests
0001e8db-556e-5a89-a9af-7372a994e240 | note | ○ 10m-40m: 4 Tests
320febe6-d6da-5e86-ac6c-ab3b8f0e87ef | note | ○ 40m-100m: 5 Tests
3c999428-6307-5465-bed5-2675e24727e8 | note | ○ 100m: 1 test per 20m
c37ccf38-edde-5ad8-a060-e90ea4ee96c9 | note | Verification Activity: Activity - H
135cf194-9511-53f2-b8dc-756b00716020 | note | Verification Activity: By - QE
| checkpoint | 5.03.05 - Side Zone Compaction Testing - Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
7e66f36d-0397-5e63-ae0f-158519f7b143 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 92% of MDD
ce4e57ae-e943-573f-bb55-c3dd6d95889e | note | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD, AS/NZS 3725:2007
490c3461-9aeb-5f2b-aa76-162ec411e8b3 | note | Verifying Document - IANZ Lab Test Report
435ddc6f-54f4-58df-bd1b-a821a216ca8f | note | Frequency - 0-5m: 2 Tests
94551932-feb9-5f3f-bbbc-fef3af3a9dc9 | note | ○ 5m-10m: 3 Tests
8d084df6-6ff6-5ebd-8947-27cb10032328 | note | ○ 10m-40m: 4 Tests
2ddef54f-e426-584a-8ca4-d03643cbdd02 | note | ○ 40m-100m: 5 Tests
08f27d32-ed34-5691-9ce7-6bef771daecd | note | ○ 100m: 1 test per 20m
70b1094e-1ea5-541b-ac72-68409d26fb28 | note | Verification Activity: Activity - H
377815e8-475f-57e7-9101-fbafb0d1c3e0 | note | Verification Activity: By - QE
| checkpoint | 5.03.06 - Overlay Compaction Testing - Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
29f801e7-b1e6-5e0b-aa84-d675150e2695 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 92% of MDD
5ca94f16-1fa0-50b1-a67a-9befb9e9b614 | note | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD, AS/NZS 3725:2007
9af48a72-2b61-544f-af7a-bf8cdb1541c7 | note | Verifying Document - IANZ Lab Test Report
cc10a700-2dcc-5b32-8147-6f2f294065ed | note | Frequency - 0-5m: 2 Tests
0c050877-5d5f-5012-a46f-d1547cd84708 | note | ○ 5m-10m: 3 Tests
c0649d09-323a-5fa4-854b-453cd9075a03 | note | ○ 10m-40m: 4 Tests
32ff98bb-4691-5d3c-ac0d-89d09c079655 | note | ○ 40m-100m: 5 Tests
86e904ea-07a6-53b1-9799-d0da4911d327 | note | ○ 100m: 1 test per 20m
ecedb7ed-d6b7-5297-9e75-2458deed2574 | note | Verification Activity: Activity - H
74e071f4-61de-50e9-b082-3724631544a0 | note | Verification Activity: By - QE
| checkpoint | 5.03.07 - Backfill Inspection
dcf91b58-b051-58d0-9d26-2f5053684b85 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
03bf4ee6-950a-51c7-ab1a-19f369d3efaf | note | Standard / Specification - Project Specification 4.3
a88f1c7a-2f09-5411-8a2f-1af1e21e4eab | note | Verifying Document - Photographs
e6527e3e-8dd0-521d-aca1-3e32488276f5 | note | Frequency - Continous
bf88d45f-22b3-5afe-8489-92be6fea5740 | note | Verification Activity: Activity - S
449f8cad-da26-5363-8b85-5c192d2faaa2 | note | Verification Activity: By - SE
| checkpoint | 5.03.08 - Survey
a7dc218e-8f72-5db4-b3cd-087141213222 | note | Acceptance / Conformance Criteria - Invert Levels: The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified.
ced861f9-5ce8-578d-a0f6-58c592bd008a | note | ○ Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm.
210e443f-20bd-59ee-8b03-82f447d31bf5 | note | ○ Gradient: For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
935c4594-bbfb-5a26-8740-d9c4274a56d3 | note | Standard / Specification - Vertical tolerance +/- 50mm, Horizontal Between Structures +/- 100mm
a210ccf6-e41c-5981-bf51-75bdfce45c89 | note | Verifying Document - Survey Data
0c242641-004d-5f84-b5b5-f7022f76127d | note | Frequency - Continous
fb6640f8-9bea-5aae-870e-ed2792c874be | note | Verification Activity: Activity - C
e2c3b92d-93ac-5342-b6fe-14415b4c32cd | note | Verification Activity: By - SV
| checkpoint | 5.03.09 - Backfill Compaction Testing
e086987c-745d-5013-a75f-4a2757f3d279 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Testing to be completed on 300mm lifts of backfill - 95% of MDD at OMC (98% Average)
a2da9514-d309-5657-abc4-cd9467e73b00 | note | Standard / Specification - PS 4.3 NZS 4402 Test 4.1.2
4d870036-3fb0-5147-bec4-220f851d04be | note | Verifying Document - IANZ Lab Test Report
2d2765c9-b717-5902-a5ad-b7704afe8924 | note | Frequency - 0-5m: 2 Tests
e5ae1199-b69f-5685-8d16-01015b1b1445 | note | ○ 5m-10m: 3 Tests
9a3e4f2b-2c46-5886-8e2d-80c95bc4e4e4 | note | ○ 10m-40m: 4 Tests
c494ba11-12b8-5fe4-bd2f-b23a22f94ea8 | note | ○ 40m-100m: 5 Tests
d5add86d-8e88-58cf-959e-306c209d238b | note | ○ 100m: 1 test per 20m
94a72d94-9963-5ecb-8b15-1ea897990349 | note | Verification Activity: Activity - H
fd165329-6ad0-5b83-97a5-0648bf771ccf | note | Verification Activity: By - QE
| checkpoint | 5.03.10 - Riprap Mix
878b4941-3a10-5414-bfb6-564c591dd6ea | note | Acceptance / Conformance Criteria - Riprap Mix Materials to be stockpiled separately and mixed in a pre-determined ratio to make a suitable riprap product
e8343953-48dc-50fe-a1bf-72e00caa754b | note | Standard / Specification - Designer
6235149d-a239-561a-b44f-d5e4ae7b4ddf | note | Verifying Document - Photographs
713842cc-94b5-5097-a161-8542d23a60e7 | note | Frequency - Prior to Use
44ec665e-a01d-5890-b5da-e03ffe673a5f | note | Verification Activity: Activity - HP
1d54fdae-9110-51e6-b7ce-8db3f99eddf6 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.03.11 - Riprap Embedment (Fish Passage)
cdfc014c-a10d-548f-8d6f-c696941ac473 | note | Acceptance / Conformance Criteria - Riprap layer within 1200mm fish passage to be 400mm high. Pipe laser to be used to ensure compliance.
dcba4e6a-60c4-5713-8ad5-82ca7a07cab5 | note | Standard / Specification - Drawings
852c1f8b-9800-5f93-a3d4-383666e767dd | note | Verifying Document - Photographs
0f210afd-685f-5e6c-825d-04d32fe614d0 | note | Frequency - During Placement
7b30e782-8588-5692-97b3-b36e1c5baa5c | note | Verification Activity: Activity - H
69aec4db-4eb2-5dca-bfb1-24f55c110edd | note | Verification Activity: By - SV
| checkpoint | 5.03.12 - CCTV
bdd9892f-823c-5caa-8cdf-7c8ca33ec5e2 | note | Acceptance / Conformance Criteria - CCTV inspection of 750mm stormwater and wastewaterline. CCTV soft copy to be provided to designer.
0a974a2b-3145-535c-baaf-40d7c7c88a59 | note | Standard / Specification - Project Specification 4.4
890e9cbe-2bec-5e1b-915e-18ad6b2f3aa9 | note | Verifying Document - Soft Copy
26593b59-9967-5f89-ace2-af0abc2c2886 | note | Frequency - Post Installation
f2b9aadb-5d8b-5f68-add9-6e4dc001927e | note | Verification Activity: Activity - H
44f350ff-13b1-55d4-97fd-f09beaca045a | note | Verification Activity: By - ITP
| checkpoint | 5.03.01 - Foundation Compliance
fd34d301-26d3-500f-8f99-0c7fb6589a5f | note | Acceptance / Conformance Criteria - Clegg Testing to be carried out on stormwater manhole foundation. Clegg Test to correlate to minimum CBR of 15.
d9503fb6-220f-5276-91c5-098ab1fee445 | note | Standard / Specification - Project Specification 4.3
e8d3e17c-a71e-5a16-90c9-e4de7de8066e | note | Verifying Document - Test Results
ae626582-caa2-5365-a507-8e99f5e60248 | note | Frequency - 1 Test/Manhole
86546370-005d-505a-b6de-7a6e27a44bca | note | Verification Activity: Activity - H
f9894d30-15f7-5846-b4e4-68aa6e70a56d | note | Verification Activity: By - QE
| checkpoint | 5.03.02 - Undercut Backfill Compliance
1ad0cb45-b924-5730-b7d1-4210a09ca065 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Minimum Compaction 95%(Average98%) of MDD
2c955765-385c-524c-9b36-c2bf200e02bd | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD, AS/NZS 2566.2/2002
6c01245b-b0d6-5ba9-b696-143972c94b08 | note | Verifying Document - IANZ Lab Test Report
7b42a5a6-6e49-5414-8d8c-bff861cab0f4 | note | Frequency - 1 Test/Manhole if Undercut required
6e1bd190-a6bb-5879-9152-ba4bdb07bb2f | note | Verification Activity: Activity - H
c9dc2025-28c8-5086-8702-13583b6304a3 | note | Verification Activity: By - QE
| checkpoint | 5.03.03 - Bedding Compaction Testing
ec77daa6-f791-5169-bb68-75edec0cbfe4 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement
5e84ee1d-c4a5-5211-9f32-7703f444b30f | note | ○ H2 Bedding outside pavement
9e7ca304-ca46-527e-8e50-0f22f431b2ae | note | ○ NDM Back Scatter
0450ab7c-3215-5452-8582-d329ea14b4b7 | note | ○ Minimum Compaction 95%(Average98%) of MDD
b8811638-806b-57a3-b416-c2a3c7bceb8e | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD, AS/NZS 2566.2/2002
4754476e-92ee-511a-9365-43c2d580e74a | note | Verifying Document - IANZ Lab Test Report
1f11f28b-b694-51a6-a649-7f240417fe99 | note | Frequency - 1 Test/Manhole
0d06c8e2-1009-502f-bacd-92d40e336d4c | note | Verification Activity: Activity - H
f47e8bfa-2b87-5112-a17b-4c8e58fde2a2 | note | Verification Activity: By - QE
| checkpoint | 5.03.04 - Backfill Inspection
f7e931f4-9c70-5218-8b3c-e17d39ab43ed | note | Acceptance / Conformance Criteria - Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
c4305192-6b53-55b8-9b9b-6ac7ca4a4ca8 | note | Standard / Specification - Project Specification 4.3
ef54d60b-78ff-5582-ae1a-7930d5d25c12 | note | Verifying Document - Photographs
91911a7b-45c7-5425-ba5d-e39a40f9c319 | note | Frequency - Continous
68122910-e3f9-5352-b9a6-592939924311 | note | Verification Activity: Activity - S
14e00c73-5837-5954-b5e6-3f25d08425d8 | note | Verification Activity: By - SE
| checkpoint | 5.03.05 - Survey
c5cf73df-46be-5122-ae3a-3b08a98b0bc0 | note | Acceptance / Conformance Criteria - Invert Levels: The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified.
2ad06ee2-e1d8-5d3a-bcab-6d1eec2d78a0 | note | Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm.
17e0db54-b35e-550d-b3a9-e407751a71aa | note | Gradient: For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
f23299f5-18aa-5103-8e5d-504be8fddd73 | note | Standard / Specification - Vertical tolerance +/- 50mm, Horizontal Between Structures +/- 100mm
e247f170-c8e5-58bf-820f-c233c5c5bad2 | note | Verifying Document - Survey Data
1a873de4-86cd-5905-853f-0d36f0322696 | note | Frequency - Continous
56d9a159-e53c-5357-9aac-58c7314f6dc0 | note | Verification Activity: Activity - C
025322d8-7f53-5f13-b4ce-a3b7351c3604 | note | Verification Activity: By - SV
| checkpoint | 5.03.06 - Backfill Compaction Testing
4c8cef46-bd8b-5c06-a6f4-615194d8c7fd | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm, Testing to be completed on 300mm lifts of backfill - 95% of MDD at OMC.
676402f0-db58-5a7a-af71-491f42dbc804 | note | Standard / Specification - Project Specification 4.3
494d7744-bba1-5594-a4b6-f8515d30506f | note | Verifying Document - IANZ Lab Test Report
8ec0ea6d-41e8-50c7-8143-da9ead265469 | note | Frequency - 4 Density test per layer at Quarter Points around the Structure
319b0245-3546-5252-86b2-86258a88746f | note | Verification Activity: Activity - H
00e9d107-9944-5c73-8268-57dc5bec2a5a | note | Verification Activity: By - QE
| checkpoint | 5.03.07 - Haunching
fa8e61c0-7abb-56ba-8cea-5ca39f06ca69 | note | Acceptance / Conformance Criteria - All the MH's needs to be haunched as per the specifications
a6cb336e-0efe-5213-a820-c9e3d843cca2 | note | Standard / Specification - RITS
57c26e68-cc09-543d-a0f4-7cda40a44e70 | note | Verifying Document - Photographs
09e57cbd-18ee-5c11-808a-c95fac4abbcc | note | Frequency - Continous
acb1dbd0-2c47-5503-b297-f7c99400d9e3 | note | Verification Activity: Activity - S
b78a01d7-79a3-5df8-8f0d-9ce0cd6ff1d7 | note | Verification Activity: By - PE
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 6.01.01 - Redline Drawings Critical Elements
5abab56a-8459-5600-badb-3738bac3673b | note | Acceptance / Conformance Criteria - Undercut/topsoil clearance. Any placed fill. Any drainage undercuts/structures.
30c42886-a473-5b08-9056-1423791a25a6 | note | Standard / Specification - Downer
f612c9f8-6b6a-50c9-85a4-8e9e38fa9f93 | note | Verifying Document - Survey Records
e33b7842-123f-555e-9dc3-5be2d91a87ec | note | Frequency - After Completion
c9be6676-5970-54f5-a6c2-dee0feb280a3 | note | Verification Activity: Activity - H
61b1032e-6fbc-55df-844e-732cf338d6e8 | note | Verification Activity: By - SV
| checkpoint | 6.01.02 - Red-line Markup
a1c16fe4-68f0-56cf-86e9-133ba4b0c69b | note | Standard / Specification - Downer
cb7eed1c-7840-597b-aed7-49daabaf0dc0 | note | Verifying Document - Red-line Markup
5433b9fd-23e6-5d94-9d72-1d0101dbe327 | note | Frequency - After Completion
bcf1c120-0ee8-5cdc-8169-70f394216c0a | note | Verification Activity: Activity - H
a26a611e-95af-5a36-b6ac-3ceeb9f24310 | note | Verification Activity: By - SE
| checklist | ITP - 134 - Concrete Islands Infill Construction Rev A | itp | ITP - 134 - Concrete Islands Infill Construction Rev A | 3afee364-1287-40b1-b4a3-ec4f24d94d01
| section | 3.01 - Site Requirements
| checkpoint | 3.01.01 - Construction Pack
ae81a148-3ca8-5190-8b63-19022415d0ab | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
704966a6-cfd3-5db1-b172-9c96cf937822 | note | Standard / Specification - Downer
3f5ff9a5-db98-5f56-a659-031ff6669f08 | note | Verifying Document - Construction Pack
fc46b3fe-d912-5783-9d3b-d532ad04f6fa | note | Frequency - Submit 10 days prior to commencement of works
017ea354-543c-5c12-a812-39b39ab38e70 | note | Activity - HP
f0d8d4fc-5ecc-5772-8c1a-bfa36b56cbaf | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.01.02 - Survey Setout
3f02d952-2854-554c-b911-b2da156d5454 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
491de3eb-2ce6-50ca-9f71-c9b9a1516925 | note | Standard / Specification - Downer
0f0f4735-d140-501c-9f7d-6a44f539df86 | note | Verifying Document - Survey Records
a6b57a64-b2e7-52dd-afa7-15965695ab87 | note | Frequency - Prior to Works
59e7b864-38ef-5610-ac93-7e86baef20a8 | note | Activity - H
dadab718-59f3-56c9-b6ed-415eee977643 | note | By - SV
| checkpoint | 3.01.03 - Service Location
13dd371e-9143-55bf-806e-23ba29f3e6f9 | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
4c52d324-be21-5d3a-922e-6bf74ba62cbe | note | Standard / Specification - Downer
7321b4dc-29a4-56f5-b98f-53b51ad1cced | note | Verifying Document - Excavation Permit
b2860919-647f-5332-a12f-4b1b88c5b771 | note | Frequency - Prior to Excavation
578ee693-2fe3-55ec-bd47-89a43c460581 | note | Activity - H
ba0bea28-fa56-53a1-8983-b9165e9c5db1 | note | By - SE
| checkpoint | 3.01.04 - Internal Permits
bd3e016f-9150-5ecd-b4a4-bc5bbd0ead7c | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
d8125674-56e0-5b26-9d7b-46d18edd44e8 | note | Standard / Specification - Downer
ead5b870-a5da-58e0-8533-58831ce0d5ea | note | Verifying Document - Internal Permits
eb91373b-6d16-54f1-bc57-8e41c3936bee | note | Frequency - Prior to Excavation
4bb2b735-e03d-58c4-a637-80647f0bc5cc | note | Activity - H
caafedf2-480f-5a98-bf92-e0ef8597e5c8 | note | By - SE
| checkpoint | 3.01.05 - External Permits
61839e6c-a50b-571c-a5ce-50ee8d310f88 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
d4e95e7a-6666-5962-912f-0ce8c41f02f7 | note | Standard / Specification - Downer
6c653100-cca9-5b64-ae29-1abee14b3be0 | note | Verifying Document - External Permits
bd94d492-2b21-51a4-9435-eb8cc859fd88 | note | Frequency - Prior to Excavation
4dff60ee-4af4-5c3a-8bda-ac6fa1911803 | note | Activity - H
fefe45d6-d10a-5d22-b29e-2cb71d397e10 | note | By - PE
| checkpoint | 3.01.06 - Approved Construction Drawings
5c14f703-3312-5f10-b3a9-e774759bd544 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
f1626f2b-c6a5-5836-8676-06dd97aea10c | note | Standard / Specification - Downer
27634d1b-4b60-5aee-b3ba-7c8eaa0b458c | note | Verifying Document - IFC Drawings
6dbee673-fcd9-5d63-85d6-786cafa6ae9e | note | Frequency - Prior to works start
86863836-1690-5090-9199-ff4ccb507417 | note | Activity - H
10322b33-ebb9-5006-8753-d8f8cce45327 | note | By - PE
| checkpoint | 3.01.07 - Previous Completed Work Packs
f69c15d3-5bf4-5b87-81b0-fb6984bba348 | note | Acceptance / Conformance Criteria - Review previously completed workpacks to ensure work completed meets the contract requirements
568936ee-067c-5326-a0ca-a604fdddafd2 | note | Standard / Specification - Downer
ef35e150-8df8-5ca6-be2c-a7d92a1c05e9 | note | Verifying Document - CONQA
0f58c8b6-9a3b-5926-935a-3ab50ff82aac | note | Frequency - Prior to works start
e75cbe3d-cdd9-5979-a698-9172de46832b | note | Activity - H
24c640c9-8812-5671-99e6-e566a5b2944f | note | By - PE
| section | 4.01 - SUB ACTIVITY
| checkpoint | 4.01.01 - GAP20
d55d4c8d-41d7-5a7a-8b6a-59bf08c4326b | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
f0770170-d2a6-5d3a-9ebd-e2b330011b1f | note | Standard / Specification - BBO
67484e98-2442-5581-9c6c-4db351b87a30 | note | Verifying Document - Source Test/Site Notes
a028151d-7393-5e6e-9fff-1f64c17e7d9e | note | Frequency - 1 source test per material type
d0ad34b4-4ce1-58dd-a56a-48113b787e43 | note | Activity - R
8c66e3fa-6f49-5d25-9d26-9b769965aa62 | note | By - SE
| checkpoint | 4.01.02 - Conrete Mix
f0a63cca-06f4-5b9a-9ea2-8d2cc3d53cb9 | note | Acceptance / Conformance Criteria - The strength of concrete as defined in NZS 3109 shall be 28-day cured in-place minimum strength 20MPa. With a 13mm size aggregate.
5189fe51-cace-54aa-bf9f-dc846fd2c38d | note | Standard / Specification - NZS 3019
4b7e40cb-b3a2-54be-a00f-f7653de42c14 | note | Verifying Document - Source Test/Site Notes/ Concrete Dockets
a7ed90df-8a9b-5d99-b21e-4d880eb3ad1a | note | Frequency - Each Pour
59fbcec2-56ab-5b55-8212-0c867840110e | note | Activity - R
4b751d7c-5893-5b8a-8726-1defa8c41087 | note | By - SE
| section | 5.01 - Traffic Islands Construction
| checkpoint | 5.01.1 - Islands Set-out
0fe6d797-9e7f-5860-8de5-ccbcf7ec30d4 | note | Acceptance / Conformance Criteria - After set-out and prior to installation of footpaths
84aa6dd8-da16-5d8e-a7a9-802b3d723273 | note | Standard / Specification - PS - 2.2.16
1d16451a-6680-5408-aed2-77b493b5094b | note | Verifying Document - Hold Point Release
bae99dda-364a-540c-8e83-29f7e18ba1a6 | note | Frequency - Min 24h Notice
123e6dc3-d902-5c5e-b9a2-fa968c825d61 | note | Activity - HP
74475f97-7ab7-546a-85c1-1e3b7ce2993d | note | By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.02 - Concrete boxing and Base
06294422-f961-597d-a121-a3fe6de20d93 | note | Acceptance / Conformance Criteria - Surveyor to check boxing for concrete pour, this includes the boxing for slots. For the front side of island aprons top boxing to be 50mm above F.L.
29afec8c-83cc-547b-964c-e447606b3d43 | note | Standard / Specification - Downer
027cc3c0-6a74-5b83-8c01-8626d8544a63 | note | Verifying Document - Hold Point Release
892e665c-cd19-57f2-aa05-94795135e172 | note | Frequency - Min 24h Notice
636d010c-0a6c-5c09-87d5-88b1672a9f6b | note | Activity - HP
20e5c5b0-1380-50f3-9a1d-60ed7450c33e | note | By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.03 - Concrete Strength & Reinforcing (Island Apron Kerb (mounatble kerb) and Infill)
a92e67be-05eb-53c0-8c50-07cd489f0d1d | note | Acceptance / Conformance Criteria - Concrete to be at minimum of 350mm on the back side of the kerb with a max of 400mm thickness for construction tolerance, with 20MPA broom finish. Island Apron/Mountable Kerb reinforcing to be D12 Bars & R5 Stirrups @ 600 centers (min 75mm cover). For the infill, two layers of 665 Mesh (75mm min cover bottom cover and 50mm top cover).
0262803d-140d-5827-b7b3-141b32dbf760 | note | Standard / Specification - Downer
263c2145-b1f7-5e21-81f2-5b94abeb72a2 | note | Verifying Document - Hold Point Release
fb7e2144-bbee-5bf1-b9d8-d53b244a77a0 | note | Frequency - Each Pour
73c9f624-45c9-5b30-b5a8-aea6e56a779a | note | Activity - HP
d03d1069-0296-54a3-b7a5-0f4723190a3e | note | By - SE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.04 - Concrete Pre-Pour
fb368de0-8112-5abc-8928-144e54eac107 | note | Acceptance / Conformance Criteria - The Contractor shall give due notice to the Engineer of the time it is intended to place any concrete and no concrete shall be placed until approval has been obtained from BBO. Pre pour check wil includes checks on cover, lap length, spacing and bar sizes are followed per drawings specifications etc.
b5f317d4-f268-5c27-b06a-ade443fe061c | note | Standard / Specification - RITS - 3.4.5.3
0a495404-fc8b-5605-b84c-0396bf83a6be | note | Verifying Document - Hold Point Release, Pre-Pour Check
b5c205da-2af3-5ccb-a1a5-ee3891749383 | note | Frequency - Min 48h Notice
4f6c5fe0-4b1e-5896-be78-30c23b44304d | note | Activity - HP
031fe49e-e9e7-5880-ad28-47805653cfba | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.05 - Ground Preparation
815aad61-551d-5d36-b96f-bcbc447b52bc | note | Acceptance / Conformance Criteria - Immediately before placing the concrete, the foundations shall be lightly dampened, and formwork shall be cleaned out. In all cases surplus water shall be removed before concrete is placed. Any foreign or organic material hall be cleaned out.
2db51c2a-8a74-51eb-a355-531c42bc3c44 | note | Standard / Specification - RITS - 3.4.5.3
03d2d28b-9373-54b1-a7bb-0ad4a84b7a27 | note | Verifying Document - Pre-Pour Check
63bb35c0-c94c-53d7-9363-c5d1b8461d6d | note | Frequency - Each Pour
1daa4a2a-2f67-5940-af39-0fe01a6256b6 | note | Activity - H
f364f2af-39cf-5680-a74e-81f1aca7cd20 | note | By - SE
| checkpoint | 5.01.06 - Frozen Ground & Unfavourable Conditions
d3120ef9-d2ac-5f48-a0b2-d41deeecf149 | note | Acceptance / Conformance Criteria - Concrete shall not be placed on frozen ground nor shall it be placed in unfavourable conditions, which may be detrimental to the quality and finish of the concrete (i.e rainfall)
dce14285-0951-52a4-b30c-5289667c0aea | note | Standard / Specification - RITS - 3.4.5.3
d2e0877a-4c06-5a69-9c01-1bb71e139452 | note | Verifying Document - Pre-Pour Check
31bb80cf-8a0f-543c-830e-e48c59f445a8 | note | Frequency - Each Pour
09f8552f-6909-5a7c-8deb-94398cd753e1 | note | Activity - I
8be1cb01-8414-559e-841c-fe3f42093304 | note | By - SE
| checkpoint | 5.01.07 - Curing Of Concrete
2b09eba1-044b-5415-8890-36c6730e95bb | note | Acceptance / Conformance Criteria - Immediately after placement, concrete shall be protected from premature drying, excessively high or low temperatures and mechanical damage and shall be maintained with minimal moisture loss for the necessary curing period and hardening of the concrete. In hot dry weather sprinklers or damp covers will need to be used.
0907f66c-1b92-59ef-a493-93204662cf13 | note | Standard / Specification - RITS - 3.4.5.5
fd7d7029-904f-5147-8a45-c969deae89c8 | note | Verifying Document - Post Pour Check
f010c34a-8f8f-5fc2-9d8e-70b826ff96da | note | Frequency - Each Pour
5975946b-acd9-5096-88b5-30e04829d049 | note | Activity - I
d2c9d4d6-413b-51d6-b024-d74c037cdbd3 | note | By - SE
| checkpoint | 5.01.08 - Concrete Compressive Strength
424acf0c-538b-5b73-8fa4-7eee531ea118 | note | Acceptance / Conformance Criteria - Concrete to meet a placed 28-day compressive strength of 20-Mpa
4c90ca90-303e-5a90-b756-dd9bb2984cfb | note | Standard / Specification - RITS - D3.3.5
b7902e3b-811a-5489-baa4-c6d05b3acf75 | note | Verifying Document - Concrete Dockets
db8e5d0f-eac2-5359-93ee-ae4ab669a2eb | note | Frequency - Each pour
7a6247e7-d549-561c-9933-40b759f6af94 | note | Activity - R
0c88d803-a735-5738-b9fb-c1dc503ae293 | note | By - SE
| checkpoint | 5.01.09 - Finished Work
e940b484-42a9-5ba1-b831-536a9937e100 | note | Acceptance / Conformance Criteria - Methods shall be used that will provide a smooth, clean and even surface on the exposed faces of all concrete work.
3c0661e6-1fad-587a-a624-8486fb0ed437 | note | Standard / Specification - RITS - 3.4.5.7
b8ebe5f5-1496-5ebf-951f-f5545e00dfe6 | note | Verifying Document - Post Pour
6dc8d683-796c-5bc4-bcef-d48b7259da5d | note | Frequency - Each Pour
bb7d2291-e932-521d-8bf0-0398ad9c9a31 | note | Activity - I
fc405d27-ebb5-5e5c-995c-e4af3ffb1761 | note | By - SE
| checkpoint | 5.01.10 - Contraction/Expansion Joints
a6e700d4-3fa9-57f2-90c0-49db570240b8 | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m. The slot shall penetrate the concrete by not less than 50mm and the mortar dressed over the cut face. The contractor shall ensure that cold joints are accurately marked and setout via total station so that the subsequent saw cut is in the cold joint. Should cracking occur adjacent to the saw cut a minimum section of 1.5 metres of the traffic island shall be removed and re-cast.
7c91362f-c808-5fd3-aaf1-ccfed1f9515d | note | Standard / Specification - RITS - 3.4.5.8
bedfa861-1ee1-5b12-a69d-b52117f75cc5 | note | Verifying Document - Post Pour
ceb6dd0b-f109-55c2-9bbc-a747de47ec63 | note | Frequency - Each Pour
ba31822c-b7f8-5585-81f8-f4603570dbd6 | note | Activity - I
fba2f8ae-88c4-50bc-94d1-6f6c87644711 | note | By - SE
| checkpoint | 5.01.11 - Finished Concrete (Surface Finish & Final Levels)
b43aee56-f805-5b5e-b84f-b943cd57f73e | note | Acceptance / Conformance Criteria - All final path and vehicle crossing surfaces shall be true to the lines and levels Specified and ‘broom’ finished. Design considerations aside, the final surface shall not vary by more than 5mm when checked with a 3m straight edge. No finished surface shall hold water.
18a87a83-b3b3-5df1-9a24-dc42f368fef0 | note | Standard / Specification - RITS - 3.4.5.10
9956a369-6b69-5c03-8027-24a28f1388b4 | note | Verifying Document - Post Pour Check
0c2a5393-9b4b-547b-80c6-fc6d0bbe1377 | note | Frequency - Each Pour
a57efa40-dacd-592f-b41c-b98237c254e3 | note | Activity - I
e1989631-cf1a-59f0-bc1c-e5d009b8bf24 | note | By - SE
| section | 6.01 - General
| checkpoint | 6.01.01 - Construction Record Compilation
27d0035e-08b9-5669-bb5c-17ada2d84a9c | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
7f068a28-7d10-55d8-a75f-daab061a9f8f | note | Standard / Specification - Downer
08bd4551-1fad-5172-8088-630d857169ee | note | Verifying Document - Records
5f05ade7-9020-5c1e-843d-2d5bb69b86e5 | note | Frequency - Post construction
b828fa67-8ff6-5895-8435-b1cc805eac95 | note | Activity - H
65e63267-c059-565a-b63e-ee3f4757c480 | note | By - SE
| checkpoint | 6.01.02 - Survey Records
bc088579-acb7-5c77-bdf1-a7ee0afcc95f | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
d7aa4f66-d175-58eb-bdd4-af3b2aa666c1 | note | Standard / Specification - Downer
26bb02c4-bf47-5c9f-9d8c-283b22cbfb35 | note | Verifying Document - Records
72fa2a73-1dda-5af6-8b8b-bf899a3a4b56 | note | Frequency - Post construction
919fc70e-f6a5-5a21-96e0-3a6b18b4fd05 | note | Activity - H
dca164d4-345e-5624-83d4-7d71d92a5afb | note | By - SV
| checkpoint | 6.01.03 - Redline Drawings
61a3cf43-7a3b-5adc-badb-a41fa17b6992 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
d31590e0-dcb1-58e5-a8a2-c97df03c7226 | note | Standard / Specification - Downer
0dae8db4-789d-57f5-996a-bc5a38c77d27 | note | Verifying Document - Redlines
cbaf7b6b-47dc-5975-8c59-9844576b11fb | note | Frequency - Post construction
87fd04d6-0518-5ce5-a613-0e99d687e8fb | note | Activity - H
681da9fd-8186-5c1e-9a8c-1bbf9e7a4f49 | note | By - PE
| checkpoint | 6.01.04 - Defect, Snag and Punch List
d79f39b2-3d21-5e97-b460-7d2d30b9d10c | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
ee942463-b2d9-57d1-9d63-2a7878cc9df7 | note | Standard / Specification - Downer
b1ae003c-f6ea-56af-9d21-ae2d8f0cab38 | note | Verifying Document - Register
12a2391f-d3ab-52f0-ba45-9651f35eb684 | note | Frequency - Post construction
9c6a1e68-bfbf-5a97-9b8c-eb6e9ec02354 | note | Activity - H
c8a6eb50-a184-53c9-a627-02bc86d328c2 | note | By - PE
| checklist | ITP - Drilling Rev 4 | itp | ITP - Drilling Rev 4 | 3962cb0e-b861-417f-a137-a0d4804e5233
| section | Pre-Construction
| checkpoint | 1.1 - Materials
6ff88db3-b4e6-5001-ab2a-caa90a72e762 | note | Responsibility - Engineer
af392e51-02df-5c6e-985a-a073367a3648 | note | Conformance Criteria Summary - PE100 SDR13.6 450mm & 630mm; Tracer Wire – Continuity test
1ef284b2-78a8-5b38-b96b-e2a60713c49d | note | Method - Docket; Include results
d2da5b80-c5c3-5a4e-87f3-38ee740b5c2a | note | Frequency - All Pipes; Each Pipeline
bd617085-0b3b-58f1-bd71-7ec20c4096bb | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Settlement monitoring and ground deformation (Baseline measurements)
a2969d97-ab77-54a6-a45f-ef9d1c42f262 | note | Responsibility - Surveyor
b471031a-853a-5290-8a51-8b29bca4d22c | note | Conformance Criteria Summary - Topo survey completed before and after drill shot, (allowed 100mm in settlement)
00693403-1e55-5aa6-8188-57f80baf7851 | note | Method - Survey
3fe88b2f-a37c-5bdd-9e71-8543fd0264a5 | note | Frequency - Every 1 m
0a6421d7-0fd3-523f-bf2b-4776ec8ad648 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Qualified staff
babc6159-e2e7-5bcf-9689-e351223cd675 | note | Responsibility - Engineer
de373cfa-b78b-5429-9ce0-e2f07b53b982 | note | Conformance Criteria Summary - Qualifications of Robbie Reeves to be submitted before start of works
f245852e-59b0-5ead-ab8b-c994bde7e9b3 | note | Method - Email
6d05fffa-08b5-5697-b3bc-604487e456da | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Tensile Test
ec32e578-be7b-5d18-82ff-9b49a5181f0d | note | Responsibility - Engineer
becbd134-98bc-5052-8be0-abf28056f7a9 | note | Specification Reference - 4.8.7
0163d04e-ef2e-5752-ad9d-0bced3edfe4b | note | Conformance Criteria Summary - 1 – Compliant test As per ISO13953-2001
f7af9cfd-d8d9-5a68-94c9-f3833128c43d | note | Method - Email
3b7597af-4100-51ab-942d-5ab4d35de8b2 | note | Frequency - 1
8add5ffb-5acb-5001-b749-113ae2272cd5 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Drilling Fluid Mix
0a0484ca-ee24-52ce-84ce-df034abc9ee6 | note | Responsibility - Supervisor/Engineer- Supplied by supplier
8f10b078-eddd-5b0d-a41d-8590896e0138 | note | Specification Reference - 4.8.5
98915550-267b-5ba2-b655-5687d88768c7 | note | Conformance Criteria Summary - Fluid design to be submitted to engineer before start of works.
4e096507-495e-53d2-b061-612983d39bfb | note | Method - Email
5a60fda4-e04d-561e-8c7d-a34b8e8a0006 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 - Alignment Pegged out
c2b01877-b42b-5181-b20d-31bcdc8d85f4 | note | Responsibility - Operator/ Engineer
5e3529a8-7d1a-585e-a6e4-4105d773d68a | note | Conformance Criteria Summary - Survey Pegs
63a424fb-4a9a-50aa-a174-b9d70c39a52b | note | Method - QC - 09
cba1f9ad-72bf-5020-8476-7f165c0d1226 | note | Frequency - Pegs 1-3m intervals
acbdaa07-a3e3-5813-a4ba-c4bb5d336ee3 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.7 - Environmental
d2454f6d-7a7c-5840-8bc1-8b22c923819c | note | Responsibility - Downer
b65c4482-8b97-5d51-8ded-79a603ee6be5 | note | Method - ESCP
6e97df66-3293-5cce-8665-cbe6361488cb | note | Frequency - Start
fe583c3d-7683-54d0-9c44-7d5e31919aa1 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.8 - Existing services
2698c22c-dcba-5cb4-aa9c-58c67b6c0fd4 | note | Responsibility - Engineer
1a511e3b-2ebc-5191-9bd2-54e25209e686 | note | Conformance Criteria Summary - No conflicting services
83ba0dae-5972-5756-9b2f-8c429623dd83 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.9 - Abandon Drill Shot
773dd662-2cb4-54c2-9e4b-ced47ba34187 | note | Responsibility - Engineer
4be36ca1-38c8-513c-8427-c11a14705bee | note | Specification Reference - 4.8.7
ed2aa2b6-7a86-5815-9265-1b447904e9b8 | note | Conformance Criteria Summary - New mix to be approved by engineer
2967c620-bf85-54c4-9498-74056f73765b | note | Method - Email
ddf4fcdb-2f48-5ded-b14c-069d9e833b49 | note | Frequency - Each abandoned hole
ce423f3d-e6d9-5e76-8023-55111f1919da | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.10 - Butt Weld Data
35ee3914-4365-5e32-9f8d-485e50458b36 | note | Responsibility - Engineer
9004f3ab-0f33-5de0-ace2-c5a8984e694a | note | Specification Reference - 4.8.7
a0b1ea38-6f82-58f3-8420-9d73d7b403e7 | note | Conformance Criteria Summary - Data to be submitted
9ba4811f-06a5-5419-91f8-7d5914691e3d | note | Method - Email
b97fe185-0bf7-5962-a8c4-f5a00dab2ead | note | Frequency - Each weld
76806c75-93b1-504e-8d96-c5fc57efdb29 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| section | Construction
| checkpoint | 2.1 - Drill Entry Angle
4823544f-51f1-52da-914b-6fb92537cf82 | note | Responsibility - Operator/ Engineer
718f988e-c648-5d1d-8e57-f22f010a54c7 | note | Conformance Criteria Summary - >8° and <20° to be measured with data logger
efae2b18-a95b-5858-bdea-a1850def554d | note | Method - QC - 09
ad279368-b9db-50ee-b51b-c4f637cb1d4c | note | Frequency - Every shot
b91b16ef-e77b-5304-9332-ce1c1c944699 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Check levels while drilling
84b14d25-f170-5bb8-aa0e-927b7879a1f0 | note | Responsibility - Locator
542a5280-10a0-5cf5-816e-44c3fb9b67e8 | note | Specification Reference - Table 4.10 PS
1264e0c7-cd6c-52ed-8124-2514e894eb9e | note | Conformance Criteria Summary - +/- 300mm Horizontal [NT1] 67.5mm (450Ø) Vertical 63mm (630Ø) Vertical
0377168a-64a6-56da-bb37-7d77d3d81bca | note | Method - QC – 09
3cf8bbf9-e142-5c66-873d-d87558bd5a51 | note | Frequency - At every peg
04113fbd-0bc8-5228-99b4-1a8d75ce4969 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Drilling Fluid Mix
5949a641-fa32-5496-ac99-4a782651ee19 | note | Responsibility - Supervisor/Engineer- Supplied by supplier
7befbf8e-ddea-53aa-b3af-24c5577a02e3 | note | Specification Reference - 4.8.5
3e1b27c3-e804-5432-aa1f-a8bb0096025d | note | Conformance Criteria Summary - Viscosity (Recorded) pH (Recorded) Bentonite due overs
cc888399-b00e-586d-9353-0ab56f534372 | note | Method - QC – 09
886f5155-c613-5bce-821f-67dd5ed4833a | note | Frequency - Every shot
27a1bb79-905a-510a-961f-aaab48b38214 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Correct Reamer used
50020b32-7d17-5b49-bc8b-e224f539da51 | note | Responsibility - Operator/ Engineer
5ba9d0a8-3507-5e0b-99dd-af5cfacc1ce3 | note | Specification Reference - 4.8.7
272d2c25-800d-512f-90b7-011635de7e9d | note | Conformance Criteria Summary - Discussed with engineer prior to starting **
8f03e162-9f63-5cae-a5ca-46a81d6551d0 | note | Method - QC – 09
98f711fd-934b-596d-a6b6-e1a8b15709ff | note | Frequency - Every Pull
e8b709ef-d4dd-5585-af59-150400a1a0ac | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Pipe Damage
1549d838-bb32-5370-b80a-1e57104b3ed9 | note | Responsibility - Engineer/Supervisor
5d2f7d8e-e56d-595d-8c64-708112618af6 | note | Conformance Criteria Summary - Check sheet completed on walk over of pipe before pull.
d5d0d196-c3be-5ba9-abda-e66b86d954d2 | note | Method - QC - 09
6bb88644-1882-5f8a-8916-8e833b4eea89 | note | Frequency - 1 per drill shot
d34305a3-ecc5-5c30-aee7-cd2c4c7a595c | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Pipe Visual Inspection
58cc539b-00c1-5801-b4e3-21b084f25a93 | note | Responsibility - Engineer
30069d36-ea86-570e-b009-c719da19be40 | note | Conformance Criteria Summary - Damage <10% of wall thickness
0ef6d46a-8b12-559b-becf-d78a0039ad64 | note | Method - QC – 09
2b8038b7-2200-5b94-8f4d-418a1cfee1cc | note | Frequency - Every Pull
3fd9a447-69e1-5f8e-9467-d2146ee776a2 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Tracer Wire
3a8dc71e-3af0-5f5e-95b1-cd4d249c4a4c | note | Responsibility - Operator/ Engineer
5140d2e4-c0d4-546e-a8b1-aaa2335fd065 | note | Specification Reference - 12.4
d044e739-b05e-5105-9526-b4b587ad35d2 | note | Conformance Criteria Summary - Minimum 4mm Taped every 3m
62dd4f03-3bfa-5eb1-b31c-6c0c6a0c4f37 | note | Method - QC – 09 and photos
9203daa5-2b55-577a-89a3-28eef11f360b | note | Frequency - Every Pull
b9ddc7ed-46e4-526a-9896-51ff16a48da4 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| section | Post Construction
| checkpoint | 3.1 - Drill Report
a2a9604f-2219-50b8-b9b8-bb128f1e3309 | note | Responsibility - Engineer
c32c78fb-3af8-5cbc-b708-fb512f35fb14 | note | Specification Reference - 7
3bed618d-ad4c-5ca2-b841-5f08a831b30a | note | Conformance Criteria Summary - Drill report to be submitted
e4a7bd1e-e6a3-5203-9071-75ede7b59eef | note | Method - Email
e4173227-f70c-55d6-bf5a-f0bca33d068c | note | Frequency - Every string installed
b4104a6b-6482-575f-850c-8fec9f4e7eba | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Settlement monitoring and ground deformation (Baseline measurements)
aebf78a6-8ff0-5da2-956c-c9d3449f852c | note | Responsibility - Surveyor
40d44da4-4d0e-5335-a3f3-78d649716599 | note | Conformance Criteria Summary - Topo survey completed before and after drill shot, (allowed 100mm in settlement)
4cb00e68-ceb0-5b9a-b49a-34d49e376aef | note | Method - Survey
2a374420-86a1-56a6-bb21-1b4aeed6851f | note | Frequency - Every 1 m
e20c2185-8cbb-5d88-bb00-ebb9de071909 | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - CCTV
bb5b9bb0-762c-57fa-8fcf-d5d675b6c16e | note | Responsibility - Engineer
a0b40396-7c83-549a-afe7-707df2bda234 | note | Specification Reference - 4.8.7
5386db2c-b469-54a9-983e-f4848df6d2ad | note | Conformance Criteria Summary - Submitted
e7b7ef73-1098-5fe1-8463-6febb3e30ac4 | note | Method - Email
79edf7b3-9e6d-5bfe-9631-288e126f9b5e | note | Frequency - Each Pipeline
975837e5-92be-56ec-959d-4d3ec59c8d2d | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - As-built including red pen
5900d80b-6cc5-5f2c-bc39-0b19c9848eed | note | Responsibility - Engineer
7e2e8e3c-970e-55fc-8c32-4cba5bd65c08 | note | Specification Reference - 4.8.8
6754efd4-586f-5bee-b348-55b3d59b93b8 | note | Conformance Criteria Summary - Submitted
cfc7129b-cb13-5730-b93b-c5a7c93f1179 | note | Method - Email
9eed492f-a84c-5138-81fb-d1ae13b2e733 | note | Frequency - Each Pipeline
ea5ab098-2f02-5dbb-908e-5e49ecb3b5eb | note | Hold / Witness Point - HOLD
| signoff | AUTHORITY HOLDPOINT
| checkpoint-no-value | Additional Notes:
b79a7d5e-107e-5721-b939-0abd897d80d3 | note | Reamer size to be confirmed with ground conditions. To be closer to diameter of the pipeline then table 4.9. (for 630 Main this is to be 775mm ideally and 550mm for 450mm line)
d00911df-9745-58d3-b196-30e4d52a8634 | note | CCTV Inclinometer is as per specifications of camera (Can not achieve a consistent or accurate grade)
de6a28b5-471a-5736-af6d-bd11321ff808 | note | 1mpa is not achievable for grouting.
f83c85e0-9593-5eb9-972e-80df4c23ce93 | note | No Critical locations
3bb8eab5-b9b7-5476-b72e-87ed949477a6 | note | Material specifications and properties determined by BBO. Please let us know if you require assistance with this.
68903ba3-267c-5e10-b4c8-6af450b1e3bf | note | Methodology and JSEA to be supplied on approval of ITP requirements.
| checklist | ITP - Earthworks |  | ITP - Earthworks | c81579b7-fafa-4f2f-8de6-dd90cc97d798
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
| checkpoint | 3.04.01 - Construction Pack
bfee9e2d-a6b7-5f70-91c0-be5382ad9749 | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
73019707-9e2c-534c-a05b-3fcde5672553 | note | Standard / Specification - Downer
fc46177b-d6da-5e5f-b473-8975092b2048 | note | Verifying Document - Construction Pack
cf028689-ebb3-5192-9152-61a6781b2e1b | note | Frequency - Submit 10 days prior to commencement of works
1053d10a-8bc4-5c7e-b34e-717289b9bdf0 | note | Verification Activity - H
769b19e6-25c2-51ef-b6c5-d49c93eb7c7b | note | Verification Activity By - PE
| checkpoint | 3.04.02 - Survey Setout
cf831fa4-9e72-5f6f-93bc-7b92ee6d3e7a | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
51686e4f-ea10-57de-b465-280fbf293317 | note | Standard / Specification - Downer
a56c6f04-de46-5fb8-aa75-7917dc94c8f6 | note | Verifying Document - Survey Records
77d6aa06-edd2-51e5-b4d1-f50385252962 | note | Frequency - Prior to Works
e9e2ae26-142d-55ca-80ae-2a4d6a362454 | note | Verification Activity - H
5ac007ba-46a3-5bdd-84ea-5f8829d48733 | note | Verification Activity By - SV
| checkpoint | 3.04.03 - Approved Construction Drawings
adac429a-f7e2-5e63-80d0-730d50cbd484 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
3b02b1a1-aed9-5211-a134-9a04eeffc8ce | note | Standard / Specification - Downer
3fdf891e-3ead-5017-b89f-18cf138d101c | note | Verifying Document - IFC Drawings
4173a28d-0312-5795-9c8c-5dbbcc1476d8 | note | Frequency - Prior to works start
cfa53cbe-96bf-5d97-a692-51a01ce4fd25 | note | Verification Activity - H
457bb499-0401-57d1-a2a5-f9335bba738f | note | Verification Activity By - PE
| checkpoint | 3.04.05 - Topographic surveys for measurement
b0ac2514-a724-594e-9ebc-d4a1ce86bf41 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
aa70e3c8-aabb-5a4e-bbe9-5a344f485278 | note | Standard / Specification - PS 2.2.12
f4e73635-e745-53ec-9c27-42e5b3f88ffa | note | Verifying Document - As-built
c95d9ef2-4b07-5466-a47b-37893c42864a | note | Frequency - Prior to works and Post Works
e0c41ef4-e1d7-542e-b948-53432b22e03a | note | Verification Activity - H
666286b2-083d-59cc-9c48-2306a176d1d0 | note | Verification Activity By - PE
| checkpoint | 3.04.06 - Permits
1086a7b0-b8fe-576d-8430-21b79737c40c | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
5795d95a-16ee-5ff4-9521-bbea691dbe15 | note | Standard / Specification - ITP Register
abf5a4ad-1f5e-5db4-adc9-de90fce74b16 | note | Verifying Document - ITP Sign Off
d59d5929-0aa7-5d0b-89cb-e4bd1357d609 | note | Frequency - Prior to commencement of construction activity
4c981c6f-8b77-5d6e-8556-3aabf085e93c | note | Verification Activity - R
412821e0-a96c-5a47-92ad-7cf6c94f8d6b | note | Verification Activity By - SE
| checkpoint | 3.04.07 - Stakeholder Management
07f0300b-dee9-5f28-9128-a0d9daf1509f | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
66cd92a6-7a53-540f-9e88-afdef00c9aed | note | Standard / Specification - Project Stakeholder Management Plan
e422661f-e345-5a54-8688-d7cd237acb92 | note | Verifying Document - ITP Sign Off
4b556bcf-42b1-56a5-bfdf-aff9f8fc919d | note | Frequency - Prior to Construction with continue updates throughout the works
b486a5da-ac9f-5a37-89a1-e4205d6f2fb7 | note | Verification Activity - R
f1c12282-a223-563a-b4af-025210d3be65 | note | Verification Activity By - SE
| section | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
| checkpoint | 3.05.01 - Environmental Controls Inspection
220fb01b-d745-5045-be14-134205e9c4ca | note | Acceptance / Conformance Criteria - After installing measures to meet environmental requirements, before any earthworks begin.
12810a36-7076-5fa3-9309-fa15bd838414 | note | Standard / Specification - PS 2.2.16
b6e38161-1c28-58dd-8003-e06fc54c07b5 | note | Verifying Document - Site Records
2468b7fa-2b30-5143-9a17-d0cf723c63b6 | note | Frequency - Min 48h Notice
82fc3266-7242-50e7-adfc-5b87a9456b0a | note | Verification Activity - HP
6fe76645-582f-5023-93da-ab8501b34efd | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | 3.05.02 - Bulk Fill Inspection
39705f9c-e934-5b3b-8800-e537f4d47d3c | note | Acceptance / Conformance Criteria - Prior to beginning bulk filling operations.
bd28e4f6-5513-5ca5-b0b9-8f398af9b0bf | note | Standard / Specification - PS 2.2.16
7f620750-7037-5f90-b423-8458b93e4bfd | note | Verifying Document - Site Records
4cc87978-3af0-54f2-a37c-2861c60b4f3f | note | Frequency - Min 48h Notice
bcaf12cf-0efa-51ad-9ded-5b8f62c0353f | note | Verification Activity - HP
4c8ec7d8-3e90-5a24-957b-45c963ead5e2 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | 3.05.03 - Service Ducting Bedding Inspection
57a8445d-fd38-5977-b749-a3db5394a8c6 | note | Acceptance / Conformance Criteria - Prior to laying any service duct, drainage/water/sewer pipeline and associated pits, fittings and structures
0bd2a218-cf77-58c3-be8b-00842a9fa36c | note | Standard / Specification - PS 2.2.16
241bcb23-ff2f-5e2e-bd32-1b66435db087 | note | Verifying Document - Site Records/ Refer to Services ITP for testing requirements
305f24c2-0703-584a-9e40-ce3157339d1e | note | Frequency - Min 48h Notice
1bc05559-a503-5c5f-8fd1-27d0207c0609 | note | Verification Activity - W
f5ac7004-e040-5094-b259-35cbbf4b3574 | note | Verification Activity By - ENG
| checkpoint | 3.05.04 - Service Ducting Backfill Inspection
7e4a7988-03c3-5c7e-87af-ed5a4d520a43 | note | Acceptance / Conformance Criteria - After laying, before backfilling any service duct, drainage/water/sewer pipeline and associated pits, fittings and structures.
5397b13e-25a0-53f7-90e6-21d21174ffa1 | note | Standard / Specification - PS 2.2.16
38f7b901-ce61-5b82-ba86-2c9d95552aab | note | Verifying Document - Site Records/ Refer to Services ITP for testing requirements
e019faaf-8fe0-58e4-a4b1-8950d688b682 | note | Frequency - Min 48h Notice
d6a597bf-c1ae-5f05-a332-0e409159e8ac | note | Verification Activity - W
9abd5920-382a-5c80-a2b5-d604334cd91e | note | Verification Activity By - ENG
| checkpoint | 3.05.05 - Geotextile Inspection
30235357-ba2a-5d0d-bf32-e108465a9ab7 | note | Acceptance / Conformance Criteria - Before placement of any geotextile.
af850139-ab11-59d3-8d6a-5ded512dd2e8 | note | Standard / Specification - PS 2.2.16
0ce6ff77-7be6-5200-8852-5d53e2272e01 | note | Verifying Document - Site Records
5cc966d5-e906-56ef-8ad4-2635435e73de | note | Frequency - Min 48h Notice
2e6fd158-bfe1-590a-9fbb-55341e4c9b58 | note | Verification Activity - HP
f63cd949-8628-5163-86d2-5e2ab51aae46 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | 3.05.06 - Subgrade Inspection
bea3bd3e-1a67-59b3-b150-ca5c3595fab9 | note | Acceptance / Conformance Criteria - Subgrade inspection/stripped surface inspection, to include proof roll, scalar penetrometer and/or shear vanes.
70fc358c-d354-5c6c-8df9-908d48a52f10 | note | Standard / Specification - PS 2.2.16
714db9ad-f46f-52ef-a07e-a27fc0f7ea8d | note | Verifying Document - Site Records/ Test Results
089e3007-f9b2-53da-8767-6fb0c3a01dd8 | note | Frequency - After surface is stripped
40c00e8f-59e9-50f6-b11f-195e2cab0563 | note | Verification Activity - HP
fb26b3b6-d7be-55a5-b920-f8455c493cc5 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | 3.05.07 - Undercut Inspection
205f430b-1d40-5338-820a-fc895c69c6b2 | note | Acceptance / Conformance Criteria - Undercut (if required) inspection, to include proof roll, scalar penetrometer and/or shear vanes.
04d27b24-5e7b-5476-a7ea-cd82483eb3f5 | note | Standard / Specification - PS 2.2.16
65d11e86-28dd-584c-80fe-f09a9af7f41b | note | Verifying Document - Site Records/ Test Results
3ff38dd2-5471-58e4-ae4a-e9a347932bd0 | note | Frequency - Prior to Subgrade Fill
cc051a3c-b0ae-58ed-85a3-2f3963327f46 | note | Verification Activity - HP
1feae0c2-2658-5f77-98b9-3f71b3aea196 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | 3.05.08 - Settlement Monitoring
977450d1-fc9f-55e5-817a-1b9283275032 | note | Acceptance / Conformance Criteria - Settlement monitoring (Settlement pins & Targets) to be assessed by Geotechnical Engineer.
6d2a8eb6-7a7b-5db6-b4f9-6b3941313504 | note | Standard / Specification - Drawing 5200
70cf0c56-fdd1-5590-bef1-518c0f108a8c | note | Verifying Document - Site Records
1a1b650a-d510-553b-b01c-32e36162d83f | note | Frequency - Prior to constructing pavement and wall
f7da49b3-2c9b-5dd0-bd85-3aeaf35709bb | note | Verification Activity - HP
111c8e86-e703-5fd2-8eb8-e9bc46da9b4a | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | 3.05.09 - Subgrade Fill
3b6d39e4-aded-5525-9a05-2f3ba7d4111b | note | Acceptance / Conformance Criteria - Inspection of completion of sub grade fill prior to placing SIL, to include proof roll.
1e9e7ca8-b008-5387-b5a7-47972e295356 | note | Standard / Specification - PS 2.2.16
53267922-2588-5542-83ec-dcce3f7fd14f | note | Verifying Document - Site Records
9c59b01f-1e26-5caf-bc10-e68acc082366 | note | Frequency - Prior to placing SIL
c72eeff7-163c-5f7e-80c2-3f277204adcb | note | Verification Activity - HP
a33638a4-2802-5015-8b04-2758f810735c | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
| checkpoint | Imported Fill Approval
45fd01c7-e910-54d4-bec7-c51dc5e869fb | note | Acceptance / Conformance Criteria - Due to the fill-deficit on this project, imported fill will be required and should be discussed with and approved by the Engineer to verify its appropriateness and quality control testing requirements prior to use.
00224ad9-b44c-5c64-925b-0bdf2c3ad0b9 | note | Standard / Specification - GWS 2.4.1
034eb994-bff4-5dce-a8f5-5ca2e39e8efb | note | Verifying Document - Lab Tests
7bda6704-2e88-5a6c-903a-5abc136f5367 | note | Frequency - At least 2 days prior to placement and compaction.
be698d53-8e18-584e-b59e-5008a430fece | note | Verification Activity - HP
1b3a4554-bdab-544a-b0fe-2f429c05b292 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | Re-Use Suitability Approval
41060b61-19fa-58c6-8795-3e53e1d8ca7d | note | Acceptance / Conformance Criteria - The Contractor shall test representative samples of the site-won material to be used as Bulk Fill and Subgrade Fill and the results are to be sent to the Engineer for approval.
71239f25-057a-5495-a65b-8059f502eb40 | note | Standard / Specification - GWS 2.4.2.1
91ac6848-60d0-5318-9a00-ed4c631f5ddb | note | Verifying Document - MDD, OMC, Shear Vane, PSD
51318647-1fc0-5090-a5bb-df5e632715e4 | note | Frequency - At least 2 days prior to placement and compaction.
4017e19b-6c59-58e0-a358-c2fb46c5bd2f | note | Verification Activity - HP
2738daad-13e6-56e2-850b-dbfe698f6491 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
13cb71d6-c1af-54a6-b7bd-21510996a303 | note | Standard / Specification - GWS
| checkpoint | Eastern Gully Weir Cohesive Fill Material Testing
7e475385-e59b-545a-a386-0317f85d7e4f | note | Acceptance / Conformance Criteria - Eastern Gully Weir Fill shall be tested for Standard Compaction, Solid Density, Plasticity Index (PI), Particle Size Distribution, and Liquid Limit for
5599aacf-9b19-556b-8071-03ee88a79288 | note | Standard / Specification - GWS 2.9.4
291d7143-24d1-5bea-a541-b52e6e678f66 | note | Verifying Document - Test Results
c80900c5-6f26-514c-925c-08033d42fde0 | note | Frequency - At least 2 days prior to placement and compaction.
5e1dd57d-db29-5032-93c2-fc611966f113 | note | Verification Activity - I
2acb792c-7756-591a-9291-3d52f360c47d | note | Verification Activity By - SE
| section | Subsoil Drainage
| checkpoint | Subsoil Pipes
3f94bf73-bf5b-5437-9da8-17e3ae97576d | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
f9a94957-2d43-5bcb-b341-3538bb894ea7 | note | Standard / Specification - GWS 3.2.1
b629c8f6-6dfd-5ea2-b72e-17917646bbc1 | note | Verifying Document - Datasheet
f4e1f338-8fa7-504b-a4cb-56b41896398e | note | Frequency - Prior to installation
1a71e582-8f83-564e-92ab-12f86985a0e1 | note | Verification Activity - C
33c9ad80-23dd-5d83-a970-60e5f6105c12 | note | Verification Activity By - SE
| checkpoint | Subsoil Drainage Aggregate
157dd5fd-3914-5a7d-b6cd-82a7e9a4aafb | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings
aa2baf26-c5d7-5049-ab44-ef2f743b3ebe | note | Standard / Specification - GWS 3.2.2 & 3.4
1248aa8d-7bc1-58cb-a514-3c47b2467f19 | note | Verifying Document - PSD, CR
7a23c5b4-57d0-5aa9-9f7e-07c02b92409f | note | Frequency - Prior to installation
5e0a201a-911e-5ee8-b97a-d9332fbdcfe8 | note | Verification Activity - C
506f0618-6e1c-5102-87bc-d361e1022c7b | note | Verification Activity By - SE
| checkpoint | Filter Cloth
40786ed1-1abb-5eab-b26d-821b1c62bf75 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings.
a0219122-25d9-528f-ae9a-22dbaf87c7a8 | note | Standard / Specification - GWS 3.2.3
f610f319-f379-53fa-8154-8b4d5bca6c13 | note | Verifying Document - Datasheet
2e3e366f-ba60-5836-9a55-28f1ba3a5d70 | note | Frequency - Every 1,000m3. At least two weeks prior to works.
951ef335-8d62-5c06-be73-7eec18ac3d1f | note | Verification Activity - C
fe3a95d8-88a3-576f-aa42-613286c0653d | note | Verification Activity By - SE
| section | Geotextile and Geogrid
| checkpoint | Geotextile Approval
9a3d2597-ebe2-539a-aa42-61368c2611c3 | note | Acceptance / Conformance Criteria - The Contractor shall submit to the Engineer for approval the details of the filter fabric they propose to use at least two weeks prior to commencement of works, including compliance certificates.
a79a093a-64b5-5be4-812d-9f9f7aa9450c | note | Standard / Specification - GWS 4.1
561e97cf-103c-5838-ac55-be14acc86d5e | note | Verifying Document - Compliance certificates
79bd7770-6037-5577-8954-1c2bdc4582d9 | note | Frequency - At least two weeks prior to works
067be5b6-4d6d-5483-92ea-3e46a124d9a9 | note | Verification Activity - HP
967372ea-a3a3-54c8-9a64-18ddb723d059 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | Uniaxial, Biaxial and Triaxial Geogrid
20af9f1b-6c10-5787-a2c6-f3c6221c2cc6 | note | Acceptance / Conformance Criteria - All uniaxial, biaxial and triaxial geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001 and shall submit to the Engineer for approval.
ef41addc-1cbe-5c0d-9ca5-8d1ef6fdbe67 | note | Standard / Specification - GWS 4.2
0c7958a6-3ee8-5743-b5ce-19e007a5a8f6 | note | Verifying Document - Datasheet
913b2d66-4c18-5767-a5e9-17b67944114f | note | Frequency - At least two weeks prior to works.
aea6a083-cef0-5f4f-85d7-58111f8e5b2e | note | Verification Activity - HP
2fb75c33-4757-5988-8eb9-2f85068131e8 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| section | Settlement Monitoring
| checkpoint | Settlement Baseplate Design
b2e13714-0793-5134-9aba-dff3f3e49e11 | note | Acceptance / Conformance Criteria - Equipment shall consist of 600mm x 600mm base plate (typically 20mm thickness),150mm PVC duct, 32mm diameter threaded bar with couplers for extensions at 1m intervals and waratahs and coloured flagging for protection following installation.
ab58a620-29e1-5cd5-9913-2c7857009c45 | note | Standard / Specification - GWS 6.2
9dc5bee6-37ba-5834-afe8-f7ef22fcf6eb | note | Verifying Document - Datasheet
177044c2-7b5a-56d8-b467-6a11c2a05f8d | note | Frequency - Prior to installation
38c7b763-7106-5ffc-9cab-8f619cc54550 | note | Verification Activity - I
9d733ae1-3eec-549d-8aba-40c2e14e2c81 | note | Verification Activity By - SE
| checkpoint | Settlement Pin Design
4993c9e1-6514-5af4-8698-bf4bb1ef0f04 | note | Acceptance / Conformance Criteria - Settlement pins are to comprise 32mm diameter Reidbar rods driven a minimum depth of 0.5m into the ground surface. The top of the pin shall be domed to ensure repeatable survey measurements.
8280e55b-aaec-5527-b3ea-2bd24da7ac4e | note | Standard / Specification - GWS 6.3
6a86ff42-72c4-56ff-9fe0-eff5fd9492fd | note | Verifying Document - Datasheet
f069dae9-7360-5fcb-a785-701687cc1afc | note | Frequency - Installed within 24 hours of reaching design subgrade level
c73ca30a-597f-5a40-b41f-829e4cedbddd | note | Verification Activity - I
33be6f18-8792-5920-bf9d-de4009c5069b | note | Verification Activity By - SE
| checkpoint | Settlement Pin Bedding
2e1cfb65-6bc6-5474-a42d-b8ec2e0429ff | note | Acceptance / Conformance Criteria - Installation of the settlement markers shall occur at the base of the fill embankment, prior to placement of any fill. They shall be installed on a 100mm thick sand layer to form an even and smooth foundation which will be levelled using a spirit level.
2e80c0cf-b430-5cf6-8078-e90a77e6de23 | note | Standard / Specification - GWS 6.2
bb88f167-2eac-5ea1-a07a-4edb43311454 | note | Verifying Document - Site Record
433e324e-7e70-5607-946b-81fc02328d45 | note | Frequency - Prior to placement of fill
f0211247-806a-5652-b84e-408b2ce9da48 | note | Verification Activity - I
8c69d77c-c146-5a3b-9c0b-2d63827771a2 | note | Verification Activity By - SE
| section | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
| checkpoint | 5.01.01 - Clearing
78082b3a-e12b-5c21-a358-53d24b788896 | note | Acceptance / Conformance Criteria - All surface objects including fences, gates, debris, wood, dumped rubbish, concrete and other protruding obstructions shall be cleared and disposed of
9da1e544-eed3-519d-91c1-83240462c755 | note | Standard / Specification - PS 3.1
b50dac47-4fde-59b0-813f-56d6371997cc | note | Verifying Document - Site Records
a64d2405-c9fc-5811-a16d-dfcafa596de9 | note | Frequency - Prior to earthworks
1ca5d8fa-084f-53ca-b716-8880263ff1fd | note | Verification Activity - C
783b14cd-f41b-5af2-ab9a-9cdee83f416d | note | Verification Activity By - SE
| checkpoint | 5.01.02 - Demolition
898e6b66-9ffd-5630-8dcf-66d7cdd5cb4e | note | Acceptance / Conformance Criteria - Remove all buildings from the site including foundations, buried services and any other remnants.
1e4b5000-6877-5ca4-84b0-743bc492ac42 | note | Standard / Specification - PS 3.2
24b04cf3-b6ce-5360-8034-99e455efb90d | note | Verifying Document - Site Records
0f5cac53-5c09-5007-b349-9f02b07fb230 | note | Frequency - Prior to earthworks
676ec549-3b82-5463-b42f-70db12e7831d | note | Verification Activity - C
0937604e-d956-5db1-bf39-00d54c56fc50 | note | Verification Activity By - SE
| checkpoint | 5.01.03 - Septic tanks
f8c973f8-deef-5746-94a7-f251b5a2a71d | note | Acceptance / Conformance Criteria - Septic tanks shall be pumped out prior to removal and backfilling
b49d37c8-cb6e-501b-a4fc-a478b803a512 | note | Standard / Specification - PS 3.2
df2c9c6a-22a3-5041-8d6d-32a328bfb5ce | note | Verifying Document - Site Records
c6bf3dbd-30cf-5317-9142-90b0a2dd1c2d | note | Frequency - Prior to earthworks
f5499a7d-03ba-57c9-b1ef-2012a2864ca5 | note | Verification Activity - C
c011ed82-15bf-5f55-9f4c-d8313d37f9ce | note | Verification Activity By - SE
| checkpoint | 5.01.04 - Plant Clearance
6d4d6e9c-4028-5c04-8cc4-6787c37ba964 | note | Acceptance / Conformance Criteria - Vegetation, Tree stumps, shrubs, plants, logs, including any roots greater than 25mm in diameter shall be cleared and disposed of
e513f065-fdac-5f75-a44b-2e4108a6638a | note | Standard / Specification - GWS 2.5
89f3f0b4-9bed-5b89-9ee8-bc47e57cad46 | note | Verifying Document - Site Records
dfdf7fa0-228d-51d6-a8d7-2b99f126969c | note | Frequency - Prior to earthworks
705917af-f81b-547e-848b-02cbfb8e0005 | note | Verification Activity - C
88634bea-cf7c-5452-9202-e6787e9c447d | note | Verification Activity By - SE
| section | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
| checkpoint | 6.1.1 - Groundwater Management
eb0e86e5-e733-5223-bbb9-927510d23d9b | note | Acceptance / Conformance Criteria - The Contractor shall provide all pumping plant and drainage systems required to ensure excavations are always free from water.
7e7617fa-fae5-5875-b604-3d92f1ae9a02 | note | Standard / Specification - PS 3.4
e28a6666-2864-58ac-b2be-d03fe009182d | note | Verifying Document - Correspondence
3c59ca22-9750-56f4-9528-71508147a1a2 | note | Frequency - Prior to excavation
963a9310-1758-5ef2-b107-9ca62263c7a2 | note | Verification Activity - W
6dad533d-9d56-562d-a873-7ac544b09ff9 | note | Verification Activity By - ENG
| checkpoint | 6.1.2 - Cut to Waste Approval
4d18e52c-8158-562d-a166-7fae841d5a02 | note | Acceptance / Conformance Criteria - The Contractor shall obtain written approval from the Engineer prior to cutting any material to waste. To include evidence and extents of cut to waste. Topography survey data of all material to leave site, photographs of material and any material test reports.
e1a13489-9a5d-55a8-902e-237a7c4a31e1 | note | Standard / Specification - GWS 2.4.3
f68f05fa-aac4-5343-bc89-5a71a59747d5 | note | Verifying Document - Correspondence/Photos/Survey
db47406d-a14b-5988-af96-e4bde7d4b0ae | note | Frequency - Prior to cut to waste
1f8dfc8b-94b1-5db0-91bf-802c87634719 | note | Verification Activity - HP
d1e607a9-75e4-5ccc-9495-77974ca634ce | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | 6.1.3 - Foundation Suitability
8f52a174-1f14-5d9c-8f84-53832a38af69 | note | Acceptance / Conformance Criteria - The foundation on which filling is to be placed must be observed by the Engineer following clearing and prior to the placement of any filling to confirm the strength of the underlying soils is sufficient.
403a8560-3fe5-5d70-8ba0-4889dd83f554 | note | Standard / Specification - GWS 2.7
190f3aa6-7334-5f5f-a3ee-8d073c6c01ad | note | Verifying Document - Site Record
9fe9f93a-da52-5774-aa98-f6a1d17205aa | note | Frequency - Prior to the placement of any filling
49c4a9bc-2a33-58b4-aa32-18d9c49e9425 | note | Verification Activity - HP
55a75d49-9d4c-53ae-b04c-d26ae7dc6395 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | 6.1.4 - Unsuitable ground
f74e983f-b3f1-52d2-a6da-8feacdfc6948 | note | Acceptance / Conformance Criteria - Unsuitable ground shall be defined as any pre-existing uncertified filling or natural silts/clays having an undrained shear strength of less than 70kPa or natural sands having less than 3 blows per 100mm penetration when tested with a Scala penetrometer. The contractor shall obtain instruction from Engineer around extent and depth of undercut.
72b8a517-2c2f-576c-ab22-8a5927e27db0 | note | Standard / Specification - GWS 2.7
20f3605a-ef82-5349-8b91-838106d91174 | note | Verifying Document - Shear Vane / Scala penetrometer
6e495bf5-1e22-523d-9860-9240145d4445 | note | Frequency - Prior to the placement of any filling
b650b8b5-6206-5b56-9962-d2e1a99ce04e | note | Verification Activity - I
5bd7b186-b7b2-5740-b0cd-6b7cd6829b31 | note | Verification Activity By - SE
| checkpoint | 6.1.5 - Preparation for Filling
a6040fbd-88ee-5361-8734-01f4b7fd8f51 | note | Acceptance / Conformance Criteria - Preparation of the firm to stiff / medium dense subgrade beneath the proposed fill areas should comprise stripping of all vegetation, topsoil, any pre-existing fill materials or weak alluvium followed by benching of the exposed subgrade where natural slopes beneath the fill exceed gradients of nominally 1:5 (vertical to horizontal).
7c91a7c3-4bf8-5b9f-be81-ab10b9428ed3 | note | Standard / Specification - GWS 2.9.2
fc234cf2-875c-50a9-bd15-e27556849159 | note | Verifying Document - Site Record
22f53065-82e3-5ab6-ae5a-39840a6267b4 | note | Frequency - Prior to placement and compaction of fill
239279e4-1553-5a57-b7d5-a078fa61cec6 | note | Verification Activity - I
aa3d6ba2-bde8-57a5-aefa-e21d85e5b1ea | note | Verification Activity By - SE
| checkpoint | 6.1.6 - Subgrade Conditioning and Proof Rolling
bd14a369-a5e5-53fe-af67-b8de5e4943c4 | note | Acceptance / Conformance Criteria - The subgrade shall be scarified and moisture conditioned where necessary and then proof rolled to verify the subgrade stiffness and consistency.
c9327137-4cde-584e-9d31-f301eced2c4f | note | Standard / Specification - GWS 2.9.2
5a215d15-4350-5e0a-b384-5db64abf102b | note | Verifying Document - Proof Rolling Sheet
437a76a4-fcbb-5fb8-b9c0-dba79aa678b3 | note | Frequency - Prior to the placement of any filling
5e876cd9-e4c1-583b-bce3-5c43af9e35ff | note | Verification Activity - V
51ccb122-fc8c-5e98-9471-2075d87f0242 | note | Verification Activity By - SE/QE/ENG
| checkpoint | 6.1.7 - Undercut Backill Compliance
34b385b3-2355-59e7-876f-ff44ad010bdd | note | Acceptance / Conformance Criteria - Test results for undercut backfill prior to bulk fill commencing, NDM, scala penetrometer, shear vane or cleggs, material dependant. TBC instruction from engineer. Undercut backfill QA to be filed/captured separately from bulk earthworks fill QA.
f2d5b609-ffe3-5060-90eb-b2aeb2b22cc6 | note | Standard / Specification - GWS 2.9.2
2a5ceae4-6204-56b2-af74-f7b852dc82ec | note | Verifying Document - Test Results
3d85fe98-17a1-5ba1-8548-1faff69eb73f | note | Frequency - Prior to bulk fill commencing
ec2b9ddc-86b4-5199-a84a-b585302e0d67 | note | Verification Activity - R
f06ec382-6ae1-5540-b7b0-49c345564686 | note | Verification Activity By - SE
| checkpoint | 6.1.8 - Topographic Survey
a5561c5b-ca9e-5395-be42-bdfcd8eb8c4f | note | Acceptance / Conformance Criteria - All subgrades and undercuts to be captured via topographic survey (GPS)
972f635b-ad00-5e9d-a764-3df28e80d140 | note | Standard / Specification - PS 2.2.12
67096b30-70fa-568b-8ca7-5c4476661a15 | note | Verifying Document - Survey Results
f665dbf1-e4ae-555a-a155-8f872335b31f | note | Frequency - Prior to cutting or filling.
4e3075c0-3f73-5c5e-acea-53b9ff9dc3aa | note | Verification Activity - R
0dd85854-02b3-5db4-9210-0eb8f56a5c43 | note | Verification Activity By - SE
| section | Stockpiles
| checkpoint | 6.2.1 - Stockpiles
bef39443-7d85-52f7-8d0c-66f2e56b1f58 | note | Acceptance / Conformance Criteria - The location of all temporary stockpiles must be approved by the Engineer prior to placement. Where stockpiles cannot be avoided above sloping ground, they should be placed over a wide area with the height restricted under the direction of the Engineer.
25ca6fa2-218e-58ee-bfc3-2c5a7c30c9df | note | Standard / Specification - GWS 2.9.3
0234ee50-2cac-5b79-8bc4-e97d89f84622 | note | Verifying Document - Stockpile Map
db7cde91-35c2-5185-9e3b-b29a79f2176d | note | Frequency - Prior to placement.
48298222-1d4e-5d30-932c-06dd5fa4628d | note | Verification Activity - HP
1497dad8-abb9-5023-a8ca-f94c8ff694a8 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| section | Earthfill
| checkpoint | 6.3.1 - Earthfill Placement and Compaction
286ede01-a444-59af-8320-caa3012c88cc | note | Acceptance / Conformance Criteria - Earthfill must be placed, spread and compacted in controlled lifts under the direction of the Engineer. All earthfill must be placed to ensure adequate knitting of successive fill lifts by ripping any surfaces that have become dry prior to placing the following fill lift.
b3cf298a-4b4e-50e8-92bc-e06a06b5c243 | note | Standard / Specification - GWS 2.9.4
0ba917b5-eebf-5035-abc0-0e37abe8cbed | note | Verifying Document - Site Record
0e81b6c5-9757-515a-b91b-e69f20515b83 | note | Frequency - Per lift
d3f4f4d1-826c-579d-b32f-e6b543e41cf7 | note | Verification Activity - HP
4406eb78-5b4b-5bc2-ac14-4fb5ba61d892 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| section | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
| checkpoint | 6.4.1 - Proof roll Testing
81e47988-85b7-532a-bae1-1a12e72c1d69 | note | Acceptance / Conformance Criteria - Each layer shall be tested via Proof roll to: 7mm maximum impression
881f0569-d51a-5ef7-8ef0-d3678621cee8 | note | Standard / Specification - GWS 2.9.4
71c058e2-0e0e-5335-9f4a-00d696132c0b | note | Verifying Document - Proof Rolling Sheet
d2cdd97d-44a2-54ec-8461-90172cb8a3be | note | Frequency - 100% of each layer
a3cf788c-318e-5cbc-adc4-8104048747c7 | note | Verification Activity - I
a6b88ab0-b9d8-5dd7-8d79-5c1cdfb29ad2 | note | Verification Activity By - SE/ENG
| checkpoint | 6.4.2 - Compaction Testing
0361ad6d-e77a-5d58-81fe-394dbecd915c | note | Acceptance / Conformance Criteria - Bulk fill shall be tested by DT at 300mm probe depth 95% MDD. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
702d3671-8874-54ae-904e-c2b546422874 | note | Standard / Specification - GWS 2.9.4
84133fc7-b8f9-55b3-a993-09885b7c8b41 | note | Verifying Document - Test Results
9d017020-3c0e-553d-b800-f863103cd6c3 | note | Frequency - 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x DT within a 3m radius)
e73f6f4f-173e-5265-a670-bd32cc5dbb1d | note | Verification Activity - R
2c57898f-d1f2-505a-abc6-d6dda53bcda1 | note | Verification Activity By - SE/ENG
| checkpoint | 6.4.3 - Scala Penetrometer Testing
f1331738-3f66-562e-aab4-9f1c14cd166a | note | Acceptance / Conformance Criteria - Bulk fill shall be tested by Scala Penetrometer every 500m3 to: 4 blows per 100mm. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
3ecfb16a-a9fc-5056-9e5c-bed455d0694e | note | Standard / Specification - GWS 2.9.4
e7df00a3-4bb3-5329-b09e-c11d8a7e7f46 | note | Verifying Document - Test Results
c5a4782b-328c-5561-92b4-2ad8f96d9ddf | note | Frequency - 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
3b2bf319-1640-5979-bca2-736dc8f5952c | note | Verification Activity - R
11826f75-4718-5556-89d7-4887d9c2d9d7 | note | Verification Activity By - SE/ENG
| section | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
| checkpoint | 6.5.1 - Vane Shear Strength Testing
dbbc0a18-ae6a-5cf7-9ce0-18ec7a7ed771 | note | Acceptance / Conformance Criteria - Bulk fill shall be tested for Vane Shear Strength to: Minimum average 120kPa over 10 tests, minimum single value 110kPa. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
36bcc3d7-db98-5639-af85-741172812629 | note | Standard / Specification - GWS 2.9.4
251ea5e9-0ef2-5550-9457-1743ce45a70b | note | Verifying Document - Test Results
1d857961-37ac-5b77-a66c-91f514f529e0 | note | Frequency - 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius)
56d13354-9e3c-5cfb-91f0-04b5ea52b5e7 | note | Verification Activity - R
2f5aef00-2b4f-5282-a689-66479c32e70b | note | Verification Activity By - SE
| checkpoint | 6.5.2 - Air Voids Testing
9901dfd8-8abf-5c33-9555-ffa623f92f70 | note | Acceptance / Conformance Criteria - Bulk fill shall be tested for Air Voids to: Maximum average 10% over 10 tests, maximum single value 12%. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
f3da272a-2c60-5787-9a8d-72ddfd15ed6c | note | Standard / Specification - GWS 2.9.4
36bf09f3-2f3e-56ec-8617-e97bc6b90620 | note | Verifying Document - Test Results
0a4d47d7-3840-5c0a-a55d-504f47de1df7 | note | Frequency - 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius)
c3c6cc28-d947-5fc1-bac2-97a43d11f29e | note | Verification Activity - R
8267f1ef-1ee0-56f7-bf44-85d36163dbe2 | note | Verification Activity By - SE
| section | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
| checkpoint | 6.6.1 - Proof roll Testing
b633fc11-6f49-5738-ae16-b70fd989c7e5 | note | Acceptance / Conformance Criteria - Each layer shall be tested via Proof roll to: 5mm maximum impression
bde7cd76-353a-543d-81ea-5b47ef0877e2 | note | Standard / Specification - GWS 2.9.4
2f034ce5-f965-53c1-9f07-ab3c43bb4201 | note | Verifying Document - Proof Rolling Sheet
bbc95283-876f-534a-a57e-454ecf07ca08 | note | Frequency - 100% of each layer
b884386a-1912-518f-82fa-88e7ffc3a8ab | note | Verification Activity - I
a9e47c7c-12af-5d6a-a677-b116b4721333 | note | Verification Activity By - SE
| checkpoint | 6.6.2 - Compaction Testing
72f4e1d4-2714-5bad-b61b-a89df2751088 | note | Acceptance / Conformance Criteria - Subgrade fill shall be tested by DT every 500m3 to: 98% MDD. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
90c5da6a-fd57-519a-af68-7f03ff4eeae2 | note | Standard / Specification - GWS 2.9.4
65582f1c-08a9-5ed4-9cca-7ae57b6fd2b2 | note | Verifying Document - Test Results
7d1f3f80-e554-5f08-8f36-5f61dd240c55 | note | Frequency - 1 set / 400m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
fb7d72f3-6266-5d2f-a84a-b8ef5a9bfb43 | note | Verification Activity - I
abf82fab-4d37-580d-834e-df632b56edbd | note | Verification Activity By - SE
| checkpoint | 6.6.3 - Scala Penetrometer Testing
fa73c0bd-67ed-5c81-b9f6-bcf874f36e76 | note | Acceptance / Conformance Criteria - Subgrade fill shall be tested by Scala Penetrometer every 500m3 to: 5 blows per 100mm. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
b52aed14-7a5f-5c32-b592-ad178c6a4ba8 | note | Standard / Specification - GWS 2.9.4
cbf75fa7-f933-50e9-81ab-d8fe0557bba2 | note | Verifying Document - Test Results
7c9d20af-a460-54be-8d2d-db9494b4edc4 | note | Frequency - 1 set / 400m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
d6175d17-dc53-576e-92fe-4c625f891373 | note | Verification Activity - I
b98e763c-d8e0-5357-ab9e-fbe30cc17c2e | note | Verification Activity By - SE
| section | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
| checkpoint | 6.7.1 - Shear Vane Testing
97b9b3e5-db79-59b2-b466-0b008ccff789 | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested by Vane shear strength to: Minimum average 140kPa over 10 tests, minimum single value 120kPa
5caf5c28-8adb-5986-ac40-117c055eb178 | note | Standard / Specification - GWS 2.9.4
08babd25-b5e1-5a0e-ab73-99303ff9fc43 | note | Verifying Document - Test Results
e2d0c240-a3cd-5182-a990-b731d77ba303 | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
76397b3a-dd0b-59ae-b0c7-b18f4785fcd5 | note | Verification Activity - I
cb0b7c5b-f49c-59af-ab6f-04fa7cf3847b | note | Verification Activity By - SE
| checkpoint | 6.7.2 - Air Voids Testing
4db17005-7815-5b97-af65-a2d559d0b55c | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested for Air Voids to: Maximum average 5% over 10 tests, maximum single value 6%. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
9e4e2f34-58e8-5cba-8f25-809593f7e3b4 | note | Standard / Specification - GWS 2.9.4
b94e47d1-f994-5e12-9c5a-ca666b8a440e | note | Verifying Document - Test Results
33c1e730-fd7a-5790-b721-486d1a8144f6 | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
8f1e6d8b-95ee-55cc-ab21-e7ba2bff47aa | note | Verification Activity - I
b2000c16-2302-5b4f-a14b-e4c0f973756c | note | Verification Activity By - SE
| checkpoint | 6.7.3 - Water Content Testing
5a8fb55b-62f9-5e81-87cf-23c8f3f5f47e | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested for Water Content to: Minimum 2% dry and maximum 6% wet of optimum water content. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
04845150-aafd-5748-987d-ec3e37a628f5 | note | Standard / Specification - GWS 2.9.4
a24404f7-d7be-5b60-acf0-37f389166146 | note | Verifying Document - Test Results
b4089446-2691-5cae-af41-2c84000040ba | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
607ffd22-9ae7-5e38-92d4-cdfc2d60fd38 | note | Verification Activity - I
0eb417e8-c6f3-58b8-9ce6-33a9fbcc8a53 | note | Verification Activity By - SE
| section | Cut Batter
| checkpoint | 6.8.1 - Cut Batter Inspections
4d324204-dd12-5e34-b757-a5805d8ba4ae | note | Acceptance / Conformance Criteria - The Contractor will need to regularly inspect the exposed soils and check for any seepages that may occur due to the layered profile of the natural soils. All inspection records are to be submitted to the Engineer within 24 hours.
2759f9f1-0521-5f18-9d18-423ac5f16661 | note | Standard / Specification - GWS 2.9.6
ce5cab41-2c26-5482-96c2-3d22d43139ce | note | Verifying Document - Inspection Programme and Records
5c505c18-e993-51f7-949a-5b47156856cc | note | Frequency - Submitted to the Engineer within 24 hours.
a43347cf-95d7-5b0a-9e04-e6157f5a29d0 | note | Verification Activity - H
eb00df9a-b10b-5382-9e6b-464ee4e94717 | note | Verification Activity By - SE
| checkpoint | Cut Batters- temporary cut
82b32635-e0da-5dbe-96c9-9eb5a24df6f3 | note | Acceptance / Conformance Criteria - The temporary cut buffer shall be maintained for 2 weeks to see if the seepage drains out, after which it may be cut to the final profile or additional drainage measures installed subject to review by the Engineer.
73e4728b-5fd1-5e00-a3de-757a7f39c0e9 | note | Standard / Specification - GWS 2.9.6
d4b60330-816d-503d-8f99-630ff7c072c6 | note | Verifying Document - Site Record
f141fdc1-eaa1-5721-93e2-10a3bf9531bd | note | Frequency - Each Cut Batter
08a7b0a1-3bd6-52cb-a687-8fd6eec5a3ed | note | Verification Activity - I
b7d155b5-2a16-51db-b7e9-418daa45c1cb | note | Verification Activity By - SE/ENG
| section | Surcharge Fill
| checkpoint | 6.9.1 - Surcharge Fill Installation
f8d6420c-f10e-5e92-8f1b-1938b79fc563 | note | Acceptance / Conformance Criteria - Surcharge filling shall be placed, spread and track rolled in 300mm layers. Surcharge fill will only be required if the settlement monitoring results exceed what was anticipated in the design. Under Engineer’s direction.
bea58f9c-832b-54dd-91d1-7738ce2a1847 | note | Standard / Specification - GWS 2.9.7
11e1b7c8-63f1-5b19-b041-37ef1a1a8150 | note | Verifying Document - Site Record
be46eeb9-b88f-5e12-adb3-e15853fa82ea | note | Frequency - Per 300mm layer
89c48506-43db-5c3d-aa52-bf114025d184 | note | Verification Activity - I
ac13cdb7-dc86-52f2-b78a-f98e874d68bc | note | Verification Activity By - SE
| section | Respread Topsoil
| checkpoint | 6.10.1 - Topsoil Respread on Steep Ground
612645e2-276d-5142-9b35-0c856ea5d03c | note | Acceptance / Conformance Criteria - On ground steeper than 1V:3H the surface should be roughened under the supervision of the Engineer prior to topsoil placement.
6e7f7b5a-7ed7-5cf2-9964-ab15f2fd2dfc | note | Standard / Specification - GWS 2.9.9
f6c2c4c1-e3aa-52d0-b069-b8bfb728a650 | note | Verifying Document - Site Record
28b6f014-6695-5478-a0ab-d75596c438bf | note | Frequency - Prior to topsoil placement
27f50561-beb4-53c0-85fd-f9ca434bb6ec | note | Verification Activity - HP
b0f3ff82-752c-51a9-aaa9-99a25793f796 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| section | Subsoil Drainage
| checkpoint | 6.11.1 - Filter Cloth Wrap Inspection
e85fb9f6-7d2b-513a-bd83-0e4c00c9f8d7 | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain.
246d901e-41b6-508b-a982-d57b285d48f6 | note | Standard / Specification - GWS 3.2.2
14272c52-0910-574a-8e68-1a008caaea01 | note | Verifying Document - Site Record
4b416b83-4d74-5080-9f4a-780e2dd7ea80 | note | Frequency - prior to backfilling
b07a666c-cab0-5dc9-b74a-e8928840c5da | note | Verification Activity - HP
2a503a6b-ecda-532e-8198-34ada9d17cca | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | 6.11.2 - Trench Backfill
9be62d94-669d-56c5-98df-f0655e525d22 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard above
9943da35-02d8-5462-9871-d8df0642290e | note | Standard / Specification - GWS 3.3
14fbb3eb-8b9a-5333-af1a-fb278cb4f91d | note | Verifying Document - Site Record
71250cca-3f46-5d4d-8b23-78956c6b7201 | note | Frequency - Each trench
63f9d961-89a4-582b-8e63-ba924b5a4aa5 | note | Verification Activity - I
e9ff29db-9280-5bcb-8127-113818b5c8f5 | note | Verification Activity By - SE
| checkpoint | 6.11.3 - Drainage Outlets and Inspection Points
e249ae11-1c7d-5447-bc71-995f46050380 | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
e46ceacf-cb8b-505d-8b15-1dc555be327f | note | Standard / Specification - GWS 3.6
85052b17-54d4-5a95-9cbb-ef0d6c71f674 | note | Verifying Document - Site Records
5ba4c355-4959-5072-8fd9-0aaf4250d5fb | note | Frequency - Each Subsoil Line
8a2d0f43-d8cf-5b99-be4a-77de64ccae73 | note | Verification Activity - I
ee8b451c-21ab-5f86-ba49-8c33a487de18 | note | Verification Activity By - SE
| checkpoint | 6.11.4 - Subsoil Flushing
ac40c030-449b-542a-af1b-0220426fe171 | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
b407e655-141b-5767-955c-3c2aa89b6d64 | note | Standard / Specification - GWS 3.6
e23d0fc8-d955-5bdd-9a2e-739dea834f0e | note | Verifying Document - Site Records
08a98415-27ac-5d92-accf-d6f9681783cf | note | Frequency - On completion of earthworks
8c87024e-7a19-523d-9d24-d7539bbdb6c3 | note | Verification Activity - HP
4f23f32d-52cd-557e-8dc4-002c5a2eda2c | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | 6.11.5 - Survey
157333d0-9f65-58aa-be41-2fc45a3a2cdd | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
1b3f7c5e-1e01-5a0e-a9e7-06bc3b3a5f3a | note | Standard / Specification - Downer
a335245c-0a90-5993-a7e9-27775cd90fca | note | Verifying Document - Records
ef32fdb5-96c4-5a3f-8230-c5c1f956c7f7 | note | Frequency - Post construction
343e4729-0a43-541b-963c-5e036c02f45f | note | Verification Activity - H
74b2f7ff-37a5-576d-8c7d-82789d0323f5 | note | Verification Activity By - SV
| section | Geotextile and Geogrid
| checkpoint | 6.12.1 - Geotextile Installation and Lap Length
76225046-1c0e-5471-957a-bb64165abba8 | note | Acceptance / Conformance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
66d8fa5b-a442-549a-bea5-c3cb7452c2ad | note | Standard / Specification - GWS 4.1
de2fd70a-1a13-5c27-a39c-70f8eed0732e | note | Verifying Document - Site Records
c2acaba6-1ca8-5cac-8371-503ab5be89c7 | note | Frequency - Between each sheet
0067de7e-b9fc-5b67-8136-0342c39ff969 | note | Verification Activity - I
f5d827bb-f426-5371-a150-e95a31726758 | note | Verification Activity By - SE
| checkpoint | 6.12.2 - Geotextile Inspection
5fce79e7-daa5-53c5-ad32-308b9a5bc3c4 | note | Acceptance / Conformance Criteria - Before placement of any geotextile should form an Engineers inspection hold point
b95f0b90-c3e4-514b-835d-2f189a655d86 | note | Standard / Specification - PS 2.2.16
f3c2b170-0327-54e3-b456-bc5cc93ab321 | note | Verifying Document - Site Records
b2d0e962-99a2-5b14-8134-5a715d35b1d2 | note | Frequency - Min 48h Notice
4ca5ca69-f231-5784-abee-83eeca3a889b | note | Verification Activity - HP
a8b167fb-fa63-5a5a-a9b8-2948ec01afe8 | note | Verification Activity By - ENG
| signoff | Hold Point (Engineer)
| checkpoint | 6.12.3 - Geogrid Prep Inspection
08108f8c-c97e-553e-9698-ffa2ad50e42c | note | Acceptance / Conformance Criteria - Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings.
5123368d-8f9e-559a-b60f-86578ebb8743 | note | Standard / Specification - GWS 4.2
80170ccc-66d3-58b2-b5d7-f14349acad85 | note | Verifying Document - Checksheet / Survey
0a1db885-bc81-5f42-85ea-012546cd27bf | note | Frequency - Prior to placement
d17f58fa-a7fc-5a1b-a210-e9612db174c1 | note | Verification Activity - I
b5070777-cb7a-5829-bc76-2a395a322d46 | note | Verification Activity By - SE
| section | Settlement Monitoring
| checkpoint | 6.13.1 - Settlement Pin Installation
99a3f15f-8fc2-5bf6-9524-d6389239a71b | note | Acceptance / Conformance Criteria - Protective waratahs and coloured flagging shall be installed around all settlement pins for protection. Settlement pins shall be installed within 24 hours of reaching design subgrade level.
2f1d0c7e-7ded-524d-9789-d329ecdea150 | note | Standard / Specification - GWS 6.3
7a072403-7d6d-584f-b3d8-2d79756c7e87 | note | Verifying Document - Checksheet
248f1536-fe7a-5a91-887f-1bd1ed65900a | note | Frequency - within 24 hours of reaching design subgrade level.
b4f59ffe-eb6b-5ea4-80c8-cf2ba8ab3538 | note | Verification Activity - C
0cef5e12-9dee-51e8-b40d-6b3fb1589e5d | note | Verification Activity By - SE
| checkpoint | 6.13.2 - Settlement Survey
112e7f80-767f-5636-946f-3932d2c8e479 | note | Acceptance / Conformance Criteria - Survey measurements are to be undertaken regularly by the Contractor as specified on the drawings, to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
212ea4ee-e52a-546b-808c-745bac8d928a | note | Standard / Specification - GWS 6.3
f1489eab-003c-5a56-a03f-13ad0877b9b2 | note | Verifying Document - Both paper and electronic formats
571d823b-77b5-53aa-8f3b-cc51567a9717 | note | Frequency - within 24 hours of each reading.
d4b9d21a-a50a-5a45-8ad8-0771fa0b609e | note | Verification Activity - H
539fae9f-0f46-5cb7-ac3e-84c6f799cda3 | note | Verification Activity By - SV/SE
| checkpoint | 6.13.3 - Retaining Wall Settlement Targets
b493ddef-686b-59cb-a6fa-20ce8a77e630 | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
3eeed169-5910-546d-849f-0c6770ded3bc | note | Standard / Specification - GWS 6.4
4fa0ca17-2e43-50c7-8881-fe23558af58b | note | Verifying Document - Checksheet
90ae0198-a4e3-5455-90ed-a258561cd1fc | note | Frequency - prior & after completion of first row of retaining blocks
be7c7a7f-d127-535b-ad98-78270c9a6907 | note | Verification Activity - I
a8e6571c-2ea6-520b-b643-50014469a9b8 | note | Verification Activity By - SV/SE
| section | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
| checkpoint | 8.1.1 - Construction Record Compilation
9e865959-c88a-5190-9f5f-9aead8c19ce6 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
f4dfd5a4-d771-5aff-a69f-4c87ca9911bb | note | Standard / Specification - Downer
89b72ad1-0a2c-5e13-a797-a0d4a5b77ccf | note | Verifying Document - Records
855af0eb-08d2-530f-a975-5f08114d94c3 | note | Frequency - Post construction
0c644f99-c56e-54d0-b27f-54f286afe727 | note | Verification Activity - H
271d3bf3-544b-50e2-a020-72c91450dfda | note | Verification Activity By - SE
| checkpoint | 8.1.2 - Survey Records
e04a5f03-809c-5321-856b-6c14bbe078c7 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
ea054228-80af-5478-8e11-c723f5ec1539 | note | Standard / Specification - Downer
fcc41489-f8ba-5261-96c6-b0f25fa9d847 | note | Verifying Document - Records
0e8d161d-391b-5bc0-a9cf-621caa90b000 | note | Frequency - Post construction
606b5e65-7591-5355-8b6f-2c9e2ee4738f | note | Verification Activity - H
a10d33be-0636-5363-b915-0104e692bbbe | note | Verification Activity By - SV
| checkpoint | 8.1.3 - Redline Drawings
c8dc263f-8b1e-52a7-beee-97d562069bee | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
e3d9d811-9f48-50aa-ad2d-fbcb143b84ad | note | Standard / Specification - Downer
c8d3d189-33f3-5e6e-a349-a2f6a1c86fce | note | Verifying Document - Redlines
bb6a84e8-3c2f-500a-8396-acf0711ef71f | note | Frequency - Post construction
fbb1edf2-dd6f-53ab-abb0-02caa90ae961 | note | Verification Activity - H
c8c2a577-65bf-5aed-9279-6ba112957dfc | note | Verification Activity By - PE
| checkpoint | 8.1.4 - Defect, Snag and Punch List
cabd4ab6-3f8c-56a6-85c9-b1978f83c065 | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
10adea13-6583-56cf-a47a-74e52be060f2 | note | Standard / Specification - Downer
ff84c247-59ba-58d6-ab15-87cde05db7b7 | note | Verifying Document - Register
7c100c2c-f6d9-5eb5-8a7c-7402ea3850ee | note | Frequency - Post construction
a81e1351-5432-54e8-9e31-499cb6261f99 | note | Verification Activity - H
6924f01b-f7f3-51bf-a1e7-f2c5e75d1ab0 | note | Verification Activity By - PE
| checkpoint | 8.1.5 - Photos
94e37964-f4ea-55f7-843c-d9cff1cab647 | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
4bbb697c-8d21-5a96-8dda-190c8bb6e3e5 | note | Standard / Specification - Downer
613458d8-44b8-5f7b-aa36-ddd3ce4f2886 | note | Verifying Document - Photo Records
706b1d90-4936-5f76-ab5e-a6ac12da6b19 | note | Frequency - Post construction
88958877-a040-53a7-a425-18f857a2b216 | note | Verification Activity - H
b80fc67a-8a18-5aef-addc-224f7da47377 | note | Verification Activity By - SE
| checklist | ITP - Hollowcore | itp | ITP - Hollowcore | 77befa5c-bfab-4027-abf5-fb80bd972b74
| section | 1.0 Pre Construction Tests
| checkpoint | 1.1 - Concrete Mix Design Approval
78f211aa-5a6d-5d2e-952f-d156b3567228 | note | Acceptance Criteria - 60 MPa at 28 days (S6014PC)
aa858af4-1c11-5fec-9807-c8bf6701d980 | note | Inspection or Test: Method - Review
d2c184e8-b5f4-5905-b93d-788ab91ca0db | note | Inspection or Test: Freq. - Once per Mix design / per supplier
17809666-3917-5c98-a776-b11dfa4ff31c | note | Inspection or Test: Responsible Person - PRECO
7fcbf47b-08ac-57d4-8bb0-1afe56b12559 | note | Verifying Document - Confirmation of Approval
3a201943-a2a7-5359-9283-ea1ac7d0928d | note | Records required for handover package: Yes/No - Y
eca077c5-ed8a-5b97-9a5e-cdf67be56ace | note | Inspection / Test Authority: Conduct - 1
cb8fb411-2aa4-5950-8709-3a3592e01c28 | note | Inspection / Test Authority: Witness - D
ab4ec765-bf98-5ad9-a7c4-5858a57c8569 | note | Inspection / Test Authority: Produce Record - 1
ffd7e38e-39d7-51a4-a0e2-e393ee9f3d6a | note | Inspection / Test Authority: Approval - D
12b13299-31df-5e0f-8a3d-1c23f32e0df1 | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 1.2 - Reinforcement Supply
c3138b85-2b05-5574-a3a6-a2e04a6675a3 | note | Acceptance Criteria - Micro Alloying Deformed Bars Grade 500E (HD)
14abb13d-df41-55f5-9965-079418bf4584 | note | Inspection or Test: Method - Review
017175fb-024a-571d-8bc6-53d393f584c2 | note | Inspection or Test: Freq. - Per Size, Per Supplier
1c69872e-6d91-5364-849d-51759dbd028a | note | Inspection or Test: Responsible Person - PRECO
70142f81-b14b-5339-ba6e-ca12006cd9e4 | note | Verifying Document - Supplier Mill Certificates
98f163b4-fae4-5b01-a913-d13ec9072468 | note | Records required for handover package: Yes/No - Y
a86b2e81-f72c-5ede-82ea-29331059eb45 | note | Inspection / Test Authority: Conduct - 4
8cca54ad-ae01-5eaa-ba78-9a4ebd814399 | note | Inspection / Test Authority: Witness - D
3f1214ed-d4af-5cd2-b9e7-7438fb04eb89 | note | Inspection / Test Authority: Produce Record - C
73d8ecd9-f1e6-524d-89af-5c9fdf3d6927 | note | Inspection / Test Authority: Approval - D
8cc5fdc0-8b51-54b7-a5c5-f6e9b2d88efa | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 1.3 - Strand Supplier Verification
4255b8e1-7562-54e5-9b12-d10442fcc85e | note | Acceptance Criteria - ACRS accredited supplier
867cf9d8-c10b-58e5-afcd-c49485bd82f8 | note | Inspection or Test: Method - Review
121bd0c4-24de-5c78-8319-dfa08a2d08c3 | note | Inspection or Test: Freq. - Per Supplier
1f928294-bd9a-58d3-9820-099b51484fcb | note | Inspection or Test: Responsible Person - PRECO
ea7943bd-f313-59cc-9d64-d02695513371 | note | Verifying Document - ACRS Accreditation
d661eee4-fff8-5c68-a2dd-5cbc821d7825 | note | Records required for handover package: Yes/No - Y
9ece86f8-116f-5b4e-ab33-20db39efcaae | note | Inspection / Test Authority: Conduct - 4
fedf724f-dd9f-50fc-9f5d-3b1ad3296fad | note | Inspection / Test Authority: Witness - D
af4df6dd-cf0c-5cc4-9bf0-f29f3fd06cf2 | note | Inspection / Test Authority: Produce Record - C
f27b0868-6259-51c2-b8d4-57ea5c1652c8 | note | Inspection / Test Authority: Approval - D
cf2a1c14-b965-53b9-ae4e-47d7133f1bbf | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 1.4 - Strand Supply
d5831ee0-71a7-52e2-bec8-36e284be9840 | note | Controlling Documents - NZS 3109
214a8a5c-c23a-5aad-80bb-b71fba686a79 | note | Acceptance Criteria - 15.2mm diam. Prestressing superstrand
4997169f-dac4-54b3-97eb-791c68fa8684 | note | Inspection or Test: Method - Review
721a8e30-e897-53a4-9c2c-d656c7765c60 | note | Inspection or Test: Freq. - Per Size, Per Supplier
1c599276-26d7-54b6-995a-2fbf01dfb740 | note | Inspection or Test: Responsible Person - PRECO
57792685-2729-5a0e-b18f-8f70006bbe90 | note | Verifying Document - Supplier Mill Certificates
a49d69ed-5b55-567a-9f10-5ed2fbd98508 | note | Records required for handover package: Yes/No - Y
72e2b36c-de11-5d10-8e79-8724da027cc1 | note | Inspection / Test Authority: Conduct - 4
286462b3-aa49-5f42-8bb2-3945620a72f2 | note | Inspection / Test Authority: Witness - D
f7a2b0f5-5fed-5c04-a321-1e58b66cbe3f | note | Inspection / Test Authority: Produce Record - C
24164605-5635-550c-b0f1-bfc4f5cd702e | note | Inspection / Test Authority: Approval - D
3e178ecb-70b8-5db9-8bc5-e9342cbd7384 | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 1.5 - Strand Certification
8dfef4d5-d92c-526e-9fa6-9601130558b1 | note | Controlling Documents - AS/NZS 4672
7e6982e4-94b6-548f-ad67-108003a3a0b5 | note | Acceptance Criteria - Conformance to AS/NZS 4672 in relation to:
4ab239d3-ccca-5821-9c30-2522ff9ea8d8 | note | ○ Chemical analysis
f801015e-c684-5f3d-81af-9a989c6bf888 | note | ○ Geometrical characteristics
6680d36a-67e8-5105-b2d1-df651faad111 | note | ○ Breaking force or tensile strength
6bd53a41-3a23-5b28-b2c4-2cfff7519141 | note | ○ Proof load or proof stress
6ba44543-2775-5a07-857c-e7c719cd7e0d | note | ○ Elongation at maximum load
8689ff12-aed6-5bac-83f6-908935756478 | note | ○ Load extension diapgram
a5bdc635-cac4-59f8-8203-4209902dc1c4 | note | ○ Ductility
2c5e90a6-933b-5cd5-b6c8-6cfbe18c960f | note | ○ Relaxation
5d19aab5-7d19-5c52-a24c-8aeec7741395 | note | Inspection or Test: Method - Review
958460c4-0198-51fc-920c-462c63ee5024 | note | Inspection or Test: Freq. - Per Size, Per Supplier
e2d1b5b3-1c0a-525d-a81b-a05b984bd7e1 | note | Inspection or Test: Responsible Person - PRECO
15936079-2d8c-520a-af28-448cfe987c26 | note | Verifying Document - Material Test Certificates
bfdf3393-8341-5999-998a-d2735a598c0f | note | Records required for handover package: Yes/No - Y
307908f2-fb06-5ef2-ba11-fc63bb9efe67 | note | Inspection / Test Authority: Conduct - 4
31b58e15-b7bc-5d95-aef4-f912fd8bc2a3 | note | Inspection / Test Authority: Witness - D
392c27e9-938c-5e17-a0b9-61668440771f | note | Inspection / Test Authority: Produce Record - C
cb9ba18e-2436-50fb-a937-167b8367d118 | note | Inspection / Test Authority: Approval - D
d1711e2b-a249-53e0-9908-a4e885436191 | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 1.6 - Shop Drawing Approval
d81037e6-4cfd-59f6-88d8-0adca4305fac | note | Controlling Documents - IFC drawing
db0fa714-a011-5b85-b0c9-658975aa0039 | note | Acceptance Criteria - Shop drawings including strand type, arrangement and stressing notes, details of debonding lengths, concrete strengths, surface finishes, location of cast in items and set-out information
b8d6e591-4cf9-585e-a730-1862fb7924e5 | note | Inspection or Test: Method - Review
054cb47b-59e4-501a-a990-f771ee88e529 | note | Inspection or Test: Freq. - Once Prior to Casting
ce166315-bb6e-5ca4-8679-0383c87297b6 | note | Inspection or Test: Responsible Person - PRECO
a45c3f2a-0cd5-50b4-bed9-cb4c47078bdc | note | Verifying Document - Approved Shop Drawings, Issued for Construction
29014ed0-46ce-5fb5-b72f-17479d57fcf2 | note | Records required for handover package: Yes/No - Y
89e8fd82-8ecd-5ef5-a4fa-572afc64881c | note | Inspection / Test Authority: Conduct - C
0be08783-6b2c-5068-964f-61ab966f482e | note | Inspection / Test Authority: Witness - D
9bad79f3-7095-5b16-be96-c68c07c5953c | note | Inspection / Test Authority: Produce Record - C
1e55555d-5f65-5029-97ad-db570de73f9d | note | Inspection / Test Authority: Approval - D
9d941f41-78fc-5299-85e9-44f1f8a921a5 | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 1.7 - Stressing Calculations
4142e4e5-f1ad-5627-9e33-d40bf29187f7 | note | Acceptance Criteria - Force remaining in each 15.2 mm dia. strand at midpoint of beam immediately after release of tensioning jacks
26fd898b-b0f5-5dd6-b3e1-6a81f4df8d9d | note | Inspection or Test: Method - Review
2125f996-2afa-5c9b-bc65-24a87238ecb8 | note | Inspection or Test: Freq. - 5 Days Prior to Casting
40427a1d-5c44-52d7-8417-b474dba02533 | note | Inspection or Test: Responsible Person - PRECO
0a3172c5-7508-5e53-847e-3213b5f29a5a | note | Verifying Document - Approved Stressing Calculations
8de58f1f-2e0e-5d67-a886-ef2d7360f8b6 | note | Records required for handover package: Yes/No - Y
698e7976-4c4a-562c-a5af-00ec5dca396d | note | Inspection / Test Authority: Conduct - C
c8e399ef-8561-5cb6-b5c6-5ca02bd6bce3 | note | Inspection / Test Authority: Witness - D
6b5065be-2022-5538-b577-8240c957fc7d | note | Inspection / Test Authority: Produce Record - C
943c788e-a1f4-5e22-869b-904e215411b3 | note | Inspection / Test Authority: Approval - D
e5d40d4a-6c54-5927-9d2d-14a8667156ae | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 1.8 - Jack Calibration
4912747c-2bce-5136-babf-2c5ef48c651d | note | Acceptance Criteria - Calibrated within tolerance
25e0f232-4bd1-517b-9285-35d662af5218 | note | Inspection or Test: Method - Certificate Inspection
c74194b3-f0c2-5267-aeca-fbb84bb25b1e | note | Inspection or Test: Freq. - Every 6 Months, Per Jack
a3976cd2-6eba-5e77-8a63-1f5b81365120 | note | Inspection or Test: Responsible Person - PRECO
d1724d1b-2de4-50e4-a7b4-db0ec34db939 | note | Verifying Document - Calibration Certificate
6687e253-a060-5987-93e6-45cc92317bfc | note | Records required for handover package: Yes/No - Y
5da45a7a-f9b6-5eee-8f02-d1e2502013f5 | note | Inspection / Test Authority: Conduct - C
5a6cfbc4-f71e-55cf-9638-1cffcab231c5 | note | Inspection / Test Authority: Produce Record - C
5b7d0374-3060-5c70-b637-56c03fb20930 | note | Inspection / Test Authority: Approval - C
ac280ed7-60d4-5318-9c00-e527014ce062 | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 1.9 - Form Release Agent
4a2f920f-06fa-5ca5-9440-2d784383edfc | note | Acceptance Criteria - Not detrimental to the application of any subsequent finishes
929a89b7-7a51-512f-a27b-dc18d97f6602 | note | Inspection or Test: Method - Review
3595fc7d-8930-5042-b0a6-bb4e2198d229 | note | Inspection or Test: Freq. - Once
3e905d85-7513-531e-8bf7-aaa26a8e6b8f | note | Inspection or Test: Responsible Person - PRECO
f13606ae-27d3-5641-bf45-a7c1536b7fb3 | note | Verifying Document - Material Data Sheet
9a6b2806-6e07-58fe-8a46-2fb8720007f5 | note | Records required for handover package: Yes/No - Y
bb7392da-1876-52b1-b66c-4332597659b9 | note | Inspection / Test Authority: Conduct - C
a11e2481-f601-5d2b-9949-dd42b7d87f04 | note | Inspection / Test Authority: Produce Record - C
0a89bb81-a0a4-5da9-9180-1e2537240abc | note | Inspection / Test Authority: Approval - C
8b999de5-2dd0-55a6-8c77-eda64208c51e | note | Hold Point - Y
| signoff | HOLD POINT
| section | 2.0 In Process Testing
| checkpoint | 2.1 - Reinforcement Traceability
61ccf0a1-8c43-5f03-ab35-a3c7e776a72e | note | Acceptance Criteria - Mill Certificate, Heat Number and Bend Schedule traceability
d1191534-d8b5-5a18-ab8f-9683ebb998b1 | note | Inspection or Test: Method - Review
e0f9d9c5-9dd9-5fce-ad34-5f3bc667a60d | note | Inspection or Test: Freq. - Per Unit
936505a9-7a6c-5f3f-8e24-0ad2c911c846 | note | Inspection or Test: Responsible Person - PRECO
79a6200d-a523-5ba8-bf8a-d8c222392f92 | note | Verifying Document - Pre-Pour Check Sheet
a2529bb7-64a7-5f1c-9f48-8fc49fe5e1d1 | note | Records required for handover package: Yes/No - Y
c06454a1-11cd-587b-8afc-f3091ffc8473 | note | Inspection / Test Authority: Conduct - C
100a881a-2b07-5500-8986-e757666b171a | note | Inspection / Test Authority: Witness - C
133786a1-f514-5b7a-b002-ef08f5898a12 | note | Inspection / Test Authority: Produce Record - C
b68e1c03-cf17-5cb6-9316-db5166e91af3 | note | Inspection / Test Authority: Approval - C
fb2e7852-2574-5cd3-ad63-6811ed026e03 | note | Hold Point - N
| checkpoint | 2.2 - Reinforcement Fixing
6d21fe64-6a0a-5282-99bf-2e718a847467 | note | Controlling Documents - NZS 3109
348f0eea-a018-5038-bf44-b5b8d3539582 | note | Acceptance Criteria - clear cover as per drawing to all reinforcing including stirrups and ties
47db6c98-d89e-5e0f-8df3-8cf606190dc2 | note | ○ Steel to be securely tied and fixed with no movement
91ba1cf8-25d4-59c5-97e9-7cc8f53ffe8b | note | Inspection or Test: Method - Inspect
b9149e45-01b4-5203-9eeb-3a2de6ff413b | note | Inspection or Test: Freq. - Per Unit
386d206d-d2c5-5da1-824a-1080525fc590 | note | Inspection or Test: Responsible Person - PRECO
52e37810-5c7f-5a82-96e5-05fd9b7853bc | note | Verifying Document - Pre pour checksheet, photos
eb431f8e-5183-57ee-9da9-e63271c0eb6c | note | Records required for handover package: Yes/No - Y
1ccf093b-81ca-591f-89b9-eee4a5a2084c | note | Inspection / Test Authority: Conduct - C
e0d5d116-4616-5a98-8058-45ed77b042d5 | note | Inspection / Test Authority: Witness - D
0f221cfb-6b22-56da-8523-eeabfec6955c | note | Inspection / Test Authority: Produce Record - C
a14218b6-312d-5ea1-ad99-a57fd49b362d | note | Inspection / Test Authority: Approval - D
80b3119a-03c3-5c6a-a60c-a208d6c10ad0 | note | Hold Point - N
| checkpoint | 2.3 - Pre Pour Inspection
d636d527-87a5-59bd-a560-2e45f82dffdf | note | Acceptance Criteria - Completed pre-pour inspection (dimension/inserts/ reo) permission to commence concrete placement
1ce3f275-5a5a-5ad5-ad39-0e8c1c6aa2a5 | note | Inspection or Test: Method - Inspect
b22b9cc4-ebad-53ca-9105-c89f97d45417 | note | Inspection or Test: Freq. - Per Beam, Per Pour
e28ca6b4-e0e2-5f69-bb6f-0c16a10e0eba | note | Inspection or Test: Responsible Person - PRECO
3f42244e-32c9-5520-b6ac-2b7f00939e36 | note | Verifying Document - Approved Pre-Pour Checksheet
429807ba-ab0c-51d3-a509-f182bc3fada0 | note | Records required for handover package: Yes/No - Y
2ee5eb8f-a096-5e8b-b2c7-2a27643b9c07 | note | Inspection / Test Authority: Conduct - D
b2709ce4-a224-523b-919a-db37d24f51b1 | note | Inspection / Test Authority: Witness - D
4bc57f2f-9ba0-5b43-b5dc-e85d3acbc1d3 | note | Inspection / Test Authority: Produce Record - C
fc9ab214-1fa1-5317-9cf0-49661b16d828 | note | Inspection / Test Authority: Approval - C
7e57bdb0-35a3-5ab9-9eca-17fde2f2be2a | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 2.4 - Concrete Placement
39fafecd-b2e9-5b48-8c7b-daf98a4d5755 | note | Controlling Documents - NZS-3109
3a3612b0-39ea-5b3c-95d5-86105f296f6c | note | Acceptance Criteria - Slump within target 120 +/-40, all concrete to be properly vibrated
cc2863c6-eb35-512c-88ee-d78aac832397 | note | Inspection or Test: Method - Inspect
b5ae8a11-7555-51c9-a5b0-828f6b61015c | note | Inspection or Test: Freq. - Per Concrete Delivery / Per Placement
97cc9910-052d-5ee8-8fe0-979d2b08d2fe | note | Inspection or Test: Responsible Person - PRECO
d0d71ce8-ae9f-568b-b2e1-01ab7409b823 | note | Verifying Document - In-Pour Checksheet / Delivery Docket
dd891b55-3834-559f-a59c-f5a4d769d5d3 | note | Records required for handover package: Yes/No - Y
1863c022-8047-5deb-8720-aa7a43389550 | note | Inspection / Test Authority: Conduct - C
de9063fe-7287-5f4b-8ab9-6fe3e1ecc0a0 | note | Inspection / Test Authority: Witness - C
92efaba6-6645-5395-8bff-9c46a435f71b | note | Inspection / Test Authority: Produce Record - C
7acaa081-f417-528c-9e45-3c8341c68e11 | note | Inspection / Test Authority: Approval - C
2721098c-0c32-5e5f-88de-48ba461fd82b | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 2.5 - Concrete Sampling/Testing
15f240f6-87cc-500e-b08d-3abc9de99072 | note | Acceptance Criteria - Compressive test 1 x 7d and 3 x 28d results + 2 stress transfer cylinder (1 for test + 1 spare) stored at curing temperature
c17174e3-fd7c-599b-bbe5-c57e91af8e4c | note | ○ 60 MPa at 28 days
d118ff8f-c305-5261-93e2-b9629fa6eaae | note | Inspection or Test: Method - Concrete Sampling/Testing
396500ee-9dd4-50cd-a15d-cd478f6fa682 | note | Inspection or Test: Freq. - One set per precast beam with an additional set taken from any truck which has water added after leaving the plant
e4182f51-8d06-50ff-b4ff-f7c4e06fb709 | note | Inspection or Test: Responsible Person - Subcontractor
9646702c-0876-5348-9c9e-85b19ba2767f | note | Verifying Document - Concrete Sample Test Results (IANZ Accredited Laboratory for 7 & 28days test)
529fd1b4-3428-5e49-8b72-571ea73d607e | note | Records required for handover package: Yes/No - Y
2721c42e-3120-5942-9935-c29f8a846037 | note | Inspection / Test Authority: Conduct - C
c5c55d80-f4d4-5c14-9844-81e70258326f | note | Inspection / Test Authority: Witness - C
672acacb-5ee7-53fe-8c14-1bb41c1c7e33 | note | Inspection / Test Authority: Produce Record - 3
0bc79d63-84e3-532c-9e7b-cc29788e9d9f | note | Inspection / Test Authority: Approval - C
339cdc9e-5a98-5236-8e67-62fa19d28db1 | note | Hold Point - Y (Designer to be notified immediately if specimen fails)
| signoff | HOLD POINT
| checkpoint | 2.6 - Heat Curing
0e5ebd5c-2e94-5ca3-bb7c-08e2ee65d371 | note | Controlling Documents - Approved Heat Curing Methodology
88a03694-72e0-5798-91f1-ab548320b5b1 | note | Acceptance Criteria - Concrete core temperature shall not exceed 70 degrees
d13251b0-a197-5602-8154-d1632a8eab7c | note | ○ Steady state inlet and outlet water temperatures recorded
85ada80e-9c11-56e1-95d2-2e0b7844af20 | note | Inspection or Test: Method - Temperature Monitoring
620b90c4-8f34-56d4-8094-0c3d4fc5af36 | note | Inspection or Test: Freq. - Per Beam
d36788b1-ca10-5785-a3e1-dde4fd2f2d22 | note | Inspection or Test: Responsible Person - PRECO
02bed0c0-3d6f-507d-a6c8-268d3c1283c3 | note | Verifying Document - In Pour Checksheet, Hot Water Curing Methodology
d53be086-79b2-5f5b-9004-641ef88b5803 | note | Records required for handover package: Yes/No - Y
dc210e64-5df0-55b3-883c-d9091295358f | note | Inspection / Test Authority: Conduct - C
7c9c17dd-5718-5b5b-af55-ba56a659fe14 | note | Inspection / Test Authority: Witness - C
13cf92ff-5eca-5ffc-86a3-70d3bc30ff36 | note | Inspection / Test Authority: Produce Record - C
7b832ff4-8065-5318-a882-b758b5faa0df | note | Inspection / Test Authority: Approval - C
0acf477d-6168-5666-9c59-a90a8d7aab75 | note | Hold Point - Y (Designer to be notified if anomalous temperature readings encountered)
| signoff | HOLD POINT
| checkpoint | 2.7 - Concrete Curing
f8bd1996-0eff-587c-82c9-cec2c936c860 | note | Controlling Documents - NZS 3109
8b4376c3-5eba-576e-a6d8-96e199a7ea80 | note | Acceptance Criteria - 7 days wet curing required following completion of accelerated curing
4ecd5945-223d-581e-84dc-40724e292517 | note | Inspection or Test: Method - Inspect
3bd1cb23-136b-580e-8d8a-2158babb60e9 | note | Inspection or Test: Freq. - Per Beam
110ce892-d8d3-5df4-9439-61440d31d9f8 | note | Inspection or Test: Responsible Person - PRECO
b7dfb368-43bb-5749-a772-93f869e24543 | note | Verifying Document - Post Pour Checksheet
cce69b92-0f21-556c-9148-62ae914dcd4a | note | Records required for handover package: Yes/No - Y
c6115285-18c6-566c-81e5-f777e6ba92ca | note | Inspection / Test Authority: Conduct - C
ac33b12b-2462-5132-9745-b874f4c18405 | note | Inspection / Test Authority: Witness - C
f2312730-daa7-5a4f-98dd-ffaaea72abe4 | note | Inspection / Test Authority: Produce Record - C
4c534583-6546-5a29-9845-4a06701677a7 | note | Inspection / Test Authority: Approval - C
9b5b94a7-929b-5d7c-9fbf-e4121869caad | note | Hold Point - Y (Designer to be notified immediately if water supply interrupted)
| signoff | HOLD POINT
| checkpoint | 2.8 - Type B Construction Joint
a74ae819-b8ef-5103-a472-48df91c81149 | note | Controlling Documents - NZS 3109
9dad99db-896b-5d9b-8671-6fce30d46560 | note | Acceptance Criteria - 5mm amplitude and free of latinece, cut with water blaster and with use of High Strength Spray on Retarder
48aacd0f-fa6b-51d2-8872-2b9d3e01e1fb | note | ○ Top surface of all beams and end blocks of integral beams
0b775548-e859-5652-89c9-b74b9c3e2233 | note | Inspection or Test: Method - Inspect
18393de2-a168-5ff5-9392-02646e26fe44 | note | Inspection or Test: Freq. - Per Beam
939edf25-0e76-5021-9b62-66ab7e966c1a | note | Inspection or Test: Responsible Person - PRECO
0e01020b-276a-5a0b-b2f6-4a095c5a6ebc | note | Verifying Document - Post Pour Checksheet
5deaeff2-7c53-50c7-84d4-5d4e1d103bd9 | note | Records required for handover package: Yes/No - Y
6ee08dfe-6301-5250-80f5-f3c9a38730f3 | note | Inspection / Test Authority: Conduct - C
5c2e87b9-0789-503f-9f77-ce612bd5fb38 | note | Inspection / Test Authority: Witness - C
91362d65-3729-5f6e-a392-aeee07db5b54 | note | Inspection / Test Authority: Produce Record - C
12d8baf7-0b1f-539b-9636-d888095d76a0 | note | Inspection / Test Authority: Approval - C
1432c686-83b0-5622-966b-a7651bdfff37 | note | Hold Point - N
| checkpoint | 2.9 - Post Pour Inspection / Draw-in Measurement
9162f016-8ac8-5c03-bc38-5f1ff150c065 | note | Controlling Documents - IFC Drawings
88c3de0b-d061-58f5-9399-b331de92a632 | note | Acceptance Criteria - Surface Finish Requirements- (F5 for seen faces) / Dimension/inserts/cut-outs as per drawing
169eb815-1eaf-5621-bea3-46009f60330a | note | Inspection or Test: Method - Inspect
e9ad51b9-25a7-5890-b286-1e69b09effdc | note | Inspection or Test: Freq. - Per Beam
cce9461e-a042-595e-8200-93f01be1ea29 | note | Inspection or Test: Responsible Person - PRECO
326621a2-1858-5b67-8699-5f659c336dc8 | note | Verifying Document - Post Pour Checksheet
240ec643-e959-55e3-a014-efd764f512a1 | note | Records required for handover package: Yes/No - Y
c22e7cd1-4c7d-5b5b-8e97-e48c349827b8 | note | Inspection / Test Authority: Conduct - C
74c592b4-0d91-5e89-8cd9-88c8ada682eb | note | Inspection / Test Authority: Witness - C
838c00c9-44e5-5c3e-b1f7-dd9dd7686d73 | note | Inspection / Test Authority: Produce Record - C
ffa656c5-4f03-544f-bf7b-96edd380595f | note | Inspection / Test Authority: Approval - C
cf5c2e86-f608-5900-8099-9073be5f505e | note | Hold Point - Y
| signoff | HOLD POINT
| section | 3.0 Stessing Related Operations
| checkpoint | 3.1 - Strand Positioning
6258448c-266c-50e8-b3cc-379f62795012 | note | Acceptance Criteria - +/- 3 mm in any direction
9efca5fe-1b6c-5003-abbd-77e03a1c4096 | note | Inspection or Test: Method - Inspect
95b32a57-8d78-53c4-8a3e-2bdf6503ef42 | note | Inspection or Test: Freq. - Per Beam
6ec0141b-4772-5f01-a262-7057c7578087 | note | Inspection or Test: Responsible Person - PRECO
d5ffe661-b0a9-508a-99eb-a60b5512324d | note | Verifying Document - Pre Pour Checksheet
48f5a84c-3824-5589-bace-f0f5e71023d8 | note | Records required for handover package: Yes/No - Y
515d378c-5c2f-5665-8908-3eb8f667a100 | note | Inspection / Test Authority: Conduct - C
9d3926c5-bb15-571a-84c5-9b4a3303e59b | note | Inspection / Test Authority: Witness - C
9de33223-6efa-5178-8d3f-d08f599672e3 | note | Inspection / Test Authority: Produce Record - C
39a6e795-e02d-52ea-bdd6-0ebb48890c67 | note | Inspection / Test Authority: Approval - C
78d81136-4187-5599-b59d-ced444f5274e | note | Hold Point - N
| checkpoint | 3.2 - Stressing
3d9002a8-01c5-516f-aa32-0b7fbb69148e | note | Acceptance Criteria - Collation of stressing records incl unit ID, strand extention, jack pressures and general comments
3fcf964a-2ab3-5f98-aefc-c745ecd0ec08 | note | Inspection or Test: Method - Review
b9cb5ece-c8fa-5d67-a4fc-aec54a035324 | note | Inspection or Test: Freq. - Per Beam
32ddf547-fd9e-5fe2-9fce-5db1916fb135 | note | Inspection or Test: Responsible Person - PRECO
920bcc17-41da-5147-8c8d-46b9929ec7c9 | note | Verifying Document - Stressing Checksheet
847a6442-5d0a-579a-9d48-12af8e079d8d | note | Records required for handover package: Yes/No - Y
884a3bd6-187e-5df1-a4d6-591ca9a59f33 | note | Inspection / Test Authority: Conduct - C
69daa57c-2297-5e68-bfb1-3ea07e1dcc5f | note | Inspection / Test Authority: Witness - C
4bcbbc71-5099-5261-bbf6-597958e0ffb9 | note | Inspection / Test Authority: Produce Record - C
91eb012b-17b4-5312-9c72-30df09ecf63b | note | Inspection / Test Authority: Approval - C
a74e6dfd-0701-5fdd-89d5-3ad8a1343262 | note | Hold Point - Y (All anomalous readings not in line with Stressing calculations to be submitted)
| signoff | HOLD POINT
| checkpoint | 3.3 - Stress Transfer
49cbe5f3-da5c-55af-96a5-7d9ba9842cd8 | note | Acceptance Criteria - Concrete Cylinder Tests to be minimum 40MPa
94a4b5d2-3479-5f60-8649-f3fedcf16812 | note | ○ Cylinder to be kept in similar conditions to beam
4338d86d-a09b-5178-84cd-b178bfcf332d | note | Inspection or Test: Method - Cylinder Compressive Strength Test
a9408e8b-177c-5e74-a06b-f6120a3e38ae | note | Inspection or Test: Freq. - Once Per Beam
2f960902-c5a4-553a-af13-74ba7f058bfc | note | Inspection or Test: Responsible Person - PRECO
83b30231-3f61-5b9b-99b7-33a17af6eaf3 | note | Verifying Document - Cylinder Compressive Strength Report (In-house)
914099fa-62cd-5cb7-8d1e-ae7aceed26f3 | note | Records required for handover package: Yes/No - Y
72a7b8e9-2617-5b6f-bf5d-6fe73f980db7 | note | Inspection / Test Authority: Conduct - S
90565c20-cf1a-5784-b374-1500459228bc | note | Inspection / Test Authority: Witness - S
2d8519bc-02a3-51a4-bbd8-2ae414fa9f56 | note | Inspection / Test Authority: Produce Record - S
1a8e7152-089a-5022-be09-417f308fb7ef | note | Inspection / Test Authority: Approval - C
f660713d-289f-590f-8588-9bcd8b850288 | note | Hold Point - Y (No Stress transfer before 30MPa)
| signoff | HOLD POINT
| section | 4.0 Final Documentation
| checkpoint | 4.2 - Producer Statement (PS3)
39010b13-1dce-56dd-9210-021be341f937 | note | Acceptance Criteria - Signed PS3
653b297f-415d-5526-b08f-50bafe58ab16 | note | Inspection or Test: Method - Report Production
b857b720-45a1-5c30-88a0-04a89f5612f3 | note | Inspection or Test: Freq. - Once
7e428ed8-e363-517f-ab8d-7ea9d283d61a | note | Inspection or Test: Responsible Person - PRECO
30d3f47b-a99b-5876-bf16-2658598ec75d | note | Verifying Document - Signed PS3
d1299c2a-f6f5-5998-a93b-64a67b2444f5 | note | Records required for handover package: Yes/No - Y
d6022bd2-cf41-569b-abb4-6a8bbe2b83fa | note | Inspection / Test Authority: Conduct - C
61dbf0dc-a414-5c3d-850d-70db3894c313 | note | Inspection / Test Authority: Witness - C
6e753d30-ec20-52bf-8bb2-dec744d82f34 | note | Inspection / Test Authority: Produce Record - C
23b51786-85de-550e-99b2-67773f6dfc58 | note | Inspection / Test Authority: Approval - D
560f212d-257b-50b8-9024-4318b05d7c13 | note | Hold Point - N
| checklist | ITP - Insitu Concrete Construction - Rev D | itp | ITP - Insitu Concrete Construction - Rev D | f880282a-5303-41c8-b460-de649d8bea41
| section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
| checkpoint | 1.01.01 - Construction Pack
92ceac3b-e1ae-56a9-a8a4-8edc0127429f | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence.
bb1125af-6e21-585f-b3ed-3c4c432cf7e6 | note | Standard / Specification - Downer
e10d0142-a1ef-54e1-bff5-a33bf202c455 | note | Verifying Document - Construction Pack
99333c1a-e691-5df8-a7b9-21f6e8bf3cab | note | Frequency - Prior to Works
97435b0c-f0b6-58db-abfe-8e5b0a0bd701 | note | Activity - H
0c8bdd52-22f3-5b18-9e0a-b829f82124db | note | By - PE
| checkpoint | 1.01.02 - Survey Setout
f12d670f-e583-5267-b1ec-73154264911d | note | Acceptance / Conformance Criteria - The Contractor shall verify the setting out position, level and line of the bridge, prior to commencing construction. The Contractor shall advise the Engineer of any apparent anomalies identified.
dcd4f506-5e3d-52ca-8c7e-7de1987a4f82 | note | Standard / Specification - Downer PS - 11.2
06f2f8c9-b3bc-59d5-98b7-c265696eca7b | note | Verifying Document - Survey Records
9164739e-ae99-5a56-8397-13f6020a5382 | note | Frequency - Prior to Works
0ca06d95-790d-5940-ade1-9894060330a4 | note | Activity - H
b4ab5ab7-90f2-57e9-8bcd-bcb06be329d3 | note | By - PE
| checkpoint | 1.01.03 - Internal Permits
80f4840d-3bfa-580f-b6f5-a1f184ba1e1f | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
b3230b35-0a45-5a98-852f-a3cb25db9056 | note | Standard / Specification - Downer
63a94c48-a964-5733-8371-176bd65816ad | note | Verifying Document - Internal Permits
e851d41e-f372-5742-a5d4-411984d20950 | note | Frequency - Prior to activity being undertaken
769fd35b-8009-5aee-afa0-7d2d105d46b9 | note | Activity - H
b0eb6535-8625-5eff-ad5d-61426d20040a | note | By - SE
| checkpoint | 1.01.04 - External Permits
b0c75fe0-5871-55d2-9b1f-c93f6186803f | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
c7067bfd-b2ec-5f88-a167-31cc524f3a1b | note | Standard / Specification - Downer
f74033ef-8e27-5e1f-bc29-48e0f0434f3b | note | Verifying Document - External Permits
96f67d5c-0691-5535-b452-3853ad0ec681 | note | Frequency - Prior to commencment of activity
346e4749-5e48-5db6-8d19-cd301687a268 | note | Activity - H
2920e4a8-56ee-5016-a5c5-749cd6b21c40 | note | By - SE
| checkpoint | 1.01.05 - Approved Construction Drawings
1ed16a31-6490-5485-9039-47ce50535f64 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
06d2a285-3919-5f61-9baf-f7d2c02c4abc | note | Standard / Specification - Downer
1cf5bce5-b4ad-5672-9966-fc2c41fc43a7 | note | Verifying Document - IFC Drawings
fcbbe479-8bd4-54c4-9734-246047b2673c | note | Frequency - Prior to works start
d0abc35a-c34b-5578-85df-419f706ec434 | note | Activity - H
a2940c52-f39d-5cfd-a146-39f060e2476b | note | By - PE
| checkpoint | 1.01.06 - Construction Methodology
8eee3c74-4023-5582-9897-44ae42bfbd0a | note | Acceptance / Conformance Criteria - The Contractor must submit their proposed construction methodology and justification to the Engineer for review at least 10 Working Days prior to commencement of bridge construction.
882e5ba8-77a9-5bd5-b4c9-1ec9d8241c96 | note | • The Engineer’s review will be limited to conceptual assessment of any potential impact on critical elements of the structure.
00d9f83f-73be-5def-bdfb-e9a4fe681359 | note | Standard / Specification - PS - 11.3, SS 2146 - 3
9480445e-5e55-59a1-addf-b56328b7b136 | note | Verifying Document - Methodology
69d03473-6184-5dfa-8b5c-c020156391f3 | note | Frequency - At least 10 Working Days prior to commencement
e2b4efc1-fe2e-582a-8d9a-5d2b61a7de44 | note | Activity - HP
ce2cdaed-9009-5812-a323-cf8303dca192 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.01.07 - Stakeholder
8653ddac-a145-5381-a9ff-9b969b62e48b | note | Acceptance / Conformance Criteria - Inform stakeholder of upcoming pours. Special considerations to early morning pours, potential for noise monitoring requirements being triggered.
9c757d6e-6cbe-508d-a785-77d359774049 | note | *Forward correspondence around notifications of early morning pours to the Engineer and HCC before pours are carried out.
992da153-9644-57b5-94c4-a319384e05e6 | note | Standard / Specification - CNVMO / CCCP
8b86c5e5-595d-534d-a339-b2ace543f345 | note | Verifying Document - correspondence with stake holders
0b278dae-55be-5246-a23c-f9c3f2038bc7 | note | Frequency - per pour
c4a21675-edfa-5911-8d04-1562a06eed9b | note | Activity - H
415edfef-9a9c-57ac-87fc-4f94ee49c61a | note | By - PE
| section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
| checkpoint | 2.01.01 - Chartered Engineer
e97e36ad-9112-57c4-a773-3508113774f1 | note | Acceptance / Conformance Criteria - The Contractor shall employ or retain a Chartered Engineer registered with Engineering New Zealand and experienced in the design of temporary works and erection engineering activities to design and provide construction oversight for all temporary works as specified in these Contract Documents and/or as may be necessary to complete the Physical Works.
456287ff-ea34-5f15-a759-0f8f14c8e545 | note | Standard / Specification - PS - 11.14
5a08e547-4262-58a4-b85f-336acfd6db64 | note | Verifying Document - Chartered Engineer Details
25250fdc-ad9f-57f9-ae22-a717e235e685 | note | Frequency - Prior to Temporary Works
790b5b0c-d4a5-5491-b136-26b1fb5a6c95 | note | Activity - HP
2cc865f4-e546-55d8-9436-735522a1f6bc | note | By - PE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.02 - Drawings and calculations
2350bf3c-f010-5c51-8368-cc6c54285425 | note | Acceptance / Conformance Criteria - The drawings and calculations for the temporary works and/or erection engineering activities prepared by the Contractor shall be submitted to the Engineer for review in advance of proceeding with any temporary works covered by the drawings and calculations to facilitate construction. In no case shall construction commence until the Engineer has reviewed and accepted the drawings and calculations.
0a98b68b-9e7e-541d-b5d4-5d469fbb9757 | note | Standard / Specification - PS - 11.14
bcc21c93-ba07-54f1-bd11-8a017d8a35e6 | note | Verifying Document - Approved Drawings and calculations
5d324e5b-0b9e-54b2-8789-e57b4208b31d | note | Frequency - Prior to Temporary Works
550f05c0-88f8-5f63-9b05-10965ca9cc04 | note | Activity - HP
b2d473e4-2d4f-559d-b54e-4cde57818eaf | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
| checkpoint | 2.02.01 - Concrete Mix Design
790b7eed-c78f-5e0f-993b-fba41557f02d | note | Acceptance / Conformance Criteria - Concrete mix design to be completed and reviewed by the contractor prior use on site. The following criteria are to be satisfied:
c3b8c670-f6d4-5bd1-a913-e38e3172cd9a | note | • Strength: 40Mpa
e5f4172f-cc4d-5530-a3e8-275c60a80349 | note | • Normal maximum aggregate size: 20mm
0c9161ff-5de2-59f3-ad7e-42076f547177 | note | • Basic drying shrinkage strain 720 microstain
51267fe0-ec17-5023-83fe-74189f90cc2f | note | • Concrete materials and manufacturing are to comply with NZS3109
47d723cb-a3fe-5b9c-90df-a7b21c45b678 | note | • All concrete shall contain a minimum of 25kg/m3 of micro silica for enhanced durability.
a97ce29e-cdaf-5d86-a982-ca6501886dde | note | • Only one brand of cement shall be used throughout the works without prior Engineer’s written acceptance.
6bdfbcc3-9886-5f8a-8a4f-4f9e07d9bba9 | note | • Details of the types and rates of application of the admixtures proposed are to be supplied to the Engineer for acceptance.
b86a6c62-b95c-5681-9070-5959aefb50e6 | note | • Trials undertaken in advance of production to verify outcomes are being achieved in accordance with mix design expectations. This is to include if the mixes will be pumped.
c06ac2d0-a25e-5139-a67c-ab8e42565839 | note | • The Contractor shall identify appropriate preventive measures and to justify those measures to the Engineer to minimise the risk of Alkali Silica Reaction (ASR).
519e7c0c-f65a-5a52-86dc-44224a35e7b4 | note | Standard / Specification - PS - 11.5, SS 2140 - 3, 4, 9, 6.1, 6.3, 6.5
3adcf6a0-65e6-54cf-a535-9ec38c49975e | note | Verifying Document - Concrete Mix Design
0a837975-280d-59b2-891c-336379f55662 | note | Frequency - All Mix Designs
8f8a16e3-0a0e-5547-9c1c-84bb434365e2 | note | Activity - H
084ccac4-c73a-57a5-a2d3-e24a4243fbf2 | note | By - PE
| checkpoint | 2.02.02 - Concrete Mix Design Checklist
84fb278d-1dd3-5e18-95b4-5d0b32e3dc71 | note | Acceptance / Conformance Criteria - Each mix design shall have a completed concrete checklist with supporting data including Trial Results, submitted at least 5 Working Days prior to production of that mix design, for the Engineer’s review and acceptance.
0a1cb2e6-40e2-5c69-b224-fd19fa9a6a23 | note | Standard / Specification - PS - 11.5, SS 2140 - 9
6fd63448-1bdd-57a1-8e00-5cdbbf67d7ae | note | Verifying Document - Concrete Checklist
ece0e023-060c-5d82-9901-18df5ea7534c | note | Frequency - 5 Working Days prior to production of that mix design
b9dd7f5d-d877-5325-91bc-30955ce392a0 | note | Activity - HP
97d25eb7-9bfb-5110-869b-6c2efb5db56b | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
| checkpoint | 2.03.01 - Reinforcement
b6afc49f-38e4-5904-ae6f-8f6491a1b94f | note | Acceptance / Conformance Criteria - 3D modelling completed, bar bending schedule checked against latest construction drawings and submitted to the Engineeer for review
a45f2372-e67f-5aab-966a-d6a5df32ceed | note | Standard / Specification - Downer
dbfc1de5-5f40-5c17-8e43-593cf9bd9c70 | note | Verifying Document - Reinforcment shop drawings
2e80847b-6e1c-5227-96f1-959c89b61a6c | note | Frequency - Each batch of reinforcement
3f3826a5-de94-5ec8-aa36-4c24e5a69c81 | note | Activity - H
b46aeed2-e77b-5800-90ec-2da66b229abb | note | By - PE
| checkpoint | 2.03.02 - Reinforcement
85787332-8b63-5e76-9aac-b236c533023d | note | Acceptance / Conformance Criteria - Mill & test certificates for each batch of reinforcement used to be provided to the Engineer. Unless specifically nominated otherwise on the Drawings, only Grade 500E reinforcement manufactured using the micro-alloyed process is acceptable.
5625c41b-0b31-55e0-9ee5-5803ddc06844 | note | Standard / Specification - SS 2142 - 3, PS - 11.6
0a98d2f9-b4f4-5648-b695-7cdff4e1be3c | note | Verifying Document - Mill Certs
fc16cd7f-c01b-5b9e-990a-a6b9d20bce96 | note | Frequency - Each Batch assigned to Each Pour
5b305dee-885d-5738-a898-35da190dff2e | note | Activity - R
6be4f6ad-b97d-55be-92b1-4398f8cd43e6 | note | By - ENG
| checkpoint | 2.03.03 - Welding reinforcing
b6b3c536-3468-51a9-b8f2-892b4ae716fd | note | Acceptance / Conformance Criteria - Prior to welding reinforcement, approval from the Engineer must be obtained. The person undertaking the weld must hold the relevant certification.
53ec7e11-e6e2-5ae2-8269-7f5dee129cca | note | Standard / Specification - SS 2142 - 9
f819f84a-616f-554d-89ff-d65ca9ba05ff | note | Verifying Document - Approval
89089fd2-0937-5402-9052-d58bcb4d9744 | note | Frequency - Prior to welding (if required)
5e77e621-5c03-5233-ba4b-fe1a71a19506 | note | Activity - HP
b23e7904-b0fb-5346-ad7c-e2ba1f29a831 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.03.04 - Steel supply
cd52136a-c9d4-5831-aea8-12213b87de04 | note | Acceptance / Conformance Criteria - Certificate of origin for all steel reinforcing supplied
c32a9e64-feb2-5357-977c-a0ea690c6f77 | note | Standard / Specification - NA
a3faaa58-6d64-5bd0-9fd7-32d043112ae0 | note | Verifying Document - Certificate
ac279921-0b83-5fc6-b65b-6a9661f31e6a | note | Frequency - Each batch of reinforcment
6ee83ece-47f2-5f84-a638-f6574082eb9c | note | Activity - R
a739393c-522c-55bc-82a7-f7848d71108d | note | By - ENG
| section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
| checkpoint | 3.01.01 - Temporary Works
7a89cb0e-af59-5896-a2b9-fb78b0fc3f45 | note | Acceptance / Conformance Criteria - Temporary works to be installed as per design drawings. Permit to load to be issued by temporary works inspector prior to loading element
7d72e1c0-8698-5fef-9d3c-00553de45152 | note | Standard / Specification - Downer
268ae1b7-092e-5e19-b760-b6280ebf8aed | note | Verifying Document - Permit to load
d58d1e61-9a2a-5061-8e60-b1f63cec00ce | note | Frequency - As defined in the temporary works design
b05aa2c5-6bf0-5f53-9fe0-72278009cc84 | note | Activity - H
12b21f7c-cbac-5728-bde7-3a3dd01e4f72 | note | By - PE
| checkpoint | 3.01.02 - Reciept of Reinforcment
29708042-3eb0-50f7-9817-eb1a9ed77b37 | note | Acceptance / Conformance Criteria - Reinforcement checked against bending schedule. Bars correct length, size, shape, grade, and free of defects.
9383dd6c-3a23-5736-9b3b-d2a687aa3ac8 | note | Standard / Specification - IFC Drawings, SS 2142
8e0a3b5d-f574-58c2-a4b4-139c394a9c31 | note | Verifying Document - Photos / delivery dockets
b219cff3-ff78-58cf-88c5-f2f1ca7b5ce7 | note | Frequency - Each pour
f5b65f4c-8970-5e55-b595-61c9db5ef0a2 | note | Activity - I
3e1874e7-c0c6-5220-814d-54eb5ab369b2 | note | By - SE
| checkpoint | 3.01.03 - Reinforcing Welding and NDT Inspections
621a163f-01e9-5398-bb79-7869eccdb7c0 | note | Acceptance / Conformance Criteria - All reinforcing steel welding should comply with AS/NZS 1554.3; and all welded splices shall also conform with NZS 3109 Clause 3.7.2 or 3.7.3.
eafe6a90-fa22-56e6-9054-351ea8087d7b | note | Standard / Specification - SS 2142 - 9, AS/NZS 1554:3, NZS 3109 Cl 3.7.2 or 3.7.3
f357cc29-75cb-5f9b-9d79-dba20552df1a | note | Verifying Document - TPI Report
f7185df9-611f-5c96-b8d6-22fc180b0bd5 | note | Frequency - Each weld prior to installation
4aafe222-7473-5909-a3ec-9b3cf74c4081 | note | Activity - H
49be0430-0e13-529c-8f5e-421ddf8ab1ee | note | By - TPI
| checkpoint | 3.01.04 - Pre pour inspection
f862655c-6cf6-5229-95bf-2a8639fd5515 | note | Acceptance / Conformance Criteria - Pre-pour inspection checklist undertaken by the Site Engineer and captured on the ConQA web app. All aspects of the element to be checked against latest construction drawings and specification requirements.
78c31cf3-c538-5847-9598-26e5ea679dc5 | note | Standard / Specification - Downer
90c72c06-1fae-5e17-918d-d497af290eb7 | note | Verifying Document - Pre Pour
5780eb5a-ac86-56ef-b2f6-012e0edd49b3 | note | Frequency - Each Pour
003b6c68-e85d-5ddb-9a70-ece8b19ef48e | note | Activity - H
18614d22-a548-5581-8157-f27809e610ce | note | By - SE
| checkpoint | 3.01.05 - Engineers Inspection
6b41f6ac-e96a-538e-a166-6433c42621c2 | note | Acceptance / Conformance Criteria - The Contractor shall advise the Engineer when he intends to commence placing concrete. No concrete shall be placed until the Engineer is satisfied that the requirements of this Specification and the Drawings relating to formwork, reinforcement and construction joints have been complied with entirely.
c571cc27-1280-586f-b69c-9bd61ea0feb8 | note | • No concrete shall be placed in the absence of the Engineer without prior acceptance.
e165b02b-77f5-5280-963d-bbb06b0c5cac | note | Standard / Specification - SS 2146 - 6, PS - 2.2.16
f9967265-bb1d-5865-a008-8406f0714223 | note | Verifying Document - Hold Point Release
1d714eeb-0c46-5abb-8d10-b6ef7993b3b7 | note | Frequency - Min 48h Notice
849b583b-8f9a-556f-89f9-972ded875f32 | note | Activity - HP
69c2d6b0-7d6f-5418-9431-68fd4cfd6861 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.01.06 - ESCP
ede482ff-3da6-56f9-80af-4253fdfed48b | note | Acceptance / Conformance Criteria - All erosion and sediment control measures are to be installed and maintained in accordance with Site Specific ESCP
eb0e2b42-e267-5574-8a3b-ac752fabcb0f | note | Standard / Specification - Site Specific ESCP
7a68ee6c-90ec-5c9c-bf70-a18db77ce92e | note | Verifying Document - Acceptance
164883cb-e145-5c11-abd4-4671c81df430 | note | Frequency - Each pour
643b731d-b5f4-5cf6-864d-ad78dae0fea6 | note | Activity - I
84d2aafe-d2bc-54ca-8537-7b0ce2e5f43e | note | By - SE
| checkpoint | 3.01.07 - Concrete Cover
2a8cbcdd-8da9-5397-ac26-b9973c34f436 | note | Acceptance / Conformance Criteria - Concrete Cover:
473fc378-500c-5a22-b5cc-6bd7fb2b8d81 | note | • 75mm - all concrete cast in contact with the ground
b48eb42f-85a6-5aa6-b267-165bada20d36 | note | • 50mm - where protected from soil contact during casting by formwork or by a suitable damp-proof membrane
38c7e5bf-a7df-5ca4-8c89-66e9dfa47b8b | note | • 40mm - standard unless noted otherwise on the drawings
d240c507-03e7-59c7-b7e7-7e75e70f775a | note | ○ Tolerances:
cc729938-3501-5cc3-a045-486d4be17f2f | note | i) In slabs and walls ...... +10, -0mm
486ee57a-6b95-54ab-bcb5-62f8e703fab5 | note | ii) In beams and columns ...... +10, -0mm
7523290d-4e03-57ff-a80a-fc860642d12e | note | iii) At ends of members ....... +25, -0mm
6ac3ed77-c9c6-5483-9468-c40bad194f4c | note | Standard / Specification - IFC Drawing, NZS 3109 Secion 3.9
664ad51c-1c8d-57ef-bb07-c9a3e47c5770 | note | Verifying Document - Approval
dd311c62-4017-5870-ba60-92a97c3e6c17 | note | Frequency - Before concreting
f1a3cc85-ee7b-5ead-8460-52c1917dbf51 | note | Activity - I
b833a218-7ebf-579b-8b7e-93d19a0f325b | note | By - SE
| section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
| checkpoint | 3.02.01 - Unfavourable Conditions - Cold Weather
6a8560a9-58c6-565f-a814-7cf8aefdf123 | note | Acceptance / Conformance Criteria - Concrete shall not be placed in conditions where temperature is below 5°C with temperature decreasing or below 2°C with temperature increasing.
5de8dc23-9812-573d-bfcb-272bd5b75b9d | note | Standard / Specification - PS - 11.5, NZS3901 cl 7.2
1159dde7-0450-587a-a76c-4bfb012db192 | note | Verifying Document - Pre Pour
e339b2d5-99f4-51e4-b667-c48eab201223 | note | Frequency - Each Pour
5b24094a-d114-5845-9076-e59f68bd32db | note | Activity - R
9cbdec74-f0ef-5b43-b9e2-9a9dd711d1ed | note | By - SE
| checkpoint | 3.02.02 - Unfavourable Conditions - Hot Weather
416f2959-f198-5ce8-b3fc-f41623f6d1c2 | note | Acceptance / Conformance Criteria - Concrete shall not be placed in excessively hot dry conditions. Concrete temperature should not be higher than 30°C
c4017fc2-5cc6-5ed2-aecc-3cd472cd11ef | note | Standard / Specification - NZS3901 Cl. 7.2.1 & Cl. 7.2.2
7cf85b13-fde5-5929-abea-2833a90b1107 | note | Verifying Document - Pre Pour
6ea5a23e-f915-56e1-af73-6e75968177d9 | note | Frequency - Each Pour
d61eb2b7-b7eb-562f-956a-849d87435111 | note | Activity - R
e53d6810-9de7-51c0-ae49-d6cd3962be32 | note | By - SE
| checkpoint | 3.02.03 - Unfavourable Conditions - Rain
5a640c52-faa6-5202-a76e-d4bd4fc98f28 | note | Acceptance / Conformance Criteria - Concrete shall not be commenced when heavy rains is falling or threathening and if rain commences during a pour, the work shall be protected as directed to prevent damage to the concrete or to any newly finished surfaces until the concrete has set to such a stage as to withstand leaching of the cement.
e38e45b4-26f3-57ea-b1f5-e6e3dfc71346 | note | Standard / Specification - BBO SS2146
eb5c7bf0-76b5-58ed-a9c4-4eb656bdac7a | note | Verifying Document - Pre / During Pour
087aa4bd-c49c-5ac5-bf64-539c410a4ea1 | note | Frequency - Each Pour
f1d81280-3f14-5896-83a3-f4865e556fa6 | note | Activity - R
a02e601d-5d77-5dcd-9aad-b1dc81b67ac2 | note | By - SE
| checkpoint | 3.02.04 - Construction Joints
fffeb533-6edb-5704-8ade-0b8ceee564ff | note | Acceptance / Conformance Criteria - Where a concrete surface is to act as a construction joint to receive infill over or adjacent, the contact surface interface shall be prepared to the Engineer’s satisfaction to be clean, free of laitance, and with a peak to trough roughness of not less than 5mm to ensure compliance with Type B construction joints as defined by NZS3109 Section 5.6.
01f58446-97c4-52e4-a945-5eb269dcf007 | note | Standard / Specification - PS - 11.5, NZS3109 Section 5.6
89bede1c-86fb-5c84-a3e2-00e8ac30792e | note | Verifying Document - Pre / Post Pour
e9cedcb0-42e5-57cf-88c1-caf41ca6b7cd | note | Frequency - Each Pour
16967cbe-34de-5cd1-89de-23142ad8c8f3 | note | Activity - I
e4973b09-f7f8-5df5-8195-db593cb80820 | note | By - SE
| checkpoint | 3.02.05 - Delivery dockets
d98a8ce7-0ca1-5985-bbb1-85afa1598766 | note | Acceptance / Conformance Criteria - Each batch delivered shall be accompanied by a delivery docket certifying the cement type, maximum aggregate size, specified strength, slump or spread, date, time mixing completed, and time water added at the plant.
f4ef2090-f71b-5210-8d0d-5a144583f357 | note | Standard / Specification - SS 2140 - 4
0aecafb4-78a9-502f-81e0-b64d12ece63d | note | Verifying Document - Dockets
9bbed5d5-e37b-5ab3-adbd-4f8f4c8afadd | note | Frequency - Each Delivery
7fa309d1-bf96-5090-bcbd-1cca35864793 | note | Activity - R
755d7aa7-da79-58b0-a4a3-bd7ce82047d1 | note | By - SE
| checkpoint | 3.02.06 - Slump tests and spread tests
f2441e49-3296-583e-9ce8-e22680f06a24 | note | Acceptance / Conformance Criteria - Slump tests or spread tests shall be taken for each delivery of concrete and the results recorded by the Contractor
e5fa4ddd-06d0-5cb1-ad88-ce4649aa726c | note | – – – – – – – – –
03f753c3-2a28-513d-88ed-3ceadc10f5d4 | note | Table 9.1 - Tolerances for nominated slump
e08bce48-9bac-5b29-88c3-8bb04ef383cc | note | Nominated slump (mm) ¦¦ Tolerance for snatch sample (mm)
dcafbe63-35bd-5a1b-a604-704578def0f8 | note | – – – – – – – – –
59f54f36-d52d-5e7a-aa04-202f56923ac4 | note | 60 or less ¦¦ ±20
232c0dd5-c132-5513-88e8-33442e1837ab | note | 70 - 110 ¦¦ ±30
ab5f2efa-b0dc-57f5-a59d-0322ffb7152b | note | Greater than 110 ¦¦ ±40
45e41b81-25b8-5954-994a-c8bf9bfef2d9 | note | – – – – – – – – –
d52ab3fe-b28c-59d8-9327-730a4b8683c6 | note | Standard / Specification - SS 2140 - 7, NZS3109 Table 9.1
f2d69254-ddb3-55ee-8197-8b08070d0f38 | note | Verifying Document - Photos or slumps and on-site records
789c6e42-93ec-5498-8f69-fe61dfb33dd9 | note | Frequency - Each Delivery
5dddbaae-acbc-52f1-9211-5852dd09874a | note | Activity - I
0fd42dd4-87cf-5055-bc83-edc7f9e2a40c | note | By - SE
| checkpoint | 3.02.07 - Time Limits
b3091f5d-d71f-5816-80b6-86c2a0670403 | note | Acceptance / Conformance Criteria - Concrete not placed and vibrated in forms after 90 minutes have lapsed from the stated time that water was added at the plant, or within 30 minutes after discharge from the mixer or agitator truck, may be rejected by the Engineer.
a456db93-00ad-592a-a56c-149b9c53da3a | note | • Concrete not placed in its final position in the forms before initial set has occurred shall not be used. For concrete mixes containing set accelerating admixtures the above times shall be halved.
d25a023b-75f1-5775-b1c3-3ed1b007a5a4 | note | Standard / Specification - SS 2146 - 7
5537c1d4-520f-5a57-b28e-4b1b001a3064 | note | Verifying Document - Site Notes, Batching record, Delivery dockets
ebb34dd9-ad84-55ca-b132-95e943400b01 | note | Frequency - Each Delivery
cc16ed49-1224-5b63-9312-84f903825769 | note | Activity - R
cf396d5c-8453-54d4-bc31-30640606f35a | note | By - SE
| checkpoint | 3.02.08 - Compression Testing
12a81dfc-2735-518f-9f95-89dc89034743 | note | Acceptance / Conformance Criteria - Compression testing shall be carried out at an independent laboratory accepted by the Engineer.
c7d783a9-365c-53f6-949c-2cb040613a66 | note | • A set of specimens for compression tests shall consist of four specimens for each concrete pour, one of which is to be tested at 7 days and the remainder at 28 days. Cylinders are to be cast on-site straight from the truck, not at the batching plant.
66c7fb1f-da87-5bcf-b5c9-ad6c8729ace6 | note | • Larger pours greater than 75m^3 will require an additional set of cylunders to be taken.
f0a2235e-fd2f-53a4-84b0-dbb67da813d3 | note | Standard / Specification - SS 2140 - 4, SS 2140 - 7
661b2ca8-b561-57ab-a20f-bd7617dc146a | note | Verifying Document - Compression Tests
dd8d6713-8be2-5337-b1ff-0335454cbec7 | note | Frequency - Each pour
31fc172e-75a7-54cb-aa92-fcefd81c6e36 | note | Activity - R
5d39b2a3-1f62-5f02-a867-1b1eefb8f56a | note | By - SE
| checkpoint | 3.02.09 - Concrete finishes
770204c3-cf45-594e-a884-cba59d9b5e04 | note | Acceptance / Conformance Criteria - Concrete finish are to be as specified by NZS3114, scheduled as follows:
80c37f66-0833-5573-8d63-4410d802eae2 | note | • Barriers: F5
e67cc16d-b274-5f09-8576-d54fe382002d | note | • Precast elements - exterior faces : F5, connecting faces to other elements: Type B construction joints to NZS3109
ee5e4f73-3490-5ba5-bcdd-ac92d38b36a5 | note | • Exposed concrete : F5
0568219d-3ef7-596c-8c35-e10629522bcd | note | • Element below ground: F2/U2
1b536b9a-0e6b-521c-aa02-5d824b0c40f2 | note | • Top surface of desk: U5
e515470c-c59a-5eef-9aa5-46ebe034f185 | note | Standard / Specification - NZS3114, NZS3109
e208738b-ba48-5e9e-be4f-46bdc6d07cf9 | note | Verifying Document - Approval
0b85def7-79c7-5118-bd36-785d474d449d | note | Frequency - Post concreting
34150cc9-920a-5e73-b544-e09b5385fc23 | note | Activity - R
cf5da204-6b8c-5b5c-ada6-11f80e6204ea | note | By - ENG
| checkpoint | 3.02.10 - Curing
5a0825fb-6bbe-5e63-ae9f-91c81e1c797d | note | Acceptance / Conformance Criteria - Minium of 7 days wet curing for all concrete including prestressed concrete after completion of accelerated curing
974a1cc4-2684-5006-89cc-b3ebecc7b10d | note | Standard / Specification - SS2146 -11 Construction Drawing
ab88c804-4ce9-555b-9084-be490325f69d | note | Verifying Document - Acceptance / Repair Details
f55a6a61-7f17-5324-b8ee-f16e7432c137 | note | Frequency - post concreting
52f72b64-4d1d-58a9-bb16-edad19b78ed1 | note | Activity - H
1db4265e-6898-54da-a6f7-e04a20073316 | note | By - SE
| section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
| checkpoint | 3.03.01 - Falsework and Formwork Removal
dec414b1-eed3-5792-b204-68a2070abe22 | note | Acceptance / Conformance Criteria - Formwork shall not be removed until minimum periods set down in Table 5.3 of NZS3109 have elapsed.
c3a30472-0545-5670-9d32-721a967f62f5 | note | • The stripping time may be reduced if it is shown by field-cured tests that compressive strength has been attained of twice the stress to which the member will be subjected at the time of stripping or as directed by the temporary works engineer.
0da5f71b-9194-5afc-ad29-138f5866a562 | note | Standard / Specification - SS 2144 - 10, NZS3109 Table 5.3 Downer
4b26deef-4ace-5f06-8d86-e0cab898fa1e | note | Verifying Document - Approval
b43b8365-e58a-5ded-9b7a-6c6a11d3a619 | note | Frequency - Before removal of Falsework and Formwork
02d06e25-cdd1-52b5-ad9f-8966c91e5686 | note | Activity - H
ddfc129c-97cc-5641-b3d6-06df2fa75f54 | note | By - SE
| checkpoint | 3.03.02 - Post Pour Inspection
0b181a42-fa10-59a6-81ca-48ba475173a3 | note | Acceptance / Conformance Criteria - Post pour inspection undertaken by the site engineer and captured in the ConQA web app. Engineer notified of any defects.
2aff5a62-dc55-5de2-8f1e-68bd2ad456cd | note | Standard / Specification - Downer
762c0092-dba1-5f27-a6da-f9d21d17bd6b | note | Verifying Document - Site Photos
63b0215c-5fc3-5895-b258-2afd6a5afb14 | note | Frequency - Each pour
de152083-4e82-5c5b-89df-3aa6966c3d6d | note | Activity - H
703189ef-6266-513f-8080-f3aa10c07f00 | note | By - SE
| checkpoint | 3.03.03 - Concrete Repair
1bdddc29-7007-5de3-b762-31e575623ae6 | note | Acceptance / Conformance Criteria - Repair of any minor surface defect or structural defect of concrete shall only be carried out with the Engineer’s acceptance. All repaired concrete shall have the same strength, durability and surface finish as the parent concrete unless otherwise accepted by the Engineer.
e8ea1016-5725-5913-87fa-d8f8d68e316a | note | Standard / Specification - SS 2146 - 11, PS - 11.5
bd095117-f326-526e-98b6-ae8000ddd20b | note | Verifying Document - Acceptance / Repair Details
5ca7e0d8-1790-5caa-8305-d19193a3ca9d | note | Frequency - Prior to Each Repair
a50e1e6f-f2d3-53a4-a30c-b8d6a50966e0 | note | Activity - HP
daa68760-d745-5e56-99da-3c3019dbefcb | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
| checkpoint | 4.01.01 - Construction Record Compilation
fa54a5fb-70fe-5579-8986-21f71eb84ba6 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
3b97f4fe-707d-51da-9fec-b13c052aade7 | note | Standard / Specification - Downer
a68ede23-427e-5f8f-80c1-daff6a0b4bf9 | note | Verifying Document - Records
4f3869bb-e03a-5c6a-b7f9-577b56010a16 | note | Frequency - Post construction
38826559-5404-5117-bba5-164388588f7d | note | Activity - H
6b7048a8-8b04-51a8-8c19-bed142084bf1 | note | By - SE
| checkpoint | 4.01.02 - Survey Records
500135bb-9cef-5337-ac14-f192690029f8 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
e7f5a82f-265f-5040-a61f-9736a97d1edc | note | Standard / Specification - Downer
97d3b3b3-b255-58a0-949a-7a6e9715afd3 | note | Verifying Document - Records
96b52f1c-77c5-5f23-b94f-c39d0692557f | note | Frequency - Post construction
b547ae6e-ba0b-58be-936a-edfd767d4e44 | note | Activity - H
8225d0b9-eeae-5070-9cd3-3ca58bdc7832 | note | By - SV
| checkpoint | 4.01.03 - Redline Drawings
df552f67-9595-5147-8470-d85d458a97c5 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
0696bef3-f497-537b-b93b-6175cd96feed | note | Standard / Specification - Downer
f3c1c9cd-0020-566d-b289-9fc5aadf7a3c | note | Verifying Document - Redlines
77cedc8e-6b60-5514-bca8-5d9867a97457 | note | Frequency - Post construction
229b9136-df9d-5d15-b775-d41a69cd622b | note | Activity - H
29bd9bb4-29d0-5090-8cbd-e8704572436d | note | By - SE
| checkpoint | 4.01.04 - Defect, Snag and Punch List
2277c0f7-9c23-56c0-89f3-2aaaf6f44777 | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
befb1dd1-769f-523f-98eb-a52a9f831694 | note | Standard / Specification - Downer
c8fff96b-f1a2-55de-bff7-67a2b0ca14df | note | Verifying Document - Register
fe712a0b-268c-5b2d-aef5-4b0680887445 | note | Frequency - Post construction
79382ceb-7c19-5aae-a5e6-6e3c6c5021fc | note | Activity - H
2a25e899-1b46-56c9-9e21-eb1b3800c0c2 | note | By - SE
| checkpoint | 4.01.05 - Delivery dockets
e62d23f9-8df3-5761-87aa-0d54b31ef97f | note | Acceptance / Conformance Criteria - At the completion of the Contract a schedule of delivery docket numbers for all concrete supplied shall be forwarded to the Engineer.
a97e0c17-6693-5ee3-9288-105e7865c27a | note | Standard / Specification - SS 2140 - 4
3448efdd-5a80-5913-a8c3-1a2e38df75c6 | note | Verifying Document - Dockets
eb9fa779-7e94-529d-a4f8-b10575b7a698 | note | Frequency - Post construction
474db2fa-1510-5eb4-ac17-126827ef5127 | note | Activity - H
5e99b310-752b-5256-bdff-e3220ed45d9d | note | By - SE
| checklist | ITP - Mangakootukutuku ST Rev 3 | itp | ITP - Mangakootukutuku ST Rev 3 | 519d0b94-e8d8-4a7b-b487-a3b9f2765890
| section | A. Pre-Construction
| checkpoint | 1 - Shop Drawing Approval
7f551341-4092-5f41-b608-365d16f7af0a | note | ACTION (Hold, Monitor, Witness) - Hold
21a25c85-7669-5e43-b881-cb382d0cdcf1 | note | Detail - Shop drawings to be submitted for approval.
bffa2df9-33f7-511b-b3fc-ab1be1a76bea | note | Reference - Structural drawings
665c516d-76b1-5aa6-9126-10f6537864fd | note | Frequency - Prior to casting
f573a840-2c00-5fb2-b5ab-a06cf4dd26d7 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
94e10edb-c26e-5561-a211-7af1d2f73c9a | note | Conformance Criteria - Approved IFC Shop Drawings
a578b38c-a938-5cc7-a081-f444b003b6cc | note | Records - Client approval
0eb78f61-f25f-583d-9e72-ec868b88f33f | note | Responsibility - Project Manager
| signoff | HOLD POINT
| checkpoint | 2 - Concrete Mix Design Approval
b4a7e83d-f7e2-5386-a8d0-bdce94a58340 | note | ACTION (Hold, Monitor, Witness) - Hold
a361c484-876b-5df1-ab52-16c3d4d3a3d1 | note | Detail - Concrete mix design to be submitted for approval prior to concrete being supplied to site.
1742277d-7193-50aa-8080-d6b50de0bcde | note | Frequency - Prior to casting
9dc02ba3-edcd-52e5-ae2e-27beb06afe27 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
8aed14d2-9e72-5d42-9292-552147cc8c76 | note | Conformance Criteria - Minimum compressive strength at 28 days 60MPa. The mix design to comply with aspects of the contract specification.
3eb4a396-88d9-5085-a6a0-3eff50c8f8db | note | Records - Client approval
8c70c253-b98f-5db0-aa4d-6fe8b1c7b33c | note | Responsibility - Project Manager
| signoff | HOLD POINT
| checkpoint | 3 - Lift Design
72a3e126-69fe-5331-8d3c-3cb9bed90c53 | note | ACTION (Hold, Monitor, Witness) - Hold
8e3c3373-6ac1-5937-81fe-bad027c8e376 | note | Detail - Lift design provided for units demoulding, storage and transportation.
247154f6-4b94-573f-b348-c9c4696d731f | note | Frequency - Prior to casting
e2060d2f-34fe-57ac-b22f-dc007a76e3d5 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
a79b995c-26bc-5e0f-9381-9f98a434f799 | note | Conformance Criteria - Specific Lift design (Lifting eyes and position) produced and followed
3483a0fd-cc1f-59a7-b920-e5e057f9c41b | note | Records - Lift design Shop Drawings
b905620a-4d8d-5d4e-a3a7-53824569a358 | note | Responsibility - Project Manager
| signoff | HOLD POINT
| checkpoint | 4 - Steel Reinforcement compliance
8a87d0fa-e2d7-5382-abbb-7559965df98c | note | ACTION (Hold, Monitor, Witness) - Hold
dc2aa740-0704-5c57-9315-5bd3434e5084 | note | Detail - Mill certificates for steel reinforcing to be provided
84b89b85-f301-5869-80df-0741626d9978 | note | Reference - AS/NZS 4671
0be59b34-46b4-59f8-be20-5324c088df7b | note | Frequency - Prior to casting
e18e88e4-798f-5709-9d17-caeba780f4f5 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
435840fc-5c7e-5ed7-8196-c57795815028 | note | Conformance Criteria - Steel to be manufactured with ACRS certificate details and verification
9aef982d-f1ee-5d4b-8c43-aa4585465456 | note | ○ Mill certificates to match ACRS certificates.
4a9eef66-564d-52e1-bdb1-749ac415648e | note | Records - Mill Certificates Detail sheets Test Certificates
224e08df-d43c-5baa-850c-365e78cbec56 | note | Responsibility - Production / Quality Coordinator
| signoff | HOLD POINT
| checkpoint | 5 - Steel pre-stressing material (Strands) compliance
31c2bab4-6967-5982-8252-679329640788 | note | ACTION (Hold, Monitor, Witness) - Hold
e6226ee2-84ea-510d-a413-1f05e36cbfda | note | Detail - Mill certificates for prestressing strand coils to be provided
32cd856e-af64-555b-bbcb-beafca175edb | note | Reference - AS/NZS 4672
0d6a44bf-7515-528e-b9ff-e27410caf60a | note | Frequency - Prior to casting
24a4e194-84f5-5cc7-bc56-9844e407437b | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
ad0406fe-662b-544c-87dc-3fa17e11c21e | note | Conformance Criteria - Prestressing strands (coils) to be supplied by ACRS accredited Manufacturer.
e681fcf6-ed21-5216-bdd0-c80ff47f280a | note | ○ Mill certificates checked against size, type and strand - mill certificate to match ACRS certificate
661a7406-1789-5ca9-8dd1-9ff81b2232f8 | note | Records - Mill Certificates ACRS Certificate
f3e0a21c-8f19-552d-acf6-27af1d03f4df | note | Responsibility - Production / Quality Coordinator
| signoff | HOLD POINT
| checkpoint | 6 - Design Stressing calculation
02e5ba00-1841-508e-88e9-39d62acb03da | note | ACTION (Hold, Monitor, Witness) - Hold
b61dc034-995f-5a8f-b50b-d857eafda1d1 | note | Detail - Design stressing calculation and calibration certificates to be submitted to the Design Engineer
c04a58dc-439f-5d7d-8fa1-63ff20c0c2d8 | note | Reference - Structural drawings
22e98be8-f1e3-57fc-a027-d820b4865448 | note | Frequency - Prior to casting
84a194d4-cd04-59ef-bc72-be360077947b | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
23dbf582-8563-551b-b047-6676ee83726d | note | Conformance Criteria - Expected extensions and gauge readings to be calculated for each cast.
0460bfcb-18af-53d5-84e9-334ab18aa823 | note | Records - Design Stressing Calculation Calibration Certificates Client Approval
b7f2b866-abde-5ca0-9e68-6218a4aed178 | note | Responsibility - Project Manager
| signoff | HOLD POINT
| section | B. During Casting
| checkpoint | 7 - Steel Reinforcement cage assembly
bbb86996-1306-53de-92bd-7b21db04436e | note | ACTION (Hold, Monitor, Witness) - Monitor
d6e9e554-3562-5659-b411-0a6dbf8fd943 | note | Detail - Steel reinforcing cage to be assembled and inspected.
d724b6cc-c017-5e9a-9bea-8e52bbcf82ee | note | Reference - Approved shop drawings
d7ab26fa-5758-5365-8712-d8e50b24bf35 | note | Frequency - Prior to each cast
3f6e926d-9ab1-5a6e-bdcc-89f9f4436e82 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
15bc6d2f-fa18-5f0b-ad6a-c27f4c806501 | note | Conformance Criteria - Cage assembly to comply with correct size, class, length, shape and location/spacing as specified in shop Dwgs.
a5492493-815d-5d4a-900f-e4bce94a1b05 | note | ○ Free from visual damage.
022fa99d-8580-5db1-94d3-9fbbb8691e3b | note | Records - Pre-Pour Inspection sheet REO detail sheets
9cfbf8d0-b2c5-52d9-bb65-65a95a91455f | note | Responsibility - Production / Quality Coordinator
| checkpoint | 8 - Mould Preparation
43fe340e-b9b0-538d-8621-ba7f3318bfb9 | note | ACTION (Hold, Monitor, Witness) - Witness
fe206031-d2ba-5e19-857b-d0740b5960e0 | note | Detail - Before casting ensure mould has been prepared to comply with tolerances.
0c681922-0513-523e-bd51-52e5225d4a57 | note | Reference - NZS3109 Table 5.1
91ae295d-84a2-5001-8bba-931750dbddd5 | note | Frequency - Prior to each cast
4663dd7a-dc7f-5241-a762-c541366ac4a8 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure
c26ea311-eda5-540f-89f0-1c218f3670a9 | note | Conformance Criteria - Tolerance on placement of moulds shall be a per NZS 3109
00d231e6-2d84-5b52-b840-9513bd292965 | note | Records - Pre-Pour Inspection sheet
76e7dcf0-de89-5a71-b6bf-23284989ec0c | note | Responsibility - Production / Quality Coordinator
| checkpoint | 9 - Pre-Stressing
9c5e267f-852c-5784-bb06-b77b0f341dd4 | note | ACTION (Hold, Monitor, Witness) - Monitor
156da291-3e2f-538c-a6f1-8f01b26d7867 | note | Detail - Review actual strand extension/pressure compliance with approved design calculation. Draw-in measurements to be taken and recorded
89d5f0b4-87a3-513c-a8bb-fde46de78203 | note | ○ Check that debonding has been included as required. Debonding shell be by plastic sleeves around the strand.
53513eea-415b-5397-bace-18380b39200a | note | Reference - Approved shop drawings Design Stressing calculation
f6443357-0e8a-5be2-920f-9388d9a4ce65 | note | Frequency - Prior to each cast
dc95e6dd-a9f5-513b-ac08-2eb177d117ce | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection/Measure
ee1c4d01-6f3b-50de-a259-994acbbcca4a | note | Conformance Criteria - Stressing data/records reported on stressing calculation sheet.
d94f394f-2237-54c6-ba30-aaa4093be6d7 | note | Records - Stressing Calculation sheet Pre-Pour Inspection sheet
6c33327f-4ece-5777-8fbe-9a8e26d44332 | note | Responsibility - Stressing Controller
| checkpoint | 10 - Steel Reinforcement Placement
71101c6f-a534-50b3-9511-2c6063359adb | note | ACTION (Hold, Monitor, Witness) - Witness
f1dd1e46-5c1b-5492-8045-ebc58b503aa4 | note | Detail - Reinforcing steel shall be handled, placed as per NZS 3109.
340e129f-d759-5aab-bbf0-6227e531e49b | note | Reference - Approved shop drawings NZS 3109
b691864c-eca4-5a3e-8d5e-a3aa6ddb08bd | note | Frequency - Prior to each cast
6c971a7b-073f-51bc-b5a5-0e8064f8f469 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
697d608b-a8b9-5e91-9866-7308204ce618 | note | Conformance Criteria - Steel reinforcing cage placed as per approved shop drawings.
c043c1fb-3973-50ca-80a1-8f4434cc8a56 | note | ○ Spacers shall be installed evenly to ensure correct cover as per shop drawings achieved.
4d4e6ca6-fc8c-567f-8dad-6d34b9197e87 | note | Records - Pre-Pour Inspection sheet
7f2a04b5-c7b0-53ef-b90e-14b915df5dc7 | note | Responsibility - Production / Quality Coordinator
| checkpoint | 11 - Cast-in Items
fe536922-ec0a-562b-8b32-da5cfe699326 | note | ACTION (Hold, Monitor, Witness) - Witness
7e6518c4-5902-5d48-880a-df652300e336 | note | Detail - All cast in items positioned as per shop drawings Lifters positioned as per lift design
fd745cbd-6b98-54d4-962f-e79c3285daac | note | Reference - NZS3109 Table 5.1 Approved shop drawings Approved Lift Design
f6f59f88-e7d5-54ce-9107-a68ee4b8806c | note | Frequency - Prior to each cast
662e8aa6-b9aa-58e6-9bb8-f5657702a15d | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
aca746dd-5131-5204-9a2b-f1cc75f1b6e6 | note | Conformance Criteria - Correct type and number of cast in items used Correct Lifters used, positioned in accordance with approved lift design
2ef43b5d-e49e-58dd-bb51-00dc5a337802 | note | Records - Pre-Pour Inspection sheet
eab0fc36-07a8-5e5a-b470-6c5fe90648d8 | note | Responsibility - Production / Quality Coordinator
| checkpoint | 12 - Pre Pour Inspections
9610250c-a6e8-5748-a901-50d9ec1f58d5 | note | ACTION (Hold, Monitor, Witness) - Hold
e169089e-503c-584e-a545-6ea525b5872e | note | Detail - Pre Pour Inspection shall be carried out before casting.
a73a93b7-54bf-577d-b463-728716aa1f09 | note | ○ The Engineer's Rep shall be advised at least 48 hours before the proposed pour.
5b7e1687-4e07-5373-ae80-e6e4c22163a3 | note | Reference - Approved shop drawings
ea266cef-f33e-5e17-8cb4-cddabe92dbd0 | note | Frequency - Prior to each cast
1a8e14fa-821b-5cbe-aba4-f90cedbbed80 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure, Document review
019ed32d-6966-5225-8f76-2a67e4bf6b5d | note | Conformance Criteria - Confirmation that the unit has been cast in accordance with approved shop drawings and NZ standards for tolerances.
a01183aa-1c69-5ad0-8267-d0479f1bcdb3 | note | Records - Pre Pour inspection sheet Marked up shop drawing, Stressing records
b5baa92c-78a5-5ac1-8c60-3f962fd9fa84 | note | Responsibility - Foreman & Production / Quality Coordinator
| signoff | HOLD POINT
| checkpoint | 13 - Concrete Mix Conformance
311117ac-3155-5539-a777-674b996bf619 | note | ACTION (Hold, Monitor, Witness) - Hold
6db8b1b3-2817-561e-bf0c-593f1b25912e | note | Detail - All concrete dockets reviewed at time of delivery.
a165b695-2965-535c-bc57-2d3d04cb5ace | note | Reference - Approved mix design
9370f9fa-3cf8-5619-a925-3d62e5b8fe41 | note | Frequency - Prior to placement of concrete
6148a39e-7d5d-5efa-9bcb-455615636d8b | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
0c458253-3efd-59d6-8e91-7791f4319959 | note | Conformance Criteria - All concrete delivered to site shall be produced in accordance with the approved mix design
b811b79f-2d25-572e-975a-a02276a48af2 | note | Records - Concrete Delivery Dockets
4c842c98-2566-5e00-ad8c-cc5d77f34cd3 | note | Responsibility - Supervisor & Production / Quality Coordinator
| signoff | HOLD POINT
| checkpoint | 14 - Concrete Mix Workability
7a334b4b-7737-5c51-866a-9c853b5cf709 | note | ACTION (Hold, Monitor, Witness) - Hold
fd3bc877-8753-5f64-9e66-453baed60ccd | note | Detail - Fresh concrete to be visually assessed for its workability compliance.
e46c0b51-3685-5315-8d13-c30cdecb41a5 | note | Reference - Approved mix design
0142e3c7-3508-5acc-9f85-df8e25e44292 | note | Frequency - Prior to placement of concrete
768a44ca-4a4a-5073-8b4f-c7328566a890 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
92f4fa5e-031d-5a99-ac4d-b449dec86fb0 | note | Conformance Criteria - Workability as per mix design.
90070146-4e54-5605-a12f-dcd06ee86053 | note | ○ Concrete slump test to be performed by concrete supplier before delivery
b6789452-9098-557d-b59a-48a6433402e6 | note | Records - Concrete Delivery Dockets
8595d649-ab63-5660-a481-42756681bb5b | note | Responsibility - Supervisor & Production / Quality Coordinator
| signoff | HOLD POINT
| checkpoint | 15 - Concrete Finish
ffda2a76-6528-5d93-a851-c9706278b15e | note | ACTION (Hold, Monitor, Witness) - Witness
48b8c739-dca4-5c03-b99a-a6d0e0aa3f04 | note | Detail - Concrete to be placed to achieve the specified formed and unformed finishes
42cd536b-8b98-5dbb-a933-2ab4e9951e9e | note | Reference - Approved shop drawings NZS3114
319497f6-1355-533d-b8d1-69845caef18f | note | Frequency - During and after placement of concrete
561d4630-0862-5e59-ad24-4fe0a5e8d775 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
47874d4f-1668-58a0-a01a-346d8df68456 | note | Conformance Criteria - ST Beam to be Type F4 finish
3ad84433-4b23-5d29-ba07-1b5d516cb884 | note | ○ All construction joints - Type B / UNO
d8c14651-d0e7-5a17-b51c-a4ff74c0bb2c | note | ○ Top surface Type B / CJ and U2 where specified
333da850-fdda-5870-9d8c-89652d76e88e | note | Records - Pre-Pour Inspection sheet
f7cb8e4d-b176-500d-9ca2-f77e871b02c6 | note | Responsibility - Foreman & Production / Quality Coordinator
| section | C. Post-Construction
| checkpoint | 16 - Curing and Release Strength
83fe2645-c52a-5ed2-b008-4d454814155d | note | ACTION (Hold, Monitor, Witness) - Hold
67eb983b-0580-5566-84c6-27120456b012 | note | Detail - Heat accelerrated curing as per approved methodology.
71c95f64-4e80-52b8-9214-c5d34640cd49 | note | ○ 7 Day post mould water curing as per approved methodology
2e1e5b66-8947-5034-8df6-9cace7b9ee3e | note | Reference - NZS 3109, NZS 3112
1b3bb031-68ca-5dce-9cee-1faf40c0532e | note | Frequency - Prior to every unit transfer
29171571-516c-5465-aa92-036c69d303c3 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Testing (Schmidt hammer or Compressive strength test)
75ce6f2f-056e-5814-9266-d4528833d946 | note | Conformance Criteria - Minimum compressive strength at transfer of prestressed units to be 40MPa prior to stripping and demoulding.
a6a1b21e-1b8d-5ec7-8363-c7038caef5c4 | note | Records - Post-Pour Inspection sheet
35e0f182-6c39-5260-b30a-0f1e47a13019 | note | Responsibility - Production Manager
| signoff | HOLD POINT
| checkpoint | 17 - Transfer
dca831aa-0a41-55d3-bdb9-23f9f12f80a4 | note | ACTION (Hold, Monitor, Witness) - Monitor
86efa140-caa3-5d23-a936-c12143ffdc1e | note | Detail - Visual inspection to ensure strands are tight and no slippage of strand into concrete. Locallised spalling around full bonded strand at transer as result of excessive slippage will be identified as non conformance and the unit will be rejected and remade.
2c15f307-7610-5f79-928a-5f76b2be7231 | note | Reference - Approved shop drawings
2f770336-c37d-5921-88d2-d5adbe33ac34 | note | Frequency - Prior to transfer
7c20d68e-d849-53fe-a90a-9e62feba776e | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
e2c67bcd-cc11-595d-81dc-e2a00aff1b10 | note | Conformance Criteria - Stressing data/records reported on stressing calculation sheet.
e4cb9fd6-82be-54a2-8137-19bf8139eb78 | note | Responsibility - Production / Quality Coordinator
| checkpoint | 18 - Draw-in
7a0c13e9-093c-5682-8d1b-e60370172781 | note | ACTION (Hold, Monitor, Witness) - Monitor
1e2fe925-028d-5379-890f-a0bd96d228bb | note | Detail - Strand draw-in to be measured on each cast. If ave draw-in for group exceeds 2mm, or 4mm for single strand, then results to be submitted to Eng
bff52761-f10d-5b32-9a96-c2e6f259adf6 | note | Reference - NZS3109 C8.72.3
66b150d8-cf4d-5c53-a9a8-19989e9dc75e | note | Frequency - Every unit - at transfer
941faba9-d19c-563d-a257-c361b146104c | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure
868bbe88-0540-544f-bde0-c635769310b0 | note | Conformance Criteria - Draw-in to be measured on each beam at transfer
efc87e3d-5551-5bc7-8473-64158b9bb748 | note | Records - Post-Pour Inspection sheet
3f5e4a31-7372-5378-8977-0209a93256c0 | note | Responsibility - Production / Quality Coordinator
| checkpoint | 19 - Lifting
c49d51f6-a795-5014-b414-bd86d118b587 | note | ACTION (Hold, Monitor, Witness) - Monitor
13ede2b5-5b4c-5a09-8046-aef69baa9e0e | note | Detail - Units are to be demoulded following lift design
60dab494-c2a1-50de-bfa2-3dc3b9ff4694 | note | Reference - Approved lift design
46f2cc6e-738f-5188-9f4b-ba8db6bbfd7e | note | Frequency - Every unit
7bfb66b1-e02d-576a-a838-e48e020d9746 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
ea91a55e-6c8b-59bb-9f0b-92c4eebc6c0e | note | Conformance Criteria - Approved lift design to be followed.
00d14c8c-7757-5442-8152-ec5f786dcde2 | note | Responsibility - Production / Quality Coordinator
| checkpoint | 20 - Marking
6ff1f621-a675-540a-aae3-a86d79a29035 | note | ACTION (Hold, Monitor, Witness) - Hold
c7fd609e-b2ac-5f38-885c-beb54ed5a4a5 | note | Detail - Units are to be clearly marked each end with unique number, cast date and installation direction (Super T).
161bd468-0322-5036-93be-26ac20754dc0 | note | Reference - Approved shop drawings
27d71e1f-5d89-55d0-8cc6-b04510b589b7 | note | Frequency - Every unit - after demoulding, prior storing
4abfe7b5-7b7c-5e98-b96d-29b109203c9e | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
abc4c0ea-d7ac-580a-9dbf-539e63312f44 | note | Conformance Criteria - Ensure every unit is clearly marked
80cebd3c-1d86-5073-baf7-4db5179ad035 | note | Responsibility - Production / Quality Coordinator
| signoff | HOLD POINT
| checkpoint | 21 - Concrete Supply Testing
a50a5106-58ac-5154-b636-4e9d9baf5168 | note | ACTION (Hold, Monitor, Witness) - Hold
524723cd-0b10-5b32-a705-0aaf1f106914 | note | Detail - Concrete compressive strength test to be carried out by supplier. 1 Set per beam with additional set for any truck with water added after leaving the batch plant
3fe6190e-caa7-5090-99f8-40eaaf9458cb | note | Reference - NZS 3112, Part 2
331227d1-8d3c-5dc4-b1b8-7ec0f3ee2639 | note | Frequency - 1 test sample for every beam [1 cylinder - at 7 days age, 3 cylinders - at 28 days age, 3 cylinders - transfer strength]
ef3e12d0-76f2-5b65-9cfb-0b4f1a44dc33 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Testing
025465c7-5017-563b-a711-8ca08e0408b2 | note | Conformance Criteria - Compressive Strength result to be a minimum orf 60MPa at 28 days
0f0c4a8d-861c-5471-969e-3658197a17f5 | note | Records - Concrete suppliers Test Reports
ee7efde4-c434-5036-a461-9dcb8ab13561 | note | Responsibility - Concrete Supplier + Production / Quality Coordinator
| signoff | HOLD POINT
| checkpoint | 22 - Post Pour Inspection
721abcd0-5901-5c3e-b54f-0ea4ebb89e4e | note | ACTION (Hold, Monitor, Witness) - Hold
f8c468dd-cbfc-59fa-840e-626b72f8d26d | note | Detail - All units shall be inspected for its compliance prior to delivery
139fc4d8-86d9-5641-a088-8d6a6481b470 | note | Reference - Approved shop drawings
f176d10f-98c5-5a13-b724-be54170c4ad9 | note | Frequency - Every unit - prior delivery
8d5e7b13-a589-5f24-9b46-c5b8cbcd54fe | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
a403cc31-9e23-5f4a-9c73-ac4489955d3b | note | Conformance Criteria - Confirmation that the unit has been cast in accordance with approved shop drawings and NZ standards
8b0f1bbd-a572-581f-953d-7b495ef12b98 | note | Records - Post-Pour Inspection sheet (red pen mark-up - as-built)
f321ff1b-89d3-5b73-b0d5-a61c496aa4bd | note | Responsibility - Production / Quality Coordinator
| signoff | HOLD POINT
| checkpoint | 23 - QA Package / Redline Drawings
2f204df4-bf44-5875-8ed5-2fc070b896f3 | note | ACTION (Hold, Monitor, Witness) - Hold
e5e86938-3e39-559e-b0f1-f12261960b37 | note | Detail - Compliance documentation is to be collated as per project requirements
9b670fca-7b98-5440-a777-b5d556f58b3f | note | Frequency - At Delivery and installation
b6d92ed9-8b0d-58f3-b32e-7c0f31b46779 | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
308eecf0-d585-5ce6-9006-1532ba7cb0b0 | note | Conformance Criteria - Compliance documentation is to be submitted to the Engineer.
9c00f19f-17d7-56d7-a209-5abed1961002 | note | Records - Post Pour inspection sheet Marked up shop drawings - as built
3a897618-00a4-59f5-88ac-593de51db2e6 | note | Responsibility - Production / Quality Coordinator
| signoff | HOLD POINT
| checklist | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | itp | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | 7dd3ad9d-10ed-4b19-84e4-665850891756
| section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
| checkpoint | 2.01.01 - Basecourse CBR
49feefc3-588f-5a18-a041-0e972e47510d | note | Acceptance / Conformance Criteria - (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand Vibrating Hammer Compaction Test at Optimum Water Content and;
60fe236d-5085-5b0d-bf42-d0daecc97a4f | note | (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%.
f2d19251-5dc6-5502-b284-ae9daf0e77c5 | note | Standard / Specification - TNZ M/4: 2006
c0fb680d-688a-5a53-8ee8-018c1be109c8 | note | Verifying Document - IANZ Lab Reports
092ee455-c68a-52da-b948-069dbee4c3e5 | note | Frequency - 10,000m3
a20f305f-4ca6-5475-b922-31e79decface | note | Activity - HP
0eea9014-d4d1-5b97-9f91-3ae4d1913b50 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.02 - Running Course Material Approval
c35c4f61-7668-59a9-8a32-5fa88411ca5e | note | Acceptance / Conformance Criteria - The running course shall have a crushing resistance of not less than 130 kN when tested in accordance with NZS 4407: 1991, Crushing Resistance Test, Test 3.10. It shall be free from all non-mineral matter.
00ee2165-c923-52c1-a7c1-c8be26b744a0 | note | • The grading of the running course shall conform with Figure 3 of TNZ B/2:2005, 10.2, when tested in the same manner as required for the parent basecourse. (IF USED)
4b73ec4b-e5d5-5465-8748-2724aaf33df6 | note | Standard / Specification - TNZ B/02: 2005 - 10.2
09652dfd-98c4-557f-b304-99834837ee0d | note | Verifying Document - IANZ Lab Reports
d8499938-8384-5e3a-974e-f813ce8ea501 | note | Frequency - 1 test every stockpile
30b3ebf3-2c6a-582c-b8dd-ec8a5461615e | note | Activity - HP
090b0c2a-58bd-525e-b9df-1cc56bfd03c0 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.03 - Basecourse MDD and OMC
4b76bb15-0733-5f17-be70-a7872640bbc9 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test on heavy compaction, vibrating hammer.
231b71bc-a331-597e-9693-4b71838c0655 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
c13ccd03-f4be-578f-9839-018fceb45966 | note | Verifying Document - IANZ Lab Reports
89535989-ce9f-5033-b5a5-0d2d0f850ac6 | note | Frequency - 1 test per material type
095585ed-5db8-560b-b506-42b6f64bb47f | note | Activity - H
4922a46a-ce96-5b3b-9f26-174f9c43f553 | note | By - PE
| checkpoint | 2.01.04 - Crushing Resistance
edb7e3ac-db99-5ab7-b928-75906bda42c0 | note | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
d7d65de4-a18b-5fc7-b83b-85abf5a7b5ef | note | Standard / Specification - NZS 4407: 1991 Test 3.10.
8556196e-9046-5bbd-ba48-6a9f2df45fa2 | note | Verifying Document - IANZ Lab Reports
e81886fc-44c2-5966-80d6-283cbbfba1a7 | note | Frequency - 2 tests per source 4 weeks before use in the works
367b8f1b-d809-5e45-93cc-53fba2acb9df | note | Activity - HP
49c94da8-65cf-53c3-9870-956af1c22f4d | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.05 - Weathering Resistance
86ae2acf-2389-5ba7-aa9f-1b3ec70d4642 | note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
98ca51b1-9259-5e18-8408-177657df2e00 | note | Standard / Specification - NZS 4407: 1991 Test 3.11
bea56576-48b0-5a51-a4b7-025c2d69fdc6 | note | Verifying Document - IANZ Lab Reports
3388c215-27fb-5b48-9360-a185b1a46bc0 | note | Frequency - 2 tests per source 4 weeks before use in the works
cb6be75d-bc7e-5543-8ee6-c9509f04b222 | note | Activity - HP
13ddf1ad-108a-5528-8c58-ba360195dc4c | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.06 - Particle Size Distribution
ea27af91-c4e8-5aca-8207-6ea4a0cd81b8 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
02b46647-7530-5d7b-a380-a55e3640f4e5 | note | Standard / Specification - TNZ M/4: 2006
da23db52-ff3f-5278-8584-c1c8331d43c4 | note | Verifying Document - IANZ Lab Reports
8d967d1b-3eed-5ec9-9777-0b99a39c3ed2 | note | Frequency - 0 to 400m³ - 2 tests
5e5fcd4f-ace5-569d-ad71-4f9f9bed611b | note | • 400 to 1,500m³ - 3 tests
2fffda83-5727-5289-aee5-19ffe6c6683e | note | • 1,500 to 4,000m³ - 4 tests
ee93229f-5f11-51a0-b51d-0029d2a1adb2 | note | • >4,000m³ - 1 test for each additional 1,000m³
0dc8fd25-ab31-5aad-82f4-810b3de3a30b | note | Activity - HP
00fd27c9-c403-5163-b669-8aa7eb6c25ee | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.07 - Sand Equivalent
5572a225-1b12-5ec7-8e4d-976f85ad6de0 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
da6de437-7513-56ce-9a69-3041123d9c89 | note | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
684c06d1-5e7b-59d1-b2e8-e5820065c7b1 | note | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
7257ff58-571b-5bcc-94a7-16d39d767a16 | note | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
25672133-332c-5316-8c22-fb96afcda8d7 | note | Verifying Document - IANZ Lab Reports
9404f767-20ec-57bc-8b9a-b05ff4161aa4 | note | Frequency - 0 to 400m³ - 2 tests
42fdb336-16c8-5801-9a29-38141af43cbc | note | • 400 to 1,500m³ - 3 tests
093f1489-71be-5cc8-a336-d0fa8111d0a5 | note | • 1,500 to 4,000m³ - 4 tests
b0fae1ce-8a94-5e2a-847a-c05f4aa5aa46 | note | • >4,000m³ - 1 test for each additional 1,000m³
a4ffeded-c0bb-5d1c-9d42-03a9244068ac | note | Activity - HP
092f8827-5d9c-5bfd-beec-decc3e8ca447 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.08 - Liquid Limit
94ea2bb8-2f99-505a-8180-8022555be423 | note | Acceptance / Conformance Criteria - The Liquid Limit shall be ≤ 25 when tested in accordance with NZS 4402 Test 2.2.
f8df0db3-87ee-5e8b-a51f-1abbf517ed5e | note | Standard / Specification - PS - 7.2.3
4743447b-1543-5fd0-8df4-19273089b6b8 | note | Verifying Document - IANZ Lab Reports
dcd6b8fd-0e3f-5326-b0d1-a2ae57b687cd | note | Frequency - 0 to 400m³ - 2 tests
ed1b49ae-d253-5dd0-a7ca-b88b10599425 | note | • 400 to 1,500m³ - 3 tests
cbe58cad-de5b-5630-877d-52cabfb0ead7 | note | • 1,500 to 4,000m³ - 4 tests
42bf96a7-239a-5fd4-9ffb-4211ff77611c | note | • >4,000m³ - 1 test for each additional 1,000m³
db9425ad-9a83-5aa4-be0f-e8e02b812dd6 | note | Activity - HP
caba5892-dec1-557e-830c-eabd731d1d79 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.09 - Plasticity Index
ca0b0430-ecf9-520f-8416-fab47706e4ad | note | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
b4d6bad6-93f6-5675-bffd-4ee930dad6c3 | note | Standard / Specification - PS - 7.2.3
07d5b80a-e1fd-5cd5-bd63-cde18bc7873a | note | Verifying Document - IANZ Lab Reports
26da61b9-4fbb-5351-92e6-cd4ebda2f352 | note | Frequency - 0 to 400m³ - 2 tests
e7ccd9e2-d84e-563c-b72a-5efa3b79d686 | note | • 400 to 1,500m³ - 3 tests
c9ef1931-3a0c-56a4-93c1-4f20cf8ba5be | note | • 1,500 to 4,000m³ - 4 tests
e70c514d-ec28-5306-9b1e-309be1e35650 | note | • >4,000m³ - 1 test for each additional 1,000m³
d9d286ee-3b26-56ce-9fd5-2744c4cc31f4 | note | Activity - HP
929aa643-972c-556c-b644-30bbf8e8fd00 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.10 - Clay Index
c5cb8138-5b5b-5f01-b352-637dda2343de | note | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
2ad9ee32-a09a-5f57-ac4f-c468049aee8c | note | Standard / Specification - PS - 7.2.3
b9754f71-3ee9-598c-80f5-6eed4874cf24 | note | Verifying Document - IANZ Lab Reports
d00de851-7991-56ce-854f-29f6020cdd60 | note | Frequency - 0 to 400m³ - 2 tests
1b71fb50-1e21-51f7-954d-368e6721ef85 | note | • 400 to 1,500m³ - 3 tests
3553b48c-be94-5eaf-933d-43138b9114d5 | note | • 1,500 to 4,000m³ - 4 tests
771b5fa2-88f6-5018-a3bb-7822e8da2eb4 | note | • >4,000m³ - 1 test for each additional 1,000m³
18ff526f-0935-5e42-b47e-0ba352cb4ff9 | note | Activity - HP
e7708385-c49e-50f2-af6f-296359364d18 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.11 - Accelerated Weathering Testing
cdacb3fe-de6e-5c12-ad45-1dbd1af37f24 | note | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
a9d66b2d-7268-5744-8c47-38883fc76356 | note | • The levels of smectite clay minerals are not classified as “abundant”
ccc5af32-24c9-55f6-90e9-53323ade5810 | note | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
74f995cb-5cbf-5689-a8aa-04f4a1dd8737 | note | Verifying Document - IANZ Lab Reports
3b2ff59f-6c50-57e2-b1f9-7295eab28dc6 | note | Frequency - 2 tests per source 4 weeks before use in the works.
e7c1bd06-7278-50d5-86d3-bb687be7ac91 | note | Activity - HP
117a5286-a1a7-5aad-b5f6-b5ad8f6bb408 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.12 - Repeat Load Triaxial Test
08b10ea8-0e4d-5cc2-accc-084aca7b4501 | note | Acceptance / Conformance Criteria - In accordance with NZTA T15
a116e146-494a-5233-bce3-d2b9ff94d20d | note | Standard / Specification - NZTA T15
f29381aa-0a34-5bd4-90eb-659c4c25497b | note | Verifying Document - IANZ Lab Reports
706b2437-18b6-5b03-b048-d2d22378dcf6 | note | Frequency - 2 tests per source 4 weeks before use in the works.
1bafa94a-9672-572d-a26e-d49166cc001b | note | Activity - HP
a08e87bb-c079-574c-bde9-416f9a9578f9 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.01.13 - Broken Face Content
1dee13a2-b73f-5338-b58c-2f21196685fe | note | Acceptance / Conformance Criteria - The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407: 1991, Test 3.14 Broken Face Test.
f57c44fc-b5a6-5d80-8fd0-bdfa97109bc1 | note | Standard / Specification - TNZ M/4: 2006, 4.2.2
72ce007a-6242-5bbd-a8d8-35849dcb2816 | note | Verifying Document - IANZ Lab Reports
184d8c50-9feb-5fae-9a01-4b7ec19c54f9 | note | Frequency - 1 Test per Source
285defd3-5103-5420-85c5-e8b8af0b82c9 | note | Activity - HP
d7fa7ff3-d18c-519a-b767-83a3181df103 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - Pavement & Surfacing - AP65 Material - Rev E | itp | ITP - Pavement & Surfacing - AP65 Material - Rev E | e7231f11-7d8f-4b8c-835c-30dba119e9c9
| section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials
| checkpoint | 5.01.01 - Sampling and testing
f587ec91-c904-5aa5-810e-812a47bf658c | note | Acceptance / Conformance Criteria - For all aggregates, test information confirming compliance shall be supplied to the Engineer not less than five working days prior to delivery of the material to site.
cbd8acf3-e0f5-55db-8156-67ac9226e388 | note | Standard / Specification - PS - 7.2.4
93885b9b-13f0-53a3-be48-b4c45fe9878c | note | Verifying Document - IANZ Lab Reports
98899682-c28d-54da-9530-1cac6628eb21 | note | Frequency - five working days prior to delivery of the material to site.
4bc3cedf-4f02-54f0-99c0-606777acf2c0 | note | Activity - HP
1684e61d-f968-5bc6-93c8-d16116aaff01 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.02 - Sampling and testing
e3222ecf-c962-562e-b51d-a385ea926d99 | note | Acceptance / Conformance Criteria - Water to be used in stabilisation - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening, strength or durability of the bound aggregate layer.
9f24b800-ed24-5e34-9fd0-3a76c6d2158e | note | • Water from sources other than public supply may have its suitability established to the satisfaction of the Engineer by repeating the final approved laboratory based mix design tests with the water now being considered for use.
75e0f194-01e2-5647-b89b-d15318f6a4c3 | note | • The results of these subsequent mix verification tests shall be greater than 90% of the final results from the previously verified mix design. In addition, work shall be stopped if any discolouration or residue is observed when adding or sprinkling water into or onto the material.”
e658a265-fcf3-51b9-b816-6da8f17ff91f | note | • Verifying documents to be dockets from fill up station, or proof of using public water supply. Or Lab reports for alternative supply.
a3c76a02-e132-5f46-bd9e-b4e2c019c057 | note | Standard / Specification - NZTA B/6 item 5
de7c7586-7099-5189-b616-4a6a29441748 | note | Verifying Document - Lab reports
92d38b6d-5ffe-54da-ae7b-214d1c0bfec0 | note | Frequency - Prior to Works start, per source
cf34b954-d990-5942-823e-8d5103020e49 | note | Activity - HP
9af1c353-0319-5f13-b777-4c09759ce4e8 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate
| checkpoint | 5.02.01 - Sub-base MDD and OMC
0a20a9e1-9754-5595-b8be-f26bb33aab64 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
dfed941e-c73f-5d66-b1a7-3eeeb24eb7fc | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
803756db-7d93-5b60-b603-1af60b69ee66 | note | Verifying Document - IANZ Lab Reports
74aba5d3-54cb-500c-83d1-edce95b9c997 | note | Frequency - 1 test per material type
b8db62ec-cc1f-509b-9903-eb4e81b83a44 | note | Activity - H
5789a56b-3eb4-5866-9ae7-24d49846f94d | note | By - PE
| checkpoint | 5.02.02 - Cement for sub-base stabilisation
90aad58e-40f2-5ded-aea7-47f72532c0c1 | note | Acceptance / Conformance Criteria - Cement for stabilisation shall meet the requirements of NZTA B6.
dbdace18-4d98-5009-8ab6-b14277b731a8 | note | Standard / Specification - PS - 7.3.2, PS - 7.2.6
e5b34312-89b5-5827-ba09-6bb0fcb8e0c7 | note | Verifying Document - Datasheets
4c4b00a1-be0f-5d87-9a3b-54576dcb3ae2 | note | Frequency - Prior to Use
47801d41-6821-5e8a-82e3-0184841d09f2 | note | Activity - H
04c79bb8-fe77-5de7-8f36-985b35480d08 | note | By - PE
| checkpoint | 5.02.05 - Crushing Resistance
41f160dc-388f-56b3-b37a-ddf10704fe4b | note | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
e2d9fc40-231b-5baf-9d2f-0fbd19fd2833 | note | Standard / Specification - NZS 4407: 1991 Test 3.10.
4822f417-d7af-50af-a334-6483bdcbd0bf | note | Verifying Document - IANZ Lab Reports
99c76d46-18fd-534a-9fd2-473398ee471a | note | Frequency - 2 tests per source 4 weeks before use in the works
7c1c7573-6dae-5717-b1b5-fc54365f8ce0 | note | Activity - HP
6977e619-cd8f-5904-a66f-a9a7645f4498 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.06 - Weathering Resistance
943638a1-740f-55b4-be99-af0fcc241c16 | note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
9db6d585-f4c9-5f36-859c-3dfb88fe2450 | note | Standard / Specification - NZS 4407: 1991 Test 3.11
094254b1-853c-5c3f-8b07-5966870ba227 | note | Verifying Document - IANZ Lab Reports
ae7cd138-fb2d-5f88-b416-1f78bfa9b31a | note | Frequency - 2 tests per source 4 weeks before use in the works
162e4230-64db-5c47-86cb-a0dfc237c92a | note | Activity - HP
17931dc9-651a-5859-8652-0f215ae0b1cd | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.07 - Particle size distribution
e5535789-0a6e-5fe0-af5c-1f047760a453 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1.
96e0ef6b-e2b6-5d89-be5a-93e58e38be79 | note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
4873cafd-8d6f-5d61-bc11-6c4e07fee6f7 | note | Verifying Document - IANZ Lab Reports
b74d783c-e32c-5f19-bd48-ba28e3d805ba | note | Frequency - 0 to 400m³ - 2 tests
d39f35a7-71b1-5d66-88ed-38a7e132652f | note | • 400 to 1,500m³ - 3 tests
68fcfe30-4312-5c70-916f-ddafa39da156 | note | • 1,500 to 4,000m³ - 4 tests
009abe47-8c79-5476-bf59-fb711379c37a | note | • >4,000m³ - 1 test for each additional 1,000m³
25bb434e-40d3-55e4-bf28-275ab9962c20 | note | Activity - HP
fb6fab50-41b0-571a-bd3c-9f033205e847 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.08 - Sand Equivalent
408360b1-394d-50d2-8cbe-d6a8bf76af41 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 25 when the aggregate is tested
ac6fcc4f-6636-515e-b5a3-d5ab9dfa131e | note | Standard / Specification - NZS 4407: 1991 Test 3.6 (Wet Method)
db322c43-e10c-59b5-86a8-357f5e898528 | note | Verifying Document - IANZ Lab Reports
4635a1fe-6265-53b9-bb2f-ebbd287eca12 | note | Frequency - 0 to 400m³ - 2 tests
d32b7222-3ce6-5d44-8117-8d53245f7295 | note | • 400 to 1,500m³ - 3 tests
6012f74f-1ac3-5d23-8a19-9e26cf3fb202 | note | • 1,500 to 4,000m³ - 4 tests
4d7c60bb-3bbe-5e64-b3bb-3f11f650b42b | note | • >4,000m³ - 1 test for each additional 1,000m³
97d1c748-b110-5bbd-b3a5-66b8a5b9eec5 | note | Activity - HP
56d76160-229c-5574-97bb-af898fe419e4 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.09 - Liquid Limit
b1f61dae-82c3-5e9e-89b9-12aec0d5b5a5 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested - The LL may also be inferred (where appropriate) from the Cone Penetrometer Limit (CPL).
d30e3560-afd1-52a2-8f65-b6d210a42614 | note | Standard / Specification - NZS 4402 Test 2.2, NZS4407:2015 Test 3.2.
a713b910-3257-556a-9998-d526eb484870 | note | Verifying Document - IANZ Lab Reports
a5c57916-56d9-5d29-af16-60561b046e11 | note | Frequency - 0 to 400m³ - 2 tests
21aff8b0-4190-58e3-b6a3-adfeb9ecaf07 | note | • 400 to 1,500m³ - 3 tests
53416fef-9ded-5deb-968d-ff0c84a6ae6e | note | • 1,500 to 4,000m³ - 4 tests
9f8f13c3-7929-5ce0-9ab2-e9daeb8a08a1 | note | • >4,000m³ - 1 test for each additional 1,000m³
39b78350-5aca-5bbb-adb5-d1db03058103 | note | Activity - HP
d696f796-fd2c-54a7-ab30-edadea7c98b0 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.10 - Plasticity Index
adcce8e1-086e-5f16-8b3e-0792d22031b6 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
3ae28c04-98fc-56f1-97c4-9da685d1244b | note | Standard / Specification - NZS 4407 Test 3.4
62fef554-b15d-5bb2-8b95-655f9be8465b | note | Verifying Document - IANZ Lab Reports
115e070d-ecf9-51ea-9828-df026b036f6c | note | Frequency - 0 to 400m³ - 2 tests
ce1f32af-869e-5563-82da-4c6ea9d83866 | note | • 400 to 1,500m³ - 3 tests
2f47e4d6-a598-554b-9088-068be9d6f2a9 | note | • 1,500 to 4,000m³ - 4 tests
34a3e50c-cae8-5b0c-b74a-03f4ee673d85 | note | • >4,000m³ - 1 test for each additional 1,000m³
a1211ea0-d576-5ad0-99b7-8cc957e13c21 | note | Activity - HP
e436f6c2-4547-52cb-908c-cc19fa506125 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.11 - Clay Index
b2bbfdd1-90e7-590d-a1f7-de299ec76b03 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
093a4d30-4c15-5956-84e0-5830b526ba2d | note | Standard / Specification - NZS 4407 Test 3.5
dd67cab4-a009-5bce-9ac1-39c19dcb481b | note | Verifying Document - IANZ Lab Reports
05b26edc-dd98-518e-b6f6-98acf445836f | note | Frequency - 0 to 400m³ - 2 tests
d716371f-afa1-5e38-97ee-1ceafba9e5e0 | note | • 400 to 1,500m³ - 3 tests
cfde53d7-841e-512c-aeba-e555c5bbfc6e | note | • 1,500 to 4,000m³ - 4 tests
9487e901-321c-5011-a414-7a0ca08a6e9b | note | • >4,000m³ - 1 test for each additional 1,000m³
ff882013-d580-5e74-b60d-a144e998ad53 | note | Activity - HP
b2ba9321-be58-5b53-8cd5-881dd664d718 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.12 - Proportion of Broken Rock
aa0b256e-7b28-5996-9be2-1f852a1da5a6 | note | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves not less than 50% by weight shall have two or more broken faces
482ec926-0b1f-5da2-9eeb-10a9f0030d74 | note | Standard / Specification - PS - 7.2.2
e333c2ba-7723-57a3-87b9-4d16523a0be3 | note | Verifying Document - IANZ Lab Reports
15deb5f3-d612-5476-bd5b-d4b23829a0bb | note | Frequency - 1 Test per source of the coarse aggregate. Additional samples if source is changed
4155f610-28fa-546a-9fe8-f175b8d82a56 | note | Activity - HP
7617584e-1f14-5d96-9a6e-06795b8d0012 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.13 - Organic Matter
ce67a179-8cd6-5d21-9f2d-650078b91c33 | note | Acceptance / Conformance Criteria - It shall be free of organic matter
91d09f65-eb33-5b6e-a4fd-f93d0a7534e8 | note | Standard / Specification - PS - 7.2.2
e70cdb01-3c8b-572a-a18f-a87e1e5cb32c | note | Verifying Document - Photos
0809aba2-401a-5ffb-b7f0-475f02e5e2e3 | note | Frequency - Continuous
1934c074-cd46-5c96-bfb5-f5c8b3778de3 | note | Activity - I
51d07c23-348a-50b1-aa98-8690dd477705 | note | By - SE/PE
| checkpoint | 5.02.14 - Accelerated Weathering Testing
0192bd9c-f10b-5fc5-a61c-ba4f96f4b151 | note | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
b273779b-40d9-52f7-8241-3fbe6fe3df57 | note | • The levels of smectite clay minerals are not classified as “abundant”
4c242fa6-3cd2-5be1-9cb0-13424bbc41c6 | note | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
41b3ea5e-a1c6-5310-8a98-443fa930bc3d | note | Verifying Document - Lab Reports
bc7814fd-f2a7-5b94-85cf-ec53b9af7904 | note | Frequency - 2 tests per source 4 weeks before use in the works.
4b884df7-5ea8-59e9-9629-47b4389dc632 | note | Activity - HP
18d8d1e0-413c-5580-aef7-de3b62856bd4 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.15 - Repeat Load Triaxial Test
d09076b1-b61f-5eb2-974a-f781cc4d3ee7 | note | Acceptance / Conformance Criteria - In accordance with NZTA T15
013ba046-1451-5298-8bfb-78a4bb304c9f | note | Standard / Specification - NZTA T15
8935eef6-8e74-5a06-bfea-84643c31fb0f | note | Verifying Document - IANZ Lab Reports
dd0ece6a-d4e7-5fe5-8423-8f7e23a191eb | note | Frequency - 2 tests per source 4 weeks before use in the works.
8ec6d9e7-5281-5db7-b6ab-613f13e2453e | note | Activity - HP
0763efe7-8190-5247-9b7e-fcbced428056 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.16 - Unconfined Compressive Strength (UCS)
b95df1b9-16bd-5fb4-8380-6ce5ceb43701 | note | Acceptance / Conformance Criteria - Unconfined Compressive Strength (UCS) testing of source aggregate for modified layers to test sensitivity to additives.
8cbd082d-b3b6-56f1-845f-7ae5f4d52587 | note | Standard / Specification - PS - Table No. 7.2
9a5e5f78-ea85-5d1a-a3e8-bd1050b974a8 | note | Verifying Document - IANZ Lab Reports
16412a24-8bb2-55e5-8dd0-893f133e87c8 | note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
fbc17876-2779-535f-902b-4ff53d219016 | note | Activity - HP
76b1b5d9-289e-520d-8bd0-dfa2ec9522d1 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.17 - Indirect Tensile Strength (ITS)
e47a2fa0-3663-5f12-aad1-d62f108d6350 | note | Acceptance / Conformance Criteria - In accordance with draft NZTA T/19 at the rate specified in Table A7.4 using 4.0%, 4.5% and 5.0% cement (with 7 days curing) and results forwarded to the Engineer not less than 7 Working Days prior to construction for confirmation or adjustment of the additive contents.
e5bb67bd-1a40-5895-a4f1-d9bb7d80efb6 | note | Standard / Specification - NZTA T/19 - Table A7.4
e7824d9c-8295-5b65-8434-4efbe8a73f4f | note | Verifying Document - IANZ Lab Reports
e16db668-c136-5947-82cf-f976b5d3771b | note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
f1e2d0a3-a3cb-558d-bf43-fbe94d13b4dc | note | Activity - HP
397eeebd-78df-50e8-9e26-e4bf565540a5 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - Pavement & Surfacing - Basecourse - Rev 1 | itp | ITP - Pavement & Surfacing - Basecourse - Rev 1 | 33752cb8-b125-4be2-a64d-64570c780a4a
| section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 1.01.01 - Construction Pack
86b41d6e-7a57-54f0-acd4-9e40ed52643f | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled, uploaded and transmitted on InEight before works commence
48b32bc9-0a62-50c7-92a9-de4758e2d5b9 | note | Standard / Specification - Downer
c2407745-6aec-5335-a45f-487d44e0628d | note | Verifying Document - Construction Pack
635d558b-83ae-53b6-8c28-324ff841586c | note | Frequency - Prior to Works start
179c0622-56ca-569d-ba6e-cef8dd739f70 | note | Activity - H
07f5d58b-597f-5e2a-9f4c-03dbb5fe0c94 | note | By - PE
| checkpoint | 1.01.02 - Survey Setout
ec56372d-7f16-5af7-9f23-164babafc370 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
28cbcb6f-c9fb-5f99-97ef-82f133603fab | note | Standard / Specification - Downer
571e6655-cf54-56a2-9cc4-32c6cf1b01a8 | note | Verifying Document - Survey Records
f8e4441a-1fc7-5887-bc24-e5e60ee6611a | note | Frequency - Prior to Works start
b24be07a-99c7-505d-bcb1-651936634b9e | note | Activity - H
eb0f9fe1-4d71-5775-8d5e-50050bef0de8 | note | By - SV
| checkpoint | 1.01.03 - Service Location
cd865226-1847-5604-87bf-c74fdf0f19a3 | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
806a9f08-5828-5c64-bc3e-a0cb61d5562b | note | Standard / Specification - Downer
5ddce83b-fb05-5414-958c-e8cb3781aa33 | note | Verifying Document - Excavation Permit
867bcb55-3fec-55a1-b73e-5f950b8c745d | note | Frequency - Prior to Excavation
f7a63b5b-8d8b-5f81-ba95-3bfcd9af5f72 | note | Activity - H
b2a6ad39-f65a-58c5-b7c7-7bde258f6dd4 | note | By - SE
| checkpoint | 1.01.04 - Internal Permits
8ef54786-5417-587e-b131-af96f335f981 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
d05b2ec1-4b76-5f23-95bc-f96aab74703d | note | Standard / Specification - Downer
3480ef1e-9618-5dc4-a9a1-7d1d972a0262 | note | Verifying Document - Internal Permits
5674f571-bbd2-58e6-ae20-7a40c27a268a | note | Frequency - Prior to activity being undertaken
21fbf00a-0cdf-5c56-b06f-31055c0966db | note | Activity - H
c5e199e6-c2fe-53c2-9477-f27de993e720 | note | By - SE
| checkpoint | 1.01.05 - External Permits
61f5d04c-2805-5c3f-abc9-de003443ecb3 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
fe163655-f22f-5068-bc08-29a102908d62 | note | Standard / Specification - Downer
9f87a84d-c1e7-5534-9993-4b54a1767bfd | note | Verifying Document - External Permits
843356da-df80-5dec-8e71-df4baaa2d60a | note | Frequency - Prior to commencment of activity
33c77b62-d5e6-5d1d-bf39-72822d0fa627 | note | Activity - H
093b1822-81bb-5110-af70-8af678b7a11e | note | By - PE
| checkpoint | 1.01.06 - Approved Construction Drawings
faadc6af-5fc5-5d53-850f-a7ec9dc5cd62 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
4bb0d13c-160f-5d2a-8221-f236cbe9a59b | note | Standard / Specification - Downer
ce420d1e-c0ed-5cdd-aa45-43bd7850568d | note | Verifying Document - IFC Drawings
5e753f69-7365-5fc6-9c5a-7b100bcdf085 | note | Frequency - Prior to works start
4b246132-854c-59e0-b14e-8bf9a1b68ab3 | note | Activity - H
b25acc76-bd2a-5e63-a65f-bfc35c711d0e | note | By - PE
| checkpoint | 1.01.07 - Subbase Approval
0c114bd5-9799-56e0-b63a-0ad5d4fb9e0b | note | Acceptance / Conformance Criteria - All subbase QA to be sent to Engineer for review 48 hours prior to placing basecourse. Final inspection of subbase required, looking for any cracks in stabilised pavement and pavement is clean, free of and contamination
22226472-fa19-56c0-a111-b205214c4dad | note | Standard / Specification - PS - Page 42
854702a8-e776-568c-a112-a6486a17a17f | note | Verifying Document - ConQA
a90e1905-ceb6-558f-80c3-6a4abce9955a | note | Frequency - Before proceeding to the next layer
29b3dba1-842b-5a4e-8b73-4613dc36d483 | note | Activity - HP
a16e36c3-e5cd-5bfe-99b1-d56bc2c4dbae | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
| checkpoint | 3.01.01 - Average Uncompacted Layer Thickness
dbbd429c-71bb-5812-85da-dcc9a18eedc9 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
a371278e-8f76-5b57-b0e1-d6b44c03d6d2 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
b40b0852-21dd-5607-a013-f8e6812c5725 | note | Verifying Document - Survey / Level Checks
8ead24d5-9c8f-5d9f-b807-27ff02162e82 | note | Frequency - 1 test per 20m
030068ab-38a5-5036-82f6-7ac7a7c1bd1e | note | Activity - I
659025bf-5cfa-55f8-856f-5b915f8d83d3 | note | By - SV / PE
| checkpoint | 3.01.02 - Basecourse MDD and OMC
9fb00a71-854c-50c7-beeb-d555fad763b0 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test to be at heavy compaction vibrating hammer, Test on Mat Samples on site.
d7dcc15a-3087-5bd3-8abd-001433a8da70 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
9938c1d4-af1e-54ec-ab05-56cbfcbe7dab | note | Verifying Document - IANZ Lab Reports
97c4a02d-759c-5772-a5d0-568ae3601e2a | note | Frequency - No less than 1 test every 5,000m³ (in place)
667eba4a-5457-54fb-b177-accc707507cc | note | Activity - R
02b79946-e421-55fa-8f12-ece77e587346 | note | By - PE
| checkpoint | 3.01.03 - Plateau Density Test
92929d68-63f0-57fb-ac65-531cb6e97659 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
7ae1ef54-9208-5e9a-9fa2-285c104c3707 | note | • Every plateau to be completed at start of works and witnessed by a member of BBO.
80a36b75-0644-57d6-b71a-01cbf8adf488 | note | Standard / Specification - PS - Table 7.2 - 2.3
1c6e177a-3638-54ba-b5da-acd2905a56f3 | note | Verifying Document - Plateau Density Report
23d37c95-78a9-507c-934c-2f3070031b71 | note | Frequency - 5 tests per 10,000m2
45af7d7f-9458-53aa-8eec-57f4e7c57ee8 | note | Activity - I
d61ec9d0-c82c-5d5b-b51c-8d408366ffc7 | note | By - PE
| checkpoint | 3.01.04 - Plasticity Index
e71f59ac-edd0-5e70-beca-82c70dca5b37 | note | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
b86b747b-e06f-56e2-b657-241efaf003a0 | note | Standard / Specification - PS - 7.2.3
c489a8b1-a8ea-5f82-80ba-4ff4eded1c9a | note | Verifying Document - IANZ Lab Reports
d0adc64e-bcd5-5457-86b4-ec52e3ab0aa1 | note | Frequency - 2 tests per 1000m3 (in place)
90bd30ec-e53e-5268-94dc-d9959a20dc19 | note | Activity - R
a78cabee-87cf-590d-9de2-bf174b81ae9d | note | By - PE
| checkpoint | 3.01.05 - Clay Index
3a8afc40-bfb2-549a-9089-5e6cbffcfc0d | note | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
18e72bbf-5f3e-5c0a-b3e4-b741b323ed91 | note | Standard / Specification - PS - 7.2.3
2cfd3280-099b-589e-b0ad-7f3ef4136fe4 | note | Verifying Document - IANZ Lab Reports
f2948c97-c966-5ad9-a79d-7bcb312db057 | note | Frequency - 2 tests per 1000m3 (in place)
3d3935ec-fb55-5601-bae8-b23d5ec8039c | note | Activity - R
512ba664-826d-5b63-aede-02a1b8d62ee4 | note | By - PE
| checkpoint | 3.01.06 - Sand Equivalent
e166ae74-624b-5e5b-8d9a-3a8218aff852 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
de055241-e1a2-5d0b-af5e-54efa88d6216 | note | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
3bcda7c7-cfe0-5d4e-9e67-ea1bf377c756 | note | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
c0544496-3ce2-5232-addd-e6938e540abe | note | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
95f11bf1-a8e0-5084-9d61-adb3d2756506 | note | Verifying Document - IANZ Lab Reports
a9ad710d-e165-5ea8-9e4a-195b132d5d53 | note | Frequency - 2 tests per 1000m3 (in place)
dc69b47a-7de9-58a0-8dc6-5dfc49859c1a | note | Activity - R
9a56c638-031b-545e-9eb5-c0d4183f3245 | note | By - PE
| checkpoint | 3.01.07 - Particle size distribution
dc243aeb-782c-5f73-b035-5d90192571f4 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
b0c97723-290e-5e45-b606-54c180dd52e6 | note | Standard / Specification - TNZ M/4: 2006
c9462b1e-4a16-5f8f-a838-4b695ad099c3 | note | Verifying Document - IANZ Lab Reports
de976264-2028-5f1e-8b40-58405ee4b2d9 | note | Frequency - 2 tests per 1000m3 (in place)
b5a313f0-8f07-5136-8235-a6fc300ace71 | note | Activity - R
b094c546-d0d7-50d0-91ac-5751b343c6f2 | note | By - PE
| checkpoint | 3.01.08 - Basecourse Pavement Layer Compaction
8450682a-d54d-54ca-a371-5bb0648b9165 | note | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95, Backscatter.
8e0dcf5b-a8df-5f00-b697-e5b4bce57cf6 | note | Standard / Specification - TNZ B/02: 2005 - 7.6
b8033767-e17d-51ab-bb92-a013d34318a7 | note | Verifying Document - NDM Report
bab4c537-af20-54f8-af38-8deb39ed41a2 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
278f4a50-e7d8-5134-80fb-5ad235f4576a | note | Activity - I
3423ebfa-0c74-5182-b8a1-5bd4e9ada4e3 | note | By - PE
| checkpoint | 3.01.09 - Surface Shape
aa160684-d90c-5c2f-8670-9c7345013797 | note | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
6fd83484-45a3-58f8-9dfb-7c1c0a96d94b | note | Standard / Specification - TNZ B/02: 2005 - 7.7
96340ffb-3e65-5eac-96b6-68c84daeac5e | note | Verifying Document - Survey / Straight edge Report
baf33aa0-13cb-5856-9ee2-6358746e87ea | note | Frequency - Prior to sealing
c7ebfe0c-56a3-53c5-927d-4715673a2ac2 | note | Activity - I
2e63751b-2609-5a3d-a6ec-0035cf8985f6 | note | By - SV / PE
| checkpoint | 3.01.10 - Holding Water
9d5e3f97-39f7-5393-8985-e46df7d9353c | note | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
9e6d2939-557c-5f76-9ccd-0aaf26976c71 | note | Standard / Specification - TNZ B/02: 2005 - 7.7
e2d3939b-60a7-5161-99e9-c40aa73acc53 | note | Verifying Document - Visual Inspection / Site Note
a9885a41-188f-5625-9424-581588ef206f | note | Frequency - Prior to sealing
c2a0b25b-48f3-5d30-9933-3bc05f48181c | note | Activity - I
a5393c6e-4bf8-5dc9-b8a0-9fe9bf6779f0 | note | By - SV / PE
| checkpoint | 3.01.11 - Maximum Width Variation
c54a8880-c803-53c9-905e-907270e1e49d | note | Acceptance / Conformance Criteria - Unconstrained : –20 mm +100 mm
4f2614cf-5d0f-5220-b839-2250b118dac0 | note | • Constrained : Zero
0a07615c-bdc7-587d-93e7-0fa6ef846f00 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
509cb0c4-b4c6-5133-83a7-abddb21b59b5 | note | Verifying Document - Survey / Level Checks
8546fa8e-8880-5859-9034-8b5f93cc0f54 | note | Frequency - Before Next layer or Surfacing
88f457ae-d9e2-5dda-96de-604c02b89acd | note | Activity - I
1b214982-fb22-5d0e-ad43-16521eead8bc | note | By - SV / PE
| checkpoint | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
b4a7ebbb-018c-5af9-9c36-b41eb6e36384 | note | Acceptance / Conformance Criteria - At or close to the lip of channel: –5 mm +5 mm
a908229c-118d-555b-8caa-30536f9ea3d8 | note | • At other locations on pavement: –5 mm +15 mm
2a799e2e-2862-583b-9ee6-f85293c43566 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
f7bac258-a191-5284-b56a-383259c8f3bc | note | Verifying Document - Survey / Level Checks
b45a69e9-5f6f-5327-84db-99e2e8e8e8ac | note | Frequency - Before Surfacing
d88b2f97-bb88-5415-8669-2314cddde2d5 | note | Activity - I
732ddd51-a403-5cbd-8243-c72ee577856a | note | By - SV / PE
| checkpoint | 3.01.13 - Maximum Crossfall Variation
5c67f160-a2f0-52f8-bd42-ca23ee461ed7 | note | Acceptance / Conformance Criteria - The crossfall between any two points more than 2m apart, transverse to the centreline, shall not depart from the crossfall shown in the documents by more than 0.5%
ea889ddb-0e1d-5c83-bc77-c98178a4b221 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
9c527da4-f334-5def-9908-16581146a1d7 | note | Verifying Document - Survey / Level Checks
12ebf109-2be6-5908-ab45-7c266f20332a | note | Frequency - Before Surfacing
11e72989-7bc6-5b31-9135-f0d7b62160fe | note | Activity - I
888d745c-7ad7-5f0a-9f6e-38e8a8b6c5ca | note | By - SV / PE
| checkpoint | 3.01.14 - Benkelman Beam
4b5b3f0a-183d-5bad-a8f7-b0818fd4feff | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer. Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
8126b007-cc77-532a-bd21-14c073978c8d | note | Standard / Specification - PS - 7.3.2
44fa1f00-8205-5566-8533-f958b07c388e | note | Verifying Document - Benkelman Beam Report
09ab0245-b2b2-5a04-ace4-d10a308c257c | note | Frequency - every 10m of each lane – staggered between left and right wheel path.
be216873-42cc-5f8a-9ca4-94e7e2d5e346 | note | Activity - R
678cb500-e4e0-5f55-a9d7-eae559b8cca6 | note | By - PE
| checkpoint | 3.01.15 - NAASRA roughness
cbc72159-c7a3-5248-b9fa-4b94345cd365 | note | Acceptance / Conformance Criteria - The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. (Recommended but not required)
e65d3e44-613d-58e9-815d-8d6ee333a610 | note | Standard / Specification - TNZ B/02: 2005 - 7.7
f1bbe188-bfad-554e-9963-e3f3b39545ba | note | Verifying Document - Test Report
802ff844-fdea-55c2-93c0-8ab81c71a1f2 | note | Frequency - Prior to sealing
b5a75739-990b-5360-a212-bfef6bf93040 | note | Activity - R
f6c7ac08-c956-5cb3-9ea3-82b27ff339de | note | By - PE
| checkpoint | 3.01.16 - Running Course
6ddc7923-4ea0-538c-ae2e-d8a58e7ee576 | note | Acceptance / Conformance Criteria - If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface.
97ad3067-b7f0-5183-9345-e0fee5d98b01 | note | Standard / Specification - TNZ B/02: 2005 - 10.1
02bd5c5e-5d29-59e1-8ff6-cae122d46f05 | note | Verifying Document - Site Notes
f865adc9-6ac9-5412-824c-c1bc4657fe59 | note | Frequency - Prior to sealing
4f958e86-7437-5460-81fa-2c20b405c6af | note | Activity - S
307c7f07-0e69-5b30-9a9c-742cac6987f0 | note | By - SUP
| checkpoint | 3.01.17 - Surface Finish post sweeping
79301678-cdc5-526b-92a5-ec40a58b15ca | note | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
f1193419-55d8-5a46-bbc4-268999939f01 | note | Standard / Specification - TNZ B/02: 2005 - 7.8
2c5eaac8-6be2-5db5-9e07-971bcecf801f | note | Verifying Document - Photos
f4da713c-d90c-560a-bec2-643d270444e3 | note | Frequency - Prior to sealing
06cb4779-3c73-5927-bd81-50253589081b | note | Activity - R
650e5f29-2aab-5136-a6e5-352e41824e4c | note | By - PE
| checkpoint | 3.01.18 - Tie in into Existing Pavement
e47c839e-10ab-52bc-9da5-4b3f5302db06 | note | Acceptance / Conformance Criteria - Where tapering of basecourse including finishing layer aggregate is necessary to provide a smooth transition from the new surface to an existing surface, placement of the basecourse or finishing layer shall be stopped at the minimum uncompacted thickness specified in clause 7.3(a).
f49955e8-2930-5eaa-8fff-4aa29fef0f12 | note | • The Contractor shall then saw cut the existing seal at the tie-in (end of taper), remove existing pavement material and replace it with approved basecourse to an average uncompacted thickness of greater than 2.5 times the maximum particle size of the basecourse used.
79ff790a-0eb1-5f0b-bdb3-8bd78d10ad67 | note | Standard / Specification - TNZ B/02: 2005, 7.4
29ad3d21-5e2a-5945-88fa-8b02f6537760 | note | Verifying Document - photos, and survey data of undercut
bd7ebd18-69e0-5efd-ba7c-bb5f6c987414 | note | Frequency - Every tying into existing pavements
91296060-7787-5b8d-8503-893e4f648768 | note | Activity - I
623ed7a7-5277-5241-9051-22912d88a908 | note | By - SV / PE
| section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 4.01.01 - Survey Records
61996f2a-360d-58ca-b002-d0ec112979d3 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and record.
ef33a047-ce94-5d83-9ec1-97210b4bb05d | note | Standard / Specification - PS - Page 42
9f15b713-aa3c-537d-a7c5-4acc6e9e898e | note | Verifying Document - Records
ee3094fe-e7d2-51aa-bc36-b1fa4b41ea8e | note | Frequency - Post construction
ce7486bf-d5e6-58ba-9bf6-7f600631abc4 | note | Activity - H
beea42b2-951f-576f-9550-2639c1a409ef | note | By - SV
| checkpoint | 4.01.02 - Redline Drawings
6b4ad168-19a5-5e59-baa8-dd5981f8c644 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
e38cab94-b76a-53bd-a428-60832ee679fb | note | Standard / Specification - Downer
95e8391a-7508-5b76-8a26-3cf9c3b3a58b | note | Verifying Document - Redlines
1808be42-969c-5144-9ffb-757393ac708f | note | Frequency - Post construction
5e63c918-6e2f-5606-9087-3b173c5b56a6 | note | Activity - H
a8b3b982-00ae-54bb-bc28-91cd1ff00f38 | note | By - PE
| checklist | ITP - Pavement & Surfacing - Kerb - Rev C |  | ITP - Pavement & Surfacing - Kerb - Rev C | b9ad1a21-d922-4727-a5be-0c8eb017dc8f
| section | SECTION 1– PRELIMINARY - KERBING
| checkpoint | 1.01 - Survey Set out
7d955466-29de-5316-9cfa-6c42ea873290 | note | Acceptance / Conformance Criteria - As per design, the surveyor to install lift pegs
97b6a2ab-3b99-59f3-9237-51a91370b802 | note | Standard / Specification - PS - 2.2.12
26c38dfb-9763-53d5-b10c-409bef813166 | note | Verifying Document - As per design
4d3edfad-dd12-5daf-a5a1-d1bc12648f78 | note | Frequency - As required for Kerb construction
3826f264-8d56-5387-b812-a1268fcd05e7 | note | Activity - A
16ed9906-4cce-57a0-82c8-faa1220be6e5 | note | By - SV
| checkpoint | 1.02 - Kerb construction Set out
7348ea96-65f5-52e4-927c-1588f047e9f4 | note | Acceptance / Conformance Criteria - Ensure that steel pins and string line are in accordance with design levels and entranceways and kerb transitions have been marked. Tolerance +/- 5mm (basecourse level tolerance at channel edge)
9adb5bc4-eace-5244-a0fe-0a5e2bc7736a | note | Standard / Specification - RITS - Page 201
e2521931-9bbb-5066-8e60-a7482a2fc932 | note | Verifying Document - Visual inspection and measurement
a516095d-e0e6-5907-8bd3-1ba4d085c40c | note | Frequency - Prior to slip forming
dc8af7b1-bae9-5b97-903e-dc56e1da1340 | note | Activity - I
b1aa47bb-a769-516e-8eaf-3faecb7c4708 | note | By - SE
| checkpoint | 1.03 - Approved kerb and Channel profiles
8c78ac23-1bb6-51fc-afb5-2f1a9c74b6b5 | note | Acceptance / Conformance Criteria - As per drawing no. 146000-002A-1901
18fcfc32-240f-5474-adc9-80409f710992 | note | Standard / Specification - As per drawing
464ca852-6c7f-522f-8227-540c92e95b91 | note | Verifying Document - As per drawing
0949db91-0086-5b5d-ab2d-a8f6802232df | note | Frequency - Prior to construction
3515316a-d3d8-5a40-882d-b135bce1d1ee | note | Activity - I
b69c62b9-f656-5e4a-a6c7-a27855f15ba1 | note | By - SE
| section | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
| checkpoint | 2.01 - Approve mix design from Certified batch Plant
e9ef93c1-b0c1-5fd7-9d24-64764cef673b | note | Acceptance / Conformance Criteria - Material meets project requirements - 20Mpa Kerbing Mix
5a0ef905-ea0d-5046-bcce-41ec7bcddaff | note | Standard / Specification - Refer to RITS - 3.4.5.2 / 3.4.5.6
ef13bb40-cf14-58bf-bbb8-a682222869bf | note | Verifying Document - INSERT APPROVED MIX CODE
55cbc80b-03cd-5e9c-8a5d-801836757880 | note | Frequency - Prior to construction commencing
83948472-7d3f-5c90-8b83-f23ecd63605d | note | Activity - C
2465b951-f961-5f00-a62a-e1a9ced4f074 | note | By - SE
| section | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
| checkpoint | 3.01 - Survey Set out Confirmation
97b3a708-4ec3-5ea4-964c-3f03734ab723 | note | Acceptance / Conformance Criteria - Ensure kerb preparation is to design level.
923bc9bc-8d0e-535f-8ab2-f2d5c9e2bec6 | note | Standard / Specification - As per design
16f6083f-6ca4-5c31-988f-54abfaca1e06 | note | Verifying Document - Survey Records
792c7781-ea5f-555d-aebe-33c0d2cdf6e8 | note | Frequency - Every steel pin
1009bd04-9c5d-5563-9afe-afb34af2ca8d | note | Activity - I
8b77a263-a130-583b-a57d-6898303d9bff | note | By - SE
| checkpoint | 3.02 - Clegg Hammer Test
3e6f909a-0839-5771-b87d-7ce49744648f | note | Acceptance / Conformance Criteria - Only if kerb and channel is constructed separate to the road, the base that the kerb and channel is founded on - Clegg Hammer must be tested every 15m at 25 CIV (where applicable)
fb0bfa8f-da6d-54cb-a3cb-70013c6fdcbc | note | Standard / Specification - Refer to RITS - 3.8.2.10
2ef0d09c-ce74-5972-bd92-777b04b6e82b | note | Verifying Document - Test Records
4ec4f351-5c24-5ba7-8c69-1ece04a4c8bf | note | Frequency - Every 15m prior to slip forming
be6223ce-c3d6-59d0-a02d-464d8ffbb2dc | note | Activity - C
d025571d-7664-5551-b043-b5225791faf4 | note | By - SE
| checkpoint | 3.03 - Pre-pour inspection
45af77d9-6b82-5f2f-a0de-f716e11e7cb1 | note | Acceptance / Conformance Criteria - As per RITS specification 3.4.5.3, BBO Engineer approval to proceed. / reo-inspection with 24 hours’ notice prior to pouring
f03b22cb-36fc-5e0d-9952-4a8e452058fb | note | Standard / Specification - Refer to RITS - 3.4.5.3 PS - 2.2.16
be021b70-d6ba-5cf3-93ba-158dc14da3ca | note | Verifying Document - Visual inspection / Photos
bf852721-07f3-534b-8942-39cc933eba36 | note | Frequency - Prior slip forming
21a22d89-90da-54d7-b43c-0dadef67a690 | note | Activity - HP
8001cba0-7ef9-5746-9d63-52760940e199 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.04 - Concrete Cylinders/Slump
ddb9f5a2-1b90-5712-9e78-932c193136ba | note | Acceptance / Conformance Criteria - Minimum 20MPa strength, 1@7-days and 3@28-days
f8ebdf82-eed3-5dde-a8dd-6f55c7ce0d94 | note | Standard / Specification - RITS requirement (Drawing D3.3.3, Note 1)
5da12b5e-1aed-553b-903a-b2fb4fe361ea | note | Verifying Document - IANZ Test Records
d7d20e1a-f544-582c-9f56-08e2a8eae494 | note | Frequency - Each pour day
1ed0ab54-0805-545d-9def-36e384b5e2ba | note | Activity - I
d6de34f8-b1bd-533c-8817-8055611e107c | note | By - SE
| checkpoint | 3.05 - Curing Of Concrete
2d7e457a-1623-518d-9b8b-a99d89e0a4d1 | note | Acceptance / Conformance Criteria - Curing period shall not be less than 36 hours
b3ff426b-615e-5670-8c03-c611187b5513 | note | Standard / Specification - Refer to RITS - 3.4.5.5 / 3.4.5.9
90535db4-5f9b-5af8-b3fd-b755221f2044 | note | Verifying Document - Visual inspection
75f8cc93-2962-5300-b563-0f9e23f9fee8 | note | Frequency - Throughout the activity
69ea095c-57d5-5861-a60c-8c201100e1e2 | note | Activity - I
398ec7d8-bfa2-56ec-a231-3e0b6ae49899 | note | By - SE
| checkpoint | 3.06 - Post-pour level check
cb1f1576-ba0f-5896-bed6-e6e7e8b0115b | note | Acceptance / Conformance Criteria - As per drawings
39811371-720c-5a52-8bfc-b16b362c0efe | note | Standard / Specification - PS - 2.2.12
28bc6470-95ac-59d5-833f-033cb02967a4 | note | Verifying Document - Total station topo and check prior to carrying on with further pavement layers
1f2a57e0-d01e-5bb3-abd5-3245436761c5 | note | Frequency - Every survey peg
ee1fe224-ff61-51df-b342-f316a7f93d55 | note | Activity - I
1c5b9fe2-4120-5d6e-a238-36aefb19ccde | note | By - SV/SE
| checkpoint | 3.07 - Contraction/Expansion Joints
ac9db46b-4000-5c9a-80ee-f2ac39bb4a78 | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m.
5a4c419d-4412-5b68-90ec-12aacb6786c7 | note | Standard / Specification - Refer to RITS - 3.4.5.8
bec91869-f51b-524a-9605-bd5f610022dc | note | Verifying Document - Visual inspection
0492c58f-995b-5fc7-b03b-1a99b0dc1fdb | note | Frequency - Every 3m.
ca5bb3a1-1e2a-5278-beca-5bb81b49f4f2 | note | Activity - I
be0b39af-554b-5a1f-b5d2-8b6597f4d8b8 | note | By - SE
| checkpoint | 3.08 - Concrete Mix Dockets
c9399c42-c5a4-5deb-81c7-357117b23aff | note | Acceptance / Conformance Criteria - Matches approved mix code
13d4a077-ec71-502a-a1b6-21162c175b8a | note | Standard / Specification - As per approved mix
5bf57c96-5735-5dde-b4a4-c6d7f111b5d4 | note | Verifying Document - Dockets
b6326348-0f0d-5545-9428-805af4e2b492 | note | Frequency - Every truck load
1c065f24-baba-5f32-8ac5-e99b9f1fc80b | note | Activity - R
273e9cba-6eca-542d-bd1d-cba2738f7296 | note | By - SE
| section | SECTION 4 – POST CONSTRUCTION – KERBING
| checkpoint | 4.01 - Post pour inspection
0f047b9f-8ee3-5bed-bca6-d64c1e72f853 | note | Acceptance / Conformance Criteria - Acceptance and sign off by the client Engineer.
83e48047-0b11-5148-b984-ddbddbd42a89 | note | Standard / Specification - Surface finish and levels acceptable
65bb29c0-80b3-5be3-af8d-d2bac7629509 | note | Verifying Document - Review of total station topo
7f87d946-d5b3-5d3f-ae15-7bbc4d7301c6 | note | Frequency - When work is complete
bdae422c-284e-5c67-b1f0-ebc7fa266e5d | note | Activity - I
169369f3-d955-5506-be6d-13c132ead951 | note | By - ENG
| checkpoint | 4.02 - Redline Drawings
8b1b8286-6eed-5797-a9a9-39828abdaf1b | note | Acceptance / Conformance Criteria - Electronic points file to be provided
0d50a8b1-6c63-596e-9ab1-a03435d3780f | note | Standard / Specification - PS - 2.2.17
e5705a29-9315-5b47-bd59-c92ee73bb244 | note | Verifying Document - Total station asbuilts
96c33f0b-bf83-5f1c-b914-125971f39f41 | note | Frequency - When work is complete
b93fa637-87ea-53b9-8322-c0f6c07828c0 | note | Activity - A
bf15c63c-7bb5-5654-9fd9-d3b4d797c932 | note | By - SV
| checklist | ITP - Pavement & Surfacing - Sealing - Rev 1 | itp | ITP - Pavement & Surfacing - Sealing - Rev 1 | 5d91c9cd-e20b-412e-acdf-1cd05718ba55
| section | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
| checkpoint | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
f72cc165-27da-5cd3-a2a3-8738244d63b5 | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
423c1f2c-1b85-59ee-8837-db3ca86913c7 | note | Standard / Specification - TNZ M/6: 2019 - 4, PS - 7.2.8
1e6e13d0-5040-53d8-a28e-9351742ac8da | note | Verifying Document - IANZ Lab Reports
b5fef9e4-b133-5ca3-aebb-24d6529f7588 | note | Frequency - 10,000m3
0702d244-1f93-5b2d-8150-2e02e09d0069 | note | Activity - HP
656e0c67-8bf9-5da6-a7f0-979ef2070a8f | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16.08.02 - Sealing Chip - Production Property Test Sampling
59d0648b-965c-593d-8c54-ee1f33d05fdf | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
0778486d-802b-5642-b787-54b28b889813 | note | Standard / Specification - TNZ M/6: 2019 - 5, PS - 7.2.8
71a87208-8ff3-548d-b433-5608c6ddf464 | note | Verifying Document - IANZ Lab Reports
7224cf73-2afe-5bed-822b-111c2b0a2550 | note | Frequency - 500m3
66a555cc-52d6-5318-9e0e-990e309fedc7 | note | Activity - HP
c9c0dd8c-5162-5885-93bc-dfc24d77576e | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16.08.03 - Bitumen
a4923ef6-0f75-58cb-87e4-5fab4ca68408 | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
9407e156-6df1-5d9d-b127-2eea90e91ff0 | note | Standard / Specification - NZTA M10:2020 - 2.3.1, NZTA M01-A, PS - 7.2.8
54c4067b-6883-5adb-9b44-8a1a385fb181 | note | Verifying Document - IANZ Lab Reports
94a8dcbe-885f-567a-8ca3-44642a550665 | note | Frequency - Prior to use
2b3e5074-080a-5dd8-8c22-8959c9398141 | note | Activity - H
6de56487-3a96-5453-bffc-225d597963ff | note | By - PE
| checkpoint | 16.08.04 - Sprayer E-2 certification
c1ed1d90-0a52-5602-b37e-1d951a9dedb8 | note | Acceptance / Conformance Criteria - E-2 certification and is up to date
750c4b85-0fdc-555e-9f7c-71e36e534785 | note | Standard / Specification - BCA E/2 Specification
8deada11-0ecf-5e45-8b19-e048947f9d87 | note | Verifying Document - Certificate
66742a5f-1fe3-5787-b935-c3b3e56445d7 | note | Frequency - Prior to use
d2acc12a-3ccd-5ded-91be-d3335f36ff2a | note | Activity - C
e315cf47-680d-58f6-a2a8-6ccd76b1ee3d | note | By - PE
| checkpoint | 16.08.05 - Sealing Design
9c9a2b3a-3972-5a7d-8895-4e4ec59e36cd | note | Acceptance / Conformance Criteria - Chip seal type, chip source, bitumen and/or emulsion grade, % kerosene, AGO and diluents, polymer (if applicable), sand report reports, hot application rate(s) including spray rates
85646657-8972-5bc1-a519-126ae5edaaba | note | Standard / Specification - PS 7.3.4.
17074ecd-fecd-57f9-92a3-b9081866afc3 | note | Verifying Document - Design Document
08a63143-714b-548f-927f-4814682e7088 | note | Frequency - Prior to use
c651762d-d5d2-5bda-8cb5-b9edd01dc852 | note | Activity - HP
66421952-0624-562d-af31-bae357bd0170 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16.08.06 - Bitumen approval
ef41b259-4f32-5713-aaf4-8c949aa03238 | note | Acceptance / Conformance Criteria - Applications for approval shall contain the information required by NZTA Q05 clause 4 and the testing information required by Table 5.1
b9cb265a-75c9-5f3e-a319-bc00a27e782d | note | Standard / Specification - table 5.1 of NZTA M1:2022
8a9787cf-c73f-5593-b9e7-8034e115c3c4 | note | Verifying Document - Report
3494da08-2937-55d7-be14-8cb442e30733 | note | Frequency - Prior to use
1ace09e4-9546-575a-86ac-9231abcff70f | note | Activity - C
8adbad93-1366-5fbf-9710-0a3b9e97c223 | note | By - PE
| checkpoint | 16.08.07 - Bitumen Quality
61d2add7-8f3f-529f-a4c6-2c9bdeeab619 | note | Acceptance / Conformance Criteria - All bitumens used for road pavements construction, supplied or blended by New Zealand-based bitumen blending facilities shall meet all the requirements of Table 6.1 or M01-A specification for the grade supplied.
3f47ea2d-af01-517a-b556-fa1a953cb7f2 | note | Standard / Specification - table 6.1 of NZTA M1:2022
3fa8115b-491d-5715-9759-01bb6995f189 | note | Verifying Document - Report
ae50f405-62a6-56c2-9693-183b399ada46 | note | Frequency - at least one test per grade supplied following delivery of a shipment into a bulk blending facility.
09b80dd6-dd9f-5329-a000-96a30cec77c1 | note | Activity - C
02ad4278-edce-5860-939c-4aa811a1de72 | note | By - PE
| section | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
| checkpoint | 28.07.01 - Sealing Procedure
dba6e33f-1c8b-5569-9fda-1cd45f031f5a | note | Acceptance / Conformance Criteria - Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, and Q/1.
a4a4f0c9-6e21-5f44-b95d-433b8ef1d6b7 | note | Standard / Specification - M/1, M/6, M/13, P/3, and Q/1.
5fc5d2df-ff01-5bd2-9ffb-10b00f3635f5 | note | Verifying Document - Methodology / Construction Pack
ed9de7e0-e62a-5439-b8a5-e510536d69f3 | note | Frequency - Prior to sealing
9f8e4f9f-c752-51d7-8bdb-f6a4a9129f2d | note | Activity - H
272e3268-25e7-5506-8897-5d0b5eb0b69e | note | By - PE
| checkpoint | 28.07.02 - Sealing Inspection
e13f8aab-ed03-55f5-8e78-f98b839e92bf | note | Acceptance / Conformance Criteria - Before sealing and resealing. A pre-seal walkover with the Engineer to ensure that the surface is swept clean of loose aggregate, dust, dirt and other deleterious matter and the sweepings shall be removed to the satisfaction of the Engineer.
281850fc-cf15-536b-9f5f-324fb470bcf2 | note | Standard / Specification - PS - 2.2.16
0f39351b-d7e3-58fa-b711-5f9a347a6ac9 | note | Verifying Document - Hold Point Release
112d7768-c8f8-57bb-ad76-f1cf1b734677 | note | Frequency - Min 48h Notice
f44c5759-933f-5e05-a26f-09374ba9092f | note | Activity - HP
157cd6f5-9fae-5594-9f70-b18acffa1e96 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 28.07.03 - Presealing Requirements
6bfc3f46-9301-5932-903b-18a175248417 | note | Acceptance / Conformance Criteria - Further to Clause 12 of NZTA B2, the degree of saturation of the basecourse prior to sealing shall be less than 60%.
e43ae18f-91be-5454-a63a-b509872abb85 | note | Standard / Specification - PS - 7.3.4
481fc55c-a247-558a-abe5-eef34f4994ac | note | Verifying Document - NDM Report
7e15df9c-a8d2-5ecc-adfc-72c8a3ed2d1b | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
2a6f4a94-045d-5ea9-8ab1-787a40b218e3 | note | Activity - HP
cc0fc382-4bdc-54b7-acb7-8d673f72ea57 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 28.07.04 - Adhesion Agents
714e7f71-3f88-5c80-b683-ebba7a9bc233 | note | Acceptance / Conformance Criteria - An adhesion agent approved and blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents shall be incorporated in the sealing binder.
9fcef9d2-abf5-544d-966d-7797e5229986 | note | Standard / Specification - TNZ M13
5a1c992a-9d0e-54bb-b63c-2f47a5134230 | note | Verifying Document - Site Notes
9a6c9667-0e13-5c8f-bf79-8ba0f02bbb4f | note | Frequency - Prior to sealing
957e939a-0437-509b-9cd1-d721bd205a3a | note | Activity - R
9c44be23-e462-51a2-a526-12d7653abe12 | note | By - SE
| checkpoint | 28.07.05 - Post Seal Inspections
4de718da-c59f-5c40-8b3e-057ea10e2816 | note | Acceptance / Conformance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
0f87b092-2b0d-5b7e-a8a5-64a8d21119e3 | note | Standard / Specification - TNZ P3
0dce8072-911c-516a-9a63-42116abbb3b3 | note | Verifying Document - Engineers Acceptance
b8cb5257-62e6-54ed-bd7e-097972155e2d | note | Frequency - Prior to TM removal and after final sweeping
c39f97eb-0abf-51ec-84e4-bd67e0b31185 | note | Activity - HP
30538ae5-fdf0-507d-84f3-4cb464919235 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 28.07.06 - Bedding in Chip
73313444-c073-515b-88db-5885511e9ac4 | note | Acceptance / Conformance Criteria - If no traffic on site to bed in Chipseal, 3 days of constant rolling with PTR's and laden HCV's will be applied to bed in the Chipseal.
f4f59b8c-77bb-5856-a645-e4801f47a3e2 | note | Standard / Specification - PS - 7.3.4
11d7b076-b24b-566a-9534-0d19043973b9 | note | Verifying Document - Site Notes
f72333df-bde2-5b2d-aeeb-28a6b881847b | note | Frequency - Post Sealing
81931cdd-bf2c-5546-b7ee-38044ba55f72 | note | Activity - R
4ddec918-3ba6-5820-8ba0-fddba1a45d6f | note | By - SE
| checkpoint | 28.07.07 - Surplus Chip Removal
ef706484-67aa-5993-8ad5-a5d28c1bc76c | note | Acceptance / Conformance Criteria - If no traffic on site, removal of surplus chip will occur 2-3 days after rolling has been completed. If traffic on site, sweeping and removal of chip will be within 48hrs.
2d0127d6-6d7d-5ab8-b035-c9fb11052ce8 | note | Standard / Specification - TNZ P3
0019d5cd-a080-599a-bf39-6dbee283253c | note | Verifying Document - Site notes
2e4999ee-a3e4-5d3a-80ba-71327225d785 | note | Frequency - 24 hours of completion of any section of seal.
7c70c37b-7cdb-5548-8118-d8554ac64740 | note | Activity - R
777fa846-33d2-508b-b217-ca42693a2721 | note | By - SE
| checkpoint | 28.07.08 - Chipseal Repairs
01937e39-1bfb-59ba-95cf-cfd96da7518d | note | Acceptance / Conformance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used
42158fc7-a86e-52a8-9201-74679aeb85d9 | note | Standard / Specification - TNZ P3
0bf8e279-9ac8-50a4-a204-62abf8cf26b6 | note | Verifying Document - Approved repair Methodology
ee3b471d-6939-5602-9644-fd38c86c7090 | note | Frequency - Prior to repairs
c0d25fdd-a140-5c55-b79c-71845879df7e | note | Activity - HP
0eda0423-5ccc-58ca-9b86-55421513367d | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 28.07.09 - Weather
2b32c452-707f-5c90-8adf-e5750f1e15d6 | note | Acceptance / Conformance Criteria - Ensure that weather is suitable prior to spraying & pavement temperature checked. Pavement surface temperature ≥ 10C.
8859ee9a-271b-54c7-9124-9a3ab5113dfa | note | Standard / Specification - Requested by BBO
c9d1dee2-1f09-54e4-9743-1ace0a24604f | note | Verifying Document - Site Notes
6195f572-a5aa-5e68-b3d2-b075afb7b1af | note | Frequency - Prior to sealing
c0d4ec4c-7ad4-5001-8a51-1a76af47a494 | note | Activity - C
ff877007-8fb3-5893-a34e-f93cbf8806f1 | note | By - PE
| checkpoint | 28.07.10 - Protect Road Furniture
33905c35-66dc-5422-bca0-d10eba9003dd | note | Acceptance / Conformance Criteria - Paper cover any concrete that could get sprayed by bitumen such as kerbs and barriers
813f33b5-0cc5-54d5-bae0-6d8c6db63a43 | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – 11.2.5.
1ae76e23-a4e2-5798-9c4e-a7d3daab8da7 | note | Verifying Document - Site Notes
02b452e3-3c94-547a-925b-3721bb9b11d9 | note | Frequency - Prior to sealing
ae6f69cf-c324-5cca-980e-1cc39acec6a2 | note | Activity - C
38846de8-a4de-51fc-8ce9-b2da71097d02 | note | By - PE
| checkpoint | 28.07.11 - Joins, Overlaps & Hand Spraying
5b9230a4-10bd-582c-bdd1-7427ce9045f6 | note | Acceptance / Conformance Criteria - Set up Spray Plan ensuring joins, overlaps and hand spraying is kept to a minimum; joins are not in wheel paths and overlaps are appropriate for curves, channels, straights
ef6da712-6974-5b5f-9560-3774b85e7112 | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11
ac3922fc-604e-5bf5-a54c-858085c3c2f0 | note | Verifying Document - Site Notes
380f76ed-c2ca-5f93-8d62-d09c60583e4a | note | Frequency - Prior to sealing
3cd1d841-702e-556f-8455-3c4a6a081375 | note | Activity - C
a6f72d9f-ead0-5257-bb80-bd4acd5db742 | note | By - PE
| checkpoint | 28.07.12 - Binder Temperature
0369770c-20bf-5e77-9cbc-4c9b666ce9af | note | Acceptance / Conformance Criteria - Temp. appropriate to base binder and additives +/- 10 degrees. Daily records
dd4e915f-62e4-5296-9b92-4a7572e088ae | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11
f9948422-218b-57c0-a169-db3d459da9f7 | note | Verifying Document - Site Notes
e2481c47-962d-5dd4-a274-5239383c5218 | note | Frequency - Prior to sealing
e514c9ce-b115-5273-afd5-6ccc70480e1b | note | Activity - C
9d75c0b4-1a1b-5a7c-ae77-8edd53c6ae5e | note | By - PE
| checkpoint | 28.07.13 - Binder Application Rates
16b8e348-6a57-51aa-9757-4e828599a2c8 | note | Acceptance / Conformance Criteria - Confirm spray rate is correct by comparing actual spray rate to that calculated. Note error in measurement increases as area reduces. Within 0.1l/m² from target on spray run.
8fe8f093-73ea-5fc8-bb93-56349251e1e6 | note | Standard / Specification - Requested by BBO
68c9a18f-0b99-505a-a999-e43d898af2e0 | note | Verifying Document - Site Notes
a2d0ac60-2a79-540d-b9d4-cf395a3e735b | note | Frequency - Daily
89d74fa4-a686-5c5f-b459-13ce3afb2eae | note | Activity - C
f18395c8-2757-5cd9-ad6b-67b6412136dc | note | By - PE
| checkpoint | 28.07.14 - Chip Application Rate
cebefc05-edac-519a-a52d-ba7f6e15b3c1 | note | Acceptance / Conformance Criteria - Monitor chip spread rate and compared to target, record volume of chip used
134a9b0d-32ef-515d-b97f-4f8762d20b07 | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11.3.7
60861daf-849e-59b6-8747-c19ed36c06b1 | note | Verifying Document - Site Notes
0784a178-482e-5ee7-ba3c-8a3d13346758 | note | Frequency - Daily
1d6ed067-6108-5e8e-87de-b6d4278e8d60 | note | Activity - C
39a55291-edb7-56fb-8bea-114c65df0b67 | note | By - PE
| checklist | ITP - Pavement & Surfacing - Subbase - Rev E | itp | ITP - Pavement & Surfacing - Subbase - Rev E | 0f5e5930-b295-4394-bef5-bf0647e45f2a
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
| checkpoint | 3.01.01 - Construction Pack
ec4e551b-3f47-528c-ae6c-fdfb3458be34 | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
eb1c5ab0-d958-5aff-9e01-8f56d5db5c3c | note | Standard / Specification - Downer
95e813a5-8719-5ac9-9ed3-db95c88daa4f | note | Verifying Document - Construction Pack
805d2c95-dc1c-508e-8b9e-fbca9c1eeaf6 | note | Frequency - Prior to Works start
fc39fb4d-ffff-5e1f-8d56-399758b18a65 | note | Activity - H
802be262-7e7e-53e8-b8bf-6038d6e34751 | note | By - PE
| checkpoint | 3.01.02 - Survey Setout
27f3be6b-b818-5263-817f-5ba924480d35 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
1f441f83-2c34-577a-90e0-73818924a2cf | note | Standard / Specification - Downer
a4fa1ba9-6110-5364-ab83-c9684041414a | note | Verifying Document - Survey Records
7fe5d102-a89b-537b-849f-5cc7bf99618c | note | Frequency - Prior to Works start
d378e4fb-1992-5af0-8e29-ab8e511f0e7e | note | Activity - H
ed48a75e-9faa-5783-b481-e3f0f2090547 | note | By - SV
| checkpoint | 3.01.03 - Service Location
07cf3e6e-2226-5ee4-b1f5-8fff7d3c89fe | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
e5694d8a-f45f-52e8-b573-2ce535af9e31 | note | Standard / Specification - Downer
b2970209-fe08-5050-ba93-b0537bd69e94 | note | Verifying Document - Excavation Permit
e872e4d7-566c-548c-8e05-f649772197fa | note | Frequency - Prior to Excavation
0ef56c5b-7c85-56e8-9a7e-aab9f6807218 | note | Activity - H
53f0bb53-59d4-5d30-9a93-b3b481462cec | note | By - SE
| checkpoint | 3.01.04 - Internal Permits
8f9ece01-d727-5876-8560-edbd9d82bcf8 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
a7ee36d2-9b73-5f58-b71b-db5ca41fe4a2 | note | Standard / Specification - Downer
85ad478e-6552-52d0-b8b4-54e1f7ffbc8d | note | Verifying Document - Internal Permits
93d4943e-f796-520a-9124-ecb481319afe | note | Frequency - Prior to activity being undertaken
ea702c86-97c6-5605-ba1e-bfeeb7f387ec | note | Activity - H
a2718418-fc15-5b59-89c6-07251b3f0c0b | note | By - SE
| checkpoint | 3.01.05 - External Permits
f23abc2d-c8ee-50ea-854a-9f64a7d9d86a | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
6b62d5fe-af97-5ca3-b301-bd92f2791dc8 | note | Standard / Specification - Downer
a02559dc-175e-589a-9b8a-8eab68d69cad | note | Verifying Document - External Permits
b2f5d673-8cc4-5dbc-8d75-deccfbe742fe | note | Frequency - Prior to commencment of activity
d3a90524-e3a6-5f9e-b9d3-b83ba77aa7bf | note | Activity - H
13bc7be9-6edd-55c9-a267-e302e9aee166 | note | By - PE
| checkpoint | 3.01.06 - Approved Construction Drawings
f56d4abb-1946-538b-aad6-86aea7955913 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
09117102-46e6-57a9-9743-cdcaf0e4e481 | note | Standard / Specification - Downer
46964b83-84c6-5336-b6bd-922be5cef306 | note | Verifying Document - IFC Drawings
39dfba69-75f7-5742-968e-a4c90dbb0b22 | note | Frequency - Prior to works start
68e4c5de-58e0-5dec-91c6-170e024e015a | note | Activity - H
3d527e69-1c47-5f3d-8273-fc7878a3c156 | note | By - PE
| checkpoint | 3.01.07 - Stabilising Methodology
f31947ca-c372-52b1-9187-bb4248d3254b | note | Acceptance / Conformance Criteria - Written approval of the Engineer with the approval of the methodology
a161a67c-8a7a-5dd1-9557-f02e91f6b027 | note | Standard / Specification - PS - 7.3.3
07fd60c0-fd43-5cf7-befe-31b3417972ce | note | Verifying Document - Correspondence
5f17963d-05de-50a8-9578-9003dcf71a00 | note | Frequency - Prior to stabilisation start
4c607593-a8eb-5c32-8ec8-95b0db6dee42 | note | Activity - HP
b8772278-c47a-56b1-a98c-0284beffbb55 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.01.08 - Acceptance of the SIL layer
f6339289-345f-5f4c-9a10-88376f46e5fd | note | Acceptance / Conformance Criteria - Written approval of the Engineer - All compliant test results for subgrade, SIL, all road crossings, storm water, wastewater, watermain, subsoil/pavement drains and any other activity that has been completed in the pavement area.
02730cba-a67f-5416-abdc-90b5998957c6 | note | Standard / Specification - PS - 4.8.3, Table 4.3
847b87f3-2330-5a62-abcc-ad8b65920f34 | note | Verifying Document - Hold point relesed / Testing reports
683e6528-9871-5c86-b102-a59b4f362661 | note | Frequency - All sections before proceeding to the next layer
c2f09181-52a5-56b6-a1b5-1c437cb54f45 | note | Activity - HP
ad1d82fa-b960-58f5-b406-029832fbcf42 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
| checkpoint | 6.02.01 - Sub-base MDD and OMC
f168b349-b948-59e0-834f-0b2ba45e5df5 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
94791044-7035-5d70-836b-5bd471f60add | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
72003631-2a30-59ed-9ccd-8bb41b9e6939 | note | Verifying Document - IANZ Lab Reports
a294e292-acfa-5d4d-8bb2-ac429ec82d86 | note | Frequency - No less than 1 test every 5,000m³ (in place)
f3890077-fa2d-5c9d-ac37-159c3531b5d4 | note | Activity - R
a55f805a-3e05-57ce-9887-0771a0f2e46b | note | By - PE
| checkpoint | 6.02.02 - Plasticity Index
1a02b294-b8c7-54a8-88ad-4b2eadf677b4 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested
de15fba3-2af3-5447-92e4-0ff93b28081b | note | Standard / Specification - Table 7.2
c8b38c01-7756-58f6-b0f0-b99d29d920dc | note | Verifying Document - IANZ Lab Reports
bfa862fa-eabc-5114-9532-f6da19c44f1a | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
bb7cea44-7b13-513c-8a99-abf001a2a74e | note | Activity - R
eadf6b0e-0f1f-54ef-b126-27840805effb | note | By - PE
| checkpoint | 6.02.03 - Clay Index
d48bd89a-2cde-500f-a65a-9c0ead3920c3 | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
24123e95-13ac-553f-becd-8e344e653d5b | note | Standard / Specification - Table 7.2
5041442d-2667-52e6-a388-347fcd1cc8bc | note | Verifying Document - IANZ Lab Reports
864c5f20-dd61-50e0-9e7c-7c6a82ee48d0 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
2c66b3e5-64c2-50ca-add7-1f48a636da59 | note | Activity - R
84b352e3-3712-5479-adda-d025a9ad206a | note | By - PE
| checkpoint | 6.02.04 - Sand Equivalent
ee50526c-e9ec-5c79-91e8-670f2c1bb39e | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
c3d6c15e-6c07-5af7-84c6-1527766f8f9a | note | Standard / Specification - Table 7.2
8181ba8f-30d8-5506-b06d-a29546a00eb8 | note | Verifying Document - IANZ Lab Reports
7f791590-653e-5bbc-b299-61b3e8ad6c10 | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
d7befb75-e056-5ad0-9068-054f15d42590 | note | Activity - R
068d12a9-5531-5e68-ad78-ad8c0ed428d7 | note | By - PE
| checkpoint | 6.02.05 - Particle size distribution
1a8c69dd-c0e2-5b47-94bb-913d372659c7 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1
ceeab263-cfbd-5a84-ae44-c53ca329d997 | note | Standard / Specification - Table 7.1
7ea3aa39-7de2-5b9f-a333-ab9d10071ce9 | note | Verifying Document - IANZ Lab Reports
836f527e-24cd-55ae-8a9c-b4fcff7cf69f | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
4df9e8bd-bbda-58ac-aec9-614f3c35ec32 | note | Activity - R
519ac218-21ef-581c-bc55-b73daef7619a | note | By - PE
| checkpoint | 6.02.06 - Average Uncompacted Layer Thickness
6b32e036-d252-594f-8ce0-3eb80aff0240 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
648b2fed-46ce-540e-9f51-a18bfb12ba86 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
a42810de-1507-53dc-be0f-446a8c7d0ee8 | note | Verifying Document - Survey / Level Checks
a0f4bd8f-6e11-51e8-bc6d-c882447e2666 | note | Frequency - 1 test per 20m
67978ffa-b835-59d4-9b56-3c8a6dad8a32 | note | Activity - I
72a4512d-e758-58f5-9856-07e0d6ca6500 | note | By - SV / PE
| checkpoint | 6.02.07 - Plateau Density Test
bc29dd99-a71a-51dc-8d02-33bf0f61312d | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
a31f8a84-a71e-59ae-80d8-12cc4a5710e9 | note | • Testing shall be at OWC.
a79e6939-4ab3-5aa1-a23e-dc5097a70f43 | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
4db60e69-808f-52cd-b326-970523d0b24a | note | Standard / Specification - PS - Table 7.2 - 2.3
d156f274-aee5-52c1-bb6b-8c7211c6a105 | note | Verifying Document - Plateau Density Report
22cb08a8-dbdb-5f03-aa42-cd222fd52a80 | note | Frequency - 5 tests per 10,000m2
0da96e90-93be-5ae0-8294-d4d6764a24d9 | note | Activity - I
bd2aacaa-57e0-578e-ab16-49fcbb5e5588 | note | By - PE
| checkpoint | 6.02.08 - Sub-basecourse Pavement Layer Compaction
a565c723-69ac-5886-b35c-2693ff3155e2 | note | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
3051c527-6171-5f07-a895-8e8d848accaf | note | Standard / Specification - TNZ B/02: 2005
fbf04794-d375-5824-a102-a8516cf4f602 | note | Verifying Document - NDM Report
001719f7-47b0-537b-8df8-97351cfd4bb3 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
4b955460-5c4e-5883-ab40-c8250043fc8c | note | Activity - I
6329ddc7-ac2c-5ed4-9026-9cdc6dfcb567 | note | By - PE
| checkpoint | 6.02.09 - Surface shape control
f6d19746-988e-53c0-bd07-7cf2bbecfe30 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
4a673db2-094e-5953-9808-6c7c3a311467 | note | • Vertical: - 25mm +5mm
3bda55bc-9b4e-5f0b-8a0e-8913bca49280 | note | • Cross fall: 0.5% on 2m straight edge
f0699e7d-4488-5930-bc24-e6bde8144145 | note | Standard / Specification - TNZ B/2
1b64c389-5f95-5892-ab77-39b0c10f8109 | note | Verifying Document - Total station Topo showing levels compared to design
2c19adde-02f1-5f99-b87f-abae30ebd503 | note | Frequency - Continuous
d69e2e2d-e889-5d9e-9ec6-25206323c908 | note | Activity - I
e95c8e22-5607-581f-acaf-8299ff2bd117 | note | By - SV / PE
| section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
| checkpoint | 6.03.01 - Stabilization Production Plan
c9ddb8f7-8811-5c24-a98e-4a7b7bde9d00 | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
da0f5c1e-3efd-569f-b2ef-0d62230cc56f | note | Standard / Specification - NZTA B/6 7.2.3
503a87ad-53dc-5338-b7d6-41d39018bdad | note | Verifying Document - Correspondence
4b686472-ead5-5dca-9e19-e1a7af89afd6 | note | Frequency - 48H hours prior sabilising commencing
cb4be3d2-1fc8-5f91-99ab-ff9da052c5f2 | note | Activity - HP
abad576a-df96-543f-9ab1-765a1ff468b2 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.03.02 - Longitudinal Joints
f2cfb2e7-40b5-5204-868e-224c0ffe7c5f | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
7b7caba1-a9c4-5c5d-a3af-5fea17a64691 | note | Standard / Specification - NZTA B/6 7.5.2
1ac5d31f-9758-50ae-9f72-48d864679110 | note | Verifying Document - Stabilisation Prodution Plan
9af7f4d5-44b2-586a-b84d-14083db10bdc | note | Frequency - 48H hours prior sabilising commencing
703a7061-48ec-50a2-bf67-28fd4c8b61f9 | note | Activity - H
3ecbad6b-6769-52d3-8371-9bae9e3e68bc | note | By - PE
| checkpoint | 6.03.03 - Stabilisation trial
aaf3fcc6-69cf-5107-bdd2-324afb462409 | note | Acceptance / Conformance Criteria - A trial shall be conducted on a minimum stabilised area of 2,000m2 to verify the performance of the stabilising operation and finished product prior to full scale production.
32d89166-cc92-5257-8a02-b42deb788bcf | note | Standard / Specification - PS - 7.3.3
fc6cde74-b4bb-53b0-8942-0552487547d2 | note | Verifying Document - Triall Report
835b815b-b849-51c9-8abc-91b75b5897e4 | note | Frequency - prior to full scale production
10b65111-54b2-5545-b5b5-be46c4838f88 | note | Activity - HP
c72f6072-5eca-5743-b96b-117fc11d2cf9 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.03.04 - Stabilising Equipment
b85e3249-9895-5172-a001-1466f4265669 | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
1ee3589b-5081-5efc-bdad-6aba26d6e9a5 | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
a3776b5d-7d91-53eb-bb08-1af17fb325a2 | note | Standard / Specification - PS - 7.3.2
3b65390a-1386-58dd-8d6a-5e763cde91a7 | note | Verifying Document - Plant Approval
88a73c18-536b-5f46-bb46-d7b80e90b423 | note | Frequency - Prior to works
83e5610e-6576-5395-a4fa-7274e96a60c7 | note | Activity - H
64cc6353-220e-5907-bfcd-449c0bc979dc | note | By - PE
| checkpoint | 6.03.05 - Stabilising Supervisor
4892293b-c97e-5f7b-8af6-863f1c449d64 | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
b82eadfd-0943-56e1-8a03-094e7c34f50c | note | Standard / Specification - PS - 7.3.2
3551a47b-12a0-5a1a-8ea5-7b63cff98b4c | note | Verifying Document - Supervisor Approval
8251bbf9-5e57-58ad-aee4-43bbe9f37c78 | note | Frequency - Prior to works
a4146f77-cb32-5f0c-9c04-6338cd5be9c9 | note | Activity - H
21f6550a-d45f-508e-b98b-d3e37a65df52 | note | By - PE
| checkpoint | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
04e2ce5c-fc23-51ac-b996-8b395cb81ee1 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
c79417a1-d3da-5554-8196-a20418d2f028 | note | • Vertical: - 25mm +5mm
be91c280-43e7-5a2f-b532-dea6df56a8d0 | note | • Cross fall: 0.5% on 2m straight edge
7ce457fc-836f-5cc6-a269-ba8371d1833a | note | Standard / Specification - TNZ B/2
84a096bf-3ee3-5f72-a1d9-f550bc29364f | note | Verifying Document - Total station Topo showing levels compared to design
038c979c-acff-5c79-bdf8-95a17d456d70 | note | Frequency - 1 test per 20m
25a6b6d3-0568-511b-98c0-be8b869b3e71 | note | Activity - I
80588976-67d6-54ca-9d40-618b6fdcc383 | note | By - SV / PE
| checkpoint | 6.03.07 - Average Uncompacted Layer Thickness
57abe783-f1ed-53d3-84cc-34e27300e213 | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
f3e06d3b-2107-5ca4-ab1d-8e980c44d108 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
b91bd336-8e5c-532c-ad9d-fea08ac6590e | note | Verifying Document - Survey / Level Checks
46a082e0-947d-55f6-9700-208f12e701e9 | note | Frequency - 1 test per 20m
b0e66bd0-e4af-5d26-8d47-bf34fe7b8ca6 | note | Activity - I
7b9507c3-415a-57b6-ad99-2fa7d63f6ca9 | note | By - SV / PE
| checkpoint | 6.03.08 - Pre Stabilisation Compaction
2de608fd-6034-5977-8b48-ace7c120a2de | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
c076cd42-6e8e-5b46-a0df-e078704d7870 | note | Standard / Specification - PS - 7.3.2
f288a3ff-d1e2-5f20-920c-7fa4a3abc914 | note | Verifying Document - IANZ NDMS
f0c423cb-1eba-5011-80ac-05005e695439 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
35184592-ddea-5789-9628-76295e981225 | note | Activity - I
5948452b-0aae-5278-993c-de000a64b387 | note | By - PE
| checkpoint | 6.03.09 - Pre Stabilisation Crossfall
7dcc80a1-3999-5c00-bfc3-bf293b8a8647 | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
cf25e97d-2159-5462-a6ce-4196b9d4293a | note | Standard / Specification - PS - 7.3.2
3b2b548d-399e-519d-9d69-9a2927c0b6b1 | note | Verifying Document - Total station Topo showing levels compared to design
5303e7de-4445-5c0f-9266-790d456b0644 | note | Frequency - 1 test per 20m Prior to stabilisation
de272e7d-a2c4-580c-9190-796fa51c3638 | note | Activity - I
ca2a2111-0158-5182-be1b-445174fedcb3 | note | By - SV / PE
| checkpoint | 6.03.10 - Stabilising Visual appearance
8f8865c0-7ffc-5b16-807d-503d621cbc5a | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
cf749d9a-5bf1-50bf-a203-7e3c464d3673 | note | Standard / Specification - PS - 7.3.2
aa34d7ad-4e05-5677-b27c-5f6f1411f00b | note | Verifying Document - Site Notes
69f6c763-0a03-51d9-bfa5-534ccacaf6ef | note | Frequency - every 100m
d91ec8a3-6ce2-52e2-80f0-1b03438f13ee | note | Activity - I
87e701c1-161f-5285-9b2e-cd20ebb3e36d | note | By - PE
| checkpoint | 6.03.11 - Cement Mat Test / Spread Rate
da3f72b4-b1e3-5657-808e-2bc54fe47d04 | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
24f9b6df-5b16-5895-9f6b-b49960501d8d | note | Standard / Specification - Table 7.2
94fee484-a5b3-5490-bb40-6bf4b0938f69 | note | Verifying Document - Stab. Sheet
99cdf68f-0152-5f34-b1a5-3760076113bb | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
7ddb2bae-c964-5cf3-8183-009d7060c3bb | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can applya
1cfad76f-afa0-56a5-94e6-cd4c58e6b657 | note | Activity - I
e92ba43f-b2f2-5c8a-9649-ee66f9671721 | note | By - PE
| checkpoint | 6.03.12 - Cement Average usage test
201f6146-1817-5edb-a22c-c29f7f45f2a0 | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
f17dd1db-7f20-5312-b139-97755128b80c | note | Standard / Specification - TNZ B6
749b65f8-ccd4-520b-90d3-1e9fdbd250c1 | note | Verifying Document - Stab. Sheet / Delivery Doc.
6586c6f9-d9c7-524c-beaf-40df78cc4131 | note | Frequency - Upon emptying the spreader and bulk tanker
914cde35-1363-5dfb-920a-556fed6e74b9 | note | Activity - R
658e3f08-7984-52e5-8b16-f6fa47795fdf | note | By - SE
| checkpoint | 6.03.13 - Control of cut depth
46b9f88e-99c9-5a60-a968-15cc96292ceb | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm. Without picking up sand from SIL
8f09f694-78a6-5532-93a0-59f7ad96ba2a | note | Standard / Specification - TNZ B6
4afa3e59-c79c-5e6c-b5c5-86d8c9c5c9b0 | note | Verifying Document - Stab. Sheet
2be0fa1c-b437-5b11-a13e-69e22b6f8b08 | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
ce80a921-3335-5a15-a8f6-c9b7326838fd | note | Activity - R
5f9d6dc1-3b64-5181-89c5-19a73f488add | note | By - SE
| checkpoint | 6.03.14 - Plateau Density Test
decd180e-26e7-56c8-a3c1-c00f8720c9e0 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
c865ae35-c13e-5881-99c9-18bc78a225a6 | note | • Testing shall be at OWC.
f64e7a3a-7098-52be-8784-a85fae85996e | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
177e1bb7-f470-50c1-bb79-20e420d6426e | note | Standard / Specification - PS - Table 7.2 - 2.4
f69b2107-9d61-5d1d-afc0-990e1ee682b7 | note | Verifying Document - Plateau Density Report
572e474c-67c5-55ad-aa87-750d7a624c7e | note | Frequency - 5 tests per 10,000m2
1e50156b-7f28-5a92-98ef-c62f718b4864 | note | Activity - I
f832f683-84fa-54d1-b808-402011fa634a | note | By - PE
| checkpoint | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
9a4fb5ed-bd27-535b-a022-bebf285b6004 | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1. A Wet sieve analysis will be completed within 4 hours after stabilizing
00eb80fa-3200-5417-b532-c46d18a37a6a | note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
c1e6242b-b982-5e22-a725-33ef54319773 | note | Verifying Document - IANZ Lab Reports
d2116d61-7adf-57d3-8106-1c51336749a8 | note | Frequency - 3 samples bag per stabilise day post hoe
a2dcec01-55c7-552c-b0b0-ddc1a435ae63 | note | Activity - I
ca9469bb-b5fa-592e-b002-a0f30567b1c6 | note | By - PE
| checkpoint | 6.03.16 - Mixed material testing (ITS)
e2b5c14a-af27-5eb6-b955-0adb175e234a | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
d688278a-6706-534e-8852-c900e1806fab | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
47d240fd-1755-530d-8cb6-4e1fc7b7bf94 | note | Standard / Specification - TNZ B6 7.5
773ab540-931e-5436-96b7-b637f29e940a | note | Verifying Document - Test Results
b5a4545b-eeba-56b5-ac7c-309e3f13ba69 | note | Frequency - 2 tests per stabilise day
9405b5d3-7923-5d1c-ab1e-7daadd0fb3c8 | note | Activity - R
a81873b5-9bab-5d3c-bab6-8f7d512b6321 | note | By - PE
| checkpoint | 6.03.17 - NDM Water correction
c25bbffd-26b9-5cd1-9007-ea0430d5425a | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density.
7094f35a-7333-5c0e-a9fd-b35dd164b270 | note | • Will get the Moisture correction factor from the Plateau report itself. That is the difference between the Moisture reading on the NDM vs the actual moisture when dried in the oven.
a4a8ac4a-1615-59b8-a711-d27a3ceeb43a | note | Standard / Specification - NZS 4407
d9b5523a-05b2-58fd-9e57-a9303f0304c4 | note | Verifying Document - Corrected NDM Results
9249129b-f15a-54ce-b381-d81ad35dac4b | note | Frequency - Per Stabilise day
245a86d9-a73e-59fa-aa80-37e87cd97e1e | note | Activity - R
8af1dd0a-24d3-5a19-a2b8-7017f0a60f45 | note | By - PE
| checkpoint | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
5d68a0f4-4196-5761-9790-d8be3e07e987 | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct Transmission
71e6b7a8-57ce-5ca8-a855-be653ee16563 | note | Standard / Specification - PS - 7.3.2
c38c893e-c4af-5435-8b10-5cea4af66292 | note | Verifying Document - IANZ Lab Reports
09c7affc-1350-5f10-b8e6-a01c82222f60 | note | Frequency - Min 5 Tests per lot 1000m2, minimum 7 days after stab.
f13edf28-3a07-5e5e-8f90-380006fa79fa | note | Activity - I
766ab5be-df67-5b77-9a8a-613a23d83192 | note | By - PE
| checkpoint | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
8b976792-3213-50e1-9b79-b17bfa92e2cd | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
bb1aaf06-ac2a-5c01-b59c-99c125149d3d | note | • Vertical: - 5mm +10mm
826abe9c-7624-52b5-81ae-9dba7f27ccbe | note | • Cross fall: 0.5% on 2m straight edge
c94a6cad-a425-5c8c-b31f-1d39bfc23390 | note | Standard / Specification - TNZ B/2
504e543b-ebf4-5caa-97da-11e2e571a421 | note | Verifying Document - Total station Topo showing levels compared to design
844977c8-ff1d-5b87-8ce8-15c352b20022 | note | Frequency - 1 test per 20m
d1b3ec14-8717-5fd1-aff6-6d207298a937 | note | Activity - I
7badf766-988c-53cd-9bbf-3c397b0a935d | note | By - SV / PE
| checkpoint | 6.03.20 - Protection, Curing and Maintenance before Overlaying
3d71e903-b505-5839-85cf-cc631955ea52 | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied. Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
2ccf6b0a-db10-5b23-b23c-8b040512c59a | note | Standard / Specification - TNZ B6 - 7.8
a1ab7aa0-62a0-586d-85bb-84e441f89c33 | note | Verifying Document - Site Notes
13fbbedb-5f36-5063-a677-5482008a00f9 | note | Frequency - For 7 days after stabilisation / Photos
aafc97a3-8cfb-53f8-b823-b6d7c5d4fecc | note | Activity - R
54e81eef-18ff-5283-8882-1692dfd66af4 | note | By - PE
| checkpoint | 6.03.21 - Benkelman Beam
86073cf5-cb7d-5788-8fad-6c6c432370b0 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
f46ea1ac-e9f1-5874-9372-f9aea3a5d9c8 | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
3efa5857-763b-54d3-8278-799e35daacd2 | note | Standard / Specification - PS - 7.3.2
9e77db51-97a0-5170-bcaa-6857975a2049 | note | Verifying Document - Benkelman Beam Report
265fb537-4cec-53b7-86ff-39b6861b114d | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
96390e81-b614-50bb-93c7-f3d2b0c95b35 | note | Activity - R
eb2d27cd-0b0d-5dd3-b96e-e4eb2ff8392a | note | By - SE
| checkpoint | 6.03.22 - MDD / OMC / SD
4f4ed41d-cb8c-59e9-8606-f95b6bac1490 | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
8ed938ff-2157-5aa2-ba7c-f6efdb4d2cfc | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
ec991d8f-7516-5322-a5ea-fb77853e2a97 | note | Verifying Document - Lab Report
f69218dc-8c78-51c4-8c14-62b6a43378b7 | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
8330547e-cf6f-5e95-ae6d-e1e3125e40a5 | note | Activity - I
8e65f206-c8d3-53c9-9d6e-4c3adf41f08d | note | By - PE
| checkpoint | 6.03.23 - Sub-base stabilisation trial
33db0125-cfac-51c2-bb13-8f2039ec729c | note | Acceptance / Conformance Criteria - After the sub-base stabilisation trial, prior to proceeding with further stabilisation.
97852424-7570-5606-b7c8-390f1c5314de | note | Standard / Specification - PS - 2.2.16
1b5a9b91-a178-56d2-a4d1-b6f3efed76b6 | note | Verifying Document - Hold Point Release
09d9073d-8a0f-5d5e-afa6-7c41e1c3daed | note | Frequency - Min 48h Notice
f548d775-5ebc-56b3-bf85-04c9216f346a | note | Activity - HP
bf8a7659-4300-5770-8079-4c595911ef49 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
| checkpoint | 6.04.01 - Stabilization Production Plan
4bc5963e-cd2c-51c9-aca5-69592b28e7b2 | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
71cb6c20-295f-57d5-a171-0161932e085a | note | Standard / Specification - NZTA B/6 7.2.3
a63946e0-13fc-5f8f-af3f-dd8702db5ce8 | note | Verifying Document - Correspondence
21058093-260c-502c-9a10-4289560be62c | note | Frequency - 48H hours prior sabilising commencing
e8b8790c-3ca2-5fdb-89d4-45c8244f3825 | note | Activity - HP
3f7f445d-4e23-5bda-9bff-1d2d926e9369 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.04.02 - Longitudinal Joints
22db6f42-ec9d-5643-90f1-7b79fa348ab3 | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
719e890d-d568-55b5-84e6-bed77f0f46a3 | note | Standard / Specification - NZTA B/6 7.5.2
78c93c41-abe6-58db-a342-afd7b48c2a61 | note | Verifying Document - Stabilisation Prodution Plan
6c9b5431-1a5a-52bb-9e62-0e81f150c6d6 | note | Frequency - 48H hours prior sabilising commencing
f59876a0-5a1f-53f6-b4bf-cb2e0bcdacd0 | note | Activity - H
1ced5c1f-5106-5c18-8962-145b62d99b22 | note | By - PE
| checkpoint | 6.04.03 - Stabilising Equipment
b8341bd7-673c-5dc2-808a-b5591245a41d | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
13969d9f-b85a-5f7a-9aa8-66e1e0edae96 | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
2deb8519-49c2-5487-9cf7-444377be1b25 | note | Standard / Specification - PS - 7.3.2
20980237-258c-5659-ade7-2366ac0b8b3f | note | Verifying Document - Plant Approval
5cdb0063-1c4f-5b26-af41-f8037bdb887a | note | Frequency - Prior to works
fd180c27-27ce-546e-80c4-4d43ec441f4b | note | Activity - H
3524338e-2ce4-5f52-b118-b96a05ccca61 | note | By - PE
| checkpoint | 6.04.04 - Stabilising Supervisor
840c29c2-0a8c-5ea5-ba9e-1cbbf8bf56ed | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
459a0a17-3115-50b1-8574-e577b9fa3289 | note | Standard / Specification - PS - 7.3.2
4931d8f6-9541-5ae3-bcab-bf8298c7c272 | note | Verifying Document - Supervisor Approval
527ee89c-1792-57ee-a5a9-287bcfcbc472 | note | Frequency - Prior to works
5f19806f-af48-5c20-b1eb-99d26cdcd076 | note | Activity - H
ed8cc6f7-ff4c-5eed-9210-4c62bf32bba9 | note | By - PE
| checkpoint | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
9d8c8e5e-11ce-58a7-860d-c33d6c7859b2 | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
616c8ede-e9b2-5437-b1f6-ce66bcd2f0e7 | note | • Vertical: - 25mm +5mm
bdb504a7-1ca9-50f7-b822-c9b3a4acf4c6 | note | • Cross fall: 0.5% on 2m straight edge
f92c3ee3-0fce-5b0f-8b35-7932831125a2 | note | Standard / Specification - TNZ B/2
71e702c3-1afe-5980-aab7-e902f1ec27f2 | note | Verifying Document - String sheet
69ce19e3-2200-5312-b708-210d89c586eb | note | Frequency - 1 test per 20m
5f7c86d0-2816-5f16-b69f-5c2bed0014c7 | note | Activity - I
16cf3505-f954-591c-92f1-db3b12cd003e | note | By - SV / PE
| checkpoint | 6.04.06 - Average Uncompacted Layer Thickness
9570be19-0fe8-57ce-bcb1-ef4816b0e78c | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
3aa0923e-f1c9-58dc-a8ae-da58cae7c067 | note | Standard / Specification - TNZ B/02: 2005 - 7.3
876ae953-7cdc-56d4-b12f-0969f34eb79e | note | Verifying Document - Survey / Level Checks
7eb6d98c-375e-576e-ac51-7e0c32aeb52e | note | Frequency - 1 test per 20m
1364f684-6351-556e-8189-03544cf0bdf0 | note | Activity - I
15f9afb4-4f6e-561c-9b64-85ec16932a31 | note | By - SV / PE
| checkpoint | 6.04.07 - Pre Stabilisation Compaction
395eae28-4c8d-59bc-bd7b-7283b16b67bb | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
614970bc-9f95-51d2-85d7-240c03166f66 | note | Standard / Specification - TNZ B/02: 2005
03cd9565-736a-5c41-b2bb-2c62bef5a03a | note | Verifying Document - IANZ NDMS
7d062746-9063-552a-8600-70c701e6de9c | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
819a1ad6-5e53-520b-ad5f-c702560be83c | note | Activity - I
ec31e201-c41b-5fc2-9b67-fefc9467feff | note | By - PE
| checkpoint | 6.04.08 - Pre Stabilisation Crossfall
9e8fe53f-a4f1-5780-8ccb-6c86d9016322 | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
71360f74-312e-57d7-bb04-30fff5aea2e0 | note | Standard / Specification - PS - 7.3.2
de23d183-7039-5637-980c-457a089db70b | note | Verifying Document - Total station Topo showing levels compared to design
60c78e68-7cc6-5c38-8fa6-1f1e015f1735 | note | Frequency - 1 test per 20m Prior to stabilisation
fc9d3184-55ac-5435-a416-d61089d7c36f | note | Activity - I
a514a1b0-5d8e-57ef-b0a0-53b72199740d | note | By - SV / PE
| checkpoint | 6.04.09 - Stabilising Visual appearance
5271a85c-4033-5182-87d5-e949d8805412 | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
7099c8a2-8d24-5440-a12e-deca0db77cbc | note | Standard / Specification - PS - 7.3.2
ea995418-cd6c-5018-87a7-dbda26d9543b | note | Verifying Document - Site Notes
51ab3f3a-0703-53a4-909f-ab0246c7ba52 | note | Frequency - every 100m
bbb26c31-a3d5-5e57-9c1f-0918ac1187c8 | note | Activity - I
26a05264-4d7b-5c54-8b74-ae3956ac22bd | note | By - PE
| checkpoint | 6.04.10 - Cement Mat Test
46c51070-6f39-5c90-b926-7f40ec685408 | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
f4280e81-30e6-5494-bf91-f3f1fd2bf034 | note | Standard / Specification - TNZ B6
e50e070d-6787-5c4a-9684-171f12480f21 | note | Verifying Document - Site Notes
797abd0c-2fe3-51b1-a8c0-306322b0abdb | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
6377a24c-c013-5ceb-a8f8-7b0711433e34 | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can apply
991cd70b-faf9-5183-8e93-ca3425890e1e | note | Activity - R
e201a738-c914-5bbe-ada2-7f7d94fe58ed | note | By - SE
| checkpoint | 6.04.11 - Cement Average usage test
68b97820-43ef-5f18-975e-3fc3c9960e38 | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
aca9e915-5aec-53eb-bc48-4f755a7c2c21 | note | Standard / Specification - TNZ B6
e3228326-a428-5903-8a5f-45c605273519 | note | Verifying Document - Site Notes
d679f51e-32a8-5a92-bb32-fecca5ba6b2c | note | Frequency - Upon emptying the spreader and bulk tanker
d541f030-6686-527f-a67e-eb3922abd445 | note | Activity - R
75111d96-39ac-520b-bbad-af92c278c2f1 | note | By - SE
| checkpoint | 6.04.12 - Maintain OMC during stabilising
67a7bf6e-5925-5f91-8b98-58f13ec66fc4 | note | Acceptance / Conformance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content by NDM
221c45c9-9783-5127-ae8a-4d9fdc76cb94 | note | Standard / Specification - TNZ B6
df070077-c6a5-5b64-b8fe-57ffd4c9d52e | note | Verifying Document - Site Notes
1d3ac4db-33db-5204-be5b-4cce824f0fa7 | note | Frequency - Continuous
afc29ce6-1580-50c0-875a-7d3aab9a5e13 | note | Activity - R
9db2b5c8-defd-582c-a4ca-837200747cbb | note | By - SE
| checkpoint | 6.04.13 - Control of cut depth
0ddfa63a-fd18-5bae-a74a-6c98f04519f3 | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm.
25ee1494-9d5b-5d4d-b5a3-a40e2a8cd101 | note | Standard / Specification - TNZ B6
ca9c51c8-b702-5df5-bf81-99449144462d | note | Verifying Document - Site Notes
37d1ce92-57b8-5546-b45e-95aa72e6d33d | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
9b9978ae-2445-5c30-b771-a7c7e932bc80 | note | Activity - R
479a411d-566d-5a03-84db-2ef8e0048266 | note | By - SE
| checkpoint | 6.04.14 - Mixed material testing (ITS)
182a9fe4-2949-5d3e-b7d3-fa5b4add3c9e | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
a16b5584-eb92-5996-a447-640616a6119e | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
794886b0-a9e7-5160-9efb-77c08cfa7659 | note | Standard / Specification - TNZ B6 7.5
d8b792e0-ef84-513a-be03-c931ca889de2 | note | Verifying Document - Test Results
aa8aa106-429b-510b-8ded-44d4974a6b19 | note | Frequency - 2 pairs of representative samples per day
2cce68a2-8e49-577d-8452-1338d837f301 | note | Activity - R
d9dd5959-3630-54c0-be19-04a149b58bc7 | note | By - PE
| checkpoint | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
1595fc51-d5fc-5df3-a8b1-0773e76f8c91 | note | Acceptance / Conformance Criteria - A Wet sieve analysis will be completed within 4 hours after stabilizing, and consist of a minimum of 3 sample bags per lot.
e177ed60-e00e-51b1-895a-acc923dfc0f0 | note | Standard / Specification - TNZ B6 7.5
b07b0c57-20d3-5c59-9388-46d75e9923ed | note | Verifying Document - Test Results
0c70ede9-d3ba-5994-b6d1-9957929423c4 | note | Frequency - 3 sample bags per lot.
574bf161-e84e-5d84-ae04-3162922faf6f | note | Activity - R
f1ad340c-ef06-5def-a22c-94cd6377d488 | note | By - PE
| checkpoint | 6.04.16 - Plateau Density Test
68a2ad58-5808-5d0c-819d-28b10696645c | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
6d0085de-57cf-557c-91b6-4672f368d027 | note | • Testing shall be at OWC.
d22a0b2c-00d9-5356-b5e9-2c972d6ecf9f | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
7bea7d1c-f70f-56a2-8442-27215f842acc | note | Standard / Specification - PS - Table 7.2 - 2.3
068b6962-d280-59ef-82e1-3d35849927d3 | note | Verifying Document - Plateau Density Report
6adfe101-3863-5448-b479-fed6fb6eecfd | note | Frequency - 5 tests per 10,000m2
6077f9fc-e466-501e-83cb-2e4a91af231b | note | Activity - I
87cbce07-02e0-52d7-a53f-d13045dca5c8 | note | By - PE
| checkpoint | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
b1a1c4c4-a226-5240-9436-4b643503254b | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct transmission
227b8354-585b-5405-b88c-7c7fcdcfeec4 | note | Standard / Specification - PS - 7.3.2
f36eb166-000e-58bf-be19-f92bb30d703b | note | Verifying Document - IANZ NDMS
cd6f29e3-2a32-5b63-ab04-d66b4b185db8 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
d9507bce-a48c-50aa-ab82-c8811ad35072 | note | Activity - I
58b68c5a-e4b7-5f89-a3b2-685edfa044cd | note | By - PE
| checkpoint | 6.04.18 - NDM Water correction
f071d565-d785-572a-922d-f08a064dbc0b | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density
2e044633-d7c7-5d9e-b5dd-dafff9d7c0bd | note | Standard / Specification - NZS 4407
836d50b3-7c26-50b4-baaf-bbe5282e1ec4 | note | Verifying Document - Corrected NDM Results
c8f85b5b-bbd3-5b8c-ab68-033d78da6733 | note | Frequency - Per Stabilise day
7e936f2b-4eb0-5b41-ab57-92180a1d77ef | note | Activity - R
83e332d0-a668-5154-84ac-e7fbc301bf14 | note | By - PE
| checkpoint | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
9526862f-91c5-5dac-95ad-70cd020f619e | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
6522fc0e-4196-5f03-afbd-9b75927f8d6d | note | • Vertical: - 5mm +10mm
f4863cc8-486b-5be9-a731-8bfa42984a1e | note | • Cross fall: 0.5% on 2m straight edge
6954ac89-9caf-5018-b91d-b28e25c03733 | note | Standard / Specification - TNZ B6 8.2
3daf20d1-728d-5007-97c3-0bb9105461f6 | note | Verifying Document - Total station Topo showing levels compared to design
d07c63a7-48c1-5be3-b5cc-1adac4534f34 | note | Frequency - Continuous
98fcf74d-8e60-596d-8907-88b9d7ef90f9 | note | Activity - R
bc888039-e7fd-5dc3-aee8-ae317a7d7b11 | note | By - SV / PE
| checkpoint | 6.04.20 - Protection, Curing and Maintenance before Overlaying
e92392ec-97c2-50e1-821a-33d79ed2472f | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied.
c8bc45de-bc79-5b30-864f-5bf260d7c2d1 | note | • Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
e0059b71-6b51-5fd4-8250-d3218d19768e | note | Standard / Specification - TNZ B6 - 7.8
c2673520-0068-526c-b733-bd1c5e249159 | note | Verifying Document - Site Notes with photos
c4df2b91-2813-55d7-a6f8-582b3ae81f62 | note | Frequency - For 7 days after stabilisation
5b871b77-b3c3-5fbe-b180-46fc780076ee | note | Activity - R
565020ac-19d7-5868-a1ba-35b0f8e9edd9 | note | By - PE
| checkpoint | 6.04.21 - Benkelman Beam
70de7fe9-6b26-586f-899f-398eec09a3f7 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
e954676f-2098-54d1-ab59-fe6251457716 | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
68252c7e-3e47-53cf-bf1d-ef2c070c1ef6 | note | Standard / Specification - PS - 7.3.2
81139e68-a273-5646-81ae-6695ea090e1f | note | Verifying Document - Benkelman Beam Report
053563ae-5872-575a-8948-c0b3e4514eb3 | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
bdccd325-dd78-5064-9cc2-edf57d634663 | note | Activity - HP
93770925-a868-5d26-a5e0-1f1fd3e3eb92 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.04.22 - MDD / OMC / SD
2630dcc7-1a5c-52aa-a82f-67d5bf7350e1 | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
173d78d7-805d-513b-b61d-766211856e8c | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
290efdc4-fa23-54c6-85e0-bab5dc5134d8 | note | Verifying Document - Lab Report
44cbef68-a14f-5753-a329-5e07e7fc9006 | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
b0f23bc1-17a6-5c33-b386-f2fee8d0dfe5 | note | Activity - I
fbe34ad3-62fb-5820-bbff-e6bdea491916 | note | By - PE
| section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
| checkpoint | 7.02.01 - Redline Drawings
e9831178-47b0-59a6-9d3e-db8fe82d67ba | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen mark up showing lot numbers and areas stabilised in different days including clear delineation of all joins.
42ae6479-0812-5f6c-9c07-a74a778776a8 | note | Standard / Specification - Downer
46a567d6-e788-5ef8-9b53-7728cb226c3d | note | Verifying Document - Redlines
52a691ee-b7b7-55cf-b940-d4a415e252dd | note | Frequency - Post construction
e23418a8-3819-5731-b4b1-40b53b1be0dc | note | Activity - H
c5e2fca2-dd50-5ce1-b220-2d2b1f521bff | note | By - PE
| checklist | ITP - Pavement Drains - Rev B | itp | ITP - Pavement Drains - Rev B | 07617a3d-1690-4fea-8873-e597f52837f9
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
f9f905ec-dac3-502f-bb0c-10f8858f0b9e | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
64202acb-dcc4-53ad-a7c8-b0edb777bdc3 | note | Standard / Specification - Downer
0e4649de-7aaa-5b42-b147-fc3af9edce0b | note | Verifying Document - Construction Pack
99e69b24-2ef8-559a-8b36-853cb81f4080 | note | Frequency - Submit 10 days prior to commencement of works
62f27ab6-cd9a-5e30-8824-fd5102c3dc6e | note | Activity - H
1c5f89a8-cb44-594e-9268-a2c140fb894e | note | By - PE
| checkpoint | 3.01.02 - Survey Setout
e8398258-2279-5bf9-a5b7-9ff664595e60 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
5816aeb8-9264-5828-b482-fe53c2cb6552 | note | Standard / Specification - Downer
f37c6830-756c-5cff-8a65-d31b68f3c4ba | note | Verifying Document - Survey Records
b09e40a4-5de5-5202-a114-0d8c5269a277 | note | Frequency - Prior to Works
ebc91c34-ab8c-5188-813c-aeae8fa3bcdf | note | Activity - H
ab80a7c3-9993-5b5b-bd1d-36bb7b2216d3 | note | By - SV
| checkpoint | 3.01.03 - Approved Construction Drawings
5dd3cf45-0f1e-5179-a129-76755e28ce4e | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
4986bf31-15c7-5782-b32b-ffc4e530cbcb | note | Standard / Specification - Downer
7091b149-f5f8-57d4-ba8e-474e7db85504 | note | Verifying Document - IFC Drawings
1fa87834-82d3-5a29-8c87-4ce1da32837b | note | Frequency - Prior to works start
d7a880fb-ee40-5de3-bed9-57e309c271d8 | note | Activity - H
ea67c3b9-7d45-549a-8fbf-e9469ca18927 | note | By - PE
| checkpoint | 3.01.04 - Topographic surveys for measurement
3270d049-2f44-501a-8d00-f1ee3abb8282 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
beb20a08-9dac-5a7a-8b7f-c9aa5fccf934 | note | Standard / Specification - PS 2.2.12
1c1d5108-bae1-5026-b409-4c885281efc6 | note | Verifying Document - As-built
65a51382-d93a-598e-8f98-972b6ebdbf49 | note | Frequency - Prior to works and Post Works
4749ceef-fab7-5f70-9251-d1ada48d7c50 | note | Activity - H
02840a85-27c0-527f-9ef6-145c8754fa88 | note | By - PE
| checkpoint | 3.01.05 - Permits
50807822-529d-505b-a163-5260822af788 | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
90b6e93b-e6e1-58c0-9936-c6693972fc15 | note | Standard / Specification - ITP Register
536c9218-f180-54c7-bfd0-48076237f10a | note | Verifying Document - ITP Sign Off
04cc1cf9-2d9d-5bfe-98df-804c10b36d4a | note | Frequency - Prior to commencement of construction activity
06a73eb2-aa91-559e-8f70-68e42bc28d2a | note | Activity - R
c4bc4db5-753d-5597-954b-c24cf6203150 | note | By - SE
| checkpoint | 3.01.06 - Stakeholder Management
86a06a11-d37c-5901-a3c7-4170d371020f | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works, Agree plans for maintaining access to properties during construction with landowners
7f6c4578-84b1-5cc5-bf3d-44319a87a4ad | note | Standard / Specification - Project Stakeholder Management Plan
1e9ebef0-55a8-5fdf-b99e-a12ee2df4cee | note | Verifying Document - ITP Sign Off
5566c7d3-d686-5ed2-b4bc-0bc271c44753 | note | Frequency - Prior to Construction with continue updates throughout the works
68b35d31-4a79-5437-badd-6b93a5b58f90 | note | Activity - R
bc6f5e99-7b6b-57a8-8e41-e1d5262397a6 | note | By - SE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 4.01.01 - Pavement Pipes
96b1a7f1-85cc-5d66-b770-6f76866fd3c9 | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 100mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
0f69f95d-6aec-5570-9b13-d8eacf3060b2 | note | Standard / Specification - GWS 3.2.1
4434c9c7-43b7-5f1b-8b22-c4453c52bad5 | note | Verifying Document - Datasheet
754a3cf0-725b-5cd1-a08a-e2d078c31fe7 | note | Frequency - Prior to installation
2d7c460e-131e-5907-8d9f-1c8f104f048d | note | Activity - C
cac7a427-106b-5f9c-b5c7-e4a37b7aeb41 | note | By - SE
| checkpoint | 4.01.02 - Pavement Drainage Aggregate (20/40)
3b6dca9c-61bd-5bc5-b686-03fbe0eeedfd | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/5 including gradings
2fae3c1e-3bfd-5ef7-9d9d-4dae40916943 | note | Standard / Specification - GWS 3.2.2 & 3.4
2b8f8a7c-4e73-59e1-83ff-4ef962505cf0 | note | Verifying Document - PSD, CR
af4c9b13-db0d-5519-aae1-62da809db0cc | note | Frequency - Prior to installation
eed3aa0b-0614-5487-9549-b87c73f1a53e | note | Activity - C
537db11d-3155-5bfb-ae34-d8a3c5ee89cb | note | By - SE
| checkpoint | 4.01.03 - Filter Cloth
d29b7dfc-b211-5b9c-9984-0ba0bf576307 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
28bad559-4928-5e5f-9f41-7122fcb75523 | note | Standard / Specification - GWS 3.2.3
43db19b4-f454-5c15-beae-a67d9cbde2bc | note | Verifying Document - Datasheet
e55becd8-4595-555d-beec-d2ea73ad571b | note | Frequency - Every 1,000m3. At least two weeks prior to works.
56a52d32-7c27-5128-b939-c78098c959da | note | Activity - C
6976b6dc-e081-5550-a1e7-0468e98a8f95 | note | By - SE
| section | SECTION 5 – CONSTRUCTION ACTIVITY
| checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
9e165128-781e-549d-89fe-6ba0bca83d9d | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain.
75acbafd-f4b7-564a-8f2e-7e3b8e6175ac | note | Standard / Specification - GWS 3.2.2
2601e94e-bfc9-5ba4-9935-34bc6e32d41a | note | Verifying Document - Site Record
f1472b9f-081e-501c-97bc-997a7550c79a | note | Frequency - Prior to backfilling
574ae29e-835a-5d55-851e-15072719c473 | note | Activity - HP
2a1aa356-e8e2-5dc1-8a69-e3bee66a163c | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.02 - Trench Backfill
c32fb6b0-6d31-50b5-a9f9-b15ce15cb266 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through
a350e562-5565-563b-be45-c7de757f35e3 | note | Standard / Specification - GWS 3.3
eb589190-0764-5bd8-b196-ab9f89aeadd3 | note | Verifying Document - Site Record
ec64a5de-6292-5125-afc8-6e484dc921d5 | note | Frequency - Each trench
96223a88-c42f-59bc-8a2f-75d750191bf5 | note | Activity - I
0fe3e741-b0c9-5b4a-950e-675b8e7a8cb4 | note | By - SE
| checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
3c810906-ab97-5027-8b14-018bdbf84883 | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each pavement drainage system to enable flushing of the system once the earthworks are complete.
8625e483-70ac-58fa-a63c-5b505f19c155 | note | Standard / Specification - GWS 3.6
acf2d88b-83dc-5f64-9576-d0852ac6e813 | note | Verifying Document - Site Records
cdb25d2a-550a-504f-b06c-c084ae70a89e | note | Frequency - Each Subsoil Line
c9725a45-5a3f-5375-8852-34fce7841b01 | note | Activity - I
3fa79c56-5063-5667-b1ed-187effecba41 | note | By - SE
| checkpoint | 5.01.04 - Subsoil Flushing
146b43a4-7c16-57cc-a6cf-da5fc2dc11fa | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
3dc5f9d6-6b7e-598a-bcf1-9ef49a626c66 | note | Standard / Specification - GWS 3.6
40597163-48fe-5bb4-abed-f49a4ab3f727 | note | Verifying Document - Site Records
81138943-d4c0-5721-8706-938fd6ea6c1e | note | Frequency - On completion of earthworks
77f50290-a8cc-5b36-8fbd-7ebde75092c5 | note | Activity - HP
80964aa3-b2e1-5303-8e6f-9b2b7f6e2b61 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.05 - Survey
83dfab8a-5f1d-5b7b-a954-59c2747642a3 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
6c26521b-8245-5d7e-b411-4c900816384e | note | Standard / Specification - Downer
2c583d67-eb6e-53d2-b2ab-3baa3432b8a6 | note | Verifying Document - Records
f17845ff-202a-5027-9bf4-c357176b925e | note | Frequency - Post construction
35f5336e-12df-51d7-be76-3fbfd57b0294 | note | Activity - H
00a72da5-033b-540e-8cfe-fd04d992fbb1 | note | By - SV
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 6.01.01 - Construction Record Compilation
94904fe6-c43b-559a-aef9-d0a9d69d2747 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
76fe4fd9-d793-5a9b-9bb6-1ba89c817758 | note | Standard / Specification - Downer
41b86b8f-efcf-5168-92e9-5c3a7cbe723e | note | Verifying Document - Records
bf359400-b405-5c46-8907-c725b0286925 | note | Frequency - Post construction
c38a501d-bb9a-5874-b05e-cc342037f315 | note | Activity - H
4abd56a4-d3e0-50b3-b3f4-45abf498776e | note | By - SE
| checkpoint | 6.01.02 - Survey Records
342e2dfe-333c-563c-ac47-bf2ad8809947 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
3ecd713b-e021-58a2-b407-73e34039e4c7 | note | Standard / Specification - Downer
f2c7697f-6ab7-5136-85d0-2c87cabad9fe | note | Verifying Document - Records
b8b21edf-472a-5f12-821e-5aa99e216de4 | note | Frequency - Post construction
c05c2993-8167-58db-91d5-a3321df9a3e2 | note | Activity - H
a58f2874-0112-5df0-af4c-ec4b73c7c8fa | note | By - SV
| checkpoint | 6.01.03 - Redline Drawings
85b5a3e2-2bbe-5298-b838-18c0854aaacc | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
48e37755-862a-50fb-9b1a-5b2267c78356 | note | Standard / Specification - Downer
76233806-0448-5389-9e1d-3a92930e7685 | note | Verifying Document - Redlines
2d0fd7b7-749a-58dc-8dc7-75b5936b0277 | note | Frequency - Post construction
f3817025-ebd0-5ca4-a077-81025f6261cd | note | Activity - H
39ae6ec5-d5c7-5a26-9e5e-2bdfc068a03b | note | By - PE
| checkpoint | 6.01.04 - Defect, Snag and Punch List
f0159e04-a466-5fe4-adc3-81a376e60577 | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
c3d28e82-3281-543a-84af-218e8ea0f0a9 | note | Standard / Specification - Downer
59d7e756-18b4-5b6a-a587-817b68df5f6a | note | Verifying Document - Register
72cbc43b-53fd-515c-ad00-f2d831c67180 | note | Frequency - Post construction
95193713-c4ce-52ef-84a6-aad9ad724f57 | note | Activity - H
7316119c-849d-55ef-985d-6b8f77e1038d | note | By - PE
| checkpoint | 6.01.05 - Photos
03b319ab-784d-5a7a-a8b1-8411dd191456 | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
da852884-2aaf-536d-9dcf-952353840ca1 | note | Standard / Specification - Downer
b08880c2-7512-5591-b327-dc150a36a882 | note | Verifying Document - Photo Records
0b59f7aa-0b29-5389-a957-c398d4254551 | note | Frequency - Post construction
2f5bb31c-dc18-5378-b91d-1fb9c4ec1d18 | note | Activity - H
f0e156ea-88a2-5ba3-9cbf-1dd50dce592f | note | By - SE
| checklist | ITP - Pavement SIL |  | ITP - Pavement SIL | c16731ae-3527-42b0-9337-2cc6a8485ecc
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
| checkpoint | 3.01.01 - Construction Pack
4b26e7cb-ace0-58bb-a616-39483fc6b83d | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
39bdd60b-5a55-5725-9d44-67dc819f7e82 | note | Standard / Specification - Downer
f37b21b6-fe75-518e-99e7-441bb2e54568 | note | Verifying Document - Construction Pack
e20b4b8a-d1f3-5800-add6-1b620896d23b | note | Frequency - Prior to Works
2c256560-e7aa-55c9-98a1-86938a36f071 | note | Verification Activity - H
5aa00b7c-8cab-5b58-9c8a-a8ebcd4457f9 | note | Verification Activity By - PE
| checkpoint | 3.01.02 - Survey Setout
e3e94e95-7461-5602-8ae5-1f475a9a9372 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
a9ccfcea-23ab-5f83-98aa-01aa55f14f09 | note | Standard / Specification - Downer
bd924ba3-e98a-5a37-88f8-deb39c1915c3 | note | Verifying Document - Survey Records
21d5543a-b500-5bb2-b23b-7150daaf8fee | note | Frequency - Prior to Works
8155419d-e2cb-5987-8b90-4a5df3da5317 | note | Verification Activity - H
651d4ceb-5a87-5cee-aa2f-1d5af93f48ca | note | Verification Activity By - SV
| checkpoint | 3.01.03 - Service Location
beea7a1c-046b-5fb7-91cd-46b86eb7ecfd | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
8c0340ae-3f3f-57df-8af6-8836db439d12 | note | Standard / Specification - Downer
eaababd1-32a0-5323-ad8b-8e999dafd51d | note | Verifying Document - Excavation Permit
558c19e0-5e33-5b6a-a931-c34e81e92a2c | note | Frequency - Prior to Excavation
85387089-5afd-5a2b-974f-78eb26637df0 | note | Verification Activity - H
33484b60-704b-5d44-8ca8-0d2f7803fb57 | note | Verification Activity By - SE
| checkpoint | 3.01.04 - Internal Permits
24c5b6b2-98a4-589a-a0ad-fa73c558e90d | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
f1ead7c5-425d-5829-b8d1-0edd0ebada26 | note | Standard / Specification - Downer
7bc080ae-d60d-55ed-9e48-c9efb7f6d7ce | note | Verifying Document - Internal Permits
f051067e-abc8-58c0-96b0-6932e794b31d | note | Frequency - Prior to activity being undertaken
518ffaca-a960-5750-b6b8-c85a4e56025c | note | Verification Activity - H
cfe1cce4-c9a2-53b0-9062-99d2666b7ccb | note | Verification Activity By - SE
| checkpoint | 3.01.05 - External Permits
b2e25bb1-ceae-59ce-be7a-ac0fa86efbac | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
26281c77-fff7-5dd4-88f3-7e33e61e9cbf | note | Standard / Specification - Downer
fb232d0f-a63d-56c9-8cef-c489fe97494c | note | Verifying Document - External Permits
9e657bb1-bd49-5ffa-98e1-3b2ad9d187b6 | note | Frequency - Prior to commencment of activity
8037d5ba-0dd4-5d90-9102-4cba9dadd771 | note | Verification Activity - H
62198747-f56f-5a64-8a05-cde299bdfa49 | note | Verification Activity By - PE
| checkpoint | 3.01.06 - Approved Construction Drawings
bb46b8a2-0124-5764-b4dd-7bdf0e69e95c | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
f9faecd7-6ccf-5952-87fc-e7dc6b36747a | note | Standard / Specification - Downer
030bf603-8060-5f9d-9f7a-d5e4d6516677 | note | Verifying Document - IFC Drawings
73c5b094-94c7-5167-9ef9-037fd27c4209 | note | Frequency - Prior to works start
cefe589e-775b-5225-b22e-07aa1e40a577 | note | Verification Activity - H
434a1998-8714-52c5-bd16-87cddbd9fb72 | note | Verification Activity By - PE
| checkpoint | 3.01.07 - Previous Layer QA Sign Off
6983331f-cd49-553d-9d1b-2fb72a289629 | note | Acceptance / Conformance Criteria - All Previous layers signed off, QA complete. Including subgrade, SW, WW, WM. Ensuring everything up to the bottom of SIL is compliant.
915f2668-b583-53ab-a791-7764dde86a86 | note | Standard / Specification - Downer
77414674-0ef9-565c-bd1e-9e79630527df | note | Verifying Document - QA Records
f3a3f4b4-c411-555b-86c7-ecf46bcdf601 | note | Frequency - Prior to works start
c6466e5e-b003-544d-bb6f-6a7c079699e2 | note | Verification Activity - H
e1d16e4b-df18-54d6-933a-5129d5ba5833 | note | Verification Activity By - PE
| section | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections)
| checkpoint | 4.01.01 - SIL Inspection
589c641a-aa63-5852-9ee0-74bb69e89f17 | note | Acceptance / Conformance Criteria - Prior to placing of sub-base pavement, to include proof roll, inspection of extents of works, general shape, and tidiness, free of organic or contaminated material, review of Benkelman Beaming of the SIL and final levels.
63d5d160-5d5e-5d1c-8f98-de84fd1bffb8 | note | Standard / Specification - PS - 2.2.16
c3cb4613-e4f5-5cfc-b1af-22f8b68c2820 | note | Verifying Document - Hold Point Release
c154df35-5954-5684-b09e-81eb77940267 | note | Frequency - Min 48h Notice
af005a20-54f3-5277-886e-7af9e988939a | note | Verification Activity - HP
18fb0707-f3d9-5d50-af1f-10287369254f | note | Verification Activity By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.01.02 - Subgrade Inspection
ccdd5453-ce4a-5556-99a1-e628c9df66ef | note | Acceptance / Conformance Criteria - Proof roll, Scalar penetrometers, and shear vanes prior to SIL fill commencing
4bc1e182-7aa8-55c3-b605-7ac285d42607 | note | Standard / Specification - PS - 2.2.16
d3d56a58-b3ff-5de8-80eb-b959f7028b02 | note | Verifying Document - Hold Point Release
daf11b30-c8b1-541a-9e0a-1f48878bd249 | note | Frequency - Min 48h Notice
3f765b21-ec87-5fc9-b2c0-516f6ba42d38 | note | Verification Activity - HP
54909fee-8367-537a-913e-c78a0b548259 | note | Verification Activity By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials
| checkpoint | 5.01.01 - Pavement Subgrade CBR
b3e03a0d-8900-51ac-be82-923b82921d09 | note | Acceptance / Conformance Criteria - The pavement design requires a soaked CBR of not less than 10 within 1.0m of the bottom of the SIL layer and 4x DCP's to a depth of 1m below subgrade level in a 1m grid around the in-situ CBR test location and 4x NDM's DT with a probe depth of 300mm in a grid around the in-situ CBR location. CBR testing of the subgrade shall be carried out by the Contractor prior to final trimming. If the soaked CBR is less than 10 the Engineer may instruct changes to the pavement design. (Push tube for Cut and Filed sample for Fill). Invitation for engineer to witness CBR testing. To be accurate representation of site
8bc2d425-ceb7-5734-bb77-d28559cf4dd1 | note | Standard / Specification - PS 7.1
7a8b0934-9135-54fb-b2a4-e6b80a154256 | note | Verifying Document - IANZ Lab Reports
1086e7dd-eabe-514b-87d6-33b88e67f9b1 | note | Frequency - One test per 2,000m2, with a minimum of three tests per material type.
d8f0f437-a191-57db-ab63-ab5fa84405d2 | note | Verification Activity - HP
07eb9ac4-2f53-5c6b-9ec0-d3b5327d7a95 | note | Verification Activity By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | 5.02 - SIL (Clean Pit Sand)
| checkpoint | 5.02.01 - SIL Conformance
7b7cbf9c-e8ee-5e03-b9c4-19e9defd7ac5 | note | Acceptance / Conformance Criteria - The SIL shall be pit sand meeting the following requirements: · 4-day soaked CBR (NZS 4402:1986 Test 6.1.1): Shall be ≥ 30. · Organic Matter: It shall be free of organic matter. · PSD (NZS 4407:2015 Test 3.8.1): Shall be <7% passing the 75μm sieve.
ab9dc707-18c8-576e-aaac-433561430047 | note | Standard / Specification - PS - 7.2.1
68faef9d-392a-59d7-bcaf-6fa1bc1f1e4f | note | Verifying Document - Lab Reports
c4fedb90-397f-5d70-8393-ddd5f80bc3ef | note | Frequency - CBR and PSD testing shall be completed at the rate of 1 test per 2,500m3, and being no less than 1 test every 3,000m2 (placed).
2aa170d9-fa30-5034-aee7-9c13a2cf0362 | note | Verification Activity - HP
ff1df35a-76b1-5238-93f8-cfc823b7b0f1 | note | Verification Activity By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
a27e8fb3-c719-5968-a595-666a016a330e | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density & Optimum Moisture Content
9401944b-e210-541c-9a33-a939c9d05c3e | note | Standard / Specification - PS - 7.2.1
008a0244-1f95-5a7a-9e8d-80305a50d1ed | note | Verifying Document - Lab Reports
05358614-5f37-5794-981b-b6ef430b82c7 | note | Frequency - 1 test per material type and no less than 1 test every 5,000m³ (in place)
0e569234-ac64-532c-a6a1-d7a30e8d6b76 | note | Verification Activity - HP
73f1f2dc-3ee4-55d4-a027-2e6d2c716e44 | note | Verification Activity By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.02.03 - Plateau Density Test
4d47d092-b781-5579-afbe-d0a041d3ac9d | note | Acceptance / Conformance Criteria - Compaction shall be undertaken using the higher of the two density targets. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
3646b1f1-33f8-54ed-978d-3519e10c9441 | note | Verifying Document - IANZ Lab Reports
292f8656-46b5-5e25-9d81-b6c1be49f298 | note | Frequency - 5 tests per 10,000m2
cf700307-c8b6-5b85-8348-1951da8bab5f | note | Verification Activity - C
c2e994f8-60dc-5a5e-808d-82e1602f55ad | note | Verification Activity By - ENG
| checkpoint | 5.02.04 - NDM
a65fdecb-7522-5aef-8f72-c9c72775f831 | note | Acceptance / Conformance Criteria - Mean Value ≥ 98, and Minimum Value ≥ 95. All NDM testing shall be undertaken via Direct Transmission method at 300mm probe depth.
737f32a6-ca14-58fd-aea3-8aff714c61e6 | note | Standard / Specification - PS - 7.3.1
e55891f8-d0de-516a-b9c8-54ad6ca789e9 | note | Verifying Document - IANZ Lab Reports
df80991c-456f-5a22-94b9-66aea17bf2ea | note | Frequency - 5 tests per layer per 1,000m2
ddeea918-5e1e-53c5-bdb0-567b4a7edd31 | note | Verification Activity - C
fa4e54ea-eb3c-5011-b31b-85f88f881e0f | note | Verification Activity By - ENG
| checkpoint | 5.02.05 - Benkelman Beam
f1e57e77-c46f-5c32-a4b7-5c36a4a04f61 | note | Acceptance / Conformance Criteria - Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm
4f236964-6a78-58bb-a2ad-29ca204c836c | note | Standard / Specification - PS - 7.3.1
9af0f383-b583-5491-8e2a-112b9bbfe9b3 | note | Verifying Document - IANZ Lab Reports
f7a61f4b-00fa-5389-858d-3782c067994b | note | Frequency - every 10m of each lane – staggered between left and right wheel path.
70f2fcc9-b04d-51bc-a428-0e43ad15a03b | note | Verification Activity - C
e7ad119b-d74a-5d5c-b2d6-3a42d6de70a8 | note | Verification Activity By - ENG
| checkpoint | 5.02.06 - Organic Material
b3e67920-8037-5400-8c1c-642e5ee8991f | note | Acceptance / Conformance Criteria - Ongoing visual and physical inspection for any roots/organic material, photos of clean sand, and any organic material removed.
a0c385bf-bf9c-5c1c-ac4e-583139a2d735 | note | Standard / Specification - PS - 7.3.2
936b6251-f4a7-5a3b-bf3c-24cba6f93080 | note | Verifying Document - Site Records, photos of clean sand, and any organic material removed
db82440f-7ec5-5382-8705-2ae2bae059b1 | note | Verification Activity - I
b5079f59-52f0-5920-ac35-007512183c86 | note | Verification Activity By - ENG
| section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction
| checkpoint | 6.01.01 - Subgrade Prep
3314eb0a-8401-58d3-a782-af26e847ee14 | note | Acceptance / Conformance Criteria - The subgrade shall be prepared in accordance with the requirements of the Geotechnical Works Specification in Appendix B, including proof rolling, Scala penetrometer and NDM testing at the specified frequencies.
4832cdc2-16f0-54fb-b9f5-b13fd4db465b | note | Standard / Specification - PS 7.1 GWW
4d5bf8ee-a1ae-53dc-83a1-b890969d9705 | note | Verifying Document - Completed Earthworks ITP
81025f5f-e79f-5ae5-98f3-223c68ae7b80 | note | Frequency - Prior to Pavement Works
08eae87e-fbb1-52e4-abc1-c936b9f15f93 | note | Verification Activity - HP
531c5d6a-0940-5478-b658-d32ba101608b | note | Verification Activity By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | 6.02 SIL (Clean Pit Sand)
| checkpoint | 6.02.01 - SIL Scala Testing
dcff1fcc-0468-5c64-97ec-07f5bb15626e | note | Acceptance / Conformance Criteria - In addition, the SIL (tested in accordance with PS Clause 7.4 below) shall achieve a Scala penetrometer blow count no less than 10 blows/100mm. Depth to be 1.5m from top of SIL.
4163e9ea-e5a1-5798-9f16-4efc158777b9 | note | Standard / Specification - PS - 7.3.1
e34d2610-b9ae-5077-ba99-de1bc7d627bb | note | Verifying Document - Scala Results
9faf4a1c-754c-5fea-ade0-407e75652614 | note | Frequency - 1 test per 200m2
894e4cdf-7c9d-5780-a212-8b8d34c34071 | note | Verification Activity - I
7f61f95f-4eb2-5bcd-b43f-2b57f7050d3c | note | Verification Activity By - PE
| checkpoint | 6.02.02 - Layer thickness
3f529307-5392-5a66-acbb-081265d82c69 | note | Acceptance / Conformance Criteria - Each layer shall be checked to ensure the required layer thickness is achieved of Maximum
0fa5048b-d270-5ea1-9593-a35fc1bbadaa | note | Standard / Specification - PS - Table 7.2 - 2.2 NZTA B/2
f5c571b2-b56a-5c59-8c5f-481204083b8b | note | Verifying Document - As-built data
5c79b190-c473-5a2d-9a81-4b6cf4384c9d | note | Frequency - 1 test per 20m
940c333f-fade-574e-82a7-6ece487ed079 | note | Verification Activity - I
da0419c8-3af1-55d4-a644-463ad1be3e53 | note | Verification Activity By - SE
| checkpoint | 6.02.03 - Plateau Density Test
20cea371-9a84-570b-8d74-aa280094c8ab | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
0aa05dd5-ffc9-504e-9a7c-60990433443a | note | Standard / Specification - PS - Table 7.2 - 2.2
51fc55fa-f4bd-5d31-af32-b4186c256bfb | note | Verifying Document - Plateau Density Report
0118de71-b76e-5cdf-8df4-d9032daf63dd | note | Frequency - 5 tests per 10,000m2
24168a1d-4d75-5639-b2fc-a4cbf8e189ca | note | Verification Activity - I
d016790e-e344-529a-93dd-38a52669b805 | note | Verification Activity By - PE
| checkpoint | 6.02.04 - Sand SIL layer compaction
dfb1d2fa-07ef-574d-824b-bdc7ebddb7a7 | note | Acceptance / Conformance Criteria - Further to Figure 2 of NZTA B/2, the acceptance criteria for compaction of the sand SIL layer shall be a Mean Value ≥ 98, and Minimum Value ≥ 95.
80e7f2c7-ef44-58a0-a547-4edbf52dec16 | note | Standard / Specification - PS - 7.3.1
72f78430-a5d7-5df8-88f4-eb2aab833a7f | note | Verifying Document - IANZ NDMS
09a46328-eb63-5bf7-b4b2-789d16cf2ce4 | note | Frequency - 5 tests per layer per 1,000m2 (Min per lot)
aac1ee29-8af1-503f-a4ab-7102ea90cd06 | note | Verification Activity - I
b6d28b73-0c57-5903-886a-50e7c7b030f5 | note | Verification Activity By - PE
| checkpoint | 6.02.05 - Proof roll
07b326c3-ea68-549d-9128-c3000d49c9de | note | Acceptance / Conformance Criteria - The SIL shall be tested via Proof roll prior to Benkelman Beam testing. Proof roll to be under supervision of engineer and verifying document to be signed off by engineer.
f5e9d4dc-40e8-58cf-a4aa-b27c60255de8 | note | Standard / Specification - PS - Table 7.2 - 2.2
564d8205-b741-54d5-b073-d48e5d67d9c6 | note | Verifying Document - Site Notes
75ed5345-a8b0-52aa-bbc1-534c1cbcdb82 | note | Frequency - 1 test per 20m
e7f0260f-c6f5-50d7-84e5-50a351b4280e | note | Verification Activity - HP
61899164-dfe5-5bc3-b907-b5b068e82afd | note | Verification Activity By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.02.06 - SIL Benkelman Beam test
1474a3bc-5812-5d34-93c3-2a76dbcbc6d8 | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be carried out on the top of the SIL layer at the rate specified in PS Clause 7.4 and reported to the Engineer. Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm. Performance verification of these target deflections shall be confirmed by the Engineer on review of results from within the pavement Stabilisation trial (PS Clause 7.3.3).
04c2be5d-e694-5630-ae8f-3cd00f7c3b8f | note | Standard / Specification - PS - 7.3.1 PS - 2.2.16
b519543d-4049-5ba0-bd30-397138d05564 | note | Verifying Document - Benkelman Beam Report
2acdff5b-4e24-5f1d-87a6-475ceff0ac5b | note | Frequency - every 10m of each lane – staggered between left and right wheel path. Min 48h Notice
e4b7f0ea-806f-538d-9a07-d162c6b4f901 | note | Verification Activity - HP
62e03724-57d9-548c-9937-de3062eaf727 | note | Verification Activity By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.02.07 - SIL Inspection
add1780d-3465-530b-bd7c-6b3040e3182b | note | Acceptance / Conformance Criteria - Before laying of any pavement SIL and metal courses. SIL inspection to be carried out under supervision of engineer, verifying document to be signed off by engineer.
aaa691c7-ddbd-559c-b7d2-ece1f6df8a75 | note | Standard / Specification - PS - 2.2.16
62109f41-cacd-5114-9387-f25dd7090a0b | note | Verifying Document - Hold Point Release
53749f59-1a97-5155-aa0f-01f9dede2b1c | note | Frequency - Min 48h Notice
8cf9b4d1-106e-5b75-8410-1d614ffa90d2 | note | Verification Activity - HP
c500ca95-c927-5ef8-8063-ff8836fab8fe | note | Verification Activity By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.02.08 - Topography
bb8d94d0-cad7-5b1c-8c9b-72bfccbba337 | note | Acceptance / Conformance Criteria - Carry out level check on trimmed SIL. Survey conformance with Total Station. Tolerance = -30mm +0mm (NZTA F/2).
dfea0969-3fe2-5fb8-b6e2-71a12b4b8f40 | note | Verifying Document - Survey PDF against IFC or similar
c4f76caa-a1e7-5193-a040-20aa641b2936 | note | Frequency - every 1m across the road (avoiding islands) at 20m intervals
9af73578-466b-5e6f-8458-cf20471145cb | note | Verification Activity - I
0f251313-de06-520b-8bad-69923864004d | note | Verification Activity By - ENG
| section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
| checkpoint | 7.01.01 - Construction Record Compilation
e33b7f2d-364e-554c-bbc9-71565eeabdcd | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
02cb16d6-62a9-5c07-b1fd-9212d27af6d9 | note | Standard / Specification - Downer
d5242ce2-72cf-5b1b-93ee-f2289178affc | note | Verifying Document - Records
89f45c46-bd82-5272-9f96-7c18301858fe | note | Frequency - Post construction
e3b23594-8fa7-5800-9495-7772a6d9da38 | note | Verification Activity - H
1f3b92d1-88f6-5192-86a8-d876bfc05b8f | note | Verification Activity By - SE
| checkpoint | 7.01.02 - Survey Records
09ede6c8-4248-52cc-ab76-a1b266afc9e7 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
64e2281b-04ef-5dd0-a95a-ed86a87e480f | note | Standard / Specification - Downer
c7cbca71-5e4d-5ee2-9c7e-338c155a00cc | note | Verifying Document - Records
6bfdd8a6-0e45-5a32-b543-6abfceba1022 | note | Frequency - Post construction
b936ae2a-5b7f-575c-b00c-96f40edeb440 | note | Verification Activity - H
239d20eb-1cda-5151-8ee0-a1a37fa759ad | note | Verification Activity By - SV
| checkpoint | 7.01.03 - Redline Drawings
4d55e902-6fc9-5949-bd90-3718360ae31b | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any increase in SIL depth.
92347465-5877-5da6-87bb-b262af7857d7 | note | Standard / Specification - Downer
9dcd9ed1-320f-5caa-9c10-bea4580085c4 | note | Verifying Document - Redlines
3bb64a96-941d-58a0-8054-c7df7e8a417b | note | Frequency - Post construction
34016d76-9cb7-5f99-ac70-5ccdd07ac80a | note | Verification Activity - H
dc0a719b-c026-5d33-b5c3-421f855beb57 | note | Verification Activity By - PE
| checkpoint | 7.01.04 - Defect, Snag and Punch List
a813cec3-db3c-59fe-ae89-11ec57536b58 | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
4b87d8eb-15fe-50d6-a4c4-3d238a68c758 | note | Standard / Specification - Downer
95b0b9db-0eec-5c01-aca1-4e4b0c7d024b | note | Verifying Document - Register
54deb3d9-5e5c-5c40-b241-f30fadd35c16 | note | Frequency - Post construction
98e8bc64-2444-52eb-abdc-f1fd9dccc045 | note | Verification Activity - H
ab26cea9-5803-55d8-a91d-5f75095d1303 | note | Verification Activity By - PE
| checklist | ITP - Piling | itp | ITP - Piling | 5005b436-682d-4485-80e7-3dcfaa4b8b14
| section | 1.0 Pre-Construction
| checkpoint | 1.1 - Accepted Method Statement
62f24d58-7b8d-5c3c-877a-87b9c30bd50d | note | Standard / Spec Reference - Project specification
a0b5d7c8-4a0d-5607-8b54-315563f25d70 | note | Acceptance Criteria - Engineer’s acceptance
28af8229-fd5f-5619-8cd4-8a74166f2400 | note | Frequency - Once prior to commencement of piling
cdf61e20-5f96-5025-bb8b-a720e08c10d0 | note | Responsibility - CLL
42dbd898-35a4-5d93-9470-cbe81a90cfc2 | note | Hold Point H/W/S - DO: H
a1ec3af8-c244-5f77-86b8-956c98095f24 | note | Hold Point H/W/S - BBO: H
70b032bf-215e-54b0-aa18-0d92e380695b | note | Hold Point H/W/S - CLL: H
3c8ff899-625e-54c0-8499-92db7435fcbc | note | Verifying Record - Email Confirmation
4a44b871-e815-52b1-ad16-4142fb42906c | note | Comment - To be submitted at least 10 days in advance.
| signoff | HOLD POINT (DO/BBO/CLL)
| checkpoint | 1.2 - Accepted Inspection and Test Plan
2ce3b27d-4838-5fdf-8ea1-5777c3137557 | note | Acceptance Criteria - Issue
06dee5e8-d630-5c38-8931-a607754c1810 | note | Frequency - Once prior to commencement of piling
dc72a423-376b-5cae-937b-223b0a105f3c | note | Responsibility - CLL
0c173d62-8c26-58af-a7a3-39f4347d19c7 | note | Hold Point H/W/S - DO: H
3df5f23f-af35-55a9-9587-e32a590ad958 | note | Hold Point H/W/S - BBO: H
5f9fee3e-3c65-5efa-9192-259130cafef3 | note | Verifying Record - Email Confirmation
| signoff | HOLD POINT (DO/BBO)
| checkpoint | 1.3 - Accepted Safety Plan - SSSP
ff600164-3277-50b6-94a3-86ea098289f5 | note | Acceptance Criteria - Issue
06052266-f1f1-54b6-a031-cb2d8e0c405d | note | Frequency - Once prior to commencement of piling
bf30a35e-ff8b-5b6f-9447-5647b88ecdf7 | note | Responsibility - CLL
97ebb5fd-1f19-5b3e-8f91-58c1104c5a15 | note | Hold Point H/W/S - DO: H
eca49034-bb54-5944-af21-bcd279d2168a | note | Verifying Record - Email Confirmation
| signoff | HOLD POINT (DO)
| checkpoint | 1.4 - Accepted support fluid details
9d9e6f8d-9bfd-52de-bbdc-1f7f1dc34fce | note | Acceptance Criteria - Issue
841f33af-4eb0-587a-88aa-b73cd866eb6d | note | Frequency - Once prior to commencement of piling
d5496b4c-34d2-531a-beb3-ae08c31d0301 | note | Responsibility - CLL
f3f25f47-92c5-56a5-b797-8c25e7eca7f7 | note | Hold Point H/W/S - DO: H
1aee7c34-a76d-50c3-8ffa-ed0ce8228d6c | note | Hold Point H/W/S - BBO: H
44f5d988-5199-51e2-bc00-c0aa67df1d6b | note | Verifying Record - Email Confirmation
| signoff | HOLD POINT (DO/BBO)
| checkpoint | 1.5 - Permits issued
33d41727-c9f2-5083-9bd9-49bba94dbb0e | note | Acceptance Criteria - Issue
4c345aab-e5df-5b13-a11f-0b728c28b7e9 | note | Frequency - Once at commencement of piling
fb36ee4d-02af-585e-889c-13435199ceda | note | Responsibility - DO
439a55e4-8990-5dd9-9727-13cdb6f987e9 | note | Hold Point H/W/S - DO: H
57a2c843-280f-5427-9e97-d1a4df1a33ad | note | Hold Point H/W/S - CLL: H
296af5e8-e172-5439-9015-be08147b2c9c | note | Verifying Record - Site Hardcopy
| signoff | HOLD POINT (DO/CLL)
| checkpoint | 1.6 - Concrete Design Mix Verification
9fe70b6a-6f02-56e1-bb40-4a94473b735a | note | Acceptance Criteria - Issue
9cc52df2-2af2-5401-94e7-bf56e94fb584 | note | Frequency - Once prior to commencement of piling
942686fb-326b-5357-831a-0ea14c4b61de | note | Responsibility - DO/BBO
7ad59786-5dd0-52fd-81bf-5124f748ce8f | note | Hold Point H/W/S - DO: H
7a6a55e0-45ce-557d-9deb-ec74e6509fef | note | Hold Point H/W/S - BBO: H
6882a143-762d-5a98-8b9f-902ff910d6af | note | Verifying Record - Email Confirmation
| signoff | HOLD POINT (DO/BBO)
| checkpoint | 1.7 - Reinforcement Steel – mill cert
f6de07d6-4d18-5c75-81da-f08f6fb541bd | note | Acceptance Criteria - Project specification
141b17c5-9fc2-586b-9410-b96125cc12a9 | note | Frequency - Post Construction for every pile
b80a6d66-54c7-55bd-95eb-f59fff342051 | note | Responsibility - CLL
cad41ae2-3493-53ae-b614-f1959efe03f1 | note | Hold Point H/W/S - DO: H
d26751fd-462b-5396-a946-21163b38326a | note | Hold Point H/W/S - BBO: H
02860350-2e3b-59fb-83e4-62c11e383e7e | note | Verifying Record - Issued by supplier - email confirmation
| signoff | HOLD POINT (DO/BBO)
| section | 2.0 Pile Boring
| checkpoint | 2.1 - Client Notification
127d74af-39ee-57b4-a28a-8cf89457a511 | note | Acceptance Criteria - Issue
49626cce-3ba4-5b4b-8e30-da4c6b2583bc | note | Frequency - Once at commencement of piling
17ffa176-be6e-5b07-ba5c-b7dd57754998 | note | Responsibility - DO
130ab38d-2a4f-5193-a58a-f7e4a2988b03 | note | Hold Point H/W/S - DO: H
f3b265fb-d836-5d1f-8d1c-866a9f0de264 | note | Hold Point H/W/S - BBO: H
21e632d0-2534-530c-871b-2a9bdf651709 | note | Hold Point H/W/S - CLL: H
77455024-dec7-509f-b8d8-de5cf34c0984 | note | Verifying Record - Email Confirmation
fdb7c117-096d-5971-a534-fcbd3b2e8936 | note | Comment - 48 hours’ notice of pile drilling commencement.
| signoff | HOLD POINT (DO/BBO/CLL)
| checkpoint | 2.2 - Check drill tool diameter
d89977b4-e455-589d-bda2-95d41c40471b | note | Standard / Spec Reference - As per HCC 1298/2022
02263750-9fb4-5713-9e34-ab9cc0be1904 | note | Acceptance Criteria - Visual Inspection
84df2b0a-dbe3-594f-aad1-ec57437387ad | note | Frequency - Prior to commencement of piling
6df99fc9-0967-5811-acba-87a73fc2c335 | note | Responsibility - CLL
2933e753-6f07-5d06-8e7a-e42ae959ac36 | note | Hold Point H/W/S - DO: W/S
393df755-3739-5884-9e6c-94e1f8fadaea | note | Hold Point H/W/S - CLL: W/S
0d6ee654-a922-56c2-8592-9d75ffecf944 | note | Verifying Record - As per pile QAC
6d6df6d9-b3b8-519c-b879-061a4b65ada3 | note | Comment - Minimum agreed diameter is 870 mm for 900 DIA piles, due to ID of permanent casing supplied by DO, and 1200 mm for 1200 DIA piles.
| checkpoint | 2.3 - Check depth gauge/instrumentation of piling rig
d6a54a60-5171-50d0-a2fb-bbf927dcb062 | note | Standard / Spec Reference - Operators Manual
065bc6b8-60ce-578b-af89-e217a11acdcb | note | Acceptance Criteria - Visual Inspection
a2d08314-7d81-5714-80c3-c8f1bc580566 | note | Frequency - Daily
db42a45b-c24c-5d96-bbde-0abc33e268e1 | note | Responsibility - Rig Operator
99da9c5d-0d27-543e-a1bf-2f05b9b06576 | note | Hold Point H/W/S - DO: W/S
740ec1ab-51f6-5ac2-900f-93198bfac9d9 | note | Hold Point H/W/S - CLL: H
a31142ee-a7b2-52b4-972f-ffc06e078136 | note | Comment - Operator daily checks
| signoff | HOLD POINT (CLL)
| checkpoint | 2.4 - Ground penetration and extraction with due diligence
f8c37aee-8bcf-566e-a8f8-a9904e57e933 | note | Standard / Spec Reference - Operators Manual
8d566718-caad-5858-81ad-cc6ea83eaf2d | note | Acceptance Criteria - Visual Monitoring
0a48287b-b7a0-5a5f-9fa3-bc09c323b0aa | note | Frequency - Every Pile
356f007f-dde7-5250-8a44-73fe0a500963 | note | Responsibility - Rig Operator
ee6e25eb-084a-523b-9584-20acecc2b8e1 | note | Hold Point H/W/S - DO: W/S
b3f2d9ff-8a74-5efe-9170-f5230537c108 | note | Hold Point H/W/S - BBO: S
8886fd93-785d-5ce6-9209-95c655a90763 | note | Hold Point H/W/S - CLL: S
ea32cdba-2701-54b6-9e29-f89140d2a1e9 | note | Comment - Operator to penetrate/extract with due diligence, no adverse effect on bore integrity.
| checkpoint | 2.5 - Check pile position/pile numbers
cc8a5683-4085-548b-a06d-f7650d7005d9 | note | Standard / Spec Reference - Drawings
92a5ffa7-ae71-57cc-85b8-cffec705debf | note | Acceptance Criteria - Visual Inspection
2cef91b0-b80f-5093-8153-34079e147fb8 | note | Frequency - Every Pile
476f8d0a-1369-57ff-88e7-0f0ac2ec346e | note | Responsibility - CLL
ed3b6a51-fe04-5388-8892-b10ac93febc3 | note | Hold Point H/W/S - DO: W/S
c59e9228-3d42-55b0-a461-1f58e181c916 | note | Hold Point H/W/S - CLL: W/S
| checkpoint | 2.6 - Pile Setout/Offsets
5265d5f9-82d3-5dd6-9a58-f8eff57c8283 | note | Standard / Spec Reference - Drawings
f24a2128-74bc-5847-8af6-c497eeafbfa7 | note | Acceptance Criteria - Hz +/- 10mm
7c7906c8-387d-5188-9b49-236c00fa0047 | note | Frequency - Every Pile
8e098ff8-97b2-5f13-ab15-adcf0b176acb | note | Responsibility - DO
84f8b9a2-ac2c-5ebd-a7ca-4c37f2f7bdb6 | note | Hold Point H/W/S - DO: W
00f62530-9241-5485-bf60-6e174363a69d | note | Hold Point H/W/S - CLL: W
d425f2f4-e41d-532b-b7f6-71474f6300f4 | note | Verifying Record - Survey record
d29e8f1c-a503-5d7b-a47b-10953ba557eb | note | Comment - Due to tight plan tolerances set-out is critical
| checkpoint | 2.7 - Casing Inspection
b1d70420-7211-5b5d-a523-795c11cee7fa | note | Standard / Spec Reference - As per HCC 1298/2022 – note minimum agreed diameters at ITP item 2.2
2a09fa2c-6c38-537f-88a4-0b7f4d770363 | note | Acceptance Criteria - Visual Inspection
1e31b424-6d87-54fe-95c5-21c32676d495 | note | Frequency - Length/diameter/Wall thickness at start of piling, RL every pile
19666f1f-b9e2-5641-93d7-5a1a94cf3d38 | note | Responsibility - CLL
d7248886-5235-5b47-938a-355fca0b2588 | note | Hold Point H/W/S - DO: H
27468874-90c7-5246-bae6-faccfa31dcab | note | Hold Point H/W/S - CLL: H
a34bd4c1-a19f-5bb3-9e49-e017835f383b | note | Verifying Record - QAC - Pile Card
3ac82270-8df9-5a7a-af3e-2ded1a6f9e18 | note | Comment - RL check pre-concrete & pre- drill
| signoff | HOLD POINT (DO/CLL)
| checkpoint | 2.8 - Measure and check position and verticality
23eddc2e-82ab-516b-92d0-61bbdcfeecfd | note | Standard / Spec Reference - As per ASGPILES - Rev G
38af7733-fcbe-538e-ae27-d87df6ad910a | note | Acceptance Criteria - Visual Inspection Permitted deviation from vertical shall be not more than 1:75 or 0.8 degree.
f96ea33d-aa2a-5392-8fcc-36c22987bf7f | note | Frequency - Every Pile
f89ccee3-f773-50f8-80e1-ba63b89582f5 | note | Responsibility - CLL
1bcaf796-ce95-5492-b124-fd429a98dfdf | note | Hold Point H/W/S - DO: W
f2a11210-b84a-5872-8699-0eae8aeedcd2 | note | Hold Point H/W/S - CLL: H
145715cb-ad7b-58c5-8371-d3a2c6719f7d | note | Verifying Record - QAC - Pile Card
69c0eac7-e7d5-504b-aba6-266beb30f2f6 | note | Comment - Spirit level has a +-0.5 degree accuracy. Verticality of pile to be checked via use of electronic level on the side of the casings & against Kelly bar.
| signoff | HOLD POINT (CLL)
| checkpoint | 2.9 - Bentonite checks
062d9b9d-4b1d-56b5-9efd-059c3b888bec | note | Standard / Spec Reference - Fluid Specification
5fe673aa-6ab8-5bb8-af0d-76175afc840c | note | Acceptance Criteria - Visual Inspection/Testing
86b6f252-d5b4-5f79-80ac-39e90ae7c1b9 | note | Frequency - Per batch, each pile prior to concreting
dc20cc6e-41b5-5948-a9f3-0d2a2b13cefa | note | Responsibility - CLL
4d57e3db-de1d-56e9-9095-d4f971652c07 | note | Hold Point H/W/S - DO: W
fccbd892-06f0-5f86-97c1-e84026cf31b1 | note | Hold Point H/W/S - CLL: H
80030517-2764-5cfb-98fe-42a66de35365 | note | Verifying Record - QAC - Pile Card
| signoff | HOLD POINT (CLL)
| checkpoint | 2.10 - Bentonite level
7110409d-ae16-5282-86de-3aa5ca979499 | note | Standard / Spec Reference - As per construction specification - Methodology
aada31d1-5145-5d1d-96f4-e39f66fd25b4 | note | Acceptance Criteria - Visual Inspection Bentonite head to be maintained at 0.5m above groundwater level or adjusted as required.
6a7aaae7-3195-5b64-9426-50157cf84b48 | note | Frequency - Each pile
6b92b846-b8e7-5b82-8593-683a180e5ef0 | note | Responsibility - CLL
ea1f1680-0813-5a0b-8b60-50e9e28c2657 | note | Hold Point H/W/S - DO: W
28a4502f-6369-56c9-bf97-85320653eacf | note | Hold Point H/W/S - CLL: H
99e7656a-56b5-587f-8b3f-d755d44ad5cf | note | Verifying Record - QAC - Pile Card
e22b5738-9a18-534e-931c-ee4065ed4aaa | note | Comment - Any significant fluid loss/stability will be addressed with Project Engineer.
| signoff | HOLD POINT (CLL)
| checkpoint | 2.11 - Soil logging and bagging
05a5cf28-2374-5f59-9c31-3616a8a99710 | note | Standard / Spec Reference - As per HCC 1298/2022 11.7
fbd76925-eca8-59d2-a939-d88d07abe294 | note | Acceptance Criteria - Visual Inspection Engineer Inspection
0a151c42-9cdf-530d-bee4-76c07ab75bf1 | note | Frequency - Every Pile
7356630e-687f-5d18-a2bb-5d85ce4ea06c | note | Responsibility - DO/CLL
1702070a-6cc6-5e5c-b0ef-d303f17de8fc | note | Hold Point H/W/S - DO: S
643415d9-95d7-5382-a7c1-9e4fab189209 | note | Hold Point H/W/S - BBO: S
2d8e6ed3-f642-558f-8257-536dd4a3f482 | note | Hold Point H/W/S - CLL: S
eb6034dd-7c82-5fbc-9d02-e8f393445fc1 | note | Verifying Record - QAC - Pile Card Labelled, bagged core samples
f1fdf6c2-d77c-55c9-a0ef-1e61e7398409 | note | Comment - Boreholes are to be continuously logged on QAC - Pile Card. Material from the base will be bagged, labelled and securely stored on site for Engineer’s inspection.
| checkpoint | 2.12 - Confirmation design minimum toe depth achieved
f50e9dec-3595-5314-ae00-dd46e1835e51 | note | Standard / Spec Reference - Construction Specification/ Drawings
adb9a044-27ee-5b93-afda-4c2160bd656a | note | Acceptance Criteria - By means of weighted tape Designer Hold Point: Maximum depth exceedance
b0040e5d-93ff-57bb-9c57-0322b1aa89c1 | note | Frequency - Every Pile
c3fdff0a-1bf1-5832-a0cc-5d34b56ba509 | note | Responsibility - BBO & DO Rep/CLL
545a7558-dd79-53b1-b2af-9bac40f9f4db | note | Hold Point H/W/S - DO: H
6544d048-4b5e-57ee-9cd1-d0d118c09b42 | note | Hold Point H/W/S - BBO: H
90620fbf-5ac0-5b79-a5c2-f951fd7f12ba | note | Hold Point H/W/S - CLL: H
2a3ddc38-bb98-51d1-98e0-68311e26d69f | note | Verifying Record - QAC - Pile Card
35ac5247-116a-50fd-a332-d2212b87d98a | note | Comment - Visual inspection not possible due to drilling under fluid. Engineer to agree correct drill depth. Designer to be notified if drilling reaches >300mm below design RL for pile toe. Maximum depth exceedance to be 40m from piling platform.
| signoff | HOLD POINT (DO/BBO/CLL)
| checkpoint | 2.13 - Base cleanliness
e1f9cbcd-2a01-5ebe-bb7c-269e23ae51e1 | note | Standard / Spec Reference - Construction Specification
82257d50-4b95-5b95-9d48-328d7f1c16da | note | Acceptance Criteria - By means of weighted tape
ee5d6323-0a66-52d8-9bc0-e825aa8ff225 | note | Frequency - Every Pile
30bdf695-1094-5aee-9fb2-eca1e3b47259 | note | Responsibility - BBO & DO Rep/CLL
98e336f8-cdf7-55c4-b3bb-cde97b83c563 | note | Hold Point H/W/S - DO: H
c3bd29d6-5ba4-537b-bdb1-ad8279ec335b | note | Hold Point H/W/S - BBO: H
8fbb5c9f-d190-5f21-bd03-c9ce09194916 | note | Hold Point H/W/S - CLL: H
6457918b-7bef-52a5-b94f-5d9dd88a9dc1 | note | Verifying Record - QAC - Pile Card
09fa7eea-a4cd-5d30-b66d-1618849fd90d | note | Comment - Visual inspection not possible due to drilling under fluid.
| signoff | HOLD POINT (DO/BBO/CLL)
| checkpoint | 2.14 - Pile Boring Monitoring
da5690c2-364c-54ba-b5bb-c44b04b0d497 | note | Standard / Spec Reference - Construction specification
a6065435-836f-5a15-8633-d9964351b9cc | note | Acceptance Criteria - Visual Monitoring
f6f28ca6-10a8-549b-888c-201999d02812 | note | Frequency - Every Pile
3a3807e6-8ce3-5acf-97a5-9c3a73876454 | note | Responsibility - Rig Operator
9b483e89-f254-5424-99b4-94ba331da17f | note | Hold Point H/W/S - DO: S
e4e7c507-d7e4-5582-849a-f80b0dcf2c7a | note | Hold Point H/W/S - BBO: S
6a180e2b-611a-5e21-be53-009e8f2c2989 | note | Hold Point H/W/S - CLL: S
6eb9b0f5-7f5c-56ba-b44b-618e668925ae | note | Verifying Record - QAC - Pile Card
66c0ec2a-e112-57cd-bd96-8583d38bf0c4 | note | Comment - Depth check, possible collapse, changing ground conditions, any unexpected occurrences
| section | 3.0 Pre-Pour Inspection
| checkpoint | 3.1 - QA check on previous pile
d9ffa3b0-f2fc-5ffb-856b-d9d0845faecb | note | Standard / Spec Reference - Engineer Specification
9a7315d4-da70-50ea-8600-34cee05752e2 | note | Acceptance Criteria - Client notification/Engineer’s Approval
dcefb148-106b-5e4f-8706-4172893e6f2c | note | Frequency - Every Pile Ongoing Engineer’s approval
e8801f3e-fb09-57f6-9efc-2d002ec58f1d | note | Responsibility - DO Rep/CLL
da467a95-7061-5faf-9080-31eea866c4a1 | note | Hold Point H/W/S - DO: H
ffd50456-cf6e-5bb2-beed-fbf83ed7e06a | note | Hold Point H/W/S - BBO: S
66620fd5-c1e0-54d9-9de7-342197c68564 | note | Hold Point H/W/S - CLL: H
9063f978-984c-53db-958a-bd6fe16cbb1c | note | Verifying Record - QAC - Pile Card
91ce59a3-8964-5126-94c0-09cb8f71bdf3 | note | Comment - Engineer’s approval to proceed with subsequent piles
| signoff | HOLD POINT (DO/CLL)
| checkpoint | 3.2 - Reinforcement Cage inspection/ check spacers, pile bore tolerances
32332388-f3b4-55a2-9d5c-c08b1c59ed2c | note | Standard / Spec Reference - BBO SS 2110 Rev 9
48b7e1b9-800d-56cf-83a8-c0e4f9770b27 | note | Acceptance Criteria - Alignment lesser of +- 4% DIA or +-75mm
d5540b5f-3471-5520-9228-6539eb73f067 | note | • Height +- 50mm
e72c4a70-0261-5b44-9219-ded85717bbf0 | note | • Reinforcement Type- As per drawings
553844e0-efd1-5c21-8bfe-bf0e46735eb0 | note | • Concrete cover: 75mm, 50mm minimum
ec2f10f5-139d-59cd-ad7c-18817e2a9d83 | note | • Bottom of pile position lesser of +-1% pile length, +-12.5% of shaft diameter, or +-400mm
0377f0a6-1588-5155-80df-064446b2858d | note | Frequency - Every Pile
b2c5375a-93e3-5631-bb55-b566d619b2bf | note | Responsibility - DO Rep/CLL
edc040f2-1b2a-5360-b2fe-f9d6b91be355 | note | Hold Point H/W/S - DO: H
c2ad4d47-631d-5ab3-8369-f005614c714b | note | Hold Point H/W/S - BBO: S
08169f5b-32ca-5a6d-9a2f-c323e831759d | note | Hold Point H/W/S - CLL: H
b7c36495-da2e-5fca-ba1f-b0783430ad08 | note | Verifying Record - QAC - Pile Card
818a252f-b1d9-5349-a139-880703f85f88 | note | Comment - Pre-installation check required of all pile sections
| signoff | HOLD POINT (DO/BBO/CLL)
| checkpoint | 3.3 - Stabilising Fluid Verification
5db9a565-4b7d-520a-ab7a-5002ffb8ec92 | note | Standard / Spec Reference - Construction Specification
61003af8-6099-572f-878d-f618d906d86a | note | Acceptance Criteria - <4% sand content acceptable
96895dee-5600-5b2f-899a-5649edfadb0d | note | Frequency - Every Pile
1b730cb4-d0e4-5279-aabd-d0ae4e97bf0c | note | Responsibility - DO Rep/CLL
5d5d8ccd-c809-5a56-b041-88f09e37347a | note | Hold Point H/W/S - DO: H
abe3398c-d030-5b8b-89e8-32292c3e894f | note | Hold Point H/W/S - BBO: S
17422081-e128-5f7e-af79-f85ad3432e47 | note | Hold Point H/W/S - CLL: H
e042cbd3-73aa-5b5d-a1bf-188e90bb416b | note | Verifying Record - QAC - Pile Card
| signoff | HOLD POINT (DO/CLL)
| checkpoint | 3.4 - Pile cage installation
c14f16e2-c6e0-5fe2-9a6a-c08be4f34bed | note | Standard / Spec Reference - BBO SS 2110 Rev 9
a366130f-a6ec-5928-b165-74f227cf6450 | note | Acceptance Criteria - Engineer Inspection
2f85f743-0569-5391-804e-03a846d65820 | note | Frequency - Every Pile
2ffb28ec-ad8b-5994-8c3c-8cd898a3b850 | note | Responsibility - BBO/CLL
d2f62d4b-a998-5546-84f9-cfe0f3c21dc2 | note | Hold Point H/W/S - DO: H
c4c98d6c-9521-536c-9071-c2245c4f36df | note | Hold Point H/W/S - BBO: H
b7c7ccec-7d4f-5066-a1aa-488ab9fa68e4 | note | Hold Point H/W/S - CLL: H
d282ff52-af4e-5eb2-a129-3fb0d079f068 | note | Verifying Record - QAC - Pile Card
5d35f620-2870-5913-9055-a5c03c33d726 | note | Comment - Pile cage to be installed immediately after Engineer inspection and acceptance
| signoff | HOLD POINT (DO/BBO/CLL)
| section | 4.0 Concrete Placement
| checkpoint | 4.1 - Verify Concrete Mix – batch times, mix
987a0787-d2b3-5b07-9263-e7e9494c1061 | note | Standard / Spec Reference - BBO SS 2140 Rev 5
103db8b0-60cb-5751-9268-1b15d271c6b0 | note | Acceptance Criteria - 401T4504R
2be52e69-9efb-5473-8caf-f9bc414ab1d7 | note | Frequency - Each delivery
33819dc0-5bb9-5115-88db-863b5140a336 | note | Responsibility - DO Rep/CLL
d23d2690-5722-5931-b595-fee021a5f480 | note | Hold Point H/W/S - DO: W/S
43bd3a62-328b-5f77-a0cb-b0132d6b601a | note | Hold Point H/W/S - BBO: S
a4459d03-2dc6-5823-a5ba-cd9e516f3176 | note | Hold Point H/W/S - CLL: W/S
f8d935ff-2af5-5d7e-b866-f9d9e2dbeae4 | note | Verifying Record - Concrete Docket
| checkpoint | 4.2 - Slump/ Spread test
fa08a831-c5de-53eb-9558-6f592339dead | note | Standard / Spec Reference - BBO SS 2140 Rev 5
45987288-bffe-5d95-8ebe-2a340eccaec8 | note | Acceptance Criteria - Slump 100-130mm +- 25mm
dbe3811c-1311-5d5f-a209-c1cd9ff2821f | note | • Spread 500mm +-100mm
2415bb64-12b8-5cfb-ab35-82ebf82ed75f | note | Frequency - Each delivery
80f8af05-ec45-587d-a244-c2ed7ba804fd | note | Responsibility - DO Rep/CLL
d5b5124b-2f99-50ca-9008-15ff5672228e | note | Hold Point H/W/S - DO: H
689c9610-76fd-5b70-9a87-5b00a6e3df64 | note | Hold Point H/W/S - BBO: S
61c250cd-15f7-5e49-91ae-e4c2264ed653 | note | Hold Point H/W/S - CLL: H
85ef6231-6847-5b11-ab6e-38c97f93da77 | note | Verifying Record - QAC - Pile Card
| signoff | HOLD POINT (DO/CLL)
| checkpoint | 4.3 - Concrete level
cf5c32d9-8b2e-5212-87e3-a22f3b3a6b60 | note | Standard / Spec Reference - BBO SS 2140 Rev 5
616a5865-4d49-5b8f-90bf-938f9945c06f | note | Acceptance Criteria - Design +50mm
d1462899-cdaa-5978-924c-52b8512a87a9 | note | Frequency - Every Pile
bdc77f32-0256-5520-a294-f327d7b77df6 | note | Responsibility - DO Rep/CLL
a3393c8c-6837-5251-ada2-d9b693e96a0c | note | Hold Point H/W/S - DO: H
8920593f-b999-56b4-bb76-4988cac6b525 | note | Hold Point H/W/S - BBO: S
74fd1a5b-2a16-5da8-9dca-a87ff8167a7d | note | Hold Point H/W/S - CLL: H
02286bfc-65f6-52c1-8372-112c2bf4c366 | note | Verifying Record - QAC - Pile Card
| signoff | HOLD POINT (DO/CLL)
| checkpoint | 4.4 - Concrete placement
4b2d27f3-d304-5954-97ca-42e3ad806688 | note | Standard / Spec Reference - HCC 1298/2022
50ec78e8-7a60-590b-880a-90d07cb85e3d | note | Acceptance Criteria - ITP Item 3.3
b99e46f2-3d8f-5c8f-97ba-a1b6aaada3e5 | note | Frequency - Every Pile
aadd7598-b457-5050-bb50-1e4909442eac | note | Responsibility - BBO/CLL
5ec50698-bb96-5c58-90fc-e33bbec12743 | note | Hold Point H/W/S - DO: W/S
b2c8600c-42f1-543e-b39d-2871d135a7cc | note | Hold Point H/W/S - BBO: S
2b2362b2-b4ac-5f42-858d-9d482142d396 | note | Hold Point H/W/S - CLL: W/S
f7a9c4b9-b545-533f-8e2a-85395f12c4e5 | note | Verifying Record - QAC - Pile Card
8296c2e6-2872-5b02-b7e0-6bdbca76b520 | note | Comment - Pile to be concreted within the same day as Engineer’s acceptance of reinforcing cage installation, ITP Item 3.3.
| checkpoint | 4.5 - Concrete pouring – Check volume
f3e683a1-f21f-5432-b184-5ac50c69bd57 | note | Standard / Spec Reference - Construction Specification
cce7751b-fd79-593a-a271-f53492199ba3 | note | Acceptance Criteria - As per QAC - Pile card
983417f3-6810-5eef-a4b7-f594983ade3a | note | Frequency - Each delivery
26737af6-8647-5ac3-8e1c-e95412dc9700 | note | Responsibility - DO Rep/CLL
384298bd-f756-5bfc-83da-38bfaaeb5852 | note | Hold Point H/W/S - DO: W
28138a08-16cb-5f31-a057-4da8dd96c255 | note | Hold Point H/W/S - BBO: S
145cef34-c356-59b3-a213-248300218be7 | note | Hold Point H/W/S - CLL: W
78cb32b7-ba2d-59e8-bffb-afc56409d1a0 | note | Verifying Record - Concrete docket, QAC - Pile Card
4bd8d361-e465-5bed-8717-bfa87d4bcb5c | note | Comment - Concrete volumes and Tremie records to be maintained as per QAC - Pile Card
| checkpoint | 4.6 - Pile concrete overpour
6b7c9fec-bb14-52a8-966e-2c2739099dfd | note | Standard / Spec Reference - HCC 1298/2022
fba889d8-b628-516c-9809-6f56ff55c148 | note | Acceptance Criteria - Visual check - Sign off by Engineer
6c87a0ad-b23b-52d9-a9f0-3b007a8513f0 | note | Frequency - Every Pile
13a64774-e81c-53d5-b24a-bac36a2941d4 | note | Responsibility - BBL/CLL
ba236230-a27e-53a6-9dcb-4239f6ee7a1e | note | Hold Point H/W/S - DO: W
5a84510a-0eda-5b08-9220-d0e33b82945d | note | Hold Point H/W/S - BBO: W
6f3a1949-8b26-5c23-9f67-fb6e263dc4c4 | note | Hold Point H/W/S - CLL: W
5fbfce19-4d3e-5a01-abaa-3efa57f45c03 | note | Verifying Record - QAC - Pile Card
8536857f-2eab-5bad-9af8-1141c44eae76 | note | Comment - Pile to be overpoured and slurry at the top of the head removed until only sound concrete is present.
| checkpoint | 4.7 - Formation of construction joint
f581d9e2-cf40-5b7c-9b91-1cee11e67b4f | note | Frequency - Every Pile
79fb3271-da92-539e-9432-4c34ce89a05a | note | Responsibility - DO Rep/CLL
6b7303eb-5980-5128-8213-65756c332029 | note | Comment - Formation of construction joint by others.
| checkpoint | 4.8 - Concrete curing (tops of piles)
3ab9db28-18b1-58b9-8375-29b082114500 | note | Standard / Spec Reference - BBO SS 2146 Rev 4
adeffec9-e085-532b-b412-08212435cc08 | note | Acceptance Criteria - 7-day wet curing required
47ea7a56-bad4-5e05-83d5-65cfcfc01141 | note | Frequency - Every Pile
348082e8-a6fd-58d0-b953-7227dbd8ff1a | note | Comment - Concrete curing by others. Curing requirements will depend on the thickness of concrete which to be removed after concreting and weather conditions.
| checkpoint | 4.9 - Compressive Strength Sampling
522b68f4-7f1a-5bd3-adbe-25fbf41c7d31 | note | Standard / Spec Reference - NZS 3112
c3c8a389-8e3f-5e23-ac9e-53b49815cf55 | note | Acceptance Criteria - 28 day - 40MPa
c5b425b0-91f0-5222-af98-f0b2dc7b10bd | note | Frequency - Batch plant sampling and testing per piles – 4no cylinders – 1no @7 days, 3no @ 28 days
3c52277d-9bc0-545f-b820-abddd70359a4 | note | Responsibility - Concrete Supplier – samples cast at plant
67d5fa2a-2c19-5428-913e-81ca3f22e876 | note | Hold Point H/W/S - Sub: H
62e37f45-5d3b-56a4-be03-47ee6d03fb66 | note | Hold Point H/W/S - DO: S
92a92103-e907-5e5b-af77-1c42ce1d2964 | note | Hold Point H/W/S - BBO: S
bff9179e-3d25-5c50-b266-6d4335e05e1f | note | Hold Point H/W/S - CLL: S
b9194c85-45aa-537b-90aa-386b69c592a8 | note | Verifying Record - Lab. Test Record
6e5ebf70-a293-5979-8666-1c5743f59f04 | note | Comment - On site independent testing to be done by others. Samples to be taken at batch plant.
| signoff | HOLD POINT (Sub)
| checkpoint | 4.10 - Post pour/ Post casing removal - Reinforcement and concrete RL, orientation check.
5da39c36-338e-5d61-a610-cad927166bfc | note | Standard / Spec Reference - As per Auckland Structural Group Piling Specification
988a0b99-7530-5211-a1ea-809b054a8511 | note | Acceptance Criteria - Alignment lesser of +- 4% DIA or +-75mm Height +- 50mm Concrete cover: 75mm, 50mm minimum
445109f9-c35c-5735-afb4-9bf9e584066d | note | Frequency - Every Pile
dfbcc84e-ca31-5d63-a996-cedd4ed942ac | note | Responsibility - DO Rep/CLL
f805c3db-43a5-528a-848f-dcfcdb3914b8 | note | Hold Point H/W/S - DO: W
63899f76-220b-5c2a-ae75-8e9eb90a4f96 | note | Hold Point H/W/S - BBO: S
0c25cf28-8d08-5695-a159-a4380545d5b7 | note | Hold Point H/W/S - CLL: W
f3708420-2a35-54c9-aa00-3b636a2bb2fc | note | Verifying Record - QAC - Pile Card
79d0df54-b810-5bfd-ae22-b36a0dc1cbeb | note | Comment - As builts by others.
| section | 5.0 Close out
| checkpoint | 5.1 - Pile Cut off level verification
60e6bef7-48b9-5403-bec6-e68922ffa1d3 | note | Standard / Spec Reference - Construction Specification
d1dff8dd-ad15-57db-94c3-8538a13d2789 | note | Acceptance Criteria - +/- 10mm
ac152506-9a0d-558b-8ab6-d519b419ff0e | note | Frequency - Every Pile
1dc3fc39-ff34-5147-aef0-8828f79642ab | note | Responsibility - DO Rep
fa793d5d-0fbc-523e-b022-a779407e78a5 | note | Hold Point H/W/S - DO: S
4c0297bb-3fc0-50a4-9bf7-e53e27873c43 | note | Hold Point H/W/S - BBO: S
08375f72-a0fc-53ff-b22c-04f7c7b8cc76 | note | Verifying Record - Survey Record
| checkpoint | 5.2 - Pile & Reinforcement Cleaning
f10bacc4-6c83-59dc-ae57-0e47e11d700a | note | Standard / Spec Reference - Construction Specification
bbc7e2a8-6728-5dc4-ae5d-9f4d738d5319 | note | Acceptance Criteria - Visual
54efc8f7-eac3-5e18-861f-28439453975b | note | Frequency - Every Pile
55699227-4f9c-56b9-996a-f2468339df0c | note | Responsibility - DO Rep
25389885-052a-54dd-83c3-ef60830d729f | note | Hold Point H/W/S - DO: S
98f9e32b-e020-5b9d-ac8b-befaf733daae | note | Hold Point H/W/S - BBO: S
67785e7e-86e3-5d48-97e6-e288a24d6435 | note | Verifying Record - QAC - Pile Card
| checkpoint | 5.3 - Reinforcement to specification
e2231008-11df-5670-ab3f-458806c1c46d | note | Standard / Spec Reference - Construction Specification
cd4704b4-6f33-50e1-92b0-7e2d5e19ca43 | note | Acceptance Criteria - Visual
4a0b20bc-43a1-50e6-ad70-4be701ee1b8a | note | Frequency - Every Pile
eaaaf82c-5480-50e5-9298-582fac5dcd44 | note | Responsibility - DO Rep
e2c90418-6ab8-594b-a1d3-8c51b06d6859 | note | Hold Point H/W/S - DO: S
75e11b29-a15b-5b1f-a177-b23bfa350852 | note | Hold Point H/W/S - BBO: S
cc52a099-c4a8-5d40-9fab-5352cf304efc | note | Verifying Record - QAC - Pile Card
| checkpoint | 5.4 - Pile records
c027e63f-fd56-5676-a6d3-e5084e17b286 | note | Standard / Spec Reference - Construction Specification
efd3822b-78c4-56fb-a0a2-4afec4dd0e0d | note | Acceptance Criteria - Collation and Submission of records
4abf990d-cf56-502c-94fa-403039ac85d0 | note | Frequency - Within 24hrs of completion, Every Pile
cf5d8ca2-1b61-55d9-9a96-c2d50d40a909 | note | Responsibility - CLL
75c2c23e-5b26-5df6-8591-b673e576d090 | note | Hold Point H/W/S - DO: H
243147c3-4704-5bb6-a66c-ab5c836f8356 | note | Hold Point H/W/S - BBO: S
3a6b8d88-311d-5206-92a9-770062142582 | note | Verifying Record - Email Confirmation
| signoff | HOLD POINT (DO)
| checklist | ITP - Precast Barrier | itp | ITP - Precast Barrier | 22e13ecd-e913-42ad-bbc5-d10e61b39c0d
| section | 1.0 Pre Construction Tests
| checkpoint | 1.1 - Concrete Mix Desisgn Approval
d8c1387e-f340-5cb6-a9cf-119cf09ff8a4 | note | Acceptance Criteria - 50 MPa at 28 days (S5019MS8)
82822e8f-c181-529b-8ae6-9b7c3e8ee282 | note | Inspection or Test: Method - Review
17e1e32a-d78f-5fb1-9f9d-d80575a7af30 | note | Inspection or Test: Freq. - Once per Mix design / per supplier
922f1a8b-5a26-5977-8b57-0cac27c84dba | note | Inspection or Test: Responsible Person - PRECO
6e97688f-cb5f-547d-9922-2f73763498cf | note | Verifying Document - Confirmation of Approval
590495b6-fb84-5ea7-b9b2-a2e350925859 | note | Records required for handover package: Yes/No - Y
b24f9295-91b2-525a-bc27-a17dc6de323f | note | Inspection / Test Authority: Conduct - 1
a4a94b2c-233f-5b8c-8b94-42a42d0f34c7 | note | Inspection / Test Authority: Witness - D
21479b33-a765-589f-997e-a1e9506e3e0b | note | Inspection / Test Authority: Produce Record - 1
ead0723a-e8ec-56ee-8426-2f4945e60bf1 | note | Inspection / Test Authority: Approval - C
e84d0568-c9d5-5add-9e54-6d49955cd793 | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 1.2 - Reinforcement Supply – Certificate of Origin
6a3b2ea9-9c3a-5aad-9002-842ec48435f1 | note | Controlling Documents - Approved Drawings
e11db8b4-4148-5e5f-8a96-d6daf72989f5 | note | Acceptance Criteria - Provide certificate of origin for all steel reinforcing supplied.
92472c27-961a-5122-be14-5ff33260c473 | note | Inspection or Test: Method - Review
41843fb2-e96d-58a0-8f59-7428c40b6ed5 | note | Inspection or Test: Freq. - Per Size, Per Supplier
1d32e0c0-28aa-5c23-807e-31c15534bbc1 | note | Inspection or Test: Responsible Person - PRECO
851cb19b-14e9-583e-9fb7-444b361cb39b | note | Verifying Document - Supplier Mill Certificates
8bcd55e9-b715-562c-aeb7-35db9a2d1780 | note | Records required for handover package: Yes/No - Y
d0897f08-0a46-5ab2-a2aa-26b4cc70e071 | note | Inspection / Test Authority: Conduct - 4
5f717aef-d570-55f5-a7e9-588facad603c | note | Inspection / Test Authority: Witness - D
978c43fd-466c-5213-8c70-200dd0e727c5 | note | Inspection / Test Authority: Produce Record - 4
8b09c1ac-afd5-5f14-9319-cb632d46e505 | note | Inspection / Test Authority: Approval - C
2b805cb5-8bd6-5a2a-a47f-e4826f8c3386 | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 1.3 - Shop Drawing Approval
01f24f63-a8a8-5533-9795-d54100f46f05 | note | Controlling Documents - IFC Drawings
82a163aa-5ebb-5a1f-be85-a4d3dd3f1988 | note | Acceptance Criteria - Shop drawings including, concrete strengths, surface finishes, location of cast in items and set-out information
05e7ca4a-ae0a-5f34-a26e-5b9670930949 | note | Inspection or Test: Method - Review
695835da-bf07-5525-8b1c-47c5b4e314cc | note | Inspection or Test: Freq. - Once Prior to Casting
997d69a6-5c30-5ad6-87d5-923d6035c8e8 | note | Inspection or Test: Responsible Person - PRECO
62d2c64d-62fe-5e04-a810-579213f4ac7e | note | Verifying Document - Approved Shop Drawings, Issued for Construction
839e54a5-4a5c-5f3d-a108-fcd224e34d4a | note | Records required for handover package: Yes/No - Y
f4fd2d1a-3534-58ab-9235-c15f5cbada6d | note | Inspection / Test Authority: Conduct - C
ab881588-246c-5c6b-a63f-3332cb50be3d | note | Inspection / Test Authority: Witness - C
b0e4bc24-e62f-5ec1-a1bd-2e8c11a5e6f0 | note | Inspection / Test Authority: Produce Record - C
190341d8-174d-5b38-a15b-1870094d5a12 | note | Inspection / Test Authority: Approval - D
20a5d1e7-b4cb-515f-b447-f892596aea77 | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 1.4 - Form Release Agent
3ae381ed-20c5-51b1-97f3-1f566263548a | note | Acceptance Criteria - Not detrimental to the application of any subsequent finishes
20128331-ac7c-5ce1-999f-2a235b14700b | note | Inspection or Test: Method - Review
7d670198-1d1a-524a-b380-7af2ceb3ef58 | note | Inspection or Test: Freq. - Once
22eb0f03-2aee-54a6-9e46-92b83d40a4ae | note | Inspection or Test: Responsible Person - PRECO
e5a880a0-5942-5372-9568-9fcbf5f0458f | note | Verifying Document - Material Data Sheet
aa2035b9-00ae-5b2f-a8a3-77293821f2c6 | note | Records required for handover package: Yes/No - Y
6a8e216c-3a6d-5a39-a1d4-e0d1cc53f8aa | note | Inspection / Test Authority: Conduct - C
437aac02-281f-549e-8aa4-dba7011957da | note | Inspection / Test Authority: Produce Record - S
8dafda5f-5c6d-5397-97d9-fd57a8fadd13 | note | Inspection / Test Authority: Approval - C
0d828057-93e9-5e69-8d1e-079094db6520 | note | Hold Point - N
| checkpoint | 1.5 - Cast-in Items
191fdecd-efd8-52c3-bf6f-fb59fbd5baa1 | note | Acceptance Criteria - Provide certificate of origin for cast-in-items
fc62b7b0-cad3-531f-b28a-dca8e9324524 | note | Inspection or Test: Method - Review
7b724a24-18dd-518e-9580-d4c69eed6379 | note | Inspection or Test: Freq. - Per batch delivered
c706b1fd-9a71-5789-84a6-97e8f67a1258 | note | Inspection or Test: Responsible Person - PRECO
76a37be5-fbc7-531b-b323-6e2757c8b25d | note | Verifying Document - Suppliers Mill Certificate
5b9e05d2-a92b-51ac-910c-0a990b6a07db | note | Records required for handover package: Yes/No - Y
c5d321b4-8305-5159-a1cb-2b116d474a21 | note | Inspection / Test Authority: Conduct - 4
3dc93ab7-004e-56a4-8fad-e30442f4cf2a | note | Inspection / Test Authority: Witness - C
474dd962-a1cb-5aa2-a069-a4dec55c6dd8 | note | Inspection / Test Authority: Produce Record - 4
2cb46a60-93aa-5849-8620-5df7c6b2f17a | note | Inspection / Test Authority: Approval - C
4078a876-a52a-5bcd-8995-a003a05e0174 | note | Hold Point - N
| section | 2.0 In Process Testing
| checkpoint | 2.1 - Inspection of The Reinforcing
8dda2c2a-6ce2-5130-a053-532dfee26c60 | note | Acceptance Criteria - 40 mm min. clear cover to all reinforcing including stirrups and ties
9482d366-67a4-5ebe-be2b-03e80b5a4174 | note | ○ Steel to be securely tied and fixed with no movement
22ac8de6-6e72-584e-ac23-0d37e0e42adc | note | Inspection or Test: Method - Inspect
59b84c6c-85b2-5826-b7bf-4afa30c31b4b | note | Inspection or Test: Freq. - Per Unit
4eab1891-96b6-59c3-957f-05e9e7f8c667 | note | Inspection or Test: Responsible Person - PRECO
980bd4e2-fede-5d11-b49a-00ca53cdf45d | note | Verifying Document - Pre pour checksheet, photos
52dd7dcb-9fb5-5455-9c91-18ea7e926987 | note | Records required for handover package: Yes/No - Y
646d609a-8a56-5657-ae06-8224973902ea | note | Inspection / Test Authority: Conduct - C
c3248dcf-db60-5ea8-987f-6b8cb50642c5 | note | Inspection / Test Authority: Witness - D
78951cc8-b562-545c-8fd6-473256170749 | note | Inspection / Test Authority: Produce Record - C
a075679e-8bd9-57ae-82a3-8853d4e7fc6f | note | Inspection / Test Authority: Approval - C
1c40571c-d8e9-536e-814a-f22448a2afff | note | Hold Point - N
| checkpoint | 2.2 - Checking Formwork
d59f7513-cf1d-528f-87ee-7f54243a1361 | note | Acceptance Criteria - Dimension including edge details and rebates as per drawing
1175cfb5-e783-560d-a6a9-d91dda4acea1 | note | Inspection or Test: Method - Inspect
f29a3f3b-d608-50aa-9650-55fc0a38d3ce | note | Inspection or Test: Freq. - Per Unit
aacc72e0-9968-58ff-92b3-8e6e4f2f5b89 | note | Inspection or Test: Responsible Person - PRECO
af983bfb-d586-5e80-9fc4-583a4cbf32a0 | note | Verifying Document - Pre pour checksheet, photos
5cac43b4-6466-5164-a815-c76dc171549c | note | Records required for handover package: Yes/No - Y
58763972-25fd-5ac6-a1d8-ef95cfabe5a5 | note | Inspection / Test Authority: Conduct - C
ecd6bf87-85e5-553c-95f0-c5d61bc48ecb | note | Inspection / Test Authority: Witness - C
f98de228-e39b-5174-9a7f-8bb2d6f92974 | note | Inspection / Test Authority: Produce Record - C
e64ec3aa-a4bc-52e1-9339-c7a2ad308c5e | note | Inspection / Test Authority: Approval - C
802ea10b-5e2f-5af8-854d-5ff010bdc2d6 | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 2.3 - Pre Pour Inspection Prior to concrete placement
9ab5217c-e2cd-5fdb-9388-5f25adfb5d63 | note | Acceptance Criteria - Completed pre-pour inspection, permission to commence concrete placement
444c6e66-1951-5b7b-8799-659954e74703 | note | Inspection or Test: Method - Inspect
10fa7972-4848-5030-92c5-a39c41f0179e | note | Inspection or Test: Freq. - Per Unit
b39d3345-104b-5d2a-901d-766e47400126 | note | Inspection or Test: Responsible Person - PRECO
273b5932-9a67-5edc-af41-00ff28326c5f | note | Verifying Document - Pre-Pour Check Sheet/ photos
87e0b84d-92d4-51f0-b63e-fb69c1e86fac | note | Records required for handover package: Yes/No - Y
6365b53b-d5f9-5e8f-b8fe-0aa99e7506be | note | Inspection / Test Authority: Conduct - C
ea11e90c-e0bb-5340-9710-b5df8f2cfde8 | note | Inspection / Test Authority: Witness - D
208f718f-0a75-5f36-aa38-1a35ca59f7a9 | note | Inspection / Test Authority: Produce Record - C
e3b7a418-9b94-5f4d-a64d-cde7d8ac481e | note | Inspection / Test Authority: Approval - C
1317ad0a-ce1c-56b9-9d31-51ef2fd53508 | note | Hold Point - Y
| signoff | HOLD POINT
| section | 3.0 Concrete Testing and Inspection
| checkpoint | 3.1 - Concrete Delivery
296c0544-627f-5cb8-8ccf-fa3c00e0c563 | note | Acceptance Criteria - Approved Mix Design (S5019MS8)
e09836e7-e944-5b41-a628-e3f722fd1112 | note | Inspection or Test: Method - Inspect
73172d08-d70c-5c91-8a6d-abc43520e3bb | note | Inspection or Test: Freq. - Per Concrete Delivery
6491128f-374a-59e8-8c93-46f50daa8abf | note | Inspection or Test: Responsible Person - PRECO
76468661-1f35-509e-987c-bb8ddef86349 | note | Verifying Document - Delivery Dockets
6a509483-7609-5bea-b5d3-42e77bb27926 | note | Records required for handover package: Yes/No - Y
7e5c1ae7-4654-51e1-a97e-8b3a557b59d6 | note | Inspection / Test Authority: Conduct - C
1d1cadf0-d5ad-5ab5-92e1-51052729e03e | note | Inspection / Test Authority: Witness - C
5fa8589e-5b9c-571f-bac9-db74040c9459 | note | Inspection / Test Authority: Produce Record - C
de346339-d61a-55a7-ba96-207fe74e50e4 | note | Inspection / Test Authority: Approval - C
70768a97-bb2e-5c6c-bb41-b6dffa215225 | note | Hold Point - Y
| signoff | HOLD POINT
| checkpoint | 3.2 - Concrete Placement
b7612537-785b-5c47-897f-0dffa8459c5c | note | Controlling Documents - NZ 3109
03d33a90-5556-5f22-8d9c-46cd3ffee61d | note | Acceptance Criteria - Vibration of concrete to ensure suitable compaction
f92b1f4a-62e7-54be-b0f6-06940e48a240 | note | ○ Slump within target 100+/-40
58a16842-dc9d-5669-81a9-f9cce43d1705 | note | Inspection or Test: Method - inspect
a09d97af-f824-5dce-98df-b0de190ff109 | note | Inspection or Test: Freq. - Per unit
077c5cd0-3f48-5446-9775-52c6ce128d2e | note | Inspection or Test: Responsible Person - PRECO
27d1c5c3-6b9a-5d30-acf9-519451febdf5 | note | Verifying Document - Witness inspection
3a7fe327-77c7-53f8-8685-610a5c572c56 | note | Records required for handover package: Yes/No - N
762ee824-9acb-51e9-80eb-fc021982475c | note | Inspection / Test Authority: Conduct - C
4bb788dd-8ff2-5043-99e2-67aa9adccb74 | note | Inspection / Test Authority: Witness - C
1b6a9469-9659-527b-9fcb-b8b9b191f43f | note | Hold Point - N
| section | 4.0 Post Concrete Testing and Inspection
| checkpoint | 4.1 - Concrete smpling / testing
ac8036a4-52c9-55c5-9048-7e4424a39e53 | note | Acceptance Criteria - 1 x 7d and 3 x 28d - 50 MPa at 28 days
cb06f198-2fc0-5a49-96ff-af413b4280e6 | note | Inspection or Test: Method - Concrete Sampling
1d3ac0ba-70e5-5047-94ee-68ff84fbdb5c | note | Inspection or Test: Freq. - Per 75 m3 (not part thereof)
73dc4b4d-6d20-50e7-a00c-53beb9e7e682 | note | Inspection or Test: Responsible Person - Subcontractor
867bc4d8-1c15-5688-8f7c-d12e26deeafe | note | Verifying Document - Concrete Sample Test Results (IANZ Accredited Laboratory)
6a8dd5b4-8114-53f0-a625-9f2a10d108ec | note | Records required for handover package: Yes/No - Y
fb47404f-d673-51d1-9dde-96e1c28ec324 | note | Inspection / Test Authority: Conduct - C
2a5b41ca-7ced-5247-a3b5-592077b03b9d | note | Inspection / Test Authority: Witness - C
555306d6-43ec-5ead-96da-7a4dadecdaed | note | Inspection / Test Authority: Produce Record - 3
a04b5bc2-3ceb-5151-9f28-03ee5bed39a1 | note | Inspection / Test Authority: Approval - C
8580c40a-f952-5a4e-b4de-ed19a5b5b4e0 | note | Hold Point - Y (Designer to be notified immediately if specimen fails)
| signoff | HOLD POINT
| checkpoint | 4.2 - Surface Finish Requirements
970ed5bd-ceb8-5bb4-9cd6-a51374433d88 | note | Controlling Documents - IFC Drawings
3a816951-23ae-5c00-be0d-9bf406e64319 | note | Acceptance Criteria - F5 / Type B construction joint to NZ 3109
2cfd5b87-68dd-5eb0-86dc-9d4f396b91b9 | note | Inspection or Test: Method - Inspect
bbcab98e-e450-5f80-96b7-dd2bc0853272 | note | Inspection or Test: Freq. - Per Unit
730970bd-c98c-5426-8a15-749f3ebf02e8 | note | Inspection or Test: Responsible Person - PRECO
d9dc372c-d89b-5b40-9169-08a8380efbea | note | Verifying Document - Post Pour Checksheet
f1075e86-4059-5992-ace8-f806ec58a37e | note | Records required for handover package: Yes/No - Y
b2e4f0f2-e6fe-537d-a7be-93bd9deb8d21 | note | Inspection / Test Authority: Conduct - C
f3c88a89-d0e9-59f4-8308-4a403d177b96 | note | Inspection / Test Authority: Witness - C
4bb6e2f2-8054-5fa2-a8f2-5fe75440994c | note | Inspection / Test Authority: Produce Record - C
7d325357-f7e2-5bf4-8242-6b2eb96e5fce | note | Inspection / Test Authority: Approval - D
cb6579f7-877d-5b49-b14f-556ce8468624 | note | Hold Point - Y (Designer to be notified if finish requirement not meant)
| signoff | HOLD POINT
| checkpoint | 4.3 - Concrete Curing
6d81ae7e-5250-5248-9ee3-94b487944a98 | note | Acceptance Criteria - Curing with curing compound (e-cure)
8e9da9c3-29f5-5d7b-96e9-5695fa15434d | note | Inspection or Test: Method - Inspect
2026a907-8246-52c2-afbc-9c7e1cb8da2f | note | Inspection or Test: Freq. - Per Unit
72b915a8-7450-50ee-9e42-0fbe53eaf8b6 | note | Inspection or Test: Responsible Person - PRECO
3c0231eb-070d-54e7-9229-07e3271c5cb3 | note | Verifying Document - Post Pour Checksheet
115a294b-f979-5d22-9393-cfeb8bbedc79 | note | Records required for handover package: Yes/No - Y
a3a2c096-c118-5c4e-9165-c4ad75f5c906 | note | Inspection / Test Authority: Conduct - C
4e8933ed-b582-5d65-8d62-5dbe6846e0a7 | note | Inspection / Test Authority: Witness - C
82c6c6c3-8dd7-5b6c-a6ec-04d5507d41de | note | Inspection / Test Authority: Produce Record - C
775663b2-4b2f-52e6-9523-c4da7e95f922 | note | Inspection / Test Authority: Approval - C
45785fe4-d994-5bd7-9d20-b13f8492185d | note | Hold Point - Y
| signoff | HOLD POINT
| section | 5.0 Final Documentation
| checkpoint | 5.1 - Producer Statement (PS3)
1a1341a6-c738-5453-a224-d291e69b0bec | note | Acceptance Criteria - Signed PS3
0cb2d76c-afdd-5abf-863e-08404ef07f13 | note | Inspection or Test: Method - Report Production
1d9396f6-ea72-58e8-8c21-22cf717d212a | note | Inspection or Test: Responsible Person - PRECO
38b5f39c-b2bd-5bd8-a5a8-7e63a9478b96 | note | Verifying Document - Signed PS3
c684c088-1b8e-5e64-9f95-d76853df1aae | note | Records required for handover package: Yes/No - Y
0d43f981-bf55-57a3-ac91-131e1ebce22c | note | Inspection / Test Authority: Conduct - C
b1fb543e-72a2-57cf-a247-ac4f7222d82d | note | Inspection / Test Authority: Produce Record - C
063d5691-9cda-5cb6-901b-6e036a4af6e0 | note | Inspection / Test Authority: Approval - D
c599dcef-8922-57d8-8daa-4b939c9f4ea3 | note | Hold Point - N
| checklist | ITP - Retaining Walls - Rev C |  | ITP - Retaining Walls | 160ff124-05ca-4c84-bec2-5dd2af07e02a
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
dfb723bb-584a-5713-be6d-07b0f19feadc | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
e2830cdf-362b-5f0e-8d22-f68f1a98219d | note | Standard / Specification - Downer
14282032-c33f-55dc-9ae6-ba093f01c0fa | note | Verifying Document - Construction Pack
9e7ee91d-d82a-5694-af12-0f67083b3c87 | note | Frequency - Submit 10 days prior to commencement of works
2a4ab9d4-071d-53fa-ac91-77f26febe2a2 | note | Activity - HP
d5d6a8c7-50e2-54b9-96ba-d6ed63ed046c | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.01.02 - Survey Setout
dc572b14-0ed6-54c7-bc8f-85ed00c03dfe | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
3e946a9d-b5c8-50e7-96e0-0400e8f6e89c | note | Standard / Specification - Downer
34bb53e5-aed2-52e3-a5c2-9f81d0a823ca | note | Verifying Document - Survey Records
61d76f5d-0ad9-583f-ac76-86ad184fa739 | note | Frequency - Prior to Works
376f33df-3b2b-5b0c-ab68-eb1a544a497d | note | Activity - H
c900da17-59f9-5691-b9d1-3bcd5996d491 | note | By - SV
| checkpoint | 3.01.03 - Service Location
b9f21eeb-7675-5741-9a79-4af249ac51cd | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
434102cd-5777-54cc-b4b5-32744d498024 | note | Standard / Specification - Downer
07a728fa-eece-56e9-af95-f512783809d3 | note | Verifying Document - Excavation Permit
077eeafa-3bad-5034-9687-5e46d0d70d1b | note | Frequency - Prior to Excavation
f621f899-2387-5113-900d-6bf9fc014ca0 | note | Activity - H
765fd8e2-b34a-5911-8b80-bd9e215f5033 | note | By - SE
| checkpoint | 3.01.04 - Internal Permits
b356337b-ff8b-5218-b916-0250a1283683 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
a1b106e9-f9c2-5c82-9b78-bc7a5e36b3d8 | note | Standard / Specification - Downer
62309b3c-27a8-5c74-8629-890633f13944 | note | Verifying Document - Internal Permits
83e97ed8-8c87-565f-9e65-f307d506c6a2 | note | Frequency - Prior to Excavation
d9a60eb7-5a01-5a8f-8f3f-6ce4ccaaa502 | note | Activity - H
3d563ef1-3b79-577d-b94f-308e34e1ca4e | note | By - SE
| checkpoint | 3.01.05 - External Permits
b3b0e978-a810-584e-aa53-c42ce3c97641 | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
da4f0b71-5efa-5c01-ad1a-988c4ed5ce74 | note | Standard / Specification - Downer
9637f9ab-b7c6-54c8-8436-24c62804f0c4 | note | Verifying Document - External Permits
86a70157-a919-5dd5-aa32-c8681501a34c | note | Frequency - Prior to Excavation
bdcdc434-1b5d-5073-8411-b8512f1171ba | note | Activity - H
9a96dd8f-f51a-5d85-90aa-2277fca1a9b8 | note | By - PE
| checkpoint | 3.01.06 - Approved Construction Drawings
9ff0acba-9273-52f4-a0a4-2ab6d34c8a37 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
35f67329-e2c7-5487-a6d4-58b982b7c249 | note | Standard / Specification - Downer
3dfe5430-9c4a-5998-aade-3c0355af63af | note | Verifying Document - IFC Drawings
2b7e4a6a-c00a-5a00-ac72-61e46e5f805a | note | Frequency - Prior to works start
64beb55c-164d-586e-993a-71bf994ecd03 | note | Activity - H
16b491c1-6520-5184-a1cd-e89a84b6dddc | note | By - PE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
| checkpoint | 4.01.01 - Stone Strong Block Molds
24a4862f-20e9-5858-9e47-682e8ebdcd0f | note | Acceptance / Conformance Criteria - Stonestrong blocks to be supplied by an approved supplier. The Contractor shall liaise with the Principal-appointed Cultural Artist to coordinate carving of the supplied blanks and the production of moulds & blocks
b7e1ac9b-4fd0-5aed-91f1-207545543544 | note | Standard / Specification - PS - 12
4fbb56e2-610f-5ab3-b571-8d5a95c19942 | note | Verifying Document - Conforming Molds Post Carving
4ea6de2e-aec5-50b2-a438-bd4bd870e686 | note | Frequency - Before Installation
d4a2256c-c353-57e5-9fce-3979c4f41a52 | note | Activity - H
1c7d0313-833b-5b02-8452-76e926b94d30 | note | By - PE
| checkpoint | 4.01.02 - MSE retaining wall backfill Material
cc3d6c38-7cdf-5ccc-b3de-82e5fa7d81b3 | note | Acceptance / Conformance Criteria - Backfill is to comprise a well graded, granular material such as GAP65 or site won Hinuera Sand, which must be free of any deleterious material. Sand backfill shall have a fines content (less than 0.075mm diameter) of no more than 10%. Labratory MDD (x2 per material type) at standard compaction
22721888-49d4-5ebd-a823-b786fde9c2dd | note | Standard / Specification - GWS - 5.3.3
f760ee7e-3e30-5748-ac8d-dd6f4cff2189 | note | Verifying Document - Lab Results
ac1f5c71-71b7-5418-a6b3-d83649055b3c | note | Frequency - Prior to works
951e9d5f-bd61-5982-b242-bf9f0c0caffb | note | Activity - H
8ebf4f1b-07e1-53f7-b331-bcd4af254b27 | note | By - PE
| checkpoint | 4.01.03 - Geogrid
a5ac5972-5125-5559-af6d-1c6c4e7dedcc | note | Acceptance / Conformance Criteria - Geogrid to be Miragrid GX200/30 or similar approved
9f8013ff-90e1-57c2-9d72-3a9dffbf0e78 | note | Standard / Specification - GWS - 5.3.1
0a7a8e2c-6643-54d0-a7a9-d2756a3ae4b4 | note | Verifying Document - Datasheet
8616060a-d369-50b8-aaba-ef3009718c94 | note | Frequency - Before Installation
a58b35f4-bec7-526e-a186-cb8cfac7ff0c | note | Activity - H
96867ef7-72bf-5c39-9276-a8fa57a392dc | note | By - PE
| checkpoint | 4.01.04 - Para web
1caebfdf-02c1-5487-a1c2-99494d3a7d32 | note | Acceptance / Conformance Criteria - Paraweb to be the correct grade: Paraweb 2D-50
fc6b5ecc-9ae5-5429-b362-4e4e740b858a | note | Standard / Specification - GWS - 5.3.2
c6a61179-13b0-5cce-86df-0b2aee73ba18 | note | Verifying Document - Datasheet
d6d44771-ac67-536d-add9-852624175da7 | note | Frequency - Before Installation
9d9aac6a-b187-50c7-bcbc-e7f671b406f3 | note | Activity - H
55508e0c-9e1b-52b3-a5d1-64da039c0ec6 | note | By - PE
| checkpoint | 4.01.05 - Drainage Pipes
7a5b659a-8903-53d2-923a-b6d92a4b1645 | note | Acceptance / Conformance Criteria - Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated corrugated pipe with filter sock
7794d7ea-668a-5c32-bb0f-3680b36f6de3 | note | Standard / Specification - GWS - 5.3.4
ea8e0216-d0f1-54d5-92d8-9b9fa06b7076 | note | Verifying Document - Datasheet
d56eee96-b50c-5a01-acdc-8056d052ceaa | note | Frequency - Before Installation
395116fd-81ab-5fbc-8151-6255ffeb4a71 | note | Activity - H
8fb5b411-f437-5583-8180-b42cdf2a2a99 | note | By - PE
| checkpoint | 4.01.06 - Geocomposite drainage board
cd6be02c-c749-5f25-acc3-4ffb2cefa944 | note | Acceptance / Conformance Criteria - Shall be Cirtex Armour flow, or similar accepted by the Engineer
ebf65b67-521d-5975-ac96-0b04a5a626cd | note | Standard / Specification - PS - 12
1de52d81-e41e-553d-9c21-f0f6340ab64c | note | Verifying Document - Datasheet
0987a3f2-09ee-5a15-a403-5dac4b2b4eb3 | note | Frequency - Before Installation
f2e98e9e-bba5-51b9-b10c-728c27a797b5 | note | Activity - H
29b83dfe-e46e-5abc-a914-d0df434d4e6f | note | By - PE
| section | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
| checkpoint | 5.01.01 - Excavation to subgrade
a44eca19-0903-53b8-b909-f430fbf6b9bf | note | Acceptance / Conformance Criteria - The foundation materials are to comprise natural Hinuera sand material, stiff Hinuera Silt or imported clean sand and must achieve a minimum of 4 blows per 100mm when tested with a Scala penetrometer. Any exposed silts must have vane shear strengths greater than 70kPa.
5722bcfc-454b-577a-9ad1-d3e3205134b4 | note | Standard / Specification - GWS - 5.2
915e6908-c8fe-5ac1-9db4-a947962d0041 | note | Verifying Document - Scala Results
a490c5fe-167a-5b44-ab44-b30841d751aa | note | Frequency - Every 10m
6289dc62-ab20-571f-9d3e-14f5140d96a5 | note | Activity - H
b7a8ce23-7996-5bcd-af78-3797ae943025 | note | By - SE
| checkpoint | 5.01.02 - Foundation Approval
88bbf40b-3a7e-5106-a1eb-b04cac8b3276 | note | Acceptance / Conformance Criteria - Results of the foundation material testing shall be supplied to the Engineer for approval and the prepared ground shall be inspected by the Engineer. Construction may not proceed until receiving Engineer’s approval.
87cf84f3-b265-54c8-91f4-8fe99cf580ac | note | Standard / Specification - GWS - 5.2
1686d54b-8287-51df-86cf-43bc7127c4b6 | note | Verifying Document - Approval
92f82e7a-8f29-5590-9360-08dca36f2305 | note | Frequency - Prior to proceeding. Min 48h notice to Engineer
75d2a1b0-4525-5583-9519-6b0bab956b25 | note | Activity - HP
13ca0be8-8086-5cfa-835c-649526f18337 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.03 - Undercut subgrade
3a1426c3-4a4b-50d6-8c92-de9a0f129814 | note | Acceptance / Conformance Criteria - Any unsuitable materials, such as uncontrolled fill, contaminated materials or any weak or organic materials, shall be undercut and replaced with compacted granular fill (WHAP65 or equivalent) or Hinuera Sand. Surveyor to capture extent of undercut (if any) to include in asbuilt.
a162c6e4-10cd-5f4e-aee1-19aebcb4c8b1 | note | Standard / Specification - GWS - 5.2
f1f6c15f-6596-5cfe-9cd1-5734db4e100b | note | Verifying Document - Survey Record/ Photo record
37cd6678-71f7-5b8a-aaae-7266b0c53b90 | note | Frequency - If required
09fca302-cdb5-5d57-a109-7acf55153583 | note | Activity - I
839acd88-9afc-5d25-87e1-5dc15047bc55 | note | By - SE
| checkpoint | 5.01.04 - Undercut backfill compaction
686827fe-56ed-5bab-9d64-495ebf6340bf | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
e5515d9a-8cc8-5f73-9ca8-e055c4cc041f | note | Standard / Specification - GWS - Table 3
08c502fa-14b9-5b61-b1a0-0533d2b91f20 | note | Verifying Document - NDM Results
49be031b-95ea-5b55-97e3-3536950c4134 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
14a27680-1a25-52b8-bd00-1fab40f44075 | note | Activity - H
c95dd2e2-6397-5c53-ba34-465a08f15a20 | note | By - SE
| checkpoint | 5.01.05 - Geogrid Installation
7c06f150-6a83-5a7f-bf9e-26add933060a | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. Engineer to inspect 1 layer prior to backfill.
8150c2df-f463-5e1e-9900-9baeb8241b95 | note | Standard / Specification - GWS - 4.1
502aec9f-4e98-5c7b-ade9-d8d49f08c81f | note | Verifying Document - Photo record
956b32f9-ff13-55e8-a916-4c3f79f7faac | note | Frequency - Each layer - 1 layer per abutment to be inspected
1f4aba03-43ec-52d8-9410-bef8fd128ad6 | note | Activity - HP
2ce0bc49-bf59-54a7-a221-56df0205defd | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.06 - Backfill Installation
c7c2d1b0-c2f8-5768-8d67-067103ab63da | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts and compacted to the following standards.
523bffe5-aaee-5a9b-8e89-14e05f013cba | note | Standard / Specification - GWS - 5.3.3
11658044-8281-56e6-9f67-20faad0299fb | note | Verifying Document - Photo record
ac859c0c-278d-5b8e-a292-46ad56fb0962 | note | Frequency - Each layer
ef9db130-4c9f-5391-867a-972b372090fa | note | Activity - I
a3687b6e-7c6b-53f0-b274-e31e41cd696f | note | By - SUP
| checkpoint | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
f8d240d7-018f-5b3f-8c5e-fe7537ae63e0 | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
ad7fa407-e378-5634-ab93-1828e1f82e34 | note | Standard / Specification - GWS - Table 3
84067f73-90f3-5c9f-bcc9-3412062ae46f | note | Verifying Document - NDM Results
215fd151-1567-5313-ab16-40cc8c973c76 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
b1904192-86c4-5dc0-983d-0c4625692197 | note | Activity - H
1759d2ab-8aaf-5e44-8271-0bca9708cfa4 | note | By - SE
| checkpoint | 5.01.08 - Clegg/Proofroll (Gap 65)
98614c55-f750-506f-9503-10c3e30e1881 | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test. Engineer to proofroll/inspect final layer of load transfer platform.
2f9fe1ac-2fbc-57be-ac76-85de65fe652e | note | Standard / Specification - GWS - Table 3
4e604154-4a81-55e9-b377-2b88c923b018 | note | Verifying Document - Clegg Result sheet
bd438c47-31e5-566a-944c-a5b5c76088c7 | note | Frequency - Each layer - final layer to be inspected
774d86f1-ba7c-50b6-94d6-30bf5a948c3f | note | Activity - HP
7364a921-2ff7-5c35-9159-3054bb9afa4c | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.09 - Scala Penetrometer (Hinuera Sand)
0de6b358-0f29-58af-ad62-e6befe37e01e | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
723574f2-3e35-56ba-972d-31c4f942de55 | note | Standard / Specification - GWS - Table 3
950d9fe5-4c1e-50e8-b794-ead1b2cf7d81 | note | Verifying Document - Scala Results
1f645c31-308b-548f-8dde-196580b6b892 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
6720fe90-9a00-56ad-8968-01ae35b290ac | note | Activity - H
714be469-f8be-5424-9050-e3ecf0a94400 | note | By - SE
| checkpoint | 5.02.01 - Level founding platform
9c8eb987-df2c-50a7-95ae-edac73b9c3d4 | note | Acceptance / Conformance Criteria - The Contractor shall construct a 200 mm thick levelling pad on top of the load transfer platform to create a level founding platform to accept the MSE retaining wall.
ca1e2ed9-2c2b-5b18-a741-e994b2b723df | note | Standard / Specification - PS - 12
43ce2579-fec0-5318-87c6-4a8e9b3a20bb | note | Verifying Document - Site Photo / Checksheet
1b680dd9-e479-578f-bbde-69c1729e3ee9 | note | Frequency - Prior to Stone Strong block installation
a9c7ed43-8613-5ebc-857e-690eca1a5585 | note | Activity - I
b5fbdddf-aa08-5620-83bd-7340b7acd380 | note | By - SUP
| checkpoint | 5.02.02 - Installation of blocks
90ef02e4-593b-5fb9-a2a3-b68fe5c81ecb | note | Acceptance / Conformance Criteria - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances.
32d1b68c-0bfe-5bb2-abd7-26cb71e423d5 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
b12d3329-7987-5247-b922-ec1c92c9ed00 | note | Table 4: MSE Tolerances
dfcb71bb-f02b-56d1-bd66-3ef672ac4eab | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
8d01ee4b-e521-522d-8a7a-9bd9cf9cf39e | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
c9b8de3b-7e7d-54be-a648-be447dff7dc0 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
18339fca-9026-508b-96e4-2fb4655e0c6a | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
7e0bf557-a381-509d-8795-4822c3e0c715 | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
a3fbd331-d3ef-513a-8a89-9470f7fdb303 | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
3c7b2ddd-a24b-5b7f-9049-436a8e69bce4 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
07037d56-3fae-5229-bb84-bcd2d797e781 | note | Standard / Specification - GWS - 5.4
48c1e9a8-8b89-527a-91c8-f72b261b72e0 | note | Verifying Document - Site Photo / Checksheet
54fda68a-448a-5dcd-8ed6-0a86c20b0e5a | note | Frequency - Each layer
913f0a58-b1ca-5bfb-8468-b952a9389447 | note | Activity - I
2396be86-4697-57ce-b7b9-b3a1d1c2257a | note | By - SUP
| checkpoint | 5.02.03 - Paraweb Installation
0bef5334-c77a-5d85-8b74-f29c3c8ca7fc | note | Acceptance / Conformance Criteria - The correct number of parawebs are to be installed as shown on the construction drawings.
622c6a80-827b-564b-a1b0-826cc8553560 | note | ○ Para web is to be placed flat or with a 1% fall toward the rear of the wall. The Para web must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
50d68f77-c004-52f2-a57e-49698bdf2f38 | note | ○ The Para web must be continuous over the design embedment length and no joins are permitted unless adequately lapped and spliced according to the Manufacturer’s instructions.
8668a89a-332f-5adb-87ff-04813367b41f | note | ○ 150mm of fill cover is required before construction equipment can travel over the area
302495c3-5f3f-555b-bf19-8ba352b3798f | note | Standard / Specification - GWS - 5.3.2
e0f8ebd4-b7ce-5d74-8e8e-61d1497a1d0e | note | Verifying Document - Site Photo / Checksheet
19a36404-73ee-57c2-ad94-ea23f2a50577 | note | Frequency - Each layer
4ed90da9-8014-54fc-aff4-4d93fce754c9 | note | Activity - I
62c634e1-5096-505b-a986-ddb7ae13ae72 | note | By - SUP
| checkpoint | 5.02.04 - Geocomposite drainage board
c4be583a-f1eb-5cd7-8b53-c99e616f142c | note | Acceptance / Conformance Criteria - Geocomposite drainage board shall be installed continuously along the back face of the block facing of all MSE retaining walls using an approved adhesive recommended by the manufacturer. Check for correct layout, orientation, and any damage prior to backfilling
78a5af09-b43a-593b-9bb0-cca35aca7587 | note | Standard / Specification - PS - 12
118e3434-7671-5ed3-835d-7fc4d8175aa3 | note | Verifying Document - Site Photo / Checksheet
660025ef-3ab6-58f4-8765-86925343e3ef | note | Frequency - During Installation
f0897641-79a2-502d-bcea-6e4441ba74e5 | note | Activity - I
d79c9d3d-ecfc-5167-a08b-44cff7e6fe7e | note | By - SUP
| checkpoint | 5.02.05 - Drainage Outlet Installation
a3d090c3-4428-5e0a-b209-adf7336af691 | note | Acceptance / Conformance Criteria - Drainage pipe wraped in filter sock to be installed along the base of the wall. Drainage outlets shall be connected to the reticulated stormwater system or other approved outlet structure at the discretion of the design engineer
6cfacb22-26fd-5135-a015-17dab1cd0170 | note | Standard / Specification - GWS - 5.3.4
2f5a5615-723b-5d5e-8c70-f4b89d64455c | note | Verifying Document - Site Photo / Checksheet
f38b6aaa-750a-5eb3-81e7-0481324cad07 | note | Frequency - During Installation
63a09817-83ab-53aa-95b2-fbb6cbd5e6e6 | note | Activity - I
64e8f6bc-35c8-50a6-aeff-2ac4d35244b0 | note | By - SUP
| checkpoint | 5.02.06 - Backfill Installation
68b82bbb-bd2b-500a-9ace-74ec7c5ebb50 | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts adnd compacted to the following standards.
31c539fd-4460-53ad-bfdf-2e97fcb8b655 | note | Standard / Specification - GWS - 5.3.3
633cfa75-f662-58c2-a120-4024e3c6b0a4 | note | Verifying Document - Site Photo / Checksheet
6d4d0c18-479a-58d2-a5ec-cf710b5f1faa | note | Frequency - Each layer
5972cd9e-2fb0-509b-bef1-f765dd7cccb7 | note | Activity - I
b83ffa94-0016-517c-bb97-f82c899c2703 | note | By - SUP
| checkpoint | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
f13ff92b-3515-51d0-a988-a8689f2dd02b | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
4a4d2b6a-8a2e-5174-a75c-a0f7cf753f69 | note | Standard / Specification - GWS - Table 3
6554928e-3918-5c68-b1ac-81e6cb332423 | note | Verifying Document - NDM Results
98493087-ecca-5702-9b92-25f0664f918b | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
554f611d-c99e-592d-bee2-843015f016da | note | Activity - H
ccf5b3da-cdf5-5795-9145-2a6b32d69f7e | note | By - SE
| checkpoint | 5.02.08 - Clegg/Proofroll (Gap 65)
003d8931-bc62-5135-b7be-32aa75313eac | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test.
3874ad51-8f8b-575e-9170-0695e7fdc9bc | note | Standard / Specification - GWS - Table 3
4d765a6d-f986-55ae-a453-6684618ffc0e | note | Verifying Document - Clegg Result sheet
12a070cf-7dac-57ab-a68e-41e36105e8a1 | note | Frequency - Each layer
0313e548-65cb-50f0-85a4-231e5e4b576b | note | Activity - H
dcd71dcd-85cb-5dee-945b-745855383c9a | note | By - SE
| checkpoint | 5.02.09 - Scala Penetrometer (Hinuera Sand)
4efbde40-a847-5874-adf2-744ee100a9d9 | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
78e0595b-f746-5ce0-b84e-30718f228843 | note | Standard / Specification - GWS - Table 3
afe343f9-b761-5bae-855e-8f1669892985 | note | Verifying Document - Scala Results
3242c858-14d8-526d-8fce-da11c78994d1 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
3b61ccc5-55eb-529c-ab6e-c36b4195619a | note | Activity - H
f0eff603-e0e2-56fe-a76e-7f727936301e | note | By - SE
| checkpoint | 5.03.01 - Settlement Pins
6be00cc8-35f7-58b4-9aac-3e2f7da37af6 | note | Acceptance / Conformance Criteria - Settlement pins shall be installed within 24 hours of reaching design subgrade level. Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
a15120ed-c718-5d31-baef-0c8bf1202b40 | note | Standard / Specification - GWS - 6.3
c328b2c9-2589-5ea8-a5a5-29f4fbb679b6 | note | Verifying Document - Survey Results (in paper as well as electronic format)
c44e4189-f4cd-5c8a-94c5-7045748d766f | note | Frequency - Weekly for the first month, then monthly
976b9f25-82ac-5367-a238-3dc87271bf9f | note | Activity - R
f42af643-c395-58bc-a22e-585a9ebaf8f8 | note | By - SV, ENG
| checkpoint | 5.03.02 - Settlement Targets
08507682-93c4-5452-97e2-8150c20bfab6 | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
480b8b47-6145-593e-9237-ad72d6db0cee | note | ○ Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
28d6069c-16cb-52bf-8b0f-2855091f5e5d | note | Standard / Specification - GWS - 6.4
4d86ed34-2564-57a8-98f7-1460af0da7f9 | note | Verifying Document - Survey Results (in paper as well as electronic format)
ee49474b-e7c1-5904-abb4-5613386fddb2 | note | Frequency - Weekly for the first month, then monthly
67d177c4-6ae0-544d-8cca-4963c96f1e14 | note | Activity - R
cd844407-15dc-5abf-ab6a-581e0b72a97e | note | By - SV, ENG
| checkpoint | 5.03.03 - Engineers Approval
129d7748-60d8-5b2a-9b1a-b1ea68c4b7f9 | note | Acceptance / Conformance Criteria - Geotechnical engineer assesment required before commencement of Pavement construction
9c535da8-1110-57cf-bd8b-4b3a4cb67048 | note | Standard / Specification - BBO
c03b5ad1-5238-50bf-94b3-a6d95d7561a5 | note | Verifying Document - Written approval
43a8c2cd-762b-5905-a363-f38629034b45 | note | Frequency - Prior to pavement construction
e735b9e1-02c3-5526-9bcd-5fbbcfc69b4f | note | Activity - HP
655aedea-3982-579f-8070-73df15d33ff2 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 6.01.02 - Draft Redline Drawings
fa2526ab-b8b9-509f-b4ec-43a5d96dfe8c | note | Acceptance / Conformance Criteria - Draft as-builts completed on the completion of MSE wall including red pen mark up to IFC drawing changes.
1b08806c-38dd-54fa-9d51-79482791edaf | note | ○ The draft as-builts shall be provided on a continual basis throughout the project for verification by the Engineer, and as a minimum shall be provided in electronic form prior to application for Practical Completion.
71c7e106-4037-5b64-8bc7-4d64f708bf04 | note | Standard / Specification - PS 2.2.17
a9791038-927a-56e8-92bc-092094da73cb | note | Verifying Document - Draft As-Builts Drawings
8b640c55-480e-521c-b672-75b78b29968d | note | Frequency - Prior to PC
66bc92ec-3655-5cdd-82f9-c85ade2d83b3 | note | Activity - H
0f0c9cf5-c28d-5026-9f36-cb989728faad | note | By - SV / PE
| checklist | ITP - Retaining Walls - Rev F | itp | ITP - Retaining Walls - Rev F | 6cec8363-521e-436f-9cd1-098d4f4cec3a
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
8a0d1e79-aa30-51a2-ba44-7e773615758e | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
12169806-1115-5ff0-ba3e-50d4314ff524 | note | Standard / Specification - Downer
af51c198-73b7-5f4f-be92-be712d6ddde9 | note | Verifying Document - Construction Pack
48603452-d2df-56b3-9899-8d1d2c56c91f | note | Frequency - Submit 10 days prior to commencement of works
5f4f30a6-272d-5089-ab98-f393eefa5a13 | note | Activity - HP
338fe5c7-f79d-5c0c-82b7-78c44e04ec25 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.01.02 - Survey Setout
dddde4ec-2ce4-5cca-b048-84ba820ffcc4 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
639f83cc-1519-586e-9361-968b514b9a9f | note | Standard / Specification - Downer
0c896799-a5c4-516e-b4c3-42555bb915b1 | note | Verifying Document - Survey Records
20c85229-60c2-503f-9538-b2beb431a551 | note | Frequency - Prior to Works
86423e76-30d9-525d-8808-f96fbd6ed7fc | note | Activity - H
ce2fcaac-b474-5060-99e2-e7888842fb8a | note | By - SV
| checkpoint | 3.01.03 - Service Location
f5628cab-5077-5102-9f11-504f9c8b3bff | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
27fe4e06-bf24-51ae-ae35-8c94c3add973 | note | Standard / Specification - Downer
f3850256-943c-5b46-b361-b26f02b009ed | note | Verifying Document - Excavation Permit
32418d8f-d2d7-54c7-b906-b4de1c2fcd78 | note | Frequency - Prior to Excavation
102a84f6-f432-51ed-a382-1be410f6a54a | note | Activity - H
4bb0a952-5ee1-5e53-9b56-e6e11ef925d0 | note | By - SE
| checkpoint | 3.01.04 - Internal Permits
e0db3084-6898-5399-a920-c969ddebc22d | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
08d928a0-089f-5a43-87c8-7d5b384d90ee | note | Standard / Specification - Downer
9fecac0d-4892-5ecb-94e5-ab2719336490 | note | Verifying Document - Internal Permits
b865ee54-2bb4-50c9-b34c-86b0bf4e81f7 | note | Frequency - Prior to Excavation
068c0dd7-62c5-5950-98c8-e67082eb895b | note | Activity - H
6ab2c64e-5cde-5a51-ac12-f1744f451166 | note | By - SE
| checkpoint | 3.01.05 - External Permits
a3982939-a09b-5f65-930a-83594b1a59aa | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
b2d0d73e-f7e2-5875-b911-e85ff1d240c9 | note | Standard / Specification - Downer
011655fb-a45e-501f-86b9-6cc831676b0d | note | Verifying Document - External Permits
16b6c62e-5868-5a39-b7c0-20e9059ab261 | note | Frequency - Prior to Excavation
9e8a8bbc-0fe7-57ea-97a1-ecb01eafcbff | note | Activity - H
546353b2-ed6c-54d3-bf31-dade141b15f2 | note | By - PE
| checkpoint | 3.01.06 - Approved Construction Drawings
60849391-f32f-54e4-8e16-62402da84e44 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
045af579-5f15-52c8-9546-02f8db13abb9 | note | Standard / Specification - Downer
904b65ac-f718-589a-95c3-4f074bd25870 | note | Verifying Document - IFC Drawings
6084e46b-70e4-51cb-b498-19cfd82da7e1 | note | Frequency - Prior to works start
68fc39e6-7547-5e92-8708-44c16e49cfdd | note | Activity - H
205ac354-d64b-5142-beea-3b7eaa98ecd2 | note | By - PE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
| checkpoint | 4.01.01 - Stone Strong Block Molds
2bd89bae-07b6-5306-a504-fa7d87898321 | note | Acceptance / Conformance Criteria - Stonestrong blocks to be supplied by an approved supplier. The Contractor shall liaise with the Principal-appointed Cultural Artist to coordinate carving of the supplied blanks and the production of moulds & blocks
5be549d7-8210-58bc-a46b-b4bdbbefdcaf | note | Standard / Specification - PS - 12
2e6b8cf7-45ab-51bb-a94d-de3b08c4ed0a | note | Verifying Document - Conforming Molds Post Carving
8cdfbb95-eb11-56c4-83d8-dc0efbed5003 | note | Frequency - Before Installation
7dbec491-e5e0-5c7d-b569-801b75228eed | note | Activity - H
1d495b03-9a7d-5d9a-bf8d-8c1d1b108639 | note | By - PE
| checkpoint | 4.01.02 - MSE retaining wall backfill and drainage Material
5f015f0a-32ca-5098-8f7e-01b6ab150fe8 | note | Acceptance / Conformance Criteria - Backfill is to comprise a well graded, granular material such as GAP65 or site won Hinuera Sand, which must be free of any deleterious material. Sand backfill shall have a fines content (less than 0.075mm diameter) of no more than 10%.
bf2155e0-85ae-5718-a69c-542b4ce59d21 | note | ○ Drainage metal to be 20/40 drainage aggregate or similar approved by engineer.
75fab186-5801-5e68-9100-4a34687cbb97 | note | ○ Labratory MDD (x2 per material type) at standard compaction
8f7afa0b-5b75-5f6b-92de-0cd7f64fce3a | note | Standard / Specification - GWS - 5.3.3
83502b73-a1c5-5a72-a2a1-987eb3f77198 | note | Verifying Document - Lab Results
e8b815d5-61b7-5376-917d-312c8aa6e454 | note | Frequency - Prior to works
b04a20ad-42ff-541f-bf2c-d10818b0936e | note | Activity - H
015ea7d7-f005-5d0b-bdf4-46bd41480460 | note | By - PE
| checkpoint | 4.01.03 - Geogrid
c06baadf-ef00-5ca8-bca2-64a9f1f46702 | note | Acceptance / Conformance Criteria - Geogrid to be Miragrid GX200/30 or similar approved
4478a1a1-70ad-5088-b9c4-8a7ddf82c58f | note | Standard / Specification - GWS - 5.3.1
144d0adb-5334-5c39-a0c9-92958b3efaae | note | Verifying Document - Datasheet
1ea05c3d-ee6a-524c-8230-329e985e9c82 | note | Frequency - Before Installation
072791d9-790d-52c3-aad4-c4a3e5c2c5fa | note | Activity - H
6b54ee3c-ecfb-57bf-9a29-f9dcb8d80120 | note | By - PE
| checkpoint | 4.01.04 - Para web
5934a350-5f2e-5022-8dfd-c10537e5288a | note | Acceptance / Conformance Criteria - Paraweb to be the correct grade: Paraweb 2D-50
f82987c4-1411-5e76-83d5-61542e7b1c87 | note | Standard / Specification - GWS - 5.3.2
209066d1-282d-5039-90e0-c0d53068ff9c | note | Verifying Document - Datasheet
0a1827ff-240b-53b7-a030-375286a892cf | note | Frequency - Before Installation
c2e8d5fd-723a-5ef3-b4a6-d9041b635f41 | note | Activity - H
5420955b-884e-51fd-b9d9-29af2ff49edc | note | By - PE
| checkpoint | 4.01.05 - Drainage Pipes
bbf9a41e-2354-54ca-9352-18bebc8e6b8e | note | Acceptance / Conformance Criteria - Shall be 160mm diameter NZTA F/2 compliant smooth bore perforated corrugated pipe with filter sock
93e7a20f-f527-5dfd-acd2-d1e2db74cc60 | note | Standard / Specification - GWS - 5.3.4
44558f33-7964-532d-8691-62d48d83acaf | note | Verifying Document - Datasheet
5da2d153-ac8e-55a4-a9e8-94503c1b61f0 | note | Frequency - Before Installation
929dcb63-f7b4-5c8a-bfdd-3ca7a972b9ed | note | Activity - H
dd3d1dc4-897b-5ec6-ba98-9ab5fc052a03 | note | By - PE
| checkpoint | 4.01.06 - Geocomposite drainage board
646bb77c-96b0-50dd-a508-936005ea6d9a | note | Acceptance / Conformance Criteria - Shall be Bidim A39 geotextile or similar equivalent
dcdea1a2-f37e-566e-9c49-5d39f3a8b913 | note | Standard / Specification - SS - 12
5a3869e5-a16f-533b-812f-86cb749ae79f | note | Verifying Document - Datasheet
e84e1b4b-607c-540b-b627-aa5ee4b4bee6 | note | Frequency - Before Installation
115e5717-fcfc-5841-8335-d0172b615d64 | note | Activity - H
5c2be74e-8680-5260-a593-221b1b1dc1fa | note | By - PE
| section | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
| checkpoint | 5.01.01 - Excavation to subgrade
98c4fafd-ab95-510b-9274-83170e7fb1ee | note | Acceptance / Conformance Criteria - The foundation materials are to comprise natural Hinuera sand material, stiff Hinuera Silt or imported clean sand and must achieve a minimum of 4 blows per 100mm when tested with a Scala penetrometer. Any exposed silts must have vane shear strengths greater than 70kPa.
56174934-ed1b-5740-8f1b-6dcfb3a2cf63 | note | Standard / Specification - GWS - 5.2
e135ce3d-fd9f-5a99-b2f9-9d52d6c35183 | note | Verifying Document - Scala Results
fa1199dc-6eab-5131-af89-dbbde3ab9d25 | note | Frequency - Every 10m
93a2abe7-a982-5303-a0e4-50f54484400e | note | Activity - H
4a8c3298-ba99-5b17-ac28-48838788e2e1 | note | By - SE
| checkpoint | 5.01.02 - Foundation Approval
b103f257-35bb-5294-a2a6-4f86aee86d31 | note | Acceptance / Conformance Criteria - Results of the foundation material testing shall be supplied to the Engineer for approval and the prepared ground shall be inspected by the Engineer. Construction may not proceed until receiving Engineer’s approval.
8c864b0f-f0a3-595f-8266-70e555cee82f | note | Standard / Specification - GWS - 5.2
01bbc8ec-34b7-5895-9e25-71a8c9322222 | note | Verifying Document - Approval
41e279c5-4f96-5aa2-a9d6-b9714b99a680 | note | Frequency - Prior to proceeding. Min 48h notice to Engineer
7cfa6829-b695-5c46-9e68-e9c742de5bcf | note | Activity - HP
2feb039d-a053-5cbe-86e2-9b523e9ec7cf | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.03 - Undercut subgrade
80ceed1b-5540-5ba5-8e69-aabd21c7c4d1 | note | Acceptance / Conformance Criteria - Any unsuitable materials, such as uncontrolled fill, contaminated materials or any weak or organic materials, shall be undercut and replaced with compacted granular fill (WHAP65 or equivalent) or Hinuera Sand. Surveyor to capture extent of undercut (if any) to include in asbuilt.
fe9af0e2-afc8-58e2-86ac-8a827f1e04f2 | note | Standard / Specification - GWS - 5.2
16b49003-06c2-577d-a206-032e2453f7c1 | note | Verifying Document - Survey Record/ Photo record
9a7c2aa7-d9db-58b4-aadc-5c7ff886dffa | note | Frequency - If required
28e9d57c-b860-5593-a71d-e9e4ede87632 | note | Activity - I
54ca8536-8ed8-56b3-97c9-264f25e0f011 | note | By - SE
| checkpoint | 5.01.04 - Undercut backfill compaction
24a7cc88-aa3d-55c8-bc85-b0d51bf4e1a5 | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
eeeb1e4d-ef2e-57a5-92df-6e015891d7e6 | note | Standard / Specification - GWS - Table 3
89e8e2fb-8c6e-5f0e-824b-142686613834 | note | Verifying Document - NDM Results
7f2d9b74-c157-5148-821d-bf10570eaa83 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
01e4886b-f8ea-5200-85aa-46b2e0927993 | note | Activity - H
12ce8d52-3adb-53a3-b4eb-1c300b027d18 | note | By - SE
| checkpoint | 5.01.05 - Geogrid Installation
4416f2f8-5c15-57a0-8811-a39439e0f963 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. Engineer to inspect 1 layer prior to backfill.
abe05164-12c7-5ef3-80ef-9c9cad1fa87f | note | Standard / Specification - GWS - 4.1
63ee82fa-9a46-521b-b7a9-09a559835c33 | note | Verifying Document - Photo record
3510d9fe-2161-50d8-b854-c10320454d31 | note | Frequency - Each layer - 1 layer per abutment to be inspected
325c9edb-3634-5b38-a1ec-8a9ec1144d30 | note | Activity - HP
c5b7876f-6bc0-53f2-b207-4773516e899e | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.06 - Backfill Installation
899e5bd8-adca-5159-96db-eb250698bf99 | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts and compacted to the following standards.
85edcc97-c060-51e9-bf7d-481a4344728c | note | Standard / Specification - GWS - 5.3.3
40d64713-6f83-55a1-b70f-66fa466ddd1c | note | Verifying Document - Photo record
cd63bee6-886d-509d-8958-fa0e37587f60 | note | Frequency - Each layer
2fa77c66-32c4-5683-86b7-11496ca08d24 | note | Activity - I
15afce54-64d6-571f-a5dd-803ba962ca64 | note | By - SUP
| checkpoint | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
87407d10-62b7-5ff5-ba90-5593726c5faa | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
30f2408f-adbe-53df-aa2c-74ef756e47a1 | note | Standard / Specification - GWS - Table 3
0b85a524-7f9b-5708-bc76-3abb9d4be284 | note | Verifying Document - NDM Results
eb4bbfde-b9a0-59ca-b3f1-42814e28d5a6 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
e4bbee84-89d6-50b3-ac3d-d4e33075692f | note | Activity - H
5d10d11b-0675-5e18-8326-8a2ebbdb6366 | note | By - SE
| checkpoint | 5.01.08 - Clegg/Proofroll (Gap 65)
6af11bef-2749-5a8a-8a5a-fff40f1bb2ab | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test. Engineer to proofroll/inspect final layer of load transfer platform.
2f991953-3d11-5eb4-ba38-2cfe91f0bee8 | note | Standard / Specification - GWS - Table 3
6d8ab319-c5ea-5f8b-bc11-b91a60e1c8ff | note | Verifying Document - Clegg Result sheet
e1ef96ea-02ac-5c4c-9717-9314287dfdc8 | note | Frequency - Each layer - final layer to be inspected
7cbbabb3-ac98-52a5-abc3-2deb617bbf37 | note | Activity - HP
cf5ab66c-e5fe-583b-8691-03257766dc41 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.09 - Scala Penetrometer (Hinuera Sand)
cde21a07-5d67-5ca1-9a7f-b339b50bc5e9 | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
972a1ee8-7b07-5741-89ee-e1b26a5ed84e | note | Standard / Specification - GWS - Table 3
41a92435-c912-5c80-9abf-7fe925708fdd | note | Verifying Document - Scala Results
cf752176-b0a8-5b9a-b7b8-75529c330a51 | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
bd1f19b6-b73f-56e2-be79-b5258d2a4ce7 | note | Activity - H
1b40fc59-8332-5ce0-908e-9cbe7280ce66 | note | By - SE
| checkpoint | 5.02.01 - Level founding platform
cd3652ed-252c-58b6-bcc5-2a17f3e24677 | note | Acceptance / Conformance Criteria - The Contractor shall construct a 200 mm thick levelling pad on top of the load transfer platform to create a level founding platform to accept the MSE retaining wall.
361f02ab-fbd9-50de-99da-cf6960afddf7 | note | Standard / Specification - PS - 12
06408132-2b51-593f-9345-3f6af46d9fea | note | Verifying Document - Site Photo / Checksheet
a4b51cc9-1120-52fa-bc34-10b3e5a57a98 | note | Frequency - Prior to Stone Strong block installation
5745bbcd-406f-5d59-b220-74e9d988a65e | note | Activity - I
8f522c83-6a6b-521c-9eae-0f46bf135fae | note | By - SUP
| checkpoint | 5.02.02 - Installation of blocks
82f65001-8ff9-5f81-b3aa-8868c968a8eb | note | Acceptance / Conformance Criteria - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances.
6f3ab58a-1676-5555-804e-c46e1b83cc25 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
aaadf9ec-7382-571e-9fda-0ba6552d382f | note | Table 4: MSE Tolerances
43c7f889-085c-5eec-840e-f3ba927d88d9 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
1bc65494-f9e6-5e2e-94ec-9988e9527c8b | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
a0f0bf7c-c8cf-5f63-9415-9e0dde785dfb | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
5078d3e4-8089-5243-ac7f-1f93b304c28c | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
b657d697-7696-53ab-b5bd-0d38b6d42719 | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
bb919e11-3810-5383-8a20-35ee44bd53f8 | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
63c06ce9-9952-5a63-a6e3-96a18dcdfb35 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
96022c5e-a42b-5b78-b512-7f105236804a | note | Standard / Specification - GWS - 5.4
78c121e1-c205-57fa-aee8-157df0802bd3 | note | Verifying Document - Site Photo / Checksheet
5e801a16-ca92-5ad3-a6e3-7164a3742bfa | note | Frequency - Each layer
148c9f71-1619-543a-8ac0-328293eeafa0 | note | Activity - I
fb3bb93e-e224-5154-ab88-dd27f30a4a78 | note | By - SUP
| checkpoint | 5.02.03 - Paraweb Installation
b2308c38-b919-5d53-ac15-1229842d1da0 | note | Acceptance / Conformance Criteria - The correct number of parawebs are to be installed as shown on the construction drawings.
19388c80-71ce-5f88-b8e0-e795761d0f72 | note | ○ Para web is to be placed flat or with a 1% fall toward the rear of the wall. The Para web must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
f89b9399-2faa-5b45-bff7-5e47f63da2f9 | note | ○ The Para web must be continuous over the design embedment length and no joins are permitted unless adequately lapped and spliced according to the Manufacturer’s instructions.
5700ca77-1484-5112-9811-8f89dd8ddf31 | note | ○ 150mm of fill cover is required before construction equipment can travel over the area
45bca719-125c-5539-a255-2122fa63fb47 | note | Standard / Specification - GWS - 5.3.2
edb3ac52-82b7-529f-be91-f62e742f6e5f | note | Verifying Document - Site Photo / Checksheet
81123ea4-c795-5c40-b10f-fbf99c68426b | note | Frequency - Each layer
5fe8ff9b-e494-5042-812f-c84ae57f4f72 | note | Activity - I
10f788f3-9055-53de-8e2d-1687d0b95e68 | note | By - SUP
| checkpoint | 5.02.04 - Geotextile
f1a8bb54-9914-5908-800a-019f85bc7027 | note | Acceptance / Conformance Criteria - Geotextile to be placed against rear excavated face with a minimum overlap of 400mm between adjacent geotextile strips. Further Geotextile required to separate drainage aggeragate and MSE wall backfill, if sand is used. Short widths of geotextile to be placed across the internal open join area on the rear face of each Stonestrong block join to contain internal block void hardfill. Geotextile to be used to block paraweb voids within Stonestrong blocks that are not in use.
94cc05b3-7ed4-549e-b03a-e2ee7b360416 | note | Standard / Specification - SS - 5
647f2bf3-b023-5467-aedc-97bbb0515d40 | note | Verifying Document - Site Photo
7279ff2c-aff4-5b1d-a3f4-f63375d504cb | note | Frequency - Each Layer
a7b243d3-c6cb-535d-90b5-65a181495255 | note | Activity - I
bd118e8a-bc42-5377-b62a-9b6acb61244a | note | By - SUP
| checkpoint | 5.02.05 - Drainage Outlet Installation
9ee8df9f-b706-55ee-8519-02e9f3ab549c | note | Acceptance / Conformance Criteria - Two x 160mm Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Transfer Platform.
a8364235-fc92-5b0f-b783-499970ee5864 | note | ○ Drainage aggregate to be placed along external perimeter of Load Transfer Platform for each MSE wall layer backfill, forming a Chimney Drain. Chimney Drain to be a minimum width of 300mm and extend to the base of the Load Transfer Platform.
bfdccc2a-f87a-559a-a09d-f22ca6b2550d | note | ○ Internal block void hardfill to be 20/40 drainage aggregate or similar approved by engineer.
f50624df-79b1-5d2c-a119-85e58c1d959e | note | ○ Additional Drainage pipe wrapped in 0.75m3/m run of drainage metal only required beneath wall embedment at toe of the outside of the wall if the slope doesn’t grade away from the toe of the wall.
a9df338d-dd93-5a01-b470-27f025b047c8 | note | ○ Drainage outlets shall be connected to the reticulated stormwater system or other approved outlet structure at the discretion of the design engineer
ba32300a-18c6-51ad-9b3e-f5c37464fe0b | note | Standard / Specification - SS - 5
53567f00-05db-5a58-917d-b1a978e56890 | note | Verifying Document - Site Photo / Checksheet
6be29782-2749-5e9e-acd2-446695c190cf | note | Frequency - During Installation
342b7fa8-1803-5fd1-9c9b-a45f3d56f346 | note | Activity - I
fd19484e-4527-5d4c-ba92-996f5eaf5baa | note | By - SUP
| checkpoint | 5.02.06 - Backfill Installation
af9d4419-c84d-5922-b84f-e4b5f9fba21f | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts adnd compacted to the following standards.
2ff5acbc-2441-5914-b466-eceb1bb021f9 | note | Standard / Specification - GWS - 5.3.3
4a7c55ba-2c0a-5085-b17c-dd45445553f8 | note | Verifying Document - Site Photo / Checksheet
30810479-7899-5c37-82a0-b47fdd9f12c6 | note | Frequency - Each layer
123779de-51e8-57df-9006-afe3c5d732e0 | note | Activity - I
8dfe733a-517e-59b2-8b5f-794fa672edb5 | note | By - SUP
| checkpoint | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
b847ce07-00bc-5608-ad0f-d3a81d9f94ed | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
4328a99a-5536-59cb-b110-ccb710847e94 | note | Standard / Specification - GWS - Table 3
c7971168-a004-5036-9f2b-1ed3ea128222 | note | Verifying Document - NDM Results
e5023db2-34bb-57e5-afed-29b12bed2459 | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
8cdff723-0bb1-5eda-b0dd-3311715e1015 | note | Activity - H
db8b0f3f-ff9c-577e-b319-25d981210cd2 | note | By - SE
| checkpoint | 5.02.08 - Clegg/Proofroll (Gap 65)
34f46bc0-660e-59a9-87b3-f7d46d61f7b1 | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test.
55b742a7-f1db-531f-a649-27c88e7838c1 | note | Standard / Specification - GWS - Table 3
d5b9941f-faf4-5d61-a2c3-0e5aaee11ab4 | note | Verifying Document - Clegg Result sheet
e3522a14-a2a0-5082-bd51-44a43486a497 | note | Frequency - Each layer
240afa7e-52fe-51d3-92d6-41ad2714d903 | note | Activity - H
7ac8ff9e-7fbb-570a-97d4-35d1bbc41844 | note | By - SE
| checkpoint | 5.02.09 - Scala Penetrometer (Hinuera Sand)
62504378-93e1-5436-8f83-4677141f4acc | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
e2de32a1-2c6d-518a-abca-f3d6ceabb328 | note | Standard / Specification - GWS - Table 3
4977a5a6-2522-5a87-8b18-23854d812a24 | note | Verifying Document - Scala Results
be1fc94d-8950-5572-91b8-2af6e059fc7f | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
12ad0ee7-bc51-5cd4-9a23-aa3216f918ed | note | Activity - H
6478289f-1f2c-5ec0-83ab-fedda90f9e95 | note | By - SE
| checkpoint | 5.03.01 - Tensar Triaxial 170
b7b6b90d-c046-44f6-84e9-98097ed32631 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 300mm is required between sheets. Engineer to inspect layer prior to backfill.
24628f91-905b-4919-9547-c3db25e1e6db | note | Standard / Specification - GWS - 4.2
54840355-d1ea-4777-9d5b-6ad907f4fc01 | note | Verifying Document - Photo record
e4c27b20-14a0-466b-932c-f2bfe6c5a0b5 | note | Frequency - Each layer - 1 layer per abutment to be inspected
92855898-8fd4-41e9-9ffc-b8cdb7a3f09f | note | Activity - HP
136c3b84-b512-41df-87e1-dba880b264ca | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.03.02 - Tensar Uniaxial RE580
0ea32e00-9760-40e8-9fe5-b080daf044a9 | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. No overlapping requirements when connected with Bodkin joints. Engineer to inspect each layer prior to backfill. Grids must be taut prior to backffilling
8fb0fc4e-66e4-4c9c-b0e4-e4b8640e477c | note | Standard / Specification - GWS - 4.2
f13ceb32-2533-41ac-bfeb-dca8e273f776 | note | Verifying Document - Photo record
022bcb15-4959-4678-b859-596c2cd1f642 | note | Frequency - Each layer - 1 layer per abutment to be inspected
b48fd9c3-bfcf-450e-b240-2de1ae9976fc | note | Activity - HP
f15f51f3-5909-43a2-9ce0-74db5d1700c4 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.04.01 - Settlement Pins
7df0273f-2726-573c-8319-234334b15439 | note | Acceptance / Conformance Criteria - Settlement pins shall be installed within 24 hours of reaching design subgrade level. Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
a8caf30b-b9d1-5a46-aeb5-4dbe3f8a424c | note | Standard / Specification - GWS - 6.3
235db810-ad9d-56f9-9b7a-832a7715a7a1 | note | Verifying Document - Survey Results (in paper as well as electronic format)
9cf7e1c7-e135-5b40-918e-94fc4847f36e | note | Frequency - Weekly for the first month, then monthly
5494d2e5-3ff5-587e-afa6-7da2c5782e66 | note | Activity - R
9ea475f8-54c7-5150-b398-7d78ec86a5f7 | note | By - SV, ENG
| checkpoint | 5.04.02 - Settlement Targets
bdf89470-9cbc-5946-80fc-b3956bda633d | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
cc54a364-6dce-5b48-9181-dadf83f2781b | note | ○ Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
2bf0e43a-b99a-57be-895d-15eca0dfe222 | note | Standard / Specification - GWS - 6.4
7dc30c5f-7c95-56a7-be44-1e1575e44215 | note | Verifying Document - Survey Results (in paper as well as electronic format)
c191b3a4-241a-5dce-9f28-f631fd35ecfb | note | Frequency - Weekly for the first month, then monthly
455b2891-a1a2-519d-a193-7630a3c712b2 | note | Activity - R
da1b9953-f7b3-5ba8-a6b6-1889d694713e | note | By - SV, ENG
| checkpoint | 5.04.03 - Engineers Approval
68ab0ad8-4387-5097-a8b1-ebe274ec1bb0 | note | Acceptance / Conformance Criteria - Geotechnical engineer assesment required before commencement of Pavement construction
daf4f6df-f633-5b49-aa86-a6ffbbe52acc | note | Standard / Specification - BBO
c0a8b60a-f1db-58b1-a845-681f2ca879f8 | note | Verifying Document - Written approval
dc733efa-8e48-5814-ac8a-c3c3cf3be8eb | note | Frequency - Prior to pavement construction
f98910be-3ed3-55ca-b6df-4fc2d1b26c55 | note | Activity - HP
c8e8760d-cc9c-5702-afd5-a55af9baf9d9 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 6.01.02 - Draft Redline Drawings
4420550a-537f-5032-818b-40f1768a8347 | note | Acceptance / Conformance Criteria - Draft as-builts completed on the completion of MSE wall including red pen mark up to IFC drawing changes.
66d1e4c9-6287-50dd-9a72-f96d4f113dcc | note | ○ The draft as-builts shall be provided on a continual basis throughout the project for verification by the Engineer, and as a minimum shall be provided in electronic form prior to application for Practical Completion.
5477e57b-d05e-5d5f-8996-79cc3de0e690 | note | Standard / Specification - PS 2.2.17
894a9d79-71c5-5fe8-b709-aff0019a8dca | note | Verifying Document - Draft As-Builts Drawings
f119bd10-b211-59ef-9d97-9a27ed553bb0 | note | Frequency - Prior to PC
c19c636b-ce51-5f62-ab48-0d6a79b16cfc | note | Activity - H
eab67930-078b-512e-bef4-5b6f5727abd7 | note | By - SV / PE
| checklist | ITP - Soft Landscaping - Rev E | itp | ITP - Soft Landscaping - Rev E | 78d2742d-c199-4b6e-b26e-a4d7d061a0b0
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
c51e2085-f336-5d09-acc4-f7b5518ef907 | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
5b4598d9-8543-5b2a-a51c-0a6069c2aeb5 | note | Standard / Specification - Downer
18a207d9-066d-50cd-8872-fb95ba7d9522 | note | Verifying Document - Construction Pack
541d1743-7db1-51ff-8d0a-83f5ee69445f | note | Frequency - Submit 10 days prior to commencement of works
37d77a77-80ad-507e-b62d-4174780b85c5 | note | Verification Activity: Activity - HP
a5898aaa-5a2e-59e7-bbda-e12d85ac3c7e | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.01.02 - Survey Setout
dbe31f68-d57b-5430-a67c-1b7e2dd2fd1c | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
74c07e46-8fa6-5d5b-a1eb-041f88d7fff4 | note | Standard / Specification - Downer
6cfc2f9c-17df-5b07-a447-f43b7d70a2f6 | note | Verifying Document - Survey Records
e6bc9c6d-b3b1-53a3-9b84-dc2aebcc42e0 | note | Frequency - Prior to Works
f4c91611-4de5-58e8-aeb0-6e62eafe386a | note | Verification Activity: Activity - H
63d06381-ae37-533b-b360-726519542bee | note | Verification Activity: By - SV
| checkpoint | 3.01.03 - Service Location
d827da96-4bd8-53bc-8b83-85dec9a8bccc | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
9cbbeb8c-fc58-5c56-b134-beb80c08359a | note | Standard / Specification - Downer
db1aa2cd-9d7d-5cb0-83e0-875746fc68a9 | note | Verifying Document - Excavation Permit
481d9b29-5545-50f4-a9e3-267b770459e1 | note | Frequency - Prior to Excavation
b980cf04-cad6-5353-9529-6da0e32a7308 | note | Verification Activity: Activity - H
00cc6941-f030-5b6b-9aa7-4ff477d092a6 | note | Verification Activity: By - SE
| checkpoint | 3.01.04 - Internal Permits
0321cc1b-cf5e-5cae-a8f8-3d97bacb2069 | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
739a1e80-1191-5299-ad07-2c770ca4350e | note | Standard / Specification - Downer
15af99d7-e9e4-5b32-b0c0-31f34f05c91d | note | Verifying Document - Internal Permits
db10d0b2-b716-5d0b-9cf9-50e4b571eaf0 | note | Frequency - Prior to Excavation
537404a9-d85f-50a5-b138-f78a393e92f4 | note | Verification Activity: Activity - H
d8af6e77-e7a2-5004-9a88-dc9f923c3a7a | note | Verification Activity: By - SE
| checkpoint | 3.01.05 - External Permits
fed65574-1061-5c22-997d-f67486696d2d | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
7551b8f8-ba78-5e07-b8e2-c38babeb9af5 | note | Standard / Specification - Downer
402a434d-5be9-59aa-add1-a2ffdc377e5b | note | Verifying Document - External Permits
62b6b3ee-b6b2-5035-93f1-1966fc9e97a5 | note | Frequency - Prior to Excavation
62f647f0-a0fb-54a6-8cf9-9de627c56cfc | note | Verification Activity: Activity - H
11469b81-4b1c-5145-a06b-d9a65326a8cf | note | Verification Activity: By - PE
| checkpoint | 3.01.06 - Approved Construction Drawings
f27f73a6-4d63-5b42-a22e-f4a3dc2d0993 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
45d6b73a-f8bb-52e4-8788-1b90f959b9a8 | note | Standard / Specification - Downer
bef69abd-26db-55c1-b986-96878fb270ff | note | Verifying Document - IFC Drawings
db4ce00a-57fa-5e27-b9b4-71183bafbe0c | note | Frequency - Prior to works start
34f84c64-cc74-5c37-9573-906e6c841910 | note | Verification Activity: Activity - H
5b78a1c3-ad6d-56af-8c59-1d5bf2730968 | note | Verification Activity: By - PE
| checkpoint | 3.01.07 - Previous Lots
95957275-ac71-5454-b8f3-dbe62b4e2cf6 | note | Acceptance / Conformance Criteria - Landscaping works to only be carried out in sections where surrounding work that will cause rework has already been completed.
49f09c73-a5db-551d-a808-49344c2bebfe | note | Standard / Specification - Downer
cdc894dc-6d29-59d6-b471-3f69773ca5b6 | note | Verifying Document - IFC Drawings
27dd5eaf-1816-5970-b177-5828f9adae78 | note | Frequency - Prior to works start
03b0349b-0484-5dce-bd33-158c9bf171bb | note | Verification Activity: Activity - H
4d114508-9824-5a9f-bf8e-ef6921488825 | note | Verification Activity: By - PE
| checkpoint | 3.01.08 - Subcontractors
22fa2562-9ecf-5b9f-bb70-0e7030ba3b54 | note | Acceptance / Conformance Criteria - Ensure that subcontract and supplier agreements have been completed.
e2166493-7bbf-5822-8f19-cd37c344c308 | note | ○ All subcontractors have been inducted.
acffce59-4ee7-5686-97d5-2edfee61a312 | note | Standard / Specification - Downer
ab4c9c44-2236-5859-b2a9-0369aa4ed5d9 | note | Verifying Document - IFC Drawings
83c3eaf6-72c9-5150-9bcf-d93aeeb93b58 | note | Frequency - Prior to works start
f57a296a-2f80-50fd-9bea-2c45f28b4387 | note | Verification Activity: Activity - H
0933a67d-44ac-5b36-b17e-7f98b1da80c0 | note | Verification Activity: By - PE
| checkpoint | 3.01.09 - Site Preparation
c14b25a1-1100-5c73-a3c6-17185b1c15e3 | note | Acceptance / Conformance Criteria - Ensure the area has been sprayed with herbicide. The area has died off and is free of noxious weeds, plant pests, annual and perennial weeds and grasses. Ensure at least two weeks has passed prior to planting.
9459dec2-c677-5784-9eca-701f799c1b5c | note | Standard / Specification - NZTA P39 Section D: Plant Pest and Animal Pest Control
c70e64ea-68e6-553c-89b0-c82a90f2af31 | note | Verifying Document -
dcefcc71-1e63-5977-b22c-7bc93e9e277d | note | Frequency - Prior to works start
a33396de-2d9f-557d-958d-648c02384b86 | note | Verification Activity: Activity - H
c24b5732-1855-5168-b8bf-49781adcf1e0 | note | Verification Activity: By - PE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 4.01.01 - Mulch
e1c7ea96-beb2-5e0c-8fb3-b84bc91d7226 | note | Acceptance / Conformance Criteria - 100% pallet mulch.
a4aca0fb-2686-53a9-bf82-5b9a34767d26 | note | ○ Material will be stored in stockpiles nearby to work areas where possible.
8967a093-aaa4-563b-9eaa-c1ef2e8bcf8a | note | Standard / Specification - NZTA P39 Section G: 3.9.1
5ea54813-bf27-5edb-9dde-d47363b3c103 | note | Verifying Document - Dockets, Record of Approval
6100b406-e384-56d5-92ee-db2b31539dfc | note | Frequency - Prior to use.
41f029b3-fef3-5ab9-b4b3-3caf91d15322 | note | Verification Activity: Activity - H
6d4356ee-0b87-59ab-b517-0857e5fad46e | note | Verification Activity: By - SE
| checkpoint | 4.01.02 - Weed Matting
83662dfa-f2a3-5d8f-8626-23f90d9498ac | note | Acceptance / Conformance Criteria - Weed matting supplied is what is specified for the contract.
f9db0fe7-be92-52a2-a836-b5546c0bf5de | note | ○ Biodegradable mulching fabric minimum 450 gsm.
44b64f58-5e14-58df-87f0-269acbaaafa2 | note | Standard / Specification - RITS Section 7.3.11, NZTA P39 Section G: 3.9.6.1
9f5bc38e-a493-5a47-aef4-18a96f7937ab | note | Verifying Document - Dockets
8bd00f54-03d4-52f4-9384-84b090838e5c | note | Frequency - Prior to use.
94c3dac2-6ceb-5ffe-a0c8-fa847328885c | note | Verification Activity: Activity - H
a4402619-feb5-5546-90f6-7721bd2681db | note | Verification Activity: By - SE
| checkpoint | 4.01.03 - Grassing
ff6276a2-0d35-50db-b046-91501417c2f4 | note | Acceptance / Conformance Criteria - Specfied grass to be used unless alternative has been approved.
8d03b8e7-1ca1-51e3-81b6-1cfbb8b3ff90 | note | ○ Perennial rye-clover seed mix has been approved for use and will be used for all permanent grass application.
216e1368-6833-57c8-92da-ba18a8370942 | note | Standard / Specification - NZTA P39 Section C: Site Preparation
697ecf4e-545f-55b4-b381-1f055603d562 | note | Verifying Document - Dockets, Checksheet
7665932b-a4ba-51a6-b8bb-50450b7e0a32 | note | Frequency - Prior to use.
846469e1-8751-564f-89a2-dc0d00c958e6 | note | Verification Activity: Activity - H
46d1d21f-6329-58ed-96d5-a7034af4be09 | note | Verification Activity: By - SE
| checkpoint | 4.01.04 - Plants
f4b19b21-75f8-5c6e-a67c-739fa8b2fff3 | note | Acceptance / Conformance Criteria - All plants and alternatives have been approved for use.
98f0b7f9-8bb1-5f86-a996-1009762106d6 | note | ○ Plants to be as per the plant lists shown in landscaping drawings and schedules.
66a30246-2690-551a-a3b9-1a8d08e8f3ea | note | Standard / Specification - NZTA P39 Section C: Site Preparation
62560723-85d8-5a46-9e85-e4e85bac6e1b | note | Verifying Document - Dockets, Checksheet
5b1f0216-678e-5307-8dfb-b155c03e3332 | note | Frequency - Prior to use.
f747db15-51f6-5410-ade7-edd6167478b8 | note | Verification Activity: Activity - H
833fb40b-5a6f-5bc6-8be5-bdbd5842fb02 | note | Verification Activity: By - SE
| checkpoint | 4.01.05 - Topsoil
63c6d1fb-cce2-5af5-889b-3588cce5de37 | note | Acceptance / Conformance Criteria - Topsoil used is good quality material, clean and free of debris.
8074f852-a088-5c50-b410-75933aec0266 | note | Topsoil should not contain rubbish, contaminated material or pest plants.
d15aa0ea-9d58-539c-b54f-8180460306d8 | note | Material will be stored in stockpiles nearby to work areas where possible.
37ed8921-0a20-5021-89e2-2b00c31dd5e6 | note | Topsoil will be managed to prevent saturation and over-compaction.
58c47f29-8313-5cc1-86dc-029b7cb7772b | note | Avoid handling topsoil immediately following any heavy rainfall events.
f8c1a9f2-d8f1-53d7-bc41-a8aec64c7043 | note | Standard / Specification - NZTA P39 Section C and F
bff45c6a-7f09-52e2-b031-8b89b30d2851 | note | Verifying Document - Photographs, Inspection
9de50a14-f8f2-5ae9-ba4f-9a098c7dcef3 | note | Frequency - Prior to use.
9a98f5fa-5c29-5bb1-a5be-a4a5ac827226 | note | Verification Activity: Activity - HP
85748278-b0d5-5f5d-bf4a-9562f8b3e0cc | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.01.06 - Root Barrier
d616d13a-dee1-5483-b221-e5b6846db3fa | note | Acceptance / Conformance Criteria - Root barrier to be 1.0mm thick, 600mm high, recycled HDPE non-ribbed material.
c9364361-e84a-5c48-a540-50be9939ee10 | note | Standard / Specification - RITS Section D7.4
aadc70b9-a8e8-5dd5-a83b-26fbf8598b3e | note | Verifying Document - Dockets, Checksheet
9bc88b34-d318-51d9-9f01-d8a80a19981d | note | Frequency - Prior to use.
06145c29-1b45-5030-945f-e65919d491f3 | note | Verification Activity: Activity - H
8964cb97-4b2a-596c-868a-8c68dc55a0f1 | note | Verification Activity: By - SE
| section | SECTION 5 – CONSTRUCTION ACTIVITY
| checkpoint | 5.01.01 - Topsoil
9171b746-42f7-5867-9756-b82b4b0b6f52 | note | Acceptance / Conformance Criteria - Minimum topsoil thickness as follows:
f5a8fa82-837f-5853-9b69-b635b7f042ca | note | – Grassing 100mm
56292213-6b6d-52d6-8dfa-5e61d569fb3b | note | – Mulching 300mm
f92fe421-5937-5f51-a54b-5ac32d6bdc76 | note | – Swales 150mm (TYP)
eaab4b49-4211-5f6f-8910-dc76de63e557 | note | – Swales 300mm (swales requiring 300mm to be advised by Landscape Architect)
96edb7b9-dc06-564d-86ee-9ca76792d331 | note | Standard / Specification - Drawings
c0a25b6d-1128-598b-887b-c5be17ffea98 | note | Verifying Document - Inspections + Checklist + Photographs
88616a3a-5bee-5bfb-8710-8c2f9640d3c9 | note | Frequency - Each Area
4a7dcc26-9600-5b79-92ad-d0ee851b38e7 | note | Verification Activity: Activity - HP
38dfe7cf-8671-5258-b11f-a7944e149634 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.02 - Planting (Dry)
13573266-01ff-5a58-ae69-97ae831d179b | note | Acceptance / Conformance Criteria - Correct amount, size and type of plants have been delivered to relevant zone on site.
3bff1209-57cd-5832-b22c-7fb85e2e021d | note | ○ Supply of plants - confirm order, inspect plants for health -
a9f56323-5cd2-512c-afba-e910cb5b94dc | note | ○ Set up a test planting area for Landscape Architect inspection. This is to benchmark and agree typical set out (once for each planting mix/type).
2f857bcd-c439-5064-bfa2-cccc3736fd10 | note | ○ Ensure plant spacing and plant numbers are correct.
cd7186cd-9d6e-5000-8785-e0a4afb568e0 | note | ○ Confirm application of slow release fertiliser tablets as per requirements - 3 per plant. (Photos)
f0373550-6b34-5ee3-8194-d20a1b013b31 | note | ○ Ensure plants are correctly planted, upright and firmly heeled in.
e20722ab-992e-5766-8602-dc3db9b51466 | note | ○ Small trees and large shrubs should be size 1.3L
fb65ec49-e59c-5104-a091-4774cb64b178 | note | ○ Delivery dockets to be provided for fertiliser tablets.
bf8e8d37-4040-557f-8242-b30752d3d8a1 | note | ○ Plants to be carried out during planting season unless approved by designer.
2dca46f8-85fd-50d5-8d6b-7bc8ea07b13e | note | Standard / Specification - Designer
7c187481-a755-548f-a471-f742f1ad31c1 | note | Verifying Document - Dockets + Inspections + Checklist + Photographs + Record of Approval
f1ac9870-4967-5999-9367-fa5d81fb22a1 | note | Frequency - Each Area
c538eddd-d1d5-5581-81d5-06d512c09501 | note | Verification Activity: Activity - H
64a3020e-1550-59e9-b327-288b26d0abec | note | Verification Activity: By - SE
| checkpoint | 5.01.03 - Wetland Planting
738d63d3-2166-50a4-8689-8baae0d01d25 | note | Acceptance / Conformance Criteria - Wetland Planting to be done outside of summer months (Dec-Feb).
91cfe9f0-d028-5c56-ab55-0d4f9f797d4b | note | Standard / Specification - Designer
aed425bf-f6ae-5143-9959-990a70740c2d | note | Verifying Document - Checklist + Site Records
afe3ca8c-003d-5705-903b-05ade877a11c | note | Frequency - Each Area
e28e2c67-d1f9-5f60-a952-b35e210d3aeb | note | Verification Activity: Activity - H
13a17881-a598-5e3f-a52c-eb19185f53a9 | note | Verification Activity: By - SE
| checkpoint | 5.01.04 - Grassing
be6c2126-e744-58e2-b193-7c1cc4250c4f | note | Acceptance / Conformance Criteria - Grass seed has been applied and has full coverage in all required areas.
9a618807-5db5-5634-a3ec-253aa5041ea2 | note | Standard / Specification - Designer
dead71e1-0058-5bce-8a24-151a4d88a750 | note | Verifying Document - Checklist + Site Records
67145d06-4e82-582e-ac63-b871f646e630 | note | Frequency - Each Area
c2718c32-02d7-5ca3-9bb6-2d72cdf5e190 | note | Verification Activity: Activity - H
212a0127-b4c6-513a-8c80-2c268acef590 | note | Verification Activity: By - SE
| checkpoint | 5.01.05 - Specimen Trees
42dc9f2b-a439-530c-ab74-39fbd922bb26 | note | Acceptance / Conformance Criteria - Site meeting held with Landscape Architect to agree specimen tree locations prior to excavation of tree pits.
804e77fa-cc70-5a74-ab01-8aad2b90620e | note | ○ Supply of trees - confirm order, inspect trees for health - landscape architect to check samples for compliance.
0b97e6f1-fcca-5e24-b361-377df7c32c34 | note | ○ Ensure tree pits have been dug out to the required dimensions (varies depending on location/slope). Check no standing water in tree pits .(Photos)
367f3bd7-7bad-5331-bdcf-9499427c7b9d | note | ○ Confirm application of three slow release fertiliser tablets per tree. Larger trees (160L) will be planted with a minimum of 8 tablets. Trees have been staked correctly.(Photos)
a442f3c4-711c-54a4-91d9-e2b69da32ecc | note | Standard / Specification - Drawings
f579d12c-3806-5a99-8d77-3614655932d3 | note | Verifying Document - Dockets + Inspections + Checklist + Photographs
80ad0064-5835-5b06-a712-077aec204991 | note | Frequency - Each Area
8ed5e62a-dbd9-5ded-8d3b-15253807ace9 | note | Verification Activity: Activity - H
57e4af49-3567-5528-a564-f2cfa68b6cde | note | Verification Activity: By - SE
| checkpoint | 5.01.06 - Mulching
2605e288-b36b-534d-828c-9f07c0449848 | note | Acceptance / Conformance Criteria - Areas that are mulched and been laid 100mm thick and depths have been checked. HP (Inspection at Completion)
bcc65685-dc80-5bc8-becf-870fc238c4c1 | note | Standard / Specification - Drawings
a4e98406-475e-5a09-851b-f0b72425153e | note | Verifying Document - Checklist + Site Records
b4303e21-5b36-5951-8657-46a27c074b05 | note | Frequency - Each Area
645d42e8-9a11-57cd-96c0-7182e96edb90 | note | Verification Activity: Activity - HP
24467f21-c218-5976-8da5-ff3f5caee286 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.07 - Herbicide
c76da0bd-03bc-554f-b3f6-8c19fc723d8a | note | Acceptance / Conformance Criteria - Avoid spraying any herbicide next to streams.
472740d5-06ac-564b-98e7-03aae4ae9bea | note | ○ Where required, only non-toxic herbicide may be applied near waterways and wetlands.
c355edd0-19b4-5490-8a0f-227d8016080f | note | Standard / Specification - GEP
caa2ab6b-c93c-5fbb-9e13-3c7afdb61216 | note | Verifying Document - Checklist
052cb266-d7ad-5c69-96a2-02ef2bf8a3d1 | note | Frequency - Each Area
ddba96a5-5ba8-5f56-afca-12ccd189d1d9 | note | Verification Activity: Activity - H
2ba201e4-ef1e-5a4e-9a1f-78fac967d898 | note | Verification Activity: By - SE
| checkpoint | 5.01.08 - Tree Pits
e8feab18-9b31-5276-af11-7a897e4cf02b | note | Acceptance / Conformance Criteria - Tree pits to be installed as per drawings. Individual pits should be 800mm wide and 850mm deep unless agreed otherwise. 150mm soil layer beneath tree pit should be scarified/loosened. Tree pits to be backfilled with topsoil and slow release fertiliser mixed with compost. Trees to be kept upright with 50mm stakes with horizontal straps no more than a third the height of the tree. Trees to be covered with 100mm mulch and pulled back from the tree trunk.
170a26cd-4830-578c-8394-4c62fd166a55 | note | Standard / Specification - Drawings
caa0fdd3-d8ca-5e5d-bdeb-45388d2a4348 | note | Verifying Document - Checklist + Site Records + Photos
966ad349-9c96-5020-86bf-e0b60053d99f | note | Frequency - Each Area
4438448b-db20-586b-b4d4-7158769220cd | note | Verification Activity: Activity - H
d914f23a-7c4e-5243-b663-8e0fb52b004c | note | Verification Activity: By - SE
| checkpoint | 5.01.09 - Root Barrier
def0ebd3-cd42-5618-a7fb-9171703914bb | note | Acceptance / Conformance Criteria - Root barrier to be installed where tree pits are close to kerbs and footpaths.
afe30ec5-6d3e-5a04-acdc-ba11b0fee15a | note | ○ Root barrier to installed 2m wide and to be 600mm deep where required for tree pits. (Photos)
3da8eed3-af79-568b-946f-867d5d57cf20 | note | Standard / Specification - Drawings
3ce0aea9-754c-53df-a678-a933cb580513 | note | Verifying Document - Checklist + Site Records + Photos
395380b9-9417-5cf4-9859-6de63e18f955 | note | Frequency - Each Area
43d62f5a-cd65-545d-be48-8970ea4a05cc | note | Verification Activity: Activity - H
4fccbe46-a86c-5371-b97d-af9d698deb72 | note | Verification Activity: By - SE
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 6.01.01 - Maintenance of Plants and Grassed Areas
c4d3e3f8-6097-566e-8767-99925bface21 | note | Acceptance / Conformance Criteria - The Contractor shall remedy all defects relating to the landscape treatment works, each year during the defects and maintenance period, at the first available opportunity. All planting defects shall be addressed duuring the correct planting season.
75d86a0e-a783-5635-b02d-17c27b808e46 | note | Standard / Specification - Landscaping Specification
02ec7518-9dcd-5c0d-8dc2-6202ca100ebc | note | Verifying Document - Site Records
9f341dfb-2660-5149-86e2-e3ee108fe03f | note | Frequency - Each Area
2e21c004-29cf-50cd-948d-9932fc37f19e | note | Verification Activity: Activity - H
05bac49b-88f4-5fa5-bf56-140213437b84 | note | Verification Activity: By - SE
| checkpoint | 6.01.02 - Redline Markup
38d95eef-2428-5668-8526-844f212d3d20 | note | Acceptance / Conformance Criteria - Redline markup of any design changes.
1079bb67-d6a9-573f-95cd-25135de87bf6 | note | Standard / Specification -
0cd5e592-db99-5450-afe9-35d487eed518 | note | Verifying Document - Redline Markup
95cbb7f4-34d6-51b8-bcf5-07edf9bc1abf | note | Frequency - Upon Completion
e2825751-4075-5af2-8a74-94003b2edcc5 | note | Verification Activity: Activity - H
e0ac8223-222d-5647-be4d-914d50678326 | note | Verification Activity: By - SE
| checkpoint | 6.01.03 - As Builts
f50e72ac-e6c2-547b-a135-fde880f49435 | note | Acceptance / Conformance Criteria - Final tree locations to be provided.
98495aae-41fc-5dc1-97f1-568dc1916ae3 | note | Standard / Specification -
cf86ca19-c6e8-5ad0-bc35-93a321985b4a | note | Verifying Document - As Built File
42b3c30b-7857-5402-9e41-09e2ede31416 | note | Frequency - Upon Completion
07de8232-3494-5730-93dc-f494ba185855 | note | Verification Activity: Activity - H
919d0b0e-8f94-5b20-90d0-1737a4d77c23 | note | Verification Activity: By - SE
| checkpoint | 6.01.03 - QA Pack Compiled
654350ad-219a-538a-9758-e579b4c89091 | note | Acceptance / Conformance Criteria - Submitted for approval.
92908d77-5c82-58d0-a9da-430ac5dec8f9 | note | Standard / Specification -
d9b266aa-a52b-544c-a677-2510c0e6fd75 | note | Verifying Document -
9b5b1e18-5999-5330-923d-0f7723a17050 | note | Frequency - Upon Completion
c2559640-c815-5f37-a7f4-e8a2bfc3ba21 | note | Verification Activity: Activity - HP
4c62059d-d17a-5f1f-81f3-674dfaa23db3 | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.01.04 - Final Acceptance
14097e6f-ec2b-54bb-aac9-381c5609e2e3 | note | Acceptance / Conformance Criteria - Planting shall achieve an 80% canopy coverage of the ground by contract completion,
5e94bd76-f651-562c-aff6-bffbdd0cad83 | note | Standard / Specification - NZTA P39 Section A
46aad054-dfd8-5c39-b7ac-5876aa108cc0 | note | Verifying Document -
5fb6b364-06f7-5a22-805e-15747d31e52d | note | Frequency - Upon Completion
e63d1c40-cf02-5712-aa36-d29b3bec66d8 | note | Verification Activity: Activity - HP
7ad83ecb-fe07-502e-86af-c639c30b16db | note | Verification Activity: By - ENG
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - Stainless Steel Pipe Site Welding | itp | ITP - Stainless Steel Pipe Site Welding | aab5a338-5f22-4628-bb0d-9259e1d7ab8a
| section | Details
| checkpoint | Inspect all pipe & fittings are correct to job requirements and no signs of damage
8cfe2aaf-721a-5de5-9d1a-7d5b55c6e849 | note | Quality: Hold Point - W
e0977afa-d426-5857-842c-23fd26825696 | note | Quality: Sign - LS
cef4f7e8-5081-521d-a422-a39a187081b8 | note | Quality: Witness - AG
| checkpoint | Inspect all pipe & fittings are correct to job requirements and no signs of damage
72a70939-b2c8-590e-90e6-d08793e3aeef | note | Quality: Sign - AK
| checkpoint | Familiarise yourself with the job
1a4133f3-4614-55df-9511-34b140e3f468 | note | Quality: Sign - AK
| checkpoint | Setup worksite, welding equipment & rollers
b4843adb-3502-560e-91d4-3dfc76e06e39 | note | Quality: Sign - AK
| checkpoint | Load length into rollers
129a13a7-b545-5beb-a3d2-0d8925781ce1 | note | Quality: Sign - AK
| checkpoint | Bevel pipe ends
473dbab3-66ee-5c3d-a29c-eaee14e9c98a | note | Quality: Sign - AK
| checkpoint | Tack weld 6m lengths into instructed lengths
b45fc73e-8716-53ab-92b5-e7a8a1a0b5df | note | Quality: Sign - AK
e902e8af-3dd1-557e-a6c1-e7f9c93d3961 | note | Quality: ID - AK1
| checkpoint | Check for straightness alignment
78322bd6-9015-5260-bb56-66680edddc32 | note | Quality: Hold Point - C
8914a38e-7940-5245-9eca-ade47d2a3cef | note | Quality: Sign - AK
94417a05-32cc-5f95-ba16-ae92d19d480c | note | Quality: Witness - AG
| checkpoint | Setup purge baloons & purge with nitrogen
30e8af7c-20ab-56a4-ac60-9026171eb594 | note | Quality: Hold Point - C
94450fec-d239-5009-8039-6d06ba261720 | note | Quality: Sign - AK
c8798ef9-cc48-58fa-9f9f-19832a405769 | note | Quality: Witness - AG
| checkpoint | Peform butt welds
6d740a76-6493-502c-8e18-89499b172d16 | note | Quality: Sign - AK
bfb56a40-f0b0-5414-bd9f-6f648d08d6aa | note | Quality: ID - AK1
| checkpoint | Tack flanges on spool lengths & check for square
cd5e67a7-8a32-5bf1-af3a-cf55de6a0735 | note | Quality: Hold Point - C
87c1b39f-af85-58f3-95ba-7c5000f5c432 | note | Quality: Sign - AK
b6efe9d1-d180-572e-a3f8-02b35bb3be75 | note | Quality: ID - AK1
375df33c-659c-5bbd-889d-35b60819e097 | note | Quality: Witness - AG
| checkpoint | Weld flanges on ends
955dca95-c19e-53d2-89b5-f92d19e3c3c0 | note | Quality: Sign - AK
ff1e457f-c928-5fef-8ad6-44e417044c94 | note | Quality: ID - AK1
| checkpoint | Passivate all welds
e5848a77-4422-5ff7-b891-234cca2dbe7e | note | Quality: Sign - AK
| checkpoint | Remove from rollers and move to lay down area
f6879104-c440-5809-af28-607ea958a40e | note | Quality: Sign - AK
| checkpoint | Final inspection
34ec5d81-65ec-5b91-ae74-6f51f5e930c6 | note | Quality: Hold Point - H
f9e5c8b0-7a12-5793-b652-770c6f2697ae | note | Quality: Sign - AG
a17d4418-f643-5665-b00b-1016f21de2ba | note | Quality: Witness - LS
| signoff | HOLD POINT
| checklist | ITP - Stormwater |  | ITP - Stormwater | 5bc76927-2573-4c4a-9088-318a8fd2547a
| section | 1. Pre-construction (P&G / EStablishment
| checkpoint | 1.1 - Extent of Line Setout
447440a5-2c0a-5624-85c7-5c5695b6237d | note | Acceptance / Conformance Criteria - Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Stormwater drawings Identify any clashes before construction.
c2a79509-fed9-5e36-b6c2-55161fc3b698 | note | Standard / Specification - Design Drawings
ca3ef045-41f3-51eb-926d-2360a7098b93 | note | Verifying Document - ITP Sign Off
98ad0bfb-34bb-5a09-9755-5781e4c3ebe3 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
9f6fba78-f4fa-5da9-aba5-069ad45174ef | note | Activity - M
8de4d596-b054-5659-bc84-16e38ba8fb5f | note | By - PE
| checkpoint | 1.2 - Environmental Protection
6612df47-d954-53c4-b894-edb8ce9af6f9 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
062afe7b-306f-5969-b9db-f7d2dc2afc15 | note | Standard / Specification - Project ESCP Plans
7a2cc52d-ca2a-57de-905e-1840593283b1 | note | Verifying Document - ITP Sign Off
b38eb8cb-5d9d-5cd6-aae7-aace11a0a128 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
de4a0ce0-290c-5f62-9d8d-6caf8dc1f487 | note | Activity - M
052d5bf8-5a20-5976-ac01-5a2ef8b5e4f3 | note | By - PE
| checkpoint | 1.3 - Stakeholder
964041ce-8f47-5f43-9ecb-4bc963a55457 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
8b5fbeb7-f07a-5d9a-8009-c74944313641 | note | Standard / Specification - Project Stakeholder Management Plan
eb2ede20-7062-5ae6-ae42-6281a683f1fd | note | Verifying Document - ITP Sign Off
d15bcff4-95f0-5150-accf-6527317b301c | note | Frequency - Prior to Construction with continue updates throughout the works
5ec3de2c-4b7c-5ade-a197-bd5ea77fcabe | note | Activity - M
4c067108-806e-5e92-9370-1ad1b8a35d89 | note | By - PE
| checkpoint | 1.4 - Permits
4c825895-8c78-55b8-b08e-a8351d233bd8 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
1d27dde7-938b-501b-832f-694ad3898bab | note | Standard / Specification - Section 2.2.10 Project Specification
ebcd1d8c-89e5-5cf8-892d-b66059936aa9 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
e8bbb9a1-2854-5867-a418-82b8a8d75d70 | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
50b252e4-9a1b-55a1-8fcd-272b57170589 | note | Activity - H
05b3ff20-3c01-57de-94a8-610a07e19afa | note | By - PE
| signoff | AUTHORITY HOLDPOINT
| section | 2. Material, Personnel & third party approval
| checkpoint | 2.1 - Pipes, Fittings and Pre-cast Structures
8cc73743-a549-5b8a-9972-bd0ed83002b2 | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes/catchpits are correct and in good condition and compliant.
99c3e5ae-e54f-5495-9913-be9258ec6a39 | note | Verifying Document - Delivery Dockets
c00daa9a-8446-5e5a-80c6-f2424b52f9d1 | note | Frequency - Each Delivery to site
a6e87c58-81fd-59d2-a37c-c5b5ea4ddfbd | note | Activity - S
34dca5cd-53ed-5e78-9eca-2b4049551dea | note | By - PE
| checkpoint | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
2f2b959f-0b91-593e-af76-befcf5d8037b | note | Acceptance / Conformance Criteria - Confirm material grading and density
df46ccd2-8662-5f7d-b6ba-bec7f384f640 | note | Verifying Document - IANZ Lab Test Report
9c4db143-fb28-5f31-bc3c-43f6c7034508 | note | Frequency - 1 Test per 1000m3
245aee90-a07b-5d58-8087-a5a14ee20ed3 | note | Activity - H
f3b05688-3c15-54c6-8fba-318cf71f63e7 | note | By - PE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Undercut Backfill Material
fe88c77f-3e70-515d-bb22-3fd140cb3a92 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
07567e87-88a2-541c-b30e-632f15b06a13 | note | Verifying Document - IANZ Lab Test Report
54e4e4a8-5298-504a-a852-f33bcd7d4d87 | note | Frequency - 1 Test per 1000m3
8c66e4e0-bc8f-506b-a85f-f5d65b949fb1 | note | Activity - HP
3d96e459-1e65-5754-b945-41afc0373867 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Geotextile/Geogrid
d07e6c50-2ff7-59c3-8fea-34e730e14a76 | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
6dbbe61e-6416-5303-b213-94a8c466f688 | note | Standard / Specification - Project Specification
e0bf4fe2-31b6-5f29-9c4a-9c35585633c8 | note | Verifying Document - Certification
9db1ab35-a02a-50b0-a859-3077e8340c2f | note | Frequency - Material Used
14c378a1-3d7d-5e88-b0b4-dc90aa22f05a | note | Activity - C
3fd12297-a538-5970-b61b-2ca319e65cd8 | note | By - PE
| section | 3.1 SW Pipeline Construction
| checkpoint | 3.1.1 - Foundation Compliance
7a04d12b-d747-5ffd-b944-2bd05ad77fc9 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
4f0e99a5-bfaf-5f02-a719-5a24a42d5913 | note | Standard / Specification - Project Specification 4.3
a9f17d3b-c88e-50fe-8d6f-ab8064428d69 | note | Verifying Document - IANZ Scala test result
f3841af3-80ba-5c41-8777-03f1b887719b | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
3575732c-7133-5f5c-849a-1c506255b232 | note | Activity - H
ff25d653-974a-54e0-a0d3-32abec523435 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.2 - Undercut Backfill Compliance
e1ff91fe-c3fb-58ee-9e70-19bef3c46199 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
a64090ac-0958-5091-b76f-c28c35eb76a9 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
93d8490e-c5e1-5da8-888e-c2e3ae4d55d2 | note | Verifying Document - IANZ Lab Test Report
8b1bde27-f241-50c2-a50d-193151536635 | note | Frequency - Based on Undercut Section
021146ef-473d-5414-88e2-ce3b10842f12 | note | Activity - H
905f63e2-3f0e-5d40-8280-5163a1b608af | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.3 - Bedding Compaction Testing
e3797ba1-d525-5fd9-a978-8a5831163f09 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
a2064d5a-38c8-55fd-a7dc-82c5a0133fc2 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
1d9d16c0-cfa7-5e49-8d48-39ef0a0d8c21 | note | Verifying Document - IANZ Lab Test Report
499bcee3-0521-5833-b992-397bfa037601 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
730ed117-3d39-5268-949a-02db9efa951e | note | Activity - H
82f85a51-88c4-5669-8e7c-07d8953148f8 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
943c75a0-548a-5877-b083-6d8b113d77be | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
98d9189b-0f93-5541-86a3-f57e2e828180 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
b6029590-f98f-5925-9315-855030e5fe08 | note | Verifying Document - IANZ Lab Test Report
db6a89fc-c15b-5eaf-9b4e-48577b15dbce | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
aa4f8012-e8f7-54c9-a4ac-7df2a309121b | note | Activity - H
c1462d73-a82d-5e15-9b73-6b6f3fd47075 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
c71bafd6-9b9a-586e-a9c4-1a21adf96b38 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
24f21671-d0d3-5a9e-bc01-b6a76b22570d | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
13b55999-794e-5122-af3b-a8aa97997815 | note | Verifying Document - IANZ Lab Test Report
32feea1a-ae98-558d-9737-dbd1f32fab48 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
4a48af67-2ab9-5de9-9c40-82b43aee0a97 | note | Activity - H
fd47be6f-6c6a-5ff9-94b2-800c521a7759 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
05192b11-1a31-586d-905f-5659d3cebd1e | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
50b2983f-227f-536d-b0eb-3584ee19e873 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
8a3c30b9-73dc-5a8a-838b-86b5b0bd2ed5 | note | Verifying Document - IANZ Lab Test Report
3d025453-8849-5aed-8278-b85d2c7e3df9 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
bea3a1ac-8116-579e-9399-b859af1663b6 | note | Activity - H
b5599516-b1eb-5110-99be-fa5c76828b21 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1.7 - Backfill Inspection
1adaab6a-26da-5cfd-b3e6-23db6fc87b44 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
3084c2a0-39cc-51ad-a0a2-094544a82dc1 | note | Standard / Specification - Project Specification 4.3
57109279-457b-5e21-a601-66ebf67dfde3 | note | Verifying Document - Photographs
191df840-3870-5720-a4de-26fffe4f3f34 | note | Frequency - Continuous
8feee862-4ff9-5b2c-96aa-b341303a3086 | note | Activity - S
398a1038-926f-5031-b65a-f2b2a115b4ea | note | By - PE
| checkpoint | 3.1.8 - Survey
74d6bc52-ea28-5f9e-a46e-d8a11a8a62aa | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
377dd711-8851-5fde-899f-26d3b19d6e49 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
779ac31a-8be8-5b43-a12a-7ce6784654ce | note | Verifying Document - Survey Data
0758b277-e14d-5292-8882-bfddd9492976 | note | Frequency - Continuous
666f3657-a9b9-5643-8c00-9d8c5e540590 | note | Activity - C
7c5f006f-2bf8-54b5-bf65-9f6706fc2204 | note | By - SV
| checkpoint | 3.1.9 - Backfill Compaction Testing
dd1b4c81-03ce-519d-86b6-a52d4bb8409b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
5a0adf60-74ff-5fe6-b4d0-bd4064d2a01e | note | Standard / Specification - Project Specification 4.3
57b31059-a1ef-5138-ac81-a2c861002c3d | note | Verifying Document - IANZ Lab Test Report
2ca7f613-162c-5ee2-83fc-db1a58a8a44f | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
3ca2a53a-d16f-538d-8f33-c2e7d8481abf | note | Activity - H
ba3f57e7-fa79-5100-999c-4e83448459c4 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| section | 3.2 SW Manhole Construction
| checkpoint | 3.2.1 - Foundation Compliance
dcec4b76-a35a-5a06-9a8d-29d8238c9847 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
00c8b96c-19a5-5475-912e-4316d41e6e37 | note | Standard / Specification - Project Specification 4.3
7d677d75-abd9-53e8-b241-5dcf600e67ef | note | Verifying Document - IANZ Scala test result
5d063390-2611-5165-8299-86528408eea5 | note | Frequency - 1 Test/Manhole
dbd0670e-e320-5db0-84a5-dd06c660d2bf | note | Activity - H
bd3b026b-9a06-55d4-bdb5-132aa5be49ca | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.2 - Undercut Backfill Compliance
39adc7b4-7c09-5d68-b4de-2afda2fef248 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
2e017776-83f1-57c1-b446-0ea74d0331e5 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
97f1d62b-680b-5711-ba4b-7f5b0f2b1450 | note | Verifying Document - IANZ Lab Test Report
b82b0243-c431-5bf6-bef2-54f9e9604ed4 | note | Frequency - 1 Test/Manhole if Undercut required
db6d6ab5-d974-5cc2-b57c-e9036d4fe47f | note | Activity - H
51b8047d-5ab9-52d7-b996-5a03129f824d | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.3 - Bedding Compaction Testing
2ae700cd-cdff-561f-9c54-c990abd4899e | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
8eb8191a-61be-5741-99e3-a38fa32a2bd4 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
15e97f48-55d1-5511-b25c-c3910dd31d24 | note | Verifying Document - IANZ Lab Test Report
6596043b-5c4a-581d-b4bd-86665c83b1dd | note | Frequency - 1 Test/Manhole
003075f7-e290-5eb6-a26a-9457ff57961c | note | Activity - H
75d1fa86-4533-5a8f-b029-aec3817e6ed7 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.4 - Backfill Inspection
80e98b3b-70ee-589d-99a7-8585136c48f5 | note | Acceptance / Conformance Criteria - Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
c72fb28c-e022-5303-a650-9e008cf50310 | note | Standard / Specification - Project Specification 4.3
87c71e3f-7a35-5568-bb19-d8524210f6d0 | note | Verifying Document - Photographs
6e2b4e89-bad4-5a42-96c2-1a70cf38076d | note | Frequency - Continuous
c5f29725-7a10-5c82-a80d-e13fc08c62b8 | note | Activity - S
5ea80f2a-4b35-53da-a64f-0b12bc74d1c2 | note | By - PE
| checkpoint | 3.2.5 - Survey
6b93d645-4ecf-56be-a7fa-df9892ec778e | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
1ac3f541-1f81-5dc6-8556-14d6f56de1d6 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
2ef1a085-438f-59d5-b3fd-50ead3ef546b | note | Verifying Document - Survey Data
235d4e1e-4ebb-569d-b7c5-6ef33aa85739 | note | Frequency - Continuous
5483ddd0-7ac7-592a-bc95-d7f40b712b95 | note | Activity - C
caf7d5bb-97cc-5104-9b91-f1fdf092b1af | note | By - SV
| checkpoint | 3.2.6 - Backfill Compaction Testing
318dea9e-f21a-516d-998f-cefd11329da4 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
3fcf6580-7b80-5d37-8434-4a4bf5773b2f | note | Standard / Specification - Project Specification 4.3
41973aa3-f55c-5b99-af6c-3e7072fe92c3 | note | Verifying Document - IANZ Lab Test Report
085388e7-2c92-5ba2-a83e-694ebd60d6ab | note | Frequency - 4 Density test per layer at Quarter Points around the Structure
c006baea-7876-523a-b03d-5b741204d653 | note | Activity - H
6e4a94cc-536c-56b9-9988-83741cadbbc5 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2.7 - Haunching
5659e5ec-fb84-5ec0-9f8c-a5b25af378c7 | note | Acceptance / Conformance Criteria - All the MH's needs to be haunched as per the specifications
40a23dd4-539d-586c-b1b7-6b350a9581dc | note | Standard / Specification - RITS
d9a6375d-0eef-528f-9a15-48556a44142e | note | Verifying Document - Photographs
2799a095-3978-5051-aa95-4d0db01a222c | note | Frequency - Continuous
6f9a12d4-fd19-5973-8db6-606ab7a73450 | note | Activity - S
08a70049-a942-524f-91d4-b28a82d75d02 | note | By - PE
| section | 3.3 SW Catchpit Construction
| checkpoint | 3.3.1 - Foundation Compliance
b5bcd2e4-2d17-56bd-a5db-81d297579443 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
6bbdf8da-2c8e-5d2b-b460-d0096881e4c4 | note | Standard / Specification - Project Specification 4.3
18d529ea-89eb-59fb-97f7-391b734c33f8 | note | Verifying Document - IANZ Scala test result
87595e9e-bb05-5747-87d5-a4ed3ece4f65 | note | Frequency - 1 Test/Catchpit
e726b3b3-be6d-5a7c-a618-aa07aebbec81 | note | Activity - H
bd723658-bc76-5c1f-bc44-f3eca7d562d1 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.2 - Undercut Backfill Compliance
80cc47a7-b6e1-5136-81bd-f07069b91b8e | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
c4c34550-803d-55f4-838d-e8392fdf9fd2 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
b7643824-0758-5387-ac1b-54ba81825658 | note | Verifying Document - IANZ Lab Test Report
f9947440-9d2b-53b7-832d-0d9d1f819fbb | note | Frequency - 1 Test/Catchpit if Undercut required
11bfade2-10e4-5df8-a782-7f7e1df7d556 | note | Activity - H
ad79f347-8d68-53d4-8203-fd74f1958ad5 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.3 - Bedding Compaction Testing
648a2b95-dd00-54ea-ac31-e22564f82a91 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
5646338b-6181-5b18-b998-28102fa4c4b3 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
60218604-2f09-54fd-9073-ae1aaed2a405 | note | Verifying Document - IANZ Lab Test Report
e7c00a95-6aa8-5929-87fa-96e4a3c4dde4 | note | Frequency - 1 Test/Catchpit
f0a01638-4414-5fa4-a096-f22a36e03247 | note | Activity - H
d558e9a6-05a1-54d6-9592-b7fe56f33911 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3.4 - Backfill Inspection
c467db57-ff4b-5807-8eee-15fae2cf0df7 | note | Acceptance / Conformance Criteria - Inspection of catchpit prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the catchpit
ffb11fbc-3b83-5abd-913a-240698c4df57 | note | Standard / Specification - Project Specification 4.3
32b11a35-8a77-5aaa-bdb1-d7cf228e6aaf | note | Verifying Document - Photographs
b6eafff6-bdea-547a-8a04-1cb3793877d3 | note | Frequency - Continuous
a1f137a5-0c59-59e3-b70b-62dc170cc355 | note | Activity - S
c9cef0a2-1b0e-535b-8f99-d8e4d17c3ecd | note | By - PE
| checkpoint | 3.3.5 - Survey
7197b535-45c2-5809-829e-ebe391e834c7 | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
a1ee0ca8-a47b-5917-bd54-f5214297b86b | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
76fa5315-b0f5-58e3-acfe-56024a1d6ac4 | note | Verifying Document - Survey Data
e150227c-5e94-5830-b10d-ea0b898175bf | note | Frequency - Continuous
5d550601-8749-5225-a5ab-5b74c1aa57c8 | note | Activity - C
16a0960f-ef12-5ca6-ba4b-afc4551b968b | note | By - SV
| checkpoint | 3.3.6 - Backfill Compaction Testing
eb686d29-26c4-5f20-adc9-e52220561e9e | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
3e46d6be-d908-593c-b47a-2cdd80cb0094 | note | Standard / Specification - Project Specification 4.3
b1763e05-12f1-56b7-8fe0-96265442db5b | note | Verifying Document - IANZ Lab Test Report
5bcd4b69-2adf-5059-bc82-158e8c321dbf | note | Frequency - 4 Density test per layer at Quarter Points around the Structure
a5f5cba0-c703-577a-af89-de2bad6a32ee | note | Activity - H
ebbf3c75-97de-50a0-b256-7d083ae04ea3 | note | By - QE
| signoff | AUTHORITY HOLDPOINT
| section | 3.4 Riprap & Boulders Installation
| checkpoint | 3.4.1 - Rip-Rap Material
b321cd8c-5e46-5864-aba5-f794ff7ad43c | note | Acceptance / Conformance Criteria - The material shall comprise imported screened quarry blasting's and/or crushed basalt, greywacke or other angular hard rock which shall conform to Density, Crushing Resistance , Weathering Classification, Abrasion Resistance, Calcite intrusions, Grading, Shape. No rock riprap or boulders shall be placed until the Contractor has provided test results to prove compliance with the requirements and obtained approval of the Engineer.
b68f6a88-b769-531b-b43d-ea229b1af715 | note | Standard / Specification - Project Specification 4.7.1
710b49eb-0085-53e1-9708-0c05bc07c290 | note | Verifying Document - IANZ Lab Report
509fd158-cd61-5f76-9574-a828fce7ffd9 | note | Frequency - Prior to placement
c4be62b1-dd9b-5431-9751-6efbea20f7f2 | note | Activity - HP
08dd237a-e262-5a54-9704-4d1aafdb9aa1 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4.2 - Soil Rip-Rap Material
ae586004-69f3-51f9-a2ab-3fb9c500fb06 | note | Acceptance / Conformance Criteria - Where soil riprap is specified on the Drawings, approved riprap rock shall be pre-mixed with topsoil from on site at a ratio of 70% riprap to 30% soil by volume.
4585a3e6-61dc-5271-b76a-4db994ee98c2 | note | Standard / Specification - Project Specification 4.7.4
5afcc23e-4686-5030-adc5-8cf217b29856 | note | Verifying Document - Dockets/Site Notes
1b6e59a7-08e6-5461-b23a-b005331f1c91 | note | Frequency - Each Batch
4f1355f3-bfa8-5d3e-95e0-b69bb3f6889a | note | Activity - R
e0e2ab75-0816-5f19-955a-022b76b98747 | note | By - PE
| checkpoint | 3.4.3 - Void Filling Rip-Rap Material
0fb9879d-1dc8-5b88-8be9-e9d76f5bee87 | note | Acceptance / Conformance Criteria - Where void-filled riprap is specified on the Drawings, the riprap rock shall be premixed with well graded granular material with a maximum particle size of 40mm (GAP 40) at a ratio of 70% riprap to 30% GAP 40 by volume.
4cd86cc3-8c69-5de8-943f-2ea0f7b3290f | note | Standard / Specification - Project Specification 4.7.5
72cb2c30-925b-5688-bcae-53c504748bb8 | note | Verifying Document - Dockets/Site Notes
2c5fc2af-b150-58a3-871e-7fda26bfac99 | note | Frequency - Each Batch
55719c40-e0df-5036-a089-ee1c0d9c9da6 | note | Activity - R
0dc87d3c-994a-52bd-bcde-99f769a51b07 | note | By - PE
| checkpoint | 3.4.4 - Grouted Boulder
5d119a4a-7190-56ea-a138-60a8225dc9f2 | note | Acceptance / Conformance Criteria - Boulders must be approved by the Engineer, prior to placement Grout used for grouted boulder structures shall meet the requirements of NZS 3109
e49b26c5-3d8c-535e-a12c-c23ce98772d4 | note | Standard / Specification - Project Specification 4.7.6
79b8a383-a5a9-5a06-969f-f6aba483cb0e | note | Verifying Document - Site Records Data Sheet
b03711ab-ad6c-5f3b-b345-55a98e6258f5 | note | Frequency - Prior to placement
1b8ab041-d166-5770-a6f6-2e79d7c9116c | note | Activity - HP
5191a328-e62a-5de8-9966-507dbde63370 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4.5 - Achieving Required Depths
953e1403-bb20-5da8-8128-631b97ed3482 | note | Acceptance / Conformance Criteria - As per IFC Drawings
830943ec-076f-5cb7-bc84-87871c978dea | note | Standard / Specification - Project Specification
4c48f30e-2955-567f-a1dd-288e00897eac | note | Verifying Document - Photos showing thickness/depth Each Section Labelled
969c046d-ac38-5cd9-9eb3-4264be2d77bf | note | Frequency - After Placement
b22883ca-794f-5d96-a004-b5aa14482988 | note | Activity - H
dc639aaa-e29a-5d1e-a35b-050828c37bdb | note | By - PE
| signoff | AUTHORITY HOLDPOINT
| section | 3.5 CCTV & Reinstatement
| checkpoint | 3.5.1 - CCTV Inspection
f0fab8de-949c-5ebc-a248-d79779f581c8 | note | Acceptance / Conformance Criteria - Quality Check on New Works
18687b5c-cc85-5a1b-b730-2eb46416a2ca | note | Standard / Specification - Project Specification 4.4 NZ Pipe Inspection Manual
63f2aecc-85a2-59a9-9b6d-adc6a21fed50 | note | Verifying Document - CCTV Report
69d35b40-75fe-5dd2-b466-ea0d100bbaa8 | note | Frequency - 1 per line
66432b17-ac2c-5cfd-967e-78fc98c03e74 | note | Activity - S
488fadbe-90bf-5b0d-8b6b-8eb71925a20a | note | By - PE
| checkpoint | 3.5.2 - Reinstatement
a312f052-372d-50f9-9883-57a8dbe105e1 | note | Acceptance / Conformance Criteria - Quality Check on New Works/All the MH Lids and Cespit Levels should align with the pavement specification in terms of level & alignment
7be67543-bfaa-5a20-997e-ed431314971f | note | Standard / Specification - Reinstate and Tie into existing surrounds
d1cee765-ff68-569f-93cc-97c4f195f95c | note | Verifying Document - Photographs & Level Checks
4d5922ad-a59f-5136-9229-4b0ba6edc19b | note | Frequency - Continuous
a287eccd-79c8-502e-9bf6-c7365abc4ed2 | note | Activity - S
63711978-92e4-5993-a92f-a80b22d2f3bd | note | By - PE
| section | 4. Post-construction (Final Inspection & Handover)
| checkpoint | 4.1 - Survey Redline Drawings
53857957-862a-5c02-affb-420f8bbcb2d4 | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
0a6e7516-d189-58bf-b63f-ed3019cfa3f0 | note | Standard / Specification - Project Specification
97975fe6-bf31-533e-aa46-c1eb07ef0da3 | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen As Built
64440248-836a-5ff7-84fb-19292f75fdaf | note | Frequency - Post works completion
eca96e49-ee5e-5cc0-966e-5e8083612ee8 | note | Activity - H
f0c23b4c-fd20-5916-b85f-437a97b969e5 | note | By - SV
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - Streetlighting - Rev C | itp | ITP - Streetlighting - Rev C | 506f46bc-6df3-48ba-a3ef-ccee4a094673
| section | 1.1 - General
| checkpoint | 1.1.1 - Drawings
a3de2d74-21d0-5582-92b4-1ae7bc58ac16 | note | Acceptance / Conformance Criteria - Prior to starting works, ensure that the construction drawings are both IFC and the Current Version.
8f9725e5-dffa-5475-b513-f3c7a432abda | note | Standard / Specification - Downer
48977b38-2a3c-5563-b98c-9206b4725e94 | note | Verifying Document - IFC Drawings
06dc42aa-f4c7-5de2-ba65-f7ab71ce7356 | note | Frequency - Prior to work planning and start
3c8f00a4-011a-5c2f-9675-062f8e61effa | note | Activity - M
3168ccd6-ebc3-5d7f-a7d5-863e0c0bf506 | note | By - PE
| checkpoint | 1.1.2 - Power Connection Application
ccd54300-d4d7-5058-b31c-7d6d34ba8fcd | note | Acceptance / Conformance Criteria - Submit new streetlighting connection request via WEL Connect portal.
4c5eae55-5181-56bd-99f7-93457375ae5f | note | Standard / Specification - WEL Requirements
cf6da2e8-7fbf-50a0-a5db-29a5aa8f0244 | note | Verifying Document - Application Form
1db5b030-fd3c-57bf-aa68-601f31651c04 | note | Frequency - Once
6a2ebb1a-804e-5c37-9f5f-2bb31b01449d | note | Activity - H
7dcb24ca-8578-5a58-94a7-c7aebeaba83e | note | By - PE
| checkpoint | 1.1.3 - Construction Pack (1)
8a6216df-bc96-5a7b-a5d6-508324b8e2b0 | note | Acceptance / Conformance Criteria - ITP to be submitted to the Engineer and approved prior to works beginning
99a26ea9-263d-5b32-813b-3bdaa137025d | note | Standard / Specification - Downer
adfe312a-266c-5b24-ba0a-62cd06db1fd8 | note | Verifying Document - In-Eight Document Approval/Acknowledgement
acd68749-24f5-5aea-9762-8580ee45d332 | note | Frequency - Submit 10 days prior to commencement of works
bb80e0e9-e097-569c-a112-fb905f182e87 | note | Activity - H
58718269-f871-5198-84d0-0c12964f5d6a | note | By - PE
| checkpoint | 1.1.3 - Construction Pack (2)
d68c3e67-fc7e-5393-abff-6c3a11024596 | note | Acceptance / Conformance Criteria - Methodology and associated documents to be prepared, reviewed and approved internally prior to work commencement.
5c2199e1-2a20-5368-85e1-19c004989898 | note | Standard / Specification - Downer
83e6e0d1-2866-53b3-a1d3-98be7f650486 | note | Verifying Document - Construction Pack Sign Off
832a34b8-c26b-57c3-8cb6-abbdfd99d78b | note | Frequency - Prior to Construction & after any major incident
b90921d0-c20e-5c18-aeed-42bb1346090b | note | Activity - M
47b29234-b37b-539a-b7ac-022807ed6a3f | note | By - PE
| checkpoint | 1.1.4 - Survey Set-out
076e2c3d-7984-5a7c-9409-aef47385f457 | note | Acceptance / Conformance Criteria - Ensure streetlight locations are set out per IFC drawings/data.
948f3092-04ec-5e4a-89ff-64e7987cfdc2 | note | Standard / Specification - Design Drawings
ea90aa83-5866-51e7-a527-82b168584f4b | note | Verifying Document - ITP Sign Off
b465bc9b-e0be-5348-b733-88cceb9f6b03 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
f84c7a7c-a29e-5e94-9896-143af8ffb392 | note | Activity - M
eb825140-f341-575f-853a-599d96e1d56d | note | By - PE
| checkpoint | 1.1.5 - Environmental Protection
82db6031-9ffa-50e7-93b9-b0240c35b755 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
62fec460-e442-58e6-a255-638e495550d2 | note | Standard / Specification - Project ESCP Plans
eec13850-623f-5b2f-a4c3-5f53916dbd39 | note | Verifying Document - ITP Sign Off
b22e0258-66e6-5635-8a28-52bfa8c69cf5 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
231e5c4a-1751-5a4b-8293-ec3381d1809c | note | Activity - M
ade57c56-b692-5aa7-95ca-e191cdaa2f71 | note | By - PE
| checkpoint | 1.1.6 - Stakeholder
d0ff9ed4-8621-510b-92f2-c0d228d4a2b4 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works. Agree plans for maintaining access to properties during construction with landowners.
fe50bc8b-5efa-5ea9-828b-35c73834152c | note | Standard / Specification - Project Stakeholder Management Plan
1a1b544b-cd6a-5b70-a36e-072d0c6fd792 | note | Verifying Document - ITP Sign Off
dee95153-7e76-5f5a-ac7a-c74e016e71b6 | note | Frequency - Prior to Construction with continue updates throughout the works
0a41c492-74cc-5b7e-ae98-bdfe791ac4c4 | note | Activity - M
fa4ce277-bace-5414-9b1e-2e809d05421f | note | By - PE
| checkpoint | 1.1.6 - Permits
0da166e2-d8ce-54bd-a796-84c21a2ec108 | note | Acceptance / Conformance Criteria - Ground Disturbance Permit must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip.
c4fa453b-967a-59a2-9b46-8f3c119a56ef | note | ? Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. Doner Permit encompasses external provider permit requirements.
f221c398-07cf-5fe9-8262-e64bd9dbb056 | note | ? All known services must be clearly marked on site and briefed to the workforce .
35ccb006-0e03-5ff7-9338-01382db03d15 | note | Standard / Specification - Section 2.2.10 Project Specification
f0d8c0b3-c31a-5c8d-918e-02309cc3acb8 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
5d46cde5-8510-552f-824f-5978bc315f07 | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
78ad1714-004e-53d8-ad4e-d23d0ea1d896 | note | Activity - H
b01936ac-c17e-5be5-aff7-167214ad7479 | note | By - PE
| section | 2.1 - General
| checkpoint | 2.1.1 - Walk-over
2d143d4c-8c17-5af2-a95a-3b2808340849 | note | Acceptance / Conformance Criteria - BBO representative to walk over and confirm/approve locations for install. Including reviewing accessibility of doors.
67ae121c-bcd5-5155-bf07-1aa9e02704c7 | note | Standard / Specification - Design Drawings / RITS 3.6.3
77440c7f-dd26-5957-a2a7-140dc7778cc8 | note | Verifying Document - Written correspondence
99c519b7-ab20-5881-8d41-faee9e08d22c | note | Frequency - Prior to construction
3306da5c-16d6-5fe1-810b-3ba7c39bf4c5 | note | Activity - HP
b94539ae-bd38-52ef-87b1-b7df994d4c54 | note | By - PE / BBO
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1.2 - Light Poles Materials/Delivery
2df090cd-abe8-5432-86cd-70cd721474f2 | note | Acceptance / Conformance Criteria - Evidence of manufacturer and product name.
a42a8f65-8703-5eab-b13c-913fd6d7ac4c | note | Standard / Specification - BBO Request
e8ab109f-73f6-5d53-877b-dc2187455ada | note | Verifying Document - Delivery Dockets
9927671c-c4d0-56d4-b6e9-7ed16b3f8f9c | note | Frequency - Once per pole group installation
2b52bb6d-2046-5761-8aba-b5cffdfd2f56 | note | Activity - M
90bce1d5-b3fe-58e5-8754-8b9bee86752d | note | By - IBEX
| section | 3.1 - Civil (Pole) Installations
| checkpoint | 3.1.1 - Ducting Backfill Material
8222565c-699f-5a03-9f0a-4e96d0da6f75 | note | Acceptance / Conformance Criteria - COVERED UNDER UTILITY TRENCH ITP.
72a9835d-dcaa-57dc-b623-07a7798b36c3 | note | ? Where there is any exposed part of the cable (i.e. between termination of the duct and entry into streetlight pole underground hatch), surround with min. 100mm thickness sand material.
90df0d16-05a1-5b62-9f6d-69ce9e4aab72 | note | Standard / Specification - WEL Requirement
3325b3eb-a509-5bad-addc-6d9349885307 | note | Verifying Document - Photographs
ed60b599-34f8-501e-8dfd-e934ea3c2cd1 | note | Frequency - Verification on random selection of poles
899316fc-6aba-5ba1-add1-e507dad579c4 | note | Activity - M
1fa822c1-9461-5929-afc8-52b6980b2bb9 | note | By - IBEX / PE
| checkpoint | 3.1.2 - Access Hatch/Door Accessibility
ee96db52-4f63-5782-8241-a5f44a5029a9 | note | Acceptance / Conformance Criteria - Visual check to ensure accessibility of doors.
1008970d-3942-50fe-a9c1-17c117b79c13 | note | Standard / Specification - RITS 3.6.3
cd84f61d-ee2b-5661-90c9-435ff63f05da | note | Verifying Document - Nil - Visual Check
84446c3e-6c42-59f2-8de0-292bd9e4ba71 | note | Frequency - Each pole
006b666d-12db-5bba-b683-47532f57fae9 | note | Activity - M
6e2178ef-8c03-5b83-96c6-076e813002ff | note | By - IBEX / PE
| checkpoint | 3.1.3 - Pole Installation Positions
86ac0252-2e53-537f-915d-dc7a37d49d13 | note | Acceptance / Conformance Criteria - Poles within following tolerances:
e3084716-5af0-5451-8b30-b3b98c5729ae | note | ? +/- 0.5m parallel to the carriageway
1fb4a3b2-13a7-511d-8231-ee27be182692 | note | ? +/- 0.2m perpendicular to the carriageway
1955698b-f110-5875-ac0a-bb6d94af9676 | note | ? +/- 0.2m vertically
df0db22f-1601-5121-a804-6d9ab2e09d5e | note | Standard / Specification - Design Drawings
8ba4e170-2fef-5cde-ba48-4c970f277719 | note | Verifying Document - As-builts
3a035543-9c9e-5149-ba5d-d3cdb785caa6 | note | Frequency - Each pole
0fa1f756-81b0-5590-b768-76d84fd7f25a | note | Activity - H
fc89723f-6e6c-5b63-9b4c-b6cb8b60b179 | note | By - PE
| section | 3.2 - Cabling, Electrical Testing and Commissioning
| checkpoint | 3.2.1 - Earth Wiring
04e0591b-bffb-5dd0-8d3c-405231de065a | note | Acceptance / Conformance Criteria - Photos of streetlight earth once completed.
11ba273d-db14-5bba-899f-d13ee78f2190 | note | Standard / Specification - BBO Request
52da4e9c-f6fe-5966-8b40-b123e87bda76 | note | Verifying Document - Photograph
80e8fb9f-55b8-53d3-8904-d0a53bba398b | note | Frequency - Each earth
fe02b727-f9db-5bf5-864e-7f3c6a20d15e | note | Activity - M
0f99849b-2d19-545b-a63f-a65f354fc19b | note | By - IBEX / PE
| checkpoint | 3.2.2 - Electrical Certification
60ed628e-c347-5e43-a2cf-313e39e188cf | note | Acceptance / Conformance Criteria - Completed and signed certificate of electrical compliance (COC) and record of inspection (ROI).
8cd95bbb-2165-561a-95f2-cdfa4e1c6a7e | note | Confirm that poles are:
2940a440-c09b-5946-9270-6a42b9d8b611 | note | ? Earthed to AS/NZS 3000:2018
916b87fa-0ffe-53c6-bafd-6c7ba048d95e | note | ? Wired to AS/NZS 3000 and AS/NZS 3008:1.2
a56cd35c-ebfd-5101-bb1d-2850a326c5ef | note | ? Conforming to the NZ Electrical (Safety) Regulations
20dc2bd8-e318-5d56-b92a-2e3cf9194ab3 | note | Standard / Specification - Design Drawings
3fba7efc-79c2-5e27-b97b-046dfb789646 | note | Verifying Document - Certificate
86bb62e9-5297-59f4-937d-aaf7b81a59cf | note | Frequency - Each pole
f55925cf-b786-5b43-a307-65616f5f8eb1 | note | Activity - H
c7c12ee1-0517-519c-8622-e88996d84bd9 | note | By - IBEX
| checkpoint | 3.2.3 - Network Company Acceptance
5d99ecc1-c413-5887-a3a6-3919ec19957d | note | Acceptance / Conformance Criteria - Written acceptance of all underground cabling and circuitry, including acceptance of assumed responsibility for future maintenance and renewal.
1f0a9489-1b13-5cd4-88ae-2fa58ca1546a | note | Standard / Specification - RITS 3.6.8
5d1abee3-2209-5100-8bdc-68a137f45aa6 | note | Verifying Document - Written Correspondance/Acceptance
3b03f4d6-bc3b-5261-bc7b-7838647e1721 | note | Frequency - Once prior to comissioning
9a8c39f0-3f9e-55fe-9953-c44bd15ca842 | note | Activity - H
e7c1bdf1-00be-5b9a-af09-67b81949a1ff | note | By - WEL
| section | 4.1 - General
| checkpoint | 4.1.1 - Survey Redline Drawings
3d242e5a-b3c9-55f0-9521-a042a3d4928d | note | Acceptance / Conformance Criteria - Asbuilts reviewed and submitted showing final location of all poles
d991739a-0e59-5272-9a31-ded1a4dfe9a9 | note | Standard / Specification - Project Specification
9f595855-e3bd-59de-ad0b-c42a74766405 | note | Verifying Document - Survey Data As Built Drawings, Photographs, Red Pen As- Builts including Undercuts
c34cd3ea-534b-5a69-9490-940ab4263809 | note | Frequency - Post Works Completion
c2416c06-035d-5532-b108-88fa948554bd | note | Activity - H
73a5bd3b-dd02-59cf-85fb-aa4a3e2ae993 | note | By - PE
| checklist | ITP - Subsoil Drainage - Rev B | itp | ITP - Subsoil Drainage - Rev B | 1147af78-4cf8-4527-ab44-ec7519302617
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
e3e4320b-0ae2-5934-8f86-f48691f90a6d | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
a5cff262-b410-5ef3-a4ed-c68ff3ccedfc | note | Standard / Specification - Downer
ed9bd141-5b48-5aad-97ce-36073ad871fe | note | Verifying Document - Construction Pack
f85a1e6e-b3ee-5bb9-8cc8-e9cfe23826e0 | note | Frequency - Submit 10 days prior to commencement of works
d94ea74e-8904-5764-8156-a617a6ac5fc7 | note | Activity - H
bc1e6f46-f6c8-598f-ba1d-340b08b6912e | note | By - PE
| checkpoint | 3.01.02 - Survey Setout
66f5e34e-d324-54c8-8b73-6557f7a98a92 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
fcead67b-af71-5ce8-8593-1f4cf7fe5175 | note | Standard / Specification - Downer
6b14f005-ad29-5551-90c6-e9748d55704d | note | Verifying Document - Survey Records
2922226c-8e5b-5dd5-b869-a226857e8214 | note | Frequency - Prior to Works
fb6b461f-dfa6-5b91-9443-7737b0ef96a5 | note | Activity - H
f1cd4e61-b516-5014-a260-98792eea5814 | note | By - SV
| checkpoint | 3.01.03 - Approved Construction Drawings
fde2da03-ff8d-5b00-a0b9-84eaa06a0153 | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
0752b5eb-71af-54dc-bb93-4cf9c204bd79 | note | Standard / Specification - Downer
dffe62dd-1ef0-51e7-aac4-0fabcb726105 | note | Verifying Document - IFC Drawings
9c70aef2-39e1-51c0-814f-d725d260b35d | note | Frequency - Prior to works start
9d1a3400-5b43-5b12-9930-7ff952aa762c | note | Activity - H
6da2d4f1-345b-5e86-bc5b-84d2012936f5 | note | By - PE
| checkpoint | 3.01.04 - Topographic surveys for measurement
247ba338-8e35-5709-9cab-dadbbba10a43 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
4dbb98dd-29b1-52dd-9a5c-8a652de07099 | note | Standard / Specification - PS 2.2.12
3ae9b607-c597-5bfb-9af8-f8c5783c9711 | note | Verifying Document - As-built
c2a3b149-b534-56d2-a2aa-fcccf7b87d6f | note | Frequency - Prior to works and Post Works
55219e30-e8ae-52f1-bb10-3d6fc1d24903 | note | Activity - H
849ec13f-9f1a-5628-8a2a-f193408133a4 | note | By - PE
| checkpoint | 3.01.05 - Permits
6ce3adac-36c3-5bce-b254-8cfcea71578f | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
e69af894-0cdf-50fd-b743-4abf087bfb2d | note | Standard / Specification - ITP Register
9294d374-5eea-5067-9d6c-a8f6fa839752 | note | Verifying Document - ITP Sign Off
89e12c86-d074-50e1-8928-59e72a1a5c3f | note | Frequency - Prior to commencement of construction activity
32991eac-0b64-550a-ab84-ebf1587c4b7b | note | Activity - R
c206fb6c-57e6-55e5-8e8f-d54261253461 | note | By - SE
| checkpoint | 3.01.06 - Stakeholder Management
20f0f9cb-1274-5fb3-8d3f-e17434c67467 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works, Agree plans for maintaining access to properties during construction with landowners
4cf723b9-eb44-5949-8b79-80925a2b783d | note | Standard / Specification - Project Stakeholder Management Plan
9f36a72e-254c-5020-a432-7a482ca704be | note | Verifying Document - ITP Sign Off
0198f785-e291-5042-ba9d-db23179da972 | note | Frequency - Prior to Construction with continue updates throughout the works
968643e6-cfa8-5234-be55-6b7dda886fda | note | Activity - R
01ed8ab7-4614-553d-a7cb-9e105236fd40 | note | By - SE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 4.01.01 - Subsoil Pipes
37447c21-d9bd-500c-aa31-0993a799cb1c | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
2dad1c15-6feb-55ce-abf9-6797ac003351 | note | Standard / Specification - GWS 3.2.1
dceab4c2-2c90-57bf-8251-d7850b54fd8e | note | Verifying Document - Datasheet
0f33bfda-b27d-591d-ae27-6d5df859df2c | note | Frequency - Prior to installation
5d5cc8ae-9729-5ed8-b644-c4f5f81cb84c | note | Activity - C
95ca03e1-3a8f-54d1-8c87-a4e56696c92c | note | By - SE
| checkpoint | 4.01.02 - Subsoil Drainage Aggregate
08f26c5a-ddb7-5f41-aebf-e033745f7d70 | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate)
46bc154b-8396-506c-a819-88adb2206f91 | note | Standard / Specification - GWS 3.2.2 & 3.4
5b88fb0c-66a1-5e49-a8d5-cdf52ccf2b07 | note | Verifying Document - PSD, CR
e2794ec9-d4ea-5a33-b94d-af86ab431f4e | note | Frequency - Prior to installation
f52c5012-1778-5580-b1ac-b7a9546f876f | note | Activity - C
b115e0dd-3911-5ce4-a236-f8e0c0966a0c | note | By - SE
| checkpoint | 4.01.03 - Filter Cloth
922f59cc-c9ee-5af3-846d-3832e8976376 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
754bd53c-6759-508d-9c9f-42b977e4a2d9 | note | Standard / Specification - GWS 3.2.3
e740d2e6-4fd6-5b6e-903e-921217257ade | note | Verifying Document - Datasheet
630075fd-f369-5692-bfda-bdfbf36ddb1a | note | Frequency - Every 1,000m3. At least two weeks prior to works.
49e776b5-1c83-5b94-a552-ee1609d1a684 | note | Activity - C
6dff5458-8576-5ab5-a9ae-2cd0058980d6 | note | By - SE
| section | SECTION 5 – CONSTRUCTION ACTIVITY
| checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
a7f90523-9f49-5e26-ab91-47fa5191045a | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain.
5c00adcd-b649-524d-893b-30f87ba37b4f | note | Standard / Specification - GWS 3.2.2
14873811-9be7-5dd0-a934-8fc540eaca5e | note | Verifying Document - Site Record
91c15215-cc28-5f2e-90d9-af4254081fd5 | note | Frequency - prior to backfilling
70b304fc-caab-5b41-aa65-ba20611aef2c | note | Activity - HP
258d4f9b-854f-5091-8ede-a89602b5f9eb | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.02 - Trench Backfill
66ad9e85-7ae4-5d97-bde4-fd6893820dde | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through
8ae9bdfe-7318-5d5c-acd2-e4f904e06bd3 | note | Standard / Specification - GWS 3.3
268d3ca8-6fa2-5c5a-aa75-5773709bba2c | note | Verifying Document - Site Record
feb75e03-0258-585e-a689-11cbdf8e701f | note | Frequency - Each trench
de040a19-fbe0-566c-acf3-e60467c03c18 | note | Activity - I
55ab3706-dfae-54c7-b76d-3052fcb93c10 | note | By - SE
| checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
344525eb-1d74-5815-a443-95266cb8a6a2 | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
545c0bc8-2804-5fa2-9d40-968af904fbd1 | note | Standard / Specification - GWS 3.6
d84dca0a-bd73-5dfd-a8ae-1c5fa6f17cb7 | note | Verifying Document - Site Records
8a03718e-b66f-56de-8367-759667fee5ce | note | Frequency - Each Subsoil Line
53639ece-8919-5cae-b3d2-853054daaddb | note | Activity - I
dc89290d-cdb7-5804-8bc6-c147bef29a5b | note | By - SE
| checkpoint | 5.01.04 - Subsoil Flushing
4d1389a4-8de2-59a9-b825-54b9750ee56a | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
b3a0eaa6-caf8-59c8-a10d-74f5d1a1950b | note | Standard / Specification - GWS 3.6
584ba4fd-01d5-5f82-9b0c-a9d438b3ce71 | note | Verifying Document - Site Records
7256c455-ef41-567d-828b-7342b5c18c49 | note | Frequency - On completion of earthworks
c55063df-be7e-5b70-8482-b2b112768188 | note | Activity - HP
77c543ea-72b4-55d3-845a-47fb7b5fc0ea | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.05 - Survey
db1a13ff-dba0-5145-8e56-f359fb847c48 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
78e8a5ad-c326-5d9a-b4c0-9541320123f3 | note | Standard / Specification - Downer
d4cfc897-ac31-5109-8f62-93afcbd35528 | note | Verifying Document - Records
d218082c-7b29-5f91-b6c0-b03dc6b27398 | note | Frequency - Post construction
c7830048-5534-5a01-bb5e-179b0df836fb | note | Activity - H
15844533-95cb-5a12-93d4-001d05753d55 | note | By - SV
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 6.01.01 - Construction Record Compilation
ee1978d8-0e6d-5526-b6a7-946047814c4c | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
67362158-2834-5d84-ade0-ae6f1b6d0ec8 | note | Standard / Specification - Downer
a24007a3-c872-524f-b455-163c07c8e5c8 | note | Verifying Document - Records
5a7e31a5-0820-545c-b971-e36ddbf1729c | note | Frequency - Post construction
77a7e5f8-02ef-530a-91af-e607f05c7651 | note | Activity - H
e5d35e8d-f86b-5af7-ba05-d945435e2114 | note | By - SE
| checkpoint | 6.01.02 - Survey Records
a0ac0cc4-631a-5133-b6fd-245b319aa958 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
180a867c-7a92-5f9f-a0fd-91b82f256260 | note | Standard / Specification - Downer
f7904889-fdb4-5a7c-a63b-71ef8b5cc375 | note | Verifying Document - Records
ee7885ad-839a-50d2-8da3-d7324de5c9b0 | note | Frequency - Post construction
8e415304-8692-5b9c-ae6f-9fdacca84ec7 | note | Activity - H
01269d07-f711-5592-bd77-e4c52e9edc87 | note | By - SV
| checkpoint | 6.01.03 - Redline Drawings
550c52a2-03c4-52ad-89da-69f702697ea6 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
bbd2f293-3849-57a7-b0f4-a1cb5997d079 | note | Standard / Specification - Downer
c46c584a-56df-561d-b43a-c0c3fe670d6b | note | Verifying Document - Redlines
7c2c55cb-1dba-50a9-b56b-7f21c8f7e44b | note | Frequency - Post construction
e60bc891-dbaf-5d0d-a7dc-20912d3afc1a | note | Activity - H
6749ce7f-a61b-584d-ac29-3573b9e1fca6 | note | By - PE
| checkpoint | 6.01.04 - Defect, Snag and Punch List
b67c12f0-4350-5fa1-844b-97db4ad2689b | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
e13536f3-0c26-5388-ac21-72bb33e681f9 | note | Standard / Specification - Downer
4bda5a0e-18b6-5cb1-9464-06e06fddf0e8 | note | Verifying Document - Register
22da4f4a-2e8d-52e6-8d1e-86cec3f847bd | note | Frequency - Post construction
9445d37f-44a8-5181-a21a-9092a2fe6a28 | note | Activity - H
4ff92d37-6aeb-5c70-af9d-64d16a45ff29 | note | By - PE
| checkpoint | 6.01.05 - Photos
a95c32cc-8cc6-5355-b4f2-5e1bb87ec90e | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
0a4eb8cb-ee4d-505e-a512-5b983f330bba | note | Standard / Specification - Downer
f1452100-2a8d-508d-b79d-8fde17341213 | note | Verifying Document - Photo Records
c69c16fa-03e6-5513-9158-4e8e0523f491 | note | Frequency - Post construction
ebc7cd71-fbb0-547b-8b4a-7904c436de14 | note | Activity - H
c5e2515f-f88b-5bcc-b12a-51916f38e97e | note | By - SE
| checklist | ITP - Subsoil Drainage - Rev C | itp | ITP - Subsoil Drainage - Rev C | 7f743aa3-2ad8-4161-9f58-b77b037f7af8
| section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 3.01.01 - Construction Pack
d7be2db3-ea6e-5081-a3fa-9f6578272af5 | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
5936e5dc-9132-5d53-b0f0-f9edfbdd1a3e | note | Standard / Specification - Downer
cfbc549f-882c-5b41-a11d-18be0dc167f0 | note | Verifying Document - Construction Pack
0319a400-84a4-55c0-8f70-441f504d8b57 | note | Frequency - Submit 10 days prior to commencement of works
598b8731-aef4-573c-9ee4-06c6f222b97c | note | Activity - H
24ef8194-9972-500e-adc3-9b62ccb8ba7a | note | By - PE
| checkpoint | 3.01.02 - Survey Setout
0b9f3034-6658-56f0-bed8-ace15c277a22 | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
9e4ed420-adcf-5040-8a91-5853fed16b09 | note | Standard / Specification - Downer
a6281da7-de12-5e2e-b68c-2038b57ad103 | note | Verifying Document - Survey Records
45bc84e6-beab-520e-969b-361fcb60ac3b | note | Frequency - Prior to Works
bbb6fcb2-e555-5583-a8a9-9810156a90e3 | note | Activity - H
d53b4c04-315b-5f54-9469-90c1e8b22600 | note | By - SV
| checkpoint | 3.01.03 - Approved Construction Drawings
bdc2842a-7d3c-5544-8137-d83b5f982a4b | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
5ef2bb59-c850-5c20-b02f-ff31fd4b6d78 | note | Standard / Specification - Downer
3b11c33a-f8b5-5aa7-91f1-10782e9fcd4c | note | Verifying Document - IFC Drawings
323def97-05b9-5489-b1f2-f8c27a4140fc | note | Frequency - Prior to works start
00cf16f7-ade9-5aed-96d5-1472f835be59 | note | Activity - H
c532f3a9-d2d4-505d-9f4f-94f7ceb8bff4 | note | By - PE
| checkpoint | 3.01.04 - Topographic surveys for measurement
e089d5f4-ced8-5485-83ad-883cd2451b09 | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
808d2cc8-9cea-5c17-bafa-6c2345d96560 | note | Standard / Specification - PS 2.2.12
e2834ee1-8f42-5772-8411-554e951bc1c2 | note | Verifying Document - As-built
b4a1ce01-172e-511d-a93b-50253d6f1411 | note | Frequency - Prior to works and Post Works
6605b2b1-c1bd-5cb6-9e50-f19229bfb5c6 | note | Activity - H
96c2efd0-54fa-513d-a450-0bd6f9b3055f | note | By - PE
| checkpoint | 3.01.05 - Permits
468dfa97-219c-50fd-923f-0d9544cbcf74 | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
49520b88-dffc-5373-8e83-2849833fa509 | note | Standard / Specification - ITP Register
919e8e00-24fc-5e88-8149-179c7690596f | note | Verifying Document - ITP Sign Off
ac6c3b17-fe3f-594c-807b-37ec131c6fa3 | note | Frequency - Prior to commencement of construction activity
300f8782-e48f-5ee4-8055-969ed04e07bf | note | Activity - R
d10c2e34-7c87-51b7-9288-001049b9f637 | note | By - SE
| checkpoint | 3.01.06 - Stakeholder Management
4037dfc7-c3bd-5aa4-9e8b-fe22489a235f | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works, Agree plans for maintaining access to properties during construction with landowners
9e03c87e-42fe-5e7a-a630-a9438155d21a | note | Standard / Specification - Project Stakeholder Management Plan
58923489-7e4e-5f9a-8035-03446e1d91ac | note | Verifying Document - ITP Sign Off
1ebff814-28de-5b91-beac-5601bddfd866 | note | Frequency - Prior to Construction with continue updates throughout the works
929d5338-bda6-5c79-9ed8-ee53912897ca | note | Activity - R
673074b5-d940-5c63-88c8-6e7532dee716 | note | By - SE
| section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 4.01.01 - Subsoil Pipes
d023e47e-0881-5696-b786-b671d17dc843 | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
c9763730-9a2a-5ad5-ba5b-077d9dc7bb95 | note | Standard / Specification - GWS 3.2.1
6b68e6b6-12fb-5968-9d52-560fe63a6581 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
c7beaa27-ccc8-5dbd-a188-c2977568a3a1 | note | Frequency - Every Delievery to Site
0cc38bc5-f539-55fd-bc56-03bf014af76d | note | Activity - C
a60f67ca-2a43-568d-af02-4a88420851c4 | note | By - SE
| checkpoint | 4.01.02 - Subsoil Drainage Aggregate
7c9b9dfc-297e-5ddf-a2f1-b17179a69881 | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11
d2089a10-530f-5bea-9d97-e03f611b919a | note | • Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
1be6988c-c61e-5bbe-9f18-091fb2c8dbf0 | note | • App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
619f493e-fa37-54ff-a2d4-7dfa142ac2e9 | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
ad40829b-6deb-568e-b971-18272b95949b | note | Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
8ac0fdb2-32b2-5131-910a-4d69cbe8d50a | note | Test Sieve Aperture (mm) Percentage Passing (%)
8b672988-c8b6-50c5-aaf2-02fc53ebf6df | note | 53 100
0e075548-0ba0-5abb-a495-2f81fee72ea4 | note | 13.2 10 (max)
cee24c29-e7a4-5fe5-9a66-851bc47a9799 | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
4497dc5e-e119-536b-8d5a-d19a998b5f97 | note | Standard / Specification - GWS 3.2.2 & 3.4
107e7486-30e9-57fd-98af-3e0ab781e9e4 | note | Verifying Document - PSD, CR
c62d37bb-463d-5741-90af-459676b5e147 | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
6e631094-f166-58c8-8aff-d3be86d61f18 | note | Activity - C
7aa1539d-3550-53e2-a337-8fe3b40077a4 | note | By - SE
| checkpoint | 4.01.03 - Filter Cloth
5faac559-bd2e-5ffe-9de8-0fa793fdfd22 | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
ef37e272-12eb-522c-b65c-9c3bfe7ca901 | note | Standard / Specification - GWS 3.2.3
ec905cb2-509e-562c-b9e8-367497b2cff9 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
6945b2fb-ae9e-5f53-a594-a73692d450c5 | note | Frequency - Every Delievery to Site
1ba31876-8f62-5f34-9b5a-5e0d22302dde | note | Activity - C
e916f350-f892-5b53-8079-3d441131cdb2 | note | By - SE
| checkpoint | 4.01.04 - Securing Pins
fa9c9129-d300-5f24-9ca8-9893d93bff4c | note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and atleast 400mm in length
80f8485c-74a0-56e3-8a13-fd03950209a5 | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
26fc6303-993b-580e-9e94-533265455d3f | note | Frequency - Every Delievery to Site
573b3469-103f-5d64-bc95-552af65d6f39 | note | Activity - C
e6e29053-4c45-59de-8849-751676e8cd38 | note | By - SE
| section | SECTION 5 – CONSTRUCTION ACTIVITY
| checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
c23e65e9-fd71-5526-a2cc-396855c6c195 | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench.
ab0d7d29-29d7-569c-8d74-719e431bc677 | note | • Cloth must fully encapsulate the aggregate.
3f79a82e-4f8f-5049-acfe-605be6782794 | note | • Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6).
1483e652-e91f-5bb0-9e6b-f016afc483be | note | • Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement).
451c6d88-06a4-5e60-9a96-571e4709de1b | note | • Verifying document, photos of trench prior to backfill, every line.
a5aca90d-3526-5f03-9d4b-ea2d31054500 | note | Standard / Specification - GWS 3.2.2
8458197e-6626-5df2-a733-745266f8ce63 | note | Verifying Document - Every line
5cf81d1e-986d-5a1c-8317-123ce26560ac | note | Frequency - Photos of trench prior to backfill
236f455f-64de-5e7e-aeaa-2af1a2729ade | note | Activity - HP
5a27d893-ed13-5da5-b7cc-d0e0405b49d1 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.02 - Trench Backfill
baa6961f-370b-5765-aa80-fe233acc44a2 | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
0ad68759-e0df-5d72-b8ff-e757fada95ef | note | Standard / Specification - GWS 3.3
8cbf68e2-3da2-5f54-9b65-4c777d4168ce | note | Verifying Document - Site Record
75aec744-3603-5fcf-b939-cea07fe6f8d9 | note | Frequency - Each trench
ddefbe9b-d63f-531a-a74c-6802bd2597cc | note | Activity - I
9b433955-7419-58fe-a75a-09c05c43ba72 | note | By - SE
| checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
fb8bfbe6-7645-5a9f-b2e1-ff0313b2f573 | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
6bd24fb9-47b1-5e5d-b005-36dc0d7659b5 | note | Standard / Specification - GWS 3.6
174559c7-247b-5d06-9388-341126234e2a | note | Verifying Document - Site Records
e1b74fef-f4c2-5be7-a0c7-42401beaae55 | note | Frequency - Each Subsoil Line
b34148a7-1ae9-549d-9c79-bb90c1a412e9 | note | Activity - I
018d7d09-84a5-51e8-9e37-149a30a9100d | note | By - SE
| checkpoint | 5.01.04 - Subsoil Flushing
48f356b9-0212-5f71-9f71-4cb92ac42b4e | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
38814faf-75f9-5fb4-845a-a5f421a3e6ef | note | Standard / Specification - GWS 3.6
a5169edf-c580-5bab-8d64-598c905b9298 | note | Verifying Document - Site Records
67309611-3ec8-584a-960b-61db5f9e0a97 | note | Frequency - On completion of earthworks
2b55c223-fcfd-5c53-bb4c-8b944a45ba1d | note | Activity - HP
de3999c4-d716-56eb-bf28-b60aa9f23c25 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.01.05 - Survey
a58656a8-b22c-5642-b872-27a204d0207f | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
46d921b2-6be6-5646-9bcb-1afc5ce57d70 | note | Standard / Specification - Downer
934afbf8-cde1-5b5c-8f1d-c645411bc0e1 | note | Verifying Document - Records
4022de56-c619-53f2-b7c7-8b85fa5c1c0c | note | Frequency - Post construction
e67df3ba-f8e0-581a-94df-028eac8b1908 | note | Activity - H
d29b5322-9ddd-542c-a502-b679078edb5e | note | By - SV
| checkpoint | 5.01.06 - Excavation
9b9ea235-3ac2-5591-acd5-5f26a4bb2cfc | note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate subsoil drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
fd79cc91-a199-5010-b0b2-fcd2dedcfea4 | note | Standard / Specification - Downer
14e0668a-eb5d-569d-b10b-c1bb1d06e6fe | note | Verifying Document - Records
ac662a63-510c-54d7-a958-b3497ae10237 | note | Frequency - Prior to laying filter cloth
3863aa9b-31d1-5020-92e0-eb4d3adf62f2 | note | Activity - I
a5ad0346-0cda-551d-9482-b30eef6a49e0 | note | By - SE
| checkpoint | 5.01.07 - Bedding
6a804908-8011-5c5e-8a96-7cb5faf734cf | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
fc728791-6a66-56da-b5b1-f2ba3b2a6187 | note | Standard / Specification - Downer
8c7e7c09-452a-558f-b85d-318a98193232 | note | Verifying Document - Records
4010a9fc-e5fa-5a12-9b06-62aa2b2938d4 | note | Frequency - Prior to laying Novacoil
34c5d6d8-bae3-517c-a4ad-f770fcd10460 | note | Activity - I
8b1f267b-943d-5697-8660-baaeb969238b | note | By - SE
| checkpoint | 5.01.08 - Joining Pipes
509f6ddd-e8e7-51a6-b823-697d653eae3d | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
c00b7388-1649-5fd0-ace2-fc8bac8049b6 | note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
c928046d-14eb-576e-9b83-1323a75989d1 | note | Frequency - Every join
443663f7-d6b2-544e-969f-6d6289bcd7e3 | note | Activity - I
6df4a7c6-4500-5925-9856-6fef7a82c5b7 | note | By - SE
| section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 6.01.01 - Construction Record Compilation
ab1b7353-5893-57a3-80bb-d6ff1ee576a6 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
cad1b062-3767-5bfa-82fd-1152ad2d913b | note | Standard / Specification - Downer
f76eaa0f-f821-5f5e-9139-d0530719ea8a | note | Verifying Document - Records
f1b37311-80e2-54f9-909e-6ea161a5ea09 | note | Frequency - Post construction
a1f5e8c7-2e0c-5b65-8b40-cf0f2b87d5ff | note | Activity - H
cb9dd30f-398b-5a35-b2c6-33209e628017 | note | By - SE
| checkpoint | 6.01.02 - Survey Records
49ab85d1-17d4-52ba-8ddd-a8233292baf4 | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
fde8f60a-25f2-5460-9306-ff372f6c3cf0 | note | Standard / Specification - Downer
92033783-7b4d-5d01-ac3c-84c3456207e3 | note | Verifying Document - Records
998b1506-d623-584c-be5d-cd0820fa307d | note | Frequency - As-builts taken every 10m prior to backfill
1bd29fdc-651a-5e99-aee2-e2a3b722f923 | note | Activity - H
c4047b37-a420-5d21-afc2-67c0aec5fbfb | note | By - SV
| checkpoint | 6.01.03 - Redline Drawings
a066bb4e-c82e-59af-8bba-6af8f6a7e272 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
f1e52e1d-0b8c-51a4-a9e5-d2600697c49d | note | Standard / Specification - Downer
f758af7c-1c61-5a10-8a0a-aa023ffe2a87 | note | Verifying Document - Redlines
1a359c63-0963-5b55-92b9-c4cc287cb5b9 | note | Frequency - Post construction
4ac95717-eebc-5c76-b0e3-4dc3b68120fa | note | Activity - H
ab194141-d0be-5408-80eb-315e3cfc0123 | note | By - PE
| checkpoint | 6.01.04 - Defect, Snag and Punch List
7e05e999-2d6f-5e8b-a62e-c4a1158182c6 | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
ab4205d6-15f8-5e34-b898-be52195197a7 | note | Standard / Specification - Downer
36a6fe75-c164-5283-8c1a-734be7f9167c | note | Verifying Document - Register
d1d138f1-e2a5-5c86-b8b3-1103ff26411f | note | Frequency - Post construction
870c1870-8b7b-5b34-b350-3a5194c5f72e | note | Activity - H
53670f27-89b5-51a6-8533-6ac698884d66 | note | By - PE
| checkpoint | 6.01.05 - Photos
b662aadc-8edf-5b86-a58b-fb6b8f1e8dbf | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
e7decdde-99c2-5795-9a38-8f781b821623 | note | Standard / Specification - Downer
951f2ec0-db06-537b-9c6b-b338465022cb | note | Verifying Document - Photo Records
7c139195-7df4-59ba-be0b-4073a6d97f85 | note | Frequency - Post construction
5512b932-9243-5b16-afb4-6359730aba0f | note | Activity - H
32d2feae-16da-5e27-91f7-9c338fecbe5b | note | By - SE
| checklist | ITP - Traffic Signals - Rev B | itp | ITP - Traffic Signals - Rev B | 9e88c576-c457-4ac3-9a25-9bedb80ea4fa
| section | 1.1 - General
| checkpoint | 1.1.1 - Drawings
1a6e2bb1-747c-58ff-8f65-242511a5d3e1 | note | Acceptance / Conformance Criteria - Prior to starting works, ensure that the construction drawings are both IFC and the Current Version.
dabe18f4-c625-50fa-9b19-8058d312fa5d | note | Standard / Specification - Downer
64e92cf0-7324-5c15-ba3b-c5ab5715c984 | note | Verifying Document - IFC Drawings
779bfdcd-6116-55e5-9081-81eaab9b7e3d | note | Frequency - Prior to work planning and start
3b80ea29-fe30-558a-a97b-6e1446f5d021 | note | Activity - M
a34f54c2-e4d0-546e-808e-6cb59268bd8f | note | By - PE
| checkpoint | 1.1.2 - Construction Pack (1)
636c29f1-6237-5088-9697-d65a2bec8b3a | note | Acceptance / Conformance Criteria - ITP to be submitted to the Engineer and approved prior to works beginning
9c8fa9be-4db8-5c2c-bc7c-40f136388ac1 | note | Standard / Specification - Downer
a01f6c13-5d40-5e1b-a7f8-bc6467959a75 | note | Verifying Document - In-Eight Document Approval/Acknowledgement
bfafaa96-f4e3-5a3a-b9ed-edabfc598172 | note | Frequency - Submit 10 days prior to commencement of works
baaafe56-bd6f-5cf7-b8e0-fe43ecf34f78 | note | Activity - H
be0f65f1-d87b-50b6-8182-0d7800660487 | note | By - PE
| checkpoint | 1.1.2 - Construction Pack (2)
14ea70de-6733-5891-b959-6f6552d388d8 | note | Acceptance / Conformance Criteria - Methodology and associated documents to be prepared, reviewed and approved internally prior to work commencement.
23fe48dc-768b-5272-912b-af54827973d4 | note | Standard / Specification - Downer
4d473c96-0e45-5bc5-aa81-92d9b81da588 | note | Verifying Document - Construction Pack Sign Off
e38724a5-9fd2-5ba5-a0e4-8d22d58af085 | note | Frequency - Prior to Construction & after any major incident
4a1ca06a-ab84-51b7-880e-6e1d47eaba38 | note | Activity - M
eb3d56df-ebd9-5f80-97fb-e323803eded7 | note | By - PE
| checkpoint | 1.1.3 - Survey Set-out
aa347b44-1ebd-50a2-b200-a2c20d36e451 | note | Acceptance / Conformance Criteria - Ensure traffic signal pole, access chamber, and controller cabinet locations are set out per IFC drawings/data.
b35e099a-d971-59f2-93fb-4438e5f5af1d | note | Standard / Specification - Design Drawings
98c0cd01-8203-58c3-bc5a-5a221d8bbfbd | note | Verifying Document - ITP Sign Off
21bc99bd-299c-5c2a-b900-9e0be27c2c36 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
3795dc87-6b2d-599b-8a05-ddb0c8eeb8e8 | note | Activity - M
c0841e63-e883-53f0-938a-fa0892d30222 | note | By - PE
| checkpoint | 1.1.4 - Walk-over (1)
1832c688-97be-59a8-b044-a7b25c9d7c1d | note | Acceptance / Conformance Criteria - HCC Traffic Engineer, BBO Designer and MSQA rep to walk over and confirm pole locations.
1459bbe7-403d-505d-a96c-7a4b40f4aafd | note | – – – – – – – – – – – – – – –
40a04483-7436-5d4f-9c5a-74b4eff50a48 | note | HCC 1st Contact:
c9340165-e38f-54e6-9d02-ccd653c8944e | note | ○ Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport
ec49a40c-3897-5eab-8107-1315ed3d40fb | note | ○ DDI: (07) 838 6638
d5e496b6-d560-5a79-b4c0-c10700271009 | note | ○ Mob: 0278086506
a184a501-f314-5f66-8bf1-e25f76011dd9 | note | ○ Email: Brandon.Harley@HCC.govt.nz
7e0e0362-ccf2-5f07-b6ec-985761eed9f0 | note | – – – – – – – – – – – – – – –
a4c700ec-3cde-5dd2-9fe7-18da7c6bdd07 | note | HCC Alt Contact:
3d4e65f7-eb58-5645-984e-8bbef2b841f6 | note | ○ Holly Blackley - Senior Transport Network Operator HCC City Transport
6ca8c43f-d9ca-5be4-9209-6412cb048b38 | note | ○ DDI: (07) 838 6817
c381824d-576d-5788-bc8f-6af1b4852166 | note | ○ Mob: 0278087593
98794dfc-71bb-535a-9cda-4b44f3b51a6a | note | ○ Email: Holly.Blackley@hcc.govt.nz
79887ac3-b09d-53cc-8bc5-a2e8b45a5a79 | note | – – – – – – – – – – – – – – –
b8ceb4fc-f372-554d-84da-ee0b9a35d1da | note | HCC 2nd Alt Contact:
37aeffee-2895-52ae-ba62-0f3210deb86a | note | ○ John Kinghorn - HCC City Transport
50e954b2-c4dd-5185-aa14-d28eca000faa | note | ○ Mobile:
211de02f-f763-50b1-be68-c46327a91b24 | note | ○ Email: John.Kinghorn@hcc.govt.nz
9202adf3-377a-5ec0-978e-3e8dfafe3fc8 | note | – – – – – – – – – – – – – – –
2aee2570-25b4-54b0-82a5-117485d7d4ee | note | BBO MSQA Contact:
ae119fd4-f500-559d-80bf-88e7eca3fb59 | note | ○ Emil Karlsson - Intermediate Site Engineer
d8fc4015-c4bc-5175-8f55-f865cdd411db | note | ○ Mobile: 0273371065
f503bb0b-95c6-5891-a132-3a0ecbbaaa5f | note | ○ Email: ekarlsson@bbo.co.nz
225e9737-66fa-5f08-9c9c-ff28a34dc46f | note | – – – – – – – – – – – – – – –
f6f3cf06-caef-5a28-955b-b8b213f5aa9e | note | BBO MSQA Alt Contact:
4c2a6f4d-39aa-5a63-9552-af47787b9835 | note | ○ Ryan Fergusson - Senior Site Engineer
c01c80b4-8e40-5532-8b34-92cea38e8707 | note | ○ Mobile: 0274060378
c0e51264-12f6-5287-a834-5a312abab6df | note | ○ Email: rfergusson@bbo.co.nz
5a99e27b-7dec-56f0-a68a-688226ceebc8 | note | – – – – – – – – – – – – – – –
d8b2b8eb-bea8-558c-ab28-0b54de4d650b | note | BBO MSQA 2nd Alt Contact:
7f10ff8c-1154-589c-a17d-2fa750f07249 | note | ○ Zion Nordstrom -
96d15509-fba5-54be-843f-81d4598ca211 | note | ○ Email: znordstrom@bbo.co.nz
c340016b-6fa6-57de-9fbd-8fb904be52fb | note | – – – – – – – – – – – – – – –
6a5c3c8b-6248-5406-96a5-6b45ad6b9d6b | note | BBO Designer:
7769d0a6-e192-5978-a5ec-f987bf7fbca3 | note | ○ TBC - MSQA to contact/bring with.
deefc935-cca1-511f-908f-b0e6db3f88dc | note | – – – – – – – – – – – – – – –
5fad894c-4d32-57bb-b45e-0de7225b5a27 | note | Standard / Specification - Design Drawings
0c344e80-a9b2-5aa2-bb60-0950fb6ef838 | note | Verifying Document - Written correspondence / Photographs
7d75a211-1758-5d5d-87c0-190805939914 | note | Frequency - Prior to construction
fc8b277f-31b6-5c74-bedd-1067a7d813f6 | note | Activity - H
9468f4eb-48e2-568a-9ff4-6ffd1a412acf | note | By - PE
| checkpoint | 1.1.4 - Walk-over (2)
afab593b-8d3b-5cbd-b9e3-d59a6d2ae234 | note | Acceptance / Conformance Criteria - BBO/HCC written confirmation of any changes made to pole positions.
d1e9eae5-d663-5988-89f9-c3e195a9c481 | note | Standard / Specification - BBO Requirement
0460501b-3fd7-5351-88bc-3760b4a9b774 | note | Verifying Document - Written Correspondence (InEight preferred)
3defeba7-8e6e-5fa2-9e6a-d3b650b670b0 | note | Frequency - Post walkover, and prior to installation
57f82451-0f3d-5e75-a8e3-be348d120262 | note | Activity - H
bddd50c6-5a0e-502f-9ba0-c058b35fb5d7 | note | By - BBO / HCC / WTOC
| checkpoint | 1.1.5 - Environmental Protection
49735070-ff18-5c44-800f-3f7456b0aec4 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans. Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events.
39f5f564-db16-5ed3-9872-0619cc6d1c3b | note | Standard / Specification - Project ESCP Plans
2004eeaf-44c8-5df7-af7d-0bf7d2737198 | note | Verifying Document - ITP Sign Off
777f47d4-a5af-5da6-87cd-f2bdfa17081e | note | Frequency - Prior to Construction. Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events.
519aaf4c-c6cb-5432-81b2-2bdf71e40823 | note | Activity - M
d914bb68-8d93-50d3-a710-ab61be805d55 | note | By - PE
| checkpoint | 1.1.6 - Stakeholder
87ed676c-547e-5965-8e5d-e0de0ebe6371 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works. Agree plans for maintaining access to properties during construction with landowners.
c384e116-be96-5400-afad-c61549035099 | note | Standard / Specification - Project Stakeholder Management Plan
ef5e934f-db4c-55a7-99d4-a4bffadaaac8 | note | Verifying Document - ITP Sign Off
042937cd-ae6c-5ced-a50f-c8cd2a063d94 | note | Frequency - Prior to Construction with continue updates throughout the works
262aad29-09c9-5202-b8b5-934c1eab70a2 | note | Activity - M
9e5e12d0-17f9-56ae-bd78-b09fd79af3ab | note | By - PE
| checkpoint | 1.1.7 - Permits
f5c29669-c2c6-5857-94b6-89390bc8dd30 | note | Acceptance / Conformance Criteria - Ground Disturbance Permit must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip.
33c003bb-a3cb-5392-a808-9f0554c2d3b3 | note | ○ Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. Doner Permit encompasses external provider permit requirements.
90b0cfa1-53b8-5281-b6b6-08dcfb0518f6 | note | ○ All known services must be clearly marked on site and briefed to the workforce .
cddf3d35-8802-5edb-af89-0ca4b040cc64 | note | Standard / Specification - Section 2.2.10 Project Specification
f0a7b0cb-f3f4-5e07-8dae-31f300dddf47 | note | Verifying Document - Ground Disturbance Permit, DN-ZH-FM043.1
f5c8fe38-a90d-5e75-9872-3d0272b52b21 | note | Frequency - Prior to Construction. Reviewed and Reissued weekly or when site conditions change.
1ccde223-d279-51ff-8add-1056d45bee31 | note | Activity - H
a8f2d274-5a2c-52b3-b20a-3b022f77d020 | note | By - PE
| section | 2.1 - General
| checkpoint | 2.1.1 - Pole Producer Statements
25d80bdb-c272-52ca-b144-dd03717e64bf | note | Acceptance / Conformance Criteria - PS1 certificate required for all pole types.
82ce7dd2-8928-54e3-97e8-a25f3b3311ed | note | Standard / Specification - Project Specification Apendix E 3.16
13231e0a-66e7-573d-93d5-ca5ba43b8e28 | note | Verifying Document - PS1 Certificates
c0e4cfed-37da-52d8-9185-8c5ffa72ea08 | note | Frequency - Prior to pole acquisition
a569f554-5998-54f1-b80c-46d8eaba402a | note | Activity - H
53f99a72-2921-5bc0-9e32-94f6986403a5 | note | By - PE
| checkpoint | 2.1.2 - Controller Cabinet
465bdb9f-250a-50f5-9616-e1c7ae31966c | note | Acceptance / Conformance Criteria - Unless otherwise specified, VC6 ELV controller (compatible with latest SCATS software) fitted with a generator socket matching existing HCC controller cabinet colours.
09971c60-27e0-5727-a093-33aa48b13689 | note | ○ Must be fitted with a sticker indicating the Site ID Number.
9671bed3-752d-5920-a8fe-60cbfe13c19b | note | Standard / Specification - Project Specification Apendix E 2.3.5/2.3.6/3.6
0ea75044-d262-5a62-bdce-92a36a5e88fd | note | Verifying Document - Nil - Visual Check
64d3e65d-21d8-53fa-b444-64a1d46d48cc | note | Frequency - Each controller/intersection
71e9b313-2aa9-5236-9a84-acee2a391a8c | note | Activity - M
3d339772-de9e-58c9-8d31-be29d9d4eaa2 | note | By - PE/TSL
| checkpoint | 2.1.3 - Site ID Number
b295847f-acd3-5c08-bc76-5ec8a3ba683a | note | Acceptance / Conformance Criteria - HCC to provide Site ID number.
1ce2fa45-c26e-580c-88ae-34a6f93aa804 | note | Standard / Specification - Project Specification Apendix E 3.6
b5d196f8-9c49-5da5-ac9c-1521ed46d403 | note | Verifying Document - Written correspondence
b618943c-3c13-5c35-afaf-89296a0c1a10 | note | Frequency - Prior to commissioning
4b1b1a3c-3802-5a1d-9069-8817b2cb99ed | note | Activity - M
c6b09014-2f2d-5835-9036-0e44fa193c6f | note | By - PE / HCC/WTOC
| checkpoint | 2.1.4 - CCTV camera
2365db74-a0ca-5cec-9c44-6b23eb5b0b56 | note | Acceptance / Conformance Criteria - HCC must approve of traffic monitoring camera which should meet requirements. Hardware is required to have a minimum 12 months warranty period.
af1ef695-496e-586e-9f67-71c557bc4e20 | note | ○ HCC preference is an Axis Q6075-E along with an Axis Q6010-E, using the Axis T91L61 pole mounts.
5d6bb55b-7444-576d-a37a-7abbad9ec41b | note | Standard / Specification - Project Specification Appendix E 3.19.1
cc32f8f7-8871-5676-9e2a-b211a5d47f2d | note | Verifying Document - Written correspondence
7f7b4a6f-1ef4-5723-b396-1b73afba1d8e | note | Frequency - Prior to material acquisition
43906920-16a2-50bf-b428-6185c4996fb3 | note | Activity - M
fd24c82d-58db-5bc8-b111-f89604ce7d8f | note | By - PE/TSL
| checkpoint | 2.1.5 - Communications Connection
6af1668f-a0c8-5e28-89d1-b6e8dc520cc6 | note | Acceptance / Conformance Criteria - Engage HCC to engage Lightwire. Project team to coordinate with for on-site installation.
6962bfe9-bd91-5bd3-a83e-de4b2cda376e | note | Standard / Specification - Project Specification Apendix E 3.18
83cc83b2-c3b1-5b32-bdb3-23d0d1f8469f | note | Verifying Document - Written correspondence
002dfaa6-6265-521f-a3cf-95d59d1c9ee1 | note | Frequency - 3 months prior to connection
29bd6f9a-b4a5-525d-8e19-8e0b19a7bc0a | note | Activity - M
c4c6481a-ddd6-5ed9-bc5a-d7c341e6311b | note | By - PE
| checkpoint | 2.1.6 - Electrical Connection
b935a22f-96b2-51c2-bc30-eda1979d4079 | note | Acceptance / Conformance Criteria - Apply for new commercial electrical connection via the WEL Networks website/login for each new signalised intersection (NC1 Form).
e55b3cad-dda8-5a4e-9e1d-2b9c9ed97c87 | note | ○ Traffic signals subontractor to confirm electrical requirements.
4ca96c70-00f6-547d-88b8-00cc564c57f2 | note | Standard / Specification - Project Specification Appendix E 3.3
9e9dcca0-f6d2-5267-ba00-c5c60d7e9b4d | note | Verifying Document - Approval document/NC1 Form with ICP number
342b291e-ef9e-5f9d-81f5-58fd5ce40a13 | note | Frequency - 3 months prior to connection
68e139cc-f2a3-5107-8efa-9d4456f050a5 | note | Activity - M
8ea2b6e9-b8f0-5008-90c7-5e5eb61232a9 | note | By - PE
| section | 3.1 - Software
| checkpoint | 3.1.1 - Software/personality files and CIS
60cde22b-6c23-5a5c-813a-4b477a912301 | note | Acceptance / Conformance Criteria - HCC to provide to contractor (Downer or TSL).
6342b3e5-13e7-5c05-95dd-b1a60b94d0fc | note | Contact (s):
f082ddc5-a221-5e9c-a9aa-8cc1f2938baf | note | – – – – – – – – – – – – – – –
8543e704-77ce-57c4-b4e9-e73f7b102bd0 | note | John Kinghorn - HCC City Transport
55f06c78-0723-519e-ae13-4d216022b32f | note | ○ Mobile:
47534d1b-9447-50d7-8e89-5346278e4a43 | note | ○ Email: John.Kinghorn@hcc.govt.nz
21c0a32c-c675-5dac-848b-83501115b66b | note | – – – – – – – – – – – – – – –
c9e65987-d52a-518b-ba5b-9a68a4715dce | note | Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport
bba9017a-b2f6-5ed5-bc10-a9f4ea62acb0 | note | ○ DDI: (07) 838 6638
8182b054-1fb8-592a-9258-97a04bfe71a6 | note | ○ Mob: 0278086506
e54ee533-8490-585a-988f-535c6f0b2342 | note | ○ Email: Brandon.Harley@HCC.govt.nz
e91ea35b-d1b0-5feb-a2b0-9f09b102491c | note | – – – – – – – – – – – – – – –
5bb1260a-e7c2-5c75-86e3-c58e7d01b120 | note | Standard / Specification - Project Specification Appendix E 3.15.3
51f28f7e-1ceb-5665-abf7-6de2d4db27e6 | note | Verifying Document - In-Eight Documents/Mail
ed2cfde4-2677-596a-8c0a-e3ae7e7e0823 | note | Frequency - Requested at least 6 weeks prior to bench testing date.
154b9348-11db-54de-a8bf-385fd0859f2a | note | Activity - H
dda461fc-ee43-5414-baca-e7f4550988f2 | note | By - HCC / WTOC
| checkpoint | 3.1.2 - Bench Test
d8b7e7a4-ac89-54c5-9c42-15994d362acb | note | Acceptance / Conformance Criteria - Traffic signals contractor to bench test files.
1d00a791-144c-566e-b2e3-45b0c6259585 | note | Standard / Specification - NZTA P43 3.15.4
0578a9b8-7778-52b1-a75c-6568a171f1aa | note | Verifying Document - PDF Document
23395378-ae37-5755-92a6-48166eb4a467 | note | Frequency - Once per intersection, at least 1 week prior to comissioning
55eb0296-c074-55db-a092-4a8802037d05 | note | Activity - H
51ee8e6b-dd34-562f-a3ff-3f23212d7b8c | note | By - PE / TSL
| section | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations
| checkpoint | 3.2.1 - Soil Bearing Strength
047416b0-54a6-58a8-9b35-c7d290bbd7d1 | note | Acceptance / Conformance Criteria - Report results. Check this meets poles deisgn (i.e. >= 50kPa).
88dded6f-381f-5c97-8616-a058211d5a83 | note | Standard / Specification - Drawings/PS1/NZTA P43 2.5.1.3
43655bbd-8b87-5a26-b7dc-2809b804c86d | note | Verifying Document - Shear Vane
1c28fb49-10a1-5f68-bdf3-27c184d11805 | note | Frequency - One pole per intersection corner (i.e. north-west, north-east etc)
fb54a97f-5a15-54a5-97ea-9768fb69c336 | note | Activity - M
5cc5f5c6-401c-539b-a50e-e67f87b86892 | note | By - PE / TSL
| checkpoint | 3.2.2 - Pole Base Photograph
58f3023b-21c6-531f-a832-9c06785c5ec2 | note | Acceptance / Conformance Criteria - Photographic evidence of each pole base to be submitted as part of PS3
6367cabf-8ed3-5d8f-b2c2-4b7f64356e6c | note | Standard / Specification - Project Specification Appendix E 3.16
c0698672-7bab-5e49-a950-7961ed3471f8 | note | Verifying Document - Photographs
8b3bae35-b336-5692-bdb9-5850f40115c9 | note | Frequency - Each pole base prior to foundation pour.
49a3e8ef-a08b-54dd-9f1e-ed513875c8d3 | note | Activity - M
9454f899-82fb-56f7-ac1a-7a47cbb5a7da | note | By - TSL
| checkpoint | 3.2.5 - Identification Numbers (1)
6d0f5826-40b3-56e1-a5b2-11f39ff7d827 | note | Acceptance / Conformance Criteria - Ensure poles are fitted with/displaying the correct number and match the CIS sheets (pole numbers match program and diagram numbers).
a29d017d-61d7-513e-b5a8-e7f2bb656a65 | note | Verifying Document - Nil - Visual Check
58b5e79c-bc8c-58fa-818c-64b1d33a2023 | note | Frequency - Each pole
9c451946-5a72-56e3-b7b2-abb1e919889b | note | Activity - M
baa14c47-4889-5191-906b-0b218feda3ce | note | By - PE
| checkpoint | 3.2.5 - Identification Numbers (2)
0cc4b449-7ef9-52c5-8652-d03c7f6777f5 | note | Acceptance / Conformance Criteria - Controller cabinet fitted with Site ID Number sticker.
4fcf2ca3-1367-5071-9ff9-868a8ee714e7 | note | Standard / Specification - Project Specification Apendix E 3.6
6756bf93-ef86-5078-9122-e874a74bfcbf | note | Verifying Document - Nil - Visual Check
6ce36705-9e67-5d65-bff5-361528dfbedf | note | Frequency - Each controller cabinet/intersection
42a6fd31-6a20-5950-b91b-5ab42301b06d | note | Activity - M
0fa6aa6c-68bd-5bc4-8e31-9c16f0450e34 | note | By - PE
| checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (1)
232d240e-5671-5ed6-a2b0-302ca86e85b7 | note | Acceptance / Conformance Criteria - Access chambers installed in the berm surrounded by 300mm wide concrete apron to 100mm deep. 25MPa 28-day compressive strength concrete.
f944099f-582d-5e36-a97c-763d00be0b1d | note | Standard / Specification - NZTA P43 4.4.2
cc767167-a126-59ef-b153-980e30bee1c1 | note | Verifying Document - Nil - Visual Check
e0ea8692-d4ca-5644-b352-c2056964a936 | note | Frequency - Each access chamber in the berm
1814b540-e146-59bd-b887-e37972d9220a | note | Activity - M
949cdb71-8ac2-58cd-9788-1d20b0116dbe | note | By - PE / TSL
| checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (2)
ebee9d24-a526-5c3f-927a-056b812cf2e6 | note | Acceptance / Conformance Criteria - KSJB to have 150mm wide concrete surround to a depth of 150mm.
3758fb48-cf89-5c34-96ae-df1f3fa6d5a0 | note | Standard / Specification - NZTA P43 4.7
a85b7a70-77ad-5ece-9013-fb27e24b372e | note | Verifying Document - Nil - Visual Check
24b8a540-07fb-5888-97d5-131ae361f2cd | note | Frequency - Each KSJB in the berm
8938d508-2bac-5413-b699-6114a5d5f346 | note | Activity - M
77277e01-16ae-5e18-93f3-b1bd7beb1a76 | note | By - PE
| checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (3)
da701216-7ac8-5d5a-a478-2732b2470707 | note | Acceptance / Conformance Criteria - Controller cabinet to be surrounded by 300mm wide concrete apron around the base of the controller, widened to 900mm on the side adjacent to the door. 100mm thick, with slight fall away from conroller.
1d860cce-81b7-5a65-bdb7-788a30d57bbd | note | Standard / Specification - NZTA P43 3.6
2bf13bfa-98de-5453-b7bc-c5da6df3e0f9 | note | Verifying Document - Nil - Visual Check
efd3fe0a-0201-5301-90b3-d5a55b3e3ef3 | note | Frequency - Each controller cabinet
c68904bc-b956-5d41-a345-5a0d48dd3d20 | note | Activity - M
e4cb13f9-0391-5a88-a30e-e10f370a7e85 | note | By - PE
| section | 3.3 - Cabling and Electrical Testing
| checkpoint | 3.3.1 - Loop Cutting (1)
1fc24752-ab2e-53ee-9538-d5795532dda4 | note | Acceptance / Conformance Criteria - Rubberised bitument adhesive sealant applied to all saw cuts in the roadway
62215710-07d8-5e5b-8482-1f579dccb943 | note | Standard / Specification - Project Specification Appendix E 3.11
485cffd0-63ee-5286-bab1-2512fcb71f05 | note | Verifying Document - Nil - Visual Check
def8ee92-d946-512b-ae01-81ca8c78166c | note | Frequency - All saw cuts
e2cbac1d-d9c7-5cea-9939-aa8e65951079 | note | Activity - M
a1cf6de2-ec56-58da-bd05-07d8baf20a0b | note | By - PE
| checkpoint | 3.3.1 - Loop Cutting (2)
f04a7442-47ee-54fe-a232-1e16949844ef | note | Acceptance / Conformance Criteria - Saw cuts made through kerb and channel to be sealed with epoxy resin motar.
4c9bb10d-82ee-5943-97e7-1a27787104aa | note | Standard / Specification - Project Specification Appendix E 4.7
e45a48bc-06cb-5416-b35b-0ce64ef751c7 | note | Verifying Document - Nil - Visual Check
fe0d18ea-a423-5dda-b0dc-5e7174766fcf | note | Frequency - All saw cuts
ca37ddbb-c429-51e0-a71e-f639024d5abd | note | Activity - M
6b2e05d3-d61c-592e-957e-8753220698c3 | note | By - PE
| checkpoint | 3.3.2 - Electrical Certification (COC)/ Record of Inspection (ROI)
2211f947-11d8-56a7-8d00-7196abb09c7e | note | Acceptance / Conformance Criteria - Completed and signed certificate of electrical compliance.
1a2ac56d-141d-5682-8b67-47c1836ae0a9 | note | Standard / Specification - NZTA P43 3.16
f02677b3-dc72-51f8-8e9d-edccf4ce0a99 | note | Verifying Document - Certificate
8df7d6f7-a6d4-55b8-b1f9-b1e80d5f1341 | note | Frequency - 1 per intersection prior to commissioning.
6a334c9b-5b91-5ab5-88be-383a65b1f7e7 | note | Activity - H
933cf4a3-4ec6-5219-909b-7bb73394bbf1 | note | By - TSL
| section | 3.4 - Site Acceptance and Commissioning
| checkpoint | 3.4.1 - SCATS Connection (1)
0ee420ac-31e8-513c-9903-714658d779d0 | note | Acceptance / Conformance Criteria - Signals contractor to notify City Transportation Unit (CTU) Operations Room at least 1 week before SCATS commnications will be available from the controller.
c3b871a2-40e3-592b-9e7f-b38d5de736f3 | note | Standard / Specification - Project Specification Appendix E 3.15.4
7d10387d-44a0-56dc-aeb4-80fd2a25ba67 | note | Verifying Document - Written correspondence
64d19790-d57f-53f5-9a56-522b259836cf | note | Frequency - 1 week prior to SCATS communication being available from controller
fb357ba3-c899-5d5a-a45c-807791bea248 | note | Activity - M
ffc8c6e4-d183-5765-846c-44546ff22dea | note | By - PE / TSL
| checkpoint | 3.4.1 - SCATS Connection (2)
8acbed91-702d-50ac-a156-2c47d4139635 | note | Acceptance / Conformance Criteria - SCATS comminication achieved for a minimum of 48hours prior to comissioning.
6133450c-a625-57cb-b2fa-78d892cdf7c8 | note | Standard / Specification - Project Specification Appendix E 3.15.4
3574a399-41e8-5e79-9089-bf99a7f1071a | note | Verifying Document - Written correspondence
9a46cd34-b991-5fea-9767-ee17f74cccdb | note | Frequency - Min 48hrs prior to comissioning
3ab532b2-fa6f-5bae-a9d9-1a49665e25d4 | note | Activity - M
c34ea619-3344-5de7-ac3d-3639d893b701 | note | By - PE / HCC / TSL
| checkpoint | 3.4.2 - Documents
e890420e-9e7e-5a8a-8f1a-6b361132f646 | note | Acceptance / Conformance Criteria - Cable termination chart, CIS and logbook placed in document pocket inside controller cabinet.
7e6dbb80-8205-53bc-a0e9-51264719cfd1 | note | Standard / Specification - NZTA P43 3.16
fe20d126-549e-509b-9aae-61d194fa264e | note | Verifying Document - Nil - Visual Check
1ed93ae0-5283-50af-aeee-69e5daa7135b | note | Frequency - Within 2 weeks of commissioning
643e9599-57b6-5c37-a93c-35e760802400 | note | Activity - H
fb4a655e-8766-5e2d-8e72-e8290d2c148c | note | By - PE
| checkpoint | 3.4.3 - Approval to Commission
6e353e84-4c25-54a8-b595-a71e3835bc71 | note | Acceptance / Conformance Criteria - RCA traffic signals representative (City Transportation) approval to switch on.
fea3e389-1286-596a-aeb0-09b7e76d04ce | note | Standard / Specification - Project Specification Appendix E 3.15.4
664aa9e4-895f-5968-9215-bb4778fb8c01 | note | Verifying Document - Written correspondence
7221bfba-f0a6-5bc9-920a-f57024bbfc14 | note | Frequency - Once per intersection
dd4b687c-67d1-542e-acd4-6c67c15c9af1 | note | Activity - H
f1efa812-174b-5d56-9a41-4d7e1e37b9f2 | note | By - PE
| checkpoint | 3.4.4 - Site Acceptance Chart
ebcaad82-2973-536c-a931-0939134b9bff | note | Acceptance / Conformance Criteria - Site Acceptance Test Chart to be filled out and signed.
9c10c38f-b4ff-50ba-bd35-ee9915290da9 | note | Standard / Specification - Project Specification E 3.15.4
7ed6e949-2e70-5e96-8934-c76ca154c47e | note | Verifying Document - SAT Form
184617c7-5954-5eef-8c83-849cb6d97720 | note | Frequency - Once per intersection
755906db-2d73-546a-996a-c4440f6a7f64 | note | Activity - H
180b763b-fc04-5805-8883-26c49aae1e29 | note | By - TSL
| section | 4.1 - General
| checkpoint | 4.1.1 - Producer Statements (1)
3780b149-2d4f-5eab-b002-9445521762f2 | note | Acceptance / Conformance Criteria - PS1 Design Producer Statement from Chartered Professional Engineer
73efe4a7-377c-5b90-9235-45ba20eb933b | note | Standard / Specification - Project Specification Appendix E 3.16
4005ac66-5fa0-5ea4-b869-06f1c2fe8d6a | note | Verifying Document - Producer Statement 1
7af5f26d-afa3-50d0-a821-821a69b5b35d | note | Frequency - Each Pole Type
3134b51f-a8b7-5027-8ee3-5fa2ea75674d | note | Activity - H
| checkpoint | 4.1.1 - Producer Statements (2)
fdf9e640-057b-5829-9b84-9a9fc1671471 | note | Acceptance / Conformance Criteria - PS3 Certificate to be accompanied by photographic evidence of each pole (see requirement above).
c5249b0d-255e-5dbc-a792-a2534f88289c | note | Standard / Specification - Project Specification Appendix E 3.16
d88e0f00-a531-5a6b-ad27-9cf58e6c6907 | note | Verifying Document - Producer Statement 3
9378fbf1-178f-5984-9917-b44e38bb5169 | note | Frequency - Each Pole Post-Installation
1ca31bc1-1a63-556f-be68-9dc95f73e4ba | note | Activity - H
| checkpoint | 4.1.2 - Site Handover/Acceptance
d6f7e099-0f46-5f78-85fd-528252858142 | note | Acceptance / Conformance Criteria - Approval from Hamilton City Council and the signals maintenance contractor.
d10ecd76-9659-513d-963b-14e34984fa2b | note | Standard / Specification - Project Specification Appendix E 2.2.2
f0eea7f1-e753-5214-9732-c854bb553359 | note | Verifying Document - Written Correspondence
954403f4-97dc-5dd2-bd6a-92468c6aacda | note | Frequency - Post Signal Works Completion
734dee76-682b-5d17-8315-a242006e3ca4 | note | Activity - H
| checkpoint | 4.1.3 - Survey Redline Drawings
9ff17772-543e-560c-856e-e2cc3ba29db2 | note | Acceptance / Conformance Criteria - Asbuilts reviewed and submitted showing final location of all poles, access chambers, KSJB, loops and cabinets.
a480559d-f93a-54ae-b37e-c7d89fe072f3 | note | Standard / Specification - Project Specification
c5a4d5a0-3ebc-5720-bb70-d7c1f5b452e3 | note | Verifying Document - Survey Data, As Built Drawings, Photographs, Red Pen As-Builts including Undercuts
90da3462-b053-52b8-a34c-6c263f765ce4 | note | Frequency - Post-installation
c5acc9be-4937-55f9-bc35-01e685937157 | note | Activity - H
| checklist | ITP - Utility Trench |  | ITP - Utility Trench | 41e0c77e-6824-42d9-a9e9-788cd01154b8
| section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 1.1 - Extent of Line Setout
1a28f932-4256-53f4-8e4a-e589e1a2a356 | note | Acceptance / Conformance Criteria - Ensure line and level of Utility Trench has been marked out and agreed with Engineer in accordance with Utility drawings Identify any clashes before construction.
e9c10589-2e58-525d-9972-a8bb57e1b6ea | note | Standard / Specification - Design Drawings
6b76dc85-10ae-5e6b-8376-49e4b134b896 | note | Verifying Document - ITP Sign Off
f9922ebe-f7cb-5b0a-a655-f0e94ea3e5ca | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
2e5d0e79-8bb5-5576-9395-510ec96d4620 | note | Activity - M
5de18377-15ae-5482-9288-87089e16f418 | note | By - PE
| checkpoint | 1.2 - Construction Drawings- Berm
c9c9b3e2-adae-50ec-9477-5b9c379c72a0 | note | Acceptance / Conformance Criteria - Provide full construction drawings as agreed upon by the Service Providers including agreed Cross Sections
71ffa5a0-dba5-5cd6-b388-7cab3c17f796 | note | Verifying Document - Drawings
2733522c-3170-5982-8f04-83454cbef071 | note | Frequency - Prior to Construction
37adc687-791d-597c-82ea-c0f3e6523730 | note | Activity - HP
7b80468f-df7b-5bd0-84ed-190a83d4d579 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Construction Drawings-Road Crossings
6ef1f90b-a514-5f74-b178-c3ca3c76b3e8 | note | Acceptance / Conformance Criteria - Provide agreed upon Cross Sections from Utility Providers for any road crossings
38a47eff-b723-55d6-88ac-a60f6c7ce80b | note | Verifying Document - Drawings
b36b68dd-ccb3-53ac-8fb5-241006f9ff6c | note | Frequency - Prior to Construction
0ddb8441-3937-525c-b62d-749ce21e391e | note | Activity - HP
cf0b9879-0582-5b3a-8fce-3437eb240640 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Environmental Protection
9e0ab3fc-be7c-5604-b9aa-51ea43847668 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
239d1081-6c8f-595d-9a88-e7f1a434afec | note | Standard / Specification - Project ESCP Plans
cf6fdba6-58e7-5d42-b38f-fb7593b3d6e5 | note | Verifying Document - ITP Sign Off
b1795489-b8ec-5af5-b5ef-1a9532f6c47e | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
d102b365-417e-5f88-b2d1-aaec33477065 | note | Activity - M
a19d99c5-e611-5073-bbb5-e1886d74f59e | note | By - PE
| checkpoint | 1.5 - Stakeholder
14360796-9a7b-536b-9f8d-f74126ac8feb | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
fe08ae50-bd03-5b8b-af4c-0ec7f7634f81 | note | Standard / Specification - Project Stakeholder Management Plan
b1c20ff8-3e6c-5bb7-a4f5-3e1c100216d1 | note | Verifying Document - ITP Sign Off
ab6e4055-f100-52ba-b36a-6b93a14d7954 | note | Frequency - Prior to Construction with continue updates throughout the works
e6bf2580-1570-5fc8-980e-e6aa25c9ee25 | note | Activity - M
a86c2579-b1f2-5f9c-9bcb-d8f8eaae3ae8 | note | By - PE
| checkpoint | 1.6 - Permits
02ae71fd-9fe0-5153-96f8-7431f8b30552 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
419aadfe-9db5-5cad-ab0f-e9876ebf69cc | note | Standard / Specification - Section 2.2.10 Project Specification
3765baed-457c-5b64-bc01-9488eff7b0d3 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
c5994fec-79d5-5e19-a835-51e8ca8c6f6a | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
78f32b25-1076-51a0-bc10-c820e2403e07 | note | Activity - H
7bc7f061-bae2-50e5-8dd1-9fa1f9851eeb | note | By - PE
| section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 2.1 - Duct Bedding
444cf632-a93a-5dcf-8297-b82fca3ec4eb | note | Acceptance / Conformance Criteria - Confirmation from service providers on bedding and shading material required
0a3b0101-aa8a-5c69-b05a-20ad1f3e289a | note | Standard / Specification - Section 10 PWRBSS Project Specification Sand from Source Specified by WEL
0a0c45ef-ce6f-5ab7-ac13-38b2bd1fbf36 | note | Verifying Document - Delivery Dockets
eca7e6d9-795a-56ac-a05d-de5961e268bb | note | Frequency - Every Delivery
52e259fc-94fa-5ac2-9e2c-b3df15087154 | note | Activity - S
ad6978ac-eb7d-5a81-9185-88b267694f46 | note | By - PE
| checkpoint | 2.2 - Trench Backfill
07df4993-1ad4-5481-be9e-9f3c64467672 | note | Acceptance / Conformance Criteria - Native soil backfill must have no stones or "hard clods" of cohesive material. Max clod or particle size to be 7mm. Trench Backfill material in carriageway to be Pit Sand
9a606214-ee38-5637-808b-5b1d731ea7f1 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
f299d433-7a82-57f0-9b2b-4a356b15b9d2 | note | Verifying Document - Visual Inspection/Pictures PSD and MDD
b9de21f8-0904-58d5-bdd1-49c59ed61c4b | note | Frequency - Ongoing
57b53d57-cfee-5dc1-bf7f-e32d3bdac779 | note | Activity - S
032bb84e-ae4f-5361-bcdd-2c3971ef799d | note | By - PE
| checkpoint | 2.3 - Duct / Pipe Material
7d4133ae-1b6d-5113-bba3-97d11bb91482 | note | Acceptance / Conformance Criteria - Obtain duct / pipe from Utility Provider Confirmation required from service providers on ducting size
e47d48e4-9a8f-51e4-9cf7-8232d79733a3 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
392046a7-d9f1-57a5-9b4e-c6e930e9cf30 | note | Verifying Document - Delivery Dockets Email
b27fdf1a-8714-5c7e-9bae-2d1a3bb916ee | note | Frequency - Every Delivery
6e1de9e2-2fae-50c3-91eb-57f984033568 | note | Activity - S
750b4f6a-4226-5ce1-9da0-1ae038b7496f | note | By - PE
| checkpoint | 2.4 - Warning Tape & Mag Slabs
9c3d76f2-41f7-503f-a557-e5bbadbf185b | note | Acceptance / Conformance Criteria - Obtain warning tape and mag slabs from Utility Provider Confirmation required from service providers if mag slab and warning tape required.
b6618b37-a549-587e-909a-3b5acb2a9649 | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
e05cabbd-4118-5782-b951-d4bf9879d825 | note | Verifying Document - Delivery Dockets Email
51cbeb2d-7cb7-5b8b-9128-aceabf5907bf | note | Frequency - Every Delivery
89bc29c9-bdaa-5beb-ac6a-0ce5218ed3b4 | note | Activity - S
bffc547a-b7af-5006-b596-c230ed7ea3ad | note | By - PE
| section | SECTION 3 – CONSTRUCTION ACTIVITY
| checkpoint | 3.1 - Excavate trench
ca5b4c07-7b26-58ec-ba8e-30c9c2f74bdc | note | Acceptance / Conformance Criteria - Excavate trench and stockpile excavation arisings. Visual inspection of excavation arisings to identify presence of stones / hard clods. Inspection of formation to identify any soft spots.
a6c1f659-2ed7-5ca7-8ada-98099357c35c | note | Standard / Specification - Section 10 PWRBSS Project Specification
030fc257-bb20-5c49-9ba8-25b478c38139 | note | Verifying Document - Visual Inspection
54c76830-99fb-5518-a371-d7df97efb890 | note | Frequency - Ongoing
13c504a9-9d2e-59df-a4fe-9fd8e57becc8 | note | Activity - S
24b694bf-079e-5b4b-aade-5cb8aabf0dd2 | note | By - PE
| checkpoint | 3.2 - Install duct bedding
bf7a3739-d868-5588-adfc-63ab2de93d47 | note | Acceptance / Conformance Criteria - Place sand as per WEL detail
4cd8021f-35cc-5a06-8c06-546e4132a1c8 | note | Standard / Specification - Section 10 PWRBSS Project Specification
5d1f8269-de16-50bb-93ad-32496650b741 | note | Verifying Document - Visual Inspection/Pictures
b6b588eb-42b6-5e62-bb33-90827527af43 | note | Frequency - Ongoing
f377a399-92d5-51f0-8583-1b5c7d72033a | note | Activity - S
e861d23c-8062-5427-9707-75cd0a76d49c | note | By - PE
| checkpoint | 3.3 - Install Ducts
4dbc32a3-b84a-57dc-98da-5b40b9cdc1ed | note | Acceptance / Conformance Criteria - Place ducts to line and level shown on design drawings and in accordance with utility provider requirements
94ce0b08-8205-5e0b-9ca0-2c97f41808fd | note | Standard / Specification - Section 10 PWRBSS Project Specification
0c88a5ba-a134-5101-be66-0dc602cf86c9 | note | Verifying Document - Visual Inspection/Pictures
f9e36f3c-7cda-58c6-b1eb-647e8e775764 | note | Frequency - Ongoing
0e569a63-4871-5955-ac8a-8f07b69bbdca | note | Activity - S
34c4bae7-851e-5b52-b133-97f0373851af | note | By - PE
| checkpoint | 3.4 - Install Draw Cord
0a01dc1d-d4f5-5798-a683-21f160cd883b | note | Acceptance / Conformance Criteria - Install draw-cord to all service ducts
f175bd4a-e569-5d92-9fc3-a56848ca48a2 | note | Standard / Specification - Section 10 PWRBSS Project Specification
bf41177c-6e86-51de-a70c-c6eabc8f7ab2 | note | Verifying Document - Visual Inspection
c4efeddb-335e-5891-8d8b-5df5424422bb | note | Frequency - Ongoing
10573828-9cb6-5e52-bb4a-18e93abfa6c4 | note | Activity - S
70b47ba3-6fd1-5144-ac39-447299d2bd92 | note | By - PE
| checkpoint | 3.5 - Install End Caps
57fa27a2-c6e1-5cbb-a097-a1b24f08367a | note | Acceptance / Conformance Criteria - Install end caps to all service ducts
414df3a8-84ae-55f3-a017-17db6429d45e | note | Standard / Specification - Section 10 PWRBSS Project Specification
a5269469-2d07-5dc2-b6d6-15cfcc39f1e9 | note | Verifying Document - Visual Inspection/Pictures
73ed089c-7649-5cf9-961d-b714e30a0b87 | note | Frequency - Ongoing
0520f1ba-2c93-5c96-90f4-c80216482e42 | note | Activity - S
8a792c63-b312-51df-98e4-7e2a75391244 | note | By - PE
| checkpoint | 3.6 - Backfill
bbb881e7-094f-52af-b460-4c169d175b2d | note | Acceptance / Conformance Criteria - Backfill and compact with selected native soils (no stones or hard clods, max. size for all soil particles and clods is 7mm) Photos of Ducts prior to backfill
43072781-cf7a-5067-9ddc-f430181c43a6 | note | Standard / Specification - Section 10 PWRBSS Project Specification
e4f7f5f6-b92b-598c-adde-b645857dd598 | note | Verifying Document - Visual Inspection/Pictures
05313ce5-ff97-53c7-b1db-5149e5ba6337 | note | Frequency - Ongoing
4c778149-df86-58c7-8eb9-b90d6215b157 | note | Activity - S
7ef44f1e-7e46-58ed-9701-946cc3f3d646 | note | By - PE
| checkpoint | 3.7 - Install Warning Tape & Mag Slabs
65648a43-d930-5e62-88da-60fdb6a41ae2 | note | Acceptance / Conformance Criteria - Install warning tapes and mag slabs to all service ducts Photos of Warning tape and Mag slabs prior to backfill
392f46e7-9361-55a4-8f16-be0ab5d8df21 | note | Standard / Specification - Section 10 PWRBSS Project Specification
a14c3b49-d5b2-5308-b18b-4cddf0ccc8d5 | note | Verifying Document - Visual Inspection/Pictures
239154e0-ed43-5bed-9b58-d0a1ba786e8e | note | Frequency - Ongoing
ce322fe5-f01b-5aa5-bf30-385cf6d073be | note | Activity - S
036e7290-08e0-5af2-9c6e-81b10789df74 | note | By - PE
| checkpoint | 3.8 - Trench Backfill (Berm)
86af2f05-aa5c-594a-9055-664c4f903fdf | note | Acceptance / Conformance Criteria - See below:
d991b9d2-a7a6-5c6d-887a-79eccf1f91dd | note | LOCATION: Within Road Corridor - SIL or within 1m of the base of SIL (Subgrade fill) GRANULAR FILL: NDM: 98% MDD; Scala: 5blows/100mm COHESIVE FILL: N/A
369ca596-9790-56c1-81f9-b5d09e93136f | note | LOCATION: Within Road Corridor - Deeper than 1m below base of SIL (Bulk fill) GRANULAR FILL: NDM: 95% MDD; Scala: 4blows/100mm COHESIVE FILL: Air Voids: Average 10%, single maximum of 12%; Sheer Vane: Average 120kPa, minimum single value of 110kPa
ff0b27e4-8370-58f4-b3f7-a401b25883ca | note | LOCATION: Berm - Beneath Footpath GRANULAR FILL: NDM: 98% MDD; Scala: 4blows/100mm COHESIVE FILL: N/A
8ef1d158-2321-53f9-8cf5-5cf3dda02a5d | note | LOCATION: Berm - Outside of Footpath GRANULAR FILL: Scala: 3blows/100mm COHESIVE FILL: Sheer Vane: 70kPa
a7340a2f-39c2-5ba7-9532-124d4fd062fd | note | Standard / Specification - As Per General Correspondence from BBO GCO-0072
f2bc8c5d-8642-5678-8ec5-0cbfee46ce3a | note | Verifying Document - Testing Reports
6d793839-d120-54e1-972d-352b30dd00f2 | note | Frequency - every 20m along trench 1 test every 5m² at driveways and footpaths
df92b3d8-9c08-5c78-b7ec-7c40c1d9e38c | note | Activity - S
441fb3cf-2c66-5172-a6c7-eff8dcaebfdc | note | By - PE
| checkpoint | 3.8 - Trench Backfill (Road Crossings)
e3069caf-ac7b-5938-ba5e-b7af23e05ba1 | note | Acceptance / Conformance Criteria - See below:
64f5a35a-24fd-5b65-982e-293bb7ab9d3b | note | LOCATION: Within Road Corridor - SIL or within 1m of the base of SIL (Subgrade fill) GRANULAR FILL: NDM: 98% MDD; Scala: 5blows/100mm COHESIVE FILL: N/A
f971f735-834e-5f57-8210-d3aac1ebf2ae | note | LOCATION: Within Road Corridor - Deeper than 1m below base of SIL (Bulk fill) GRANULAR FILL: NDM: 95% MDD; Scala: 4blows/100mm COHESIVE FILL: Air Voids: Average 10%, single maximum of 12%; Sheer Vane: Average 120kPa, minimum single value of 110kPa
df159860-a002-5dfa-9c42-f60ca8545b9f | note | LOCATION: Berm - Beneath Footpath GRANULAR FILL: NDM: 98% MDD; Scala: 4blows/100mm COHESIVE FILL: N/A
15dbe736-f4fd-56c3-a62e-04748e3b5a7e | note | LOCATION: Berm - Outside of Footpath GRANULAR FILL: Scala: 3blows/100mm COHESIVE FILL: Sheer Vane: 70kPa
646446e1-42ed-5641-a553-f997e0b07cc9 | note | Standard / Specification - As Per General Correspondence from BBO GCO-0072
2ec6e3f8-a1fc-524a-a509-fadacc262ad6 | note | Verifying Document - Testing Reports
6c48dc5d-c3a7-5239-b270-9c799050ad89 | note | Frequency - Every 10m along trench
7fd95c35-09f9-51fa-a8e9-e81c379639ac | note | Activity - S
b919f3fd-1dcd-5342-9a40-fca4b36e9f95 | note | By - PE
| checkpoint | 3.9 - Install Service
33c58a5f-ead1-560e-8234-9fd01dd58d82 | note | Acceptance / Conformance Criteria - Services installed in ducts by Utility Providers
8fa09378-46fa-56da-8ea1-8e25e99b2856 | note | Standard / Specification - Performed by Utility Provider under their QA / QC Systems and Controls
7b2545f6-36ec-50af-8442-0d8dbe9ae8d6 | note | Verifying Document - N/A
d067f1f0-dadd-52cc-a908-8dca32195346 | note | Frequency - N/A
| checkpoint | 3.1 - Reinstate
ae1b20e6-8844-5778-baf8-35d5bf01eff6 | note | Acceptance / Conformance Criteria - Reinstate and tie-into to existing surrounds
9acb322c-e4b7-59ea-b319-1e3c41a5b5ca | note | Verifying Document - Visual Inspection/Pictures
f9b96b11-ccf2-5513-84d7-cc0dd1d0061e | note | Frequency - Upon Completion of Each Section
fc9bc56e-4c60-5d68-8bdd-8768a6bfe8f6 | note | Activity - S
10383bc4-81b4-5272-bad5-9684ca75a2d1 | note | By - PE
| section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 4.1 - Survey Redline Drawings
dc1c3dda-d46d-5493-83a4-ed992a74c7eb | note | Acceptance / Conformance Criteria - GPS Survey of every joint in every duct / 6m centres on continuous pipe. Survey point naming protocols to be agreed between subcontractor and Downer Survey Manager. Draft As Built Drawings. Photograph of formation, all ducts immediately before backfill, warning tape / mag slabs immediately before backfill.
f81e2f98-ab70-599e-8fab-14dd0ea09089 | note | Standard / Specification - Section 2.2.17 PWRBSS Specification
a7188ac8-db8a-5504-857c-c81ffc2501cc | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen Asbuilt including Undercuts/Any changes from original design, including any change in road crossing locations
f73d8d9f-3c77-58f6-b89a-f0b8d113ae6f | note | Frequency - Post works completion
377e2c0a-cce7-5704-877f-d5cfb42a2d24 | note | Activity - H
b9d2b744-054c-52aa-b0ca-673b30e6246e | note | By - SV
| checklist | ITP - Wastewater-PVC - Rev F |  | ITP - Wastewater-PVC - Rev F | c542aac1-81a3-495e-8502-c63793504e9f
| section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 1.1 - Extent of Line Setout
0d5eef49-d0fc-5a1c-8a82-fd3a74f4033f | note | Acceptance / Conformance Criteria - Ensure line and level of Wastewater has been marked out and agreed with Engineer in accordance with Wastewater drawings Identify any clashes before construction.
0d071870-11c5-5eec-84c9-292c12037ea6 | note | Standard / Specification - Design Drawings
0c26aa56-26c6-57ec-a2ad-e0bcf160427c | note | Verifying Document - ITP Sign Off
3a52920e-aaf1-52da-881b-91fe241aef3f | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
63977a38-fd54-570a-b231-ab58a3755fd8 | note | Verification Activity - M
4f7e095f-a708-5e2a-93ee-5ab5f300b976 | note | Verification Activity - By: - PE
| checkpoint | 1.2 - Environmental Protection
7bc6ee02-e63f-597c-b980-314821ff6b01 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
f3e9a12d-8c5a-5a8e-bf90-8ede8d1fa0b1 | note | Standard / Specification - Project ESCP Plans
46bfa01b-553c-5913-8caf-ebdd8474fbde | note | Verifying Document - ITP Sign Off
b29f2714-073d-5b81-bd59-5a1cbe02af26 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
93e14ecb-207f-5822-9af8-0cdb07361ee8 | note | Verification Activity - M
3ea2dbb3-c6bf-5dc0-aa59-59f7b80d4a4e | note | Verification Activity - By: - PE
| checkpoint | 1.3 - Stakeholder
afaf20fc-c54e-5524-8f33-e4380c3567a9 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
a09a546d-55fe-5f19-b899-ae01546cb169 | note | Standard / Specification - Project Stakeholder Management Plan
967077ad-1d63-5426-901a-2aa6bc33d6d4 | note | Verifying Document - ITP Sign Off
e5e9c320-9f09-5c08-9a43-e161dbb5bf39 | note | Frequency - Prior to Construction with continue updates throughout the works
0ace0bfb-bfcd-5b85-a19a-a83a01875460 | note | Verification Activity - M
e39f3135-cafb-5b0b-b29c-fb105c9bd876 | note | Verification Activity - By: - PE
| checkpoint | 1.4 - Permits
bd0fe073-cba0-5f59-a016-aeda24e18447 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
79645441-64ea-58ef-b789-aad531bc2ad6 | note | Standard / Specification - Section 2.2.10 Project Specification
b67b4743-30a9-590a-9b37-350070f50604 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
27583fad-0c9b-50eb-8194-8c8a1b4cadbd | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
47dad4cc-2d8d-5614-bf1e-4055e6a65556 | note | Verification Activity - H
e7cd61f0-d1fa-5369-b44a-ccc53d21f64e | note | Verification Activity - By: - PE
| section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 2.1 - Pipes, Fittings and Pre-cast Structures
8380fd18-221b-5c3b-b14b-e692cc846559 | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes are correct and in good condition and compliant.
89890d6c-4980-5009-8325-2eac61e918d2 | note | Standard / Specification - PS Appendix L
825234e5-2d1d-5fcc-bee4-6ba02fbafbc4 | note | Verifying Document - Delivery Dockets
d408a0c9-efa7-5344-8e51-029ba33d35a3 | note | Frequency - Each Delivery to site
e04f09b9-b48a-57e2-b870-52ecbafd7093 | note | Verification Activity - S
f922cdaf-e2bb-5a91-824f-41c0d5865dc0 | note | Verification Activity - By: - PE
| checkpoint | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
5a2cfb08-ad89-50f2-91cf-4777f1275762 | note | Acceptance / Conformance Criteria - Confirm material grading and density
08a7f806-f8b9-5dc8-8aa8-cc410ee0a080 | note | Standard / Specification - PS Appendix L
382be309-4d8d-5371-87b1-05587f94db3d | note | Verifying Document - IANZ Lab Test Report
9a444a70-31d6-5dbc-8f4c-291d55f3dc8e | note | Frequency - 1 Test per 1000m3
918e6dc4-ffed-53b9-9f63-766d42c0ad5d | note | Verification Activity - H
9bdc96f3-272f-5e88-a260-7aceb61b2360 | note | Verification Activity - By: - PE
| checkpoint | 2.3 - Undercut Backfill Material
4b89be8b-43b8-59cd-815f-9acf1c08a812 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
8097d6a7-b180-5018-87b6-12ab0464a2da | note | Standard / Specification - Engineer to Specify
eb77f4cc-821b-5bf8-856a-e20ceefb325b | note | Verifying Document - IANZ Lab Test Report
d3c2e5fa-8c1a-534e-a747-67fbeb9ed6a0 | note | Frequency - 1 Test per 1000m3
953f3b31-d3fb-5be7-b265-54d13f455913 | note | Verification Activity - HP
1ffea821-fd4e-5674-be51-72fc6127f647 | note | Verification Activity - By: - ENG
| checkpoint | 2.4 - Geotextile/Geogrid
b083675e-9d2f-5fed-89e2-735bd98c3563 | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
5323cb79-91c0-54e4-ba4f-641d2790f3ee | note | Standard / Specification - Project Specification
e3b2c732-9e5e-55ec-a969-076070e60ae1 | note | Verifying Document - Certification
72b70309-dbc1-5449-ab59-d58f87e9de84 | note | Frequency - Material Used
b0cb6815-4b18-5e59-beae-9613ff549fb5 | note | Verification Activity - C
ddfd5a19-6932-5ea2-b283-6fcd127b262d | note | Verification Activity - By: - PE
| section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction
| checkpoint | 3.1.1 - Foundation Compliance
f9114ed8-508c-56c9-a70c-105d2888782a | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
a805edc5-2b44-584f-9213-01a09c81f559 | note | Standard / Specification - Project Specification 4.3
e67b2dea-eeca-538c-b086-d2d763af8ade | note | Verifying Document - IANZ Scala test result
76acdc33-ead8-5322-8ee5-98920d33eb07 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
48757397-c016-5f0b-8e74-9a848cff25f1 | note | Verification Activity - H
0302830c-7332-59de-ab66-34ab747280cf | note | Verification Activity - By: - QE
| checkpoint | 3.1.2 - Undercut Backfill Compliance
f165b5fe-6212-5080-a1c4-07cc213160c4 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
05404d60-6262-571c-ab7f-97e9889a0080 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70% or 95% of MDD AS/NZS 2566.2/2002
ada43e11-038b-5cb0-b5ba-bf0ac6a35a16 | note | Verifying Document - IANZ Lab Test Report
9fc59673-dcbd-5795-991b-f459c7995aa9 | note | Frequency - Based on Undercut Section
457b1941-1530-51c1-bb06-563a243bd414 | note | Verification Activity - H
e347b3d0-785a-5cf7-bef9-359eb06d128f | note | Verification Activity - By: - QE
| checkpoint | 3.1.3 - Bedding Compaction Testing
4459e1c9-44f2-5a1e-b6e6-870f04c8b5f9 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
9fee4cc3-00a2-53f5-b535-ebb65125d555 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
d47bb5bc-3ae8-5178-bcf3-82784e72ec0b | note | Verifying Document - IANZ Lab Test Report
d95580df-35a2-5e6a-a3da-b87260e02da5 | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
9977cecc-7656-5d5a-9b70-86e5ef67f597 | note | Verification Activity - H
e4969a6f-e491-5a9e-bd68-00560b809a5d | note | Verification Activity - By: - QE
| checkpoint | 3.1.4 - Haunch/Side Zone Compaction Testing
8c6f233a-cfe9-5745-abd0-57f1e432f484 | note | Acceptance / Conformance Criteria - NDM Back Scatter Minimum Compaction 95% of MDD
078c54b1-a2cc-5641-8f40-4e135e103f94 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS-25566.2/2002
0d979ae5-b690-5c70-8586-3dcd359bc89c | note | Verifying Document - IANZ Lab Test Report
ec877efa-f836-5fce-914d-65c42133af1d | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
355f9922-7a96-5092-a53c-a6bd5a79e540 | note | Verification Activity - H
d4d8b25b-c759-58fb-a058-5867a07868db | note | Verification Activity - By: - QE
| checkpoint | 3.1.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
d7cbb21f-3c7f-5065-be72-bf6e19634a05 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95% of MDD
c3985824-6639-5243-924a-357dafeea0e7 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS-25566.2/2002
bdab0c55-e44f-5a38-8d40-da3eb921643f | note | Verifying Document - IANZ Lab Test Report
3a706429-ce3b-5a5c-acac-d7b3c99d521d | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
a97b6fb4-2749-5197-bfd2-9893f23d2fa3 | note | Verification Activity - H
52a59d26-f675-5687-bd40-33937c0b61d1 | note | Verification Activity - By: - QE
| checkpoint | 3.1.6 - Backfill Inspection
12db7e92-b9dc-5d44-b13b-fdedc2975145 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
63a956f9-715e-5e8e-a332-afe4588e4d02 | note | Standard / Specification - Project Specification 4.3
60d444b2-3c15-5124-8354-6dfaf78f9c41 | note | Verifying Document - Photographs
b1ab14f6-6ece-5cb0-adf6-9ae9ae772d75 | note | Frequency - Continuous
d54c2165-d850-5b0a-b89c-5600270b3fc1 | note | Verification Activity - S
166bcfcb-cc5e-5ab0-ac87-a2b26da10865 | note | Verification Activity - By: - PE
| checkpoint | 3.1.7 - Survey
d8b2d5c6-c725-5a65-a847-243a2bf19db2 | note | Acceptance / Conformance Criteria - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 10mm. Pipe invert checks shall be carried out at least once per day with a maximum of 30m between checks.
a3f876d4-dfde-5223-aecf-28ebe92dcf94 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
939644b9-8a94-5996-9d09-89e56788d01b | note | Verifying Document - Survey Data
ee51bd9c-6cf2-561b-82dd-22c6a02b957a | note | Frequency - Continuous
be32b652-6e68-51e1-a54e-2bfb34d520dd | note | Verification Activity - C
4617b38a-d3e0-5d7a-8052-83f11b5687f0 | note | Verification Activity - By: - SV
| checkpoint | 3.1.8 - Backfill Compaction Testing
69683509-f357-55f2-b443-9e2678eda21f | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC. Minimum Compaction 95%(Average 98%) of MDD
3132503d-6548-527d-ae32-76e55cc744cf | note | Standard / Specification - MDD Average of 98% with minimum of 95% PS 4.5
3960ff87-9875-59b6-9e35-c1e15d31c11b | note | Verifying Document - IANZ Lab Test Report
01f28adc-3ecc-512a-82d4-a6d1771e7a6c | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
3d0bf983-a5b1-5f0a-ab83-067fc76bcffe | note | Verification Activity - H
f589be2b-bdcf-5825-b553-dac0aa9a08c9 | note | Verification Activity - By: - QE
| checkpoint | 3.1.9 - Manhole Foundation Compliance
677d09e1-70bc-5ef1-9c4a-0ad3a5e67cd3 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa Engineer to confirm undercut depth (If Required)
cf849772-ecad-55b4-aa02-0b5fce719a44 | note | Standard / Specification - Project Specification 4.3
5aa1ed71-ef58-55c3-983f-29ac1d35e5bc | note | Verifying Document - IANZ Scala test result
5c3f2d8c-1fcb-59cf-9887-729cde761a98 | note | Frequency - 1 Test/Manhole
97cdda2f-e76e-5655-840e-23cadfc13db6 | note | Verification Activity - H
f7a9b1b8-70e2-5f25-84bf-26b7e30c2455 | note | Verification Activity - By: - QE
| checkpoint | 3.1.10 - Undercut Backfill Compliance
f5d28d44-e770-5c37-9b43-0262b26bcf56 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
e237cff0-422d-5a3e-b95b-96ef53bed8f3 | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 3725:2012
fd7aba61-0d96-53cc-97eb-5cde4f3d2ba1 | note | Verifying Document - IANZ Lab Test Report
6fe58900-5a8b-50d7-ab64-590c7c065ad2 | note | Frequency - 1 Test/Manhole if Undercut required
800b5487-1c28-541a-8329-d8a94d8e400c | note | Verification Activity - H
917fbdb0-418e-5466-a6fe-b12d3fa9290d | note | Verification Activity - By: - QE
| checkpoint | 3.1.11 - Bedding Compaction Testing
2d183ad2-6329-5085-8bc5-13ac4e92f2d6 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
e1b29de3-a730-53c7-8d76-2d7e993deabb | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 3725:2012
aebdbf95-4e5e-5d9a-bab5-737c9a2935ba | note | Verifying Document - IANZ Lab Test Report
ccdc68b2-6f5b-5697-a585-59cc69549c59 | note | Frequency - 1 Test/Manhole
b4501a13-5213-5924-ad78-9145b0b42f90 | note | Verification Activity - H
f423f03e-2f08-5bb3-b771-74422f0c3e41 | note | Verification Activity - By: - QE
| checkpoint | 3.1.12 - Backfill Inspection
8dacf914-9b08-546f-a9e3-9b3fe5cc4935 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
2b084272-b8b6-5df0-84fb-13f3de659b9a | note | Standard / Specification - Project Specification 4.3
489cd81e-404c-5c4b-ba53-7198caa05a74 | note | Verifying Document - Photographs
ff693eec-23da-5e77-803d-4b7e0423c663 | note | Frequency - Continuous
fe61226b-e6d3-5623-88fe-7475c5d1ae37 | note | Verification Activity - S
9dab9a60-219b-5f79-882e-27df70458dac | note | Verification Activity - By: - PE
| checkpoint | 3.1.13 - Backfill Testing
fd68ce07-ed6f-58e1-b85d-f91538958ac6 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC. Minimum Compaction 95%(Average 98%) of MDD
19760d10-412f-548c-9738-59448210c203 | note | Standard / Specification - MDD Average of 98% with minimum of 95% PS 4.5
05f3cf0b-31a7-5f95-8904-b79bba7c79f0 | note | Verifying Document - IANZ Lab Test Report
da9eb4b7-f5d6-5ace-ba2d-717b88dfae8f | note | Frequency - 4 Density tests per layer at Quarter Points Around Structure
3b9e8475-dca7-5e35-82ed-7a6cb0da0c7d | note | Verification Activity - H
716af32b-ddd9-52de-8389-d6cab9845209 | note | Verification Activity - By: - QE
| checkpoint | 3.1.14 - Low Air pressure Test of Pipeline
66364606-a2c3-534e-ace6-3048f1d43445 | note | Acceptance / Conformance Criteria - Low Air Pressure Testing as per Appendix C2 NZS 4404 Refer to NZ/AS 2566.2 M5 (Constant pressure tests) "NTT 009"
de612459-5f70-5818-9692-8bde69981beb | note | Standard / Specification - Pump Air to 25kpa and maintain pressure for 3 minutes
d81c550e-1daa-5078-9784-1a7264ea80d5 | note | Verifying Document - Pressure Test Report
9e335dd2-ef48-5369-8897-e27b45acb834 | note | Frequency - 1 Per Line
f35c8c92-2a0a-5072-9fde-de6d1b2d5141 | note | Verification Activity - H
856a6127-b419-5d5b-b6e4-2b248fae3ec8 | note | Verification Activity - By: - PE
| checkpoint | 3.1.15 - Manhole Vacuum Test
00738fef-8cb6-51f0-87dd-c30b5c6b57c3 | note | Acceptance / Conformance Criteria - Manhole Leakage Test hold time as per Table 5-12
e87bf1ec-326e-58da-82df-2ee38be298c7 | note | Standard / Specification - Draw Vacuum of -254mm Hg
3fcacb97-bdb6-5b03-be3c-d256bf3bce66 | note | Verifying Document - Vacuum Test Report
b50aef71-5614-53b4-bc87-a8e119ba010b | note | Frequency - 1 Per Manhole
606da953-b867-5a2f-87be-2d07646604e2 | note | Verification Activity - H
1aa57890-8a66-5cb1-b2f5-79a96fc4593f | note | Verification Activity - By: - PE
| section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement
| checkpoint | 3.2.1 - CCTV Inspection
49f7fb21-4d94-5678-95fe-f78b9df17770 | note | Acceptance / Conformance Criteria - Quality Check on New Works
915e5944-4095-5105-869c-b21edf93b491 | note | Standard / Specification - Project Specification 4.4 NZ Pipe Inspection Manual
9f223a2a-a09e-5164-a383-f07deaf708cc | note | Verifying Document - CCTV Report
bfc6f1be-dacf-5632-8129-6326a89ba06b | note | Frequency - 1 per line
5811b338-c224-5676-8dfd-eb01666d8fb5 | note | Verification Activity - S
d67a37a1-99ff-58c0-a5d0-99876a68a702 | note | Verification Activity - By: - PE
| checkpoint | 3.2.2 - Reinstatement
d84a7d3f-8416-5520-9539-6112b4667f48 | note | Acceptance / Conformance Criteria - Quality Check on New Works/All the MH Lids and Cesspit Levels should align with the pavement specification in terms of level & alignment
e1ade64f-2cba-5b1a-b0bc-5b8923388c1a | note | Standard / Specification - Reinstate and Tie into existing surrounds
7a7a35f1-5faa-523e-b6ef-c17b9712f2e8 | note | Verifying Document - Photographs & Level Checks
2a9de3dd-83d1-5702-bc8a-b157cdfdfc7b | note | Frequency - Continuous
5e940cb0-86cd-5929-bcdd-a32bb4e182a2 | note | Verification Activity - S
861e3c21-a38e-5d21-88fb-f33e9ed47378 | note | Verification Activity - By: - PE
| section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 4.1 - Survey Redline Drawings
591e64be-7b5b-5756-ba5c-5c480cb802b9 | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
88b6021a-3110-5045-8d91-2e60fb1249e0 | note | Standard / Specification - Project Specification
7237c198-5606-5126-876a-6ef80ae0fee9 | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen Asbuilt Including Undercut Sections
33e15c37-82ba-5b45-b3a6-055493fdfcdb | note | Frequency - Post works completion
394dac1e-4d42-5da3-b3eb-6cd692c55060 | note | Verification Activity - H
71d6ef71-a603-5a9e-92cb-01a6dfd75c70 | note | Verification Activity - By: - SV
| checklist | ITP - Watermain PVC |  | ITP - Watermain PVC | 32e6b2e5-b60f-4e12-88ad-ddd4a32c832c
| section | 1. Pre-construction (P&G / Establishment)
| checkpoint | 1.1 - Extent of Line Setout
2188c8af-1b0e-5f69-b95b-5375efd86476 | note | Acceptance / Conformance Criteria - Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Watermain drawings Identify any clashes before construction.
52de05b7-2523-5da6-8f80-d5d818ab628f | note | Standard / Specification - Design Drawings
e61c2fd1-b475-5e0b-9891-8eb078397d5c | note | Verifying Document - ITP Sign Off
4c435d60-892e-549b-ad93-35365a7448d1 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
1b47d63b-488e-5cb4-9561-a648677e6e11 | note | Activity - M
74725284-9d13-53b3-adb8-e716dfb7ab4f | note | By - PE
| checkpoint | 1.2 - Environmental Protection
2daa111b-fb92-56cb-95f0-a0893bb7d5a7 | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
90e89d68-cdce-5951-807d-af0f8df8df9d | note | Standard / Specification - Project ESCP Plans
0c7e2196-45e7-501f-b491-48fbc3679d4b | note | Verifying Document - ITP Sign Off
183c9709-e340-589b-8e50-25dde0b61fe6 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
58063758-ff8f-5ae4-8b2f-6df8e28b5bd3 | note | Activity - M
cb9fe534-57a2-5c13-bc53-f991d52f3827 | note | By - PE
| checkpoint | 1.3 - Stakeholder
9989e892-ba99-5f46-94d1-2ad757eaa13b | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
7d849347-4c2f-51c4-9572-a3141cde43c8 | note | Standard / Specification - Project Stakeholder Management Plan
92486058-ca48-5a73-8b08-5850dfbedada | note | Verifying Document - ITP Sign Off
e0d10c68-8f54-592b-ae3e-ce2b6314547a | note | Frequency - Prior to Construction with continue updates throughout the works
86e0b0bb-7529-57e6-9e4e-984c639ef986 | note | Activity - M
f0b731bf-77b1-5b67-9e5f-a719015147f2 | note | By - PE
| checkpoint | 1.4 - Permits
6dc1956a-3aec-55c3-ba28-fa3b08efcdc1 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
37f81dcf-5bd4-55f4-acf6-85e9f7454b47 | note | Standard / Specification - Section 2.2.10 Project Specification
858dc8ce-814c-557c-8854-687c8c26c1a9 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
484256f6-9cf4-5e56-bc22-cd9ce8cca84f | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
8f71f728-3673-5fbe-9e40-0033bce41387 | note | Activity - H
c9df6b3c-5476-5a0f-a223-54b76ae6401d | note | By - PE
| section | 2. Material, Personnel & third party approval
| checkpoint | 2.1 - Pipes & Fittings
cb6bd198-cb74-5f66-a3a6-58ecf46e544e | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/fittings are correct and in good condition and compliant.
25841545-1c58-586f-9e80-ecf24d1107b7 | note | Verifying Document - Delivery Dockets
0b67eb3e-77fd-5648-bc0e-f15359c84a7b | note | Frequency - Each Delivery to Site
436ec73b-2a28-5f66-a0d0-4cacba4928ce | note | Activity - S
e86680e5-61d2-5449-9f68-97554420befe | note | By - PE
| checkpoint | 2.2 - Bedding/Overlay
ac3ee39b-6f57-5478-a442-c7b907d45e1b | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material
5d3234bd-54fe-55b6-b03b-87c35187af3b | note | Verifying Document - IANZ Lab Test Reports
61ba510d-a74b-5af1-ad03-82e66121b21c | note | Frequency - 1 Test per 1000m3
f97c4424-e8b9-5ca9-a68e-bbbec2432e03 | note | Activity - H
8057e399-7390-53b4-a075-ad6c78bb59fb | note | By - PE
| checkpoint | 2.3 - Backfill Material Compliance
0fd748e4-0fb9-504a-adf6-f623c6b4d7af | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material Use selected native soils in berm
8fa15a36-e044-5740-a8a2-9311781670ef | note | Verifying Document - IANZ Lab Test Reports
77be99f0-dc14-540f-91ce-14cf9920a5d0 | note | Frequency - 1 Test per 1000m3
c80191a8-c3bd-5a2a-bc63-9e54b7a980cc | note | Activity - H
a8b7c56f-354d-5900-86a1-235d2be3eda1 | note | By - PE
| checkpoint | 2.4 - Undercut Backfill Material
3cb47e54-1418-5622-ab41-d615c9382364 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
675eb2f7-2d4e-5dd8-9a6a-44367de039b6 | note | Verifying Document - IANZ Lab Test Reports
5c0e5624-6b46-5f4e-8374-970dee1428ec | note | Frequency - 1 Test per 1000m3
6cfa0a74-20c1-5572-80f3-2efc11be00d6 | note | Activity - HP
c075b68e-f3e8-556b-a880-b2e139659d80 | note | By - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Geotextile/Geogrid
92069664-6ed8-5673-8056-9568d2bfba26 | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
c0adf8e0-1d1f-5027-ac8a-bae157691020 | note | Standard / Specification - Project Specification
1217c2d7-7332-559c-b7f7-4a23ae4e0757 | note | Verifying Document - Certification Photos of Delivery Dockets
8ae1e8ac-9cc7-5151-a8b3-88d75e34bda1 | note | Frequency - Material Used
08f4eefd-17ae-566f-9c7a-c4931b9dc2b4 | note | Activity - C
305ec3b4-fd80-5ba6-9290-213684fa245d | note | By - PE
| checkpoint | 2.6 - Warning Tape
f1e47766-a3f3-5215-a1ce-135f9e9dbb47 | note | Acceptance / Conformance Criteria - Obtain Warning Tape from supplier
b71ee51d-495e-5b89-b505-abbfb185ea0b | note | Verifying Document - Delivery Dockets
90b99526-3ed0-5be3-9aea-1e794c893eae | note | Frequency - Each Delivery to Site
c663b7c0-cb53-5627-ad7d-f5d83742f76e | note | Activity - S
1121b458-64ce-5dca-b110-8108945ceb30 | note | By - PE
| section | 3. Construction Activity
| checkpoint | 3.1 - Trench Excavation
f12678f6-c0fd-5ed9-9d41-7545f383290c | note | Acceptance / Conformance Criteria - Excavate trench to design height, placing spoil in approved area and benching as required Visual Inspection to any hard stones or rocks to be removed Any archaeological finds to be reported Inspections to any formation of soft spots
b510b474-29a2-5d0c-81a5-9a5212a8460f | note | Standard / Specification - Project Specification 4.3
4b59d9da-33f7-53d4-8f30-f408e131b057 | note | Verifying Document - Scala test result
cda8a064-9dfd-5a8c-8458-f1134750ce46 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
78a2c85b-1eaa-5acb-bf9f-a76a82062ae1 | note | Activity - H
46695756-bbb6-58f9-8696-bed72f90f8fd | note | By - QE
| checkpoint | 3.2 - Foundation Compliance
276d0ce0-dfa4-5bd5-a550-9580a3b5dd3e | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
cf10a023-8a94-5086-b4a7-7c0d119805d7 | note | Standard / Specification - Project Specification 4.3
f2dc0382-c218-52d7-8977-e280dd16c5b1 | note | Verifying Document - Scala test result
d4810fc8-9e04-5194-9ec3-fc30e1853e85 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
06a8366a-dfc5-5baa-9e15-0b508bbbed80 | note | Activity - H
26295be7-846f-5ad0-9afa-1dd19a084b78 | note | By - QE
| checkpoint | 3.3 - Undercut Backfill Compliance
34324fc7-d773-54db-8aeb-fc5b1c2f454a | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
a38999ed-4542-576e-9f74-959326a18952 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
baf96eeb-3529-5ca7-b763-cf0dfe756ffc | note | Verifying Document - IANZ Lab Test Report
1a703f4d-039c-5d00-ac58-61d47565037c | note | Frequency - Based on Undercut Section
02dcf23e-0ddf-5af9-9f2f-489a85c3bd0f | note | Activity - H
96a5d9f8-dd74-57ae-b8fd-a669eca0bac1 | note | By - QE
| checkpoint | 3.4 - Bedding Compaction Testing
08a3cf70-2b4a-517e-9869-336e34e1f911 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
cbf448d3-5bf3-5c35-be34-24363e0e426b | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
c18f590f-57f1-5d88-b849-183772593ece | note | Verifying Document - IANZ Lab Test Report
05c60a7a-bba7-500d-bb44-44a474905a1f | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
d3c46b89-d758-5e27-b802-1ad98e98ab2b | note | Activity - H
1798524e-a004-51ef-af4b-104ac3f8c2da | note | By - QE
| checkpoint | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
bfbf2e9a-fbc9-5fd0-973b-8095fcfb763b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
969fa821-e653-5c9f-8897-7ec7ae2f0083 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
028a07b5-3f8a-52e8-8de4-6fba06ab734f | note | Verifying Document - IANZ Lab Test Report
437a0105-39f6-512b-b69b-44bd64fab130 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
9260299f-8ef5-52bc-bd37-83f49bdb4e74 | note | Activity - H
a5e58f80-6f41-59e1-af0d-001fe6c370e9 | note | By - QE
| checkpoint | 3.6 - Backfill Inspection
990919b2-90bb-5bf4-bc57-bdc954877ec6 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
106a340e-9051-54e1-89a9-15bf607d4d77 | note | Standard / Specification - Project Specification 4.3
7ed35f7c-4b27-5ebd-8390-370abfc9f814 | note | Verifying Document - Photographs
6b2fe735-3696-533d-bab8-16980d8f1304 | note | Frequency - Continuous
2e70d804-bb9d-5d4f-9903-b55ab30e5653 | note | Activity - S
da1687ab-91ab-58e9-91b6-1b6e97041a12 | note | By - PE
| checkpoint | 3.7 - Install Warning Tape
89ad8ee1-db8e-53c5-b079-f92974f40951 | note | Acceptance / Conformance Criteria - For open trenching, detector tape shall be placed approximately 200mm below final ground level and metallic ‘detector’ tape coloured blue, stipulating ‘Danger – Water Main Below’ (or similar) shall be laid.
d0d4470d-e0c0-5649-9097-5dea6fc91f18 | note | Standard / Specification - RITS
21b7fcef-c235-5990-a6fd-f5e7757bfb27 | note | Verifying Document - Photographs
30ab73b0-3683-507d-ac37-9477ae9dc08e | note | Frequency - Continuous
1927f6e7-bf71-5f57-b600-bc4d095c4728 | note | Activity - S
ec5e7354-bd30-5124-93d6-dd96acb2018c | note | By - PE
| checkpoint | 3.8 - Survey
a5d031ac-99e2-5ea8-bc94-c509b478106f | note | Acceptance / Conformance Criteria - All Water Mains shall be laid in a straight line or following street layout. The deviation from approved design alignment permitted either in plan or elevation shall be: Open Cut – ± 50mm on straight and 100mm in curves All pipes, fitting and thrust blocks to be as built prior to backfilling
681466f1-4732-5e3b-b0ea-286d982015e0 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
2c0c5481-84e6-5bff-8007-7a844c38bedf | note | Verifying Document - Survey Data
66759fe9-2a36-5335-a22c-25c4b5dd3229 | note | Frequency - Continuous
9ba33e89-78d1-5cef-9805-8f994815413b | note | Activity - C
69778e5c-9b81-5ce5-8d17-dd4ed98cc005 | note | By - SV
| checkpoint | 3.9 - Backfill Compaction Testing
c788c146-bfb9-5a96-b95c-3518e3b3e9f7 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
931f3c70-962d-5967-b81f-1b19a97e7bf3 | note | Standard / Specification - RITS
c9458d99-170d-53ae-8103-b196f1f0fa35 | note | Verifying Document - IANZ Lab Test Report
e9547088-f957-51a1-8c0e-ee8a1f0b6997 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
298dad17-495a-52c9-be43-f3bbe3b937ed | note | Activity - H
c9717a72-4c7f-5c9d-a696-26defe658e28 | note | By - QE
| checkpoint | 3.1 - Pressure Testing
5d69a420-1957-5b1c-9290-3c51d88e388b | note | Acceptance / Conformance Criteria - At least one working day advance notice shall be given to council for pressure testing of pipelines. All pipelines shall be pressure tested and backfilled after anchor blocks, specials and fittings are completed, but with joints and connections visible. The final tests are to be witnessed by Council prior to the pipe being connected to the ‘live’ network. No further connections will be permitted after this stage. Refer to NZS 4404 Appendix C3 for the requirements or if this not available, the pipe manufacturer’s procedure.
5b2454ea-1cc6-594d-a88e-513232a2193d | note | Standard / Specification - 6.3.10 RITS
6e90bbf9-09d4-54e5-b7e6-9a44629abfc2 | note | Verifying Document - Visual Inspection & Report
f2c3c247-ebb0-5874-a6dc-294338df015c | note | Frequency - Completion of Works
5bde098e-eb81-5021-b0e8-32eedf795680 | note | Activity - S
6b55841c-7a86-5f6e-a16d-f8ba94e5ce4c | note | By - PE
| checkpoint | 3.11 - Disinfection & Flushing
a04ef4c3-e232-5cb6-bf4a-b48be7c1cbb3 | note | Acceptance / Conformance Criteria - Appendix D of NZS 4404 – Water Supply Disinfection Specification shall apply Discharge of Testing or Chlorinated Water from pipelines may require a resource consent from the regional council
72e62171-3897-5595-bacf-de1ed94ce84e | note | Standard / Specification - 6.3.11 RITS
1a077abb-5e7e-54ee-b677-bc5d79b10d96 | note | Verifying Document - Visual Inspection & Report
012e07a0-eb0d-5930-b43a-b7ed3ebb79d4 | note | Frequency - Completion of Works
480678f5-c94c-5bce-9be6-d7378074e353 | note | Activity - S
80577bfd-b617-5499-b284-b5dae1307d01 | note | By - PE
| checkpoint | 3.12 - Bacteriological Test
ecf71ef6-9afe-54ef-b387-99bad42254b0 | note | Acceptance / Conformance Criteria - In commissioning new pipelines, Council shall be given 24 hours’ notice as to when sampling for bacteriological tests is to be carried out. Water in the pipeline shall be sampled between 12 hours and 48 hours after postchlorination flushing and the samples tested for the presence of E.coli, Coliforms and Heterotrophic Plate Count by a Ministry of Health Approved laboratory with IANZ accreditation for this type of test. The number of samples shall be at least one for projects involving less than 100m of pipe, two for projects up to 200m length, etc. “A satisfactory result is s <1 MPN/100ml for E.coli and Total Coliforms and less than 20 CFU/ml for Heterotrophic Plate Counts.” If E.coli is detected the pipeline shall be swabbed, flushed, disinfected, flushed again and then the bacteriological tests repeated. The process shall be repeated until such time a clear test is recorded. Note: There are high risks of test failure due to sample contamination so it is recommended that the testing laboratory is also involved in collecting the sample.
8458ae3b-7797-5a0a-814d-f2e6b72268ae | note | Standard / Specification - 6.3.11.2 RITS
e3bb0c54-bcd9-5b91-92e8-cb2da86ad9a5 | note | Verifying Document - Visual Inspection & Report
1c926b7a-e073-5363-94e9-287f94a4c5f7 | note | Frequency - Completion of Works
1cb5f6b7-91a6-5b74-b072-c914ba3092a9 | note | Activity - S
6a48d096-0034-56d8-868a-c78b608d8349 | note | By - PE
| checkpoint | 3.13 - Reinstatement
8ec17bcc-d926-596a-8ec1-55e292b11670 | note | Acceptance / Conformance Criteria - Quality Check on New Works
12c240a7-5851-5a10-a894-dfc1f21a71de | note | Standard / Specification - Reinstate and Tie into existing surrounds
26665455-42e7-5cf8-af92-81a44a978efc | note | Verifying Document - Photographs
cf7cef0f-8302-5fa6-8771-1d4718d773d3 | note | Frequency - Continuous
6b0fbabb-ce6a-568c-be52-0fa22a06b6a6 | note | Activity - S
606b0568-359a-5ac7-a423-5451cf87de4f | note | By - PE
| section | 4. Post-construction (Final Inspection & Handover)
| checkpoint | 4.01.01 - Survey Redline Drawings
970a77da-11d9-53d6-a1c1-82d62e20424c | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
989fa426-033b-5cca-bab8-65ba09ef6e49 | note | Standard / Specification - Project Specification
f78817de-6c2e-573e-ac02-c1c19369129d | note | Verifying Document - Survey Data As Built Drawings Photographs
8c5281e5-f67d-50b7-b542-966288db2b75 | note | Frequency - Post Works Completion
45c3f513-76b5-5f0e-a367-64bc9aaa06ad | note | Activity - H
5dc829e6-c403-5afa-9d2f-41b4948b6ec6 | note | By - SV
| checklist | ITP - Watermain-PE - Rev C |  | ITP - Watermain-PE - Rev C | 8acd6cf4-a7a3-4ade-a9e1-fd08547dc0a2
| section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
| checkpoint | 1.1 - Extent of Line Setout
0a95db99-801f-5b64-b0e4-276d1fa2e264 | note | Acceptance / Conformance Criteria - Ensure line and level of Watermain has been marked out and agreed with Engineer in accordance with Watermain drawings Identify any clashes before construction.
abc94a23-054b-5d39-b35c-be522fbf1f99 | note | Standard / Specification - Design Drawings
1e4a6c2b-0712-54b5-a084-37293bc07f79 | note | Verifying Document - ITP Sign Off
04d90d08-9c86-529d-bdc7-d7f606d767e0 | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
4e07d6b6-c8ca-5939-a4a0-b2fdc77acff1 | note | Verification Activity - M
6512d3fd-65b8-5c93-81fc-3e7f4b28fcc3 | note | Verification Activity - By: - PE
| checkpoint | 1.2 - Environmental Protection
65087ed9-b989-5020-8054-6ed613639f0d | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
82587d2b-c8ca-5163-a5e7-9c3bfa2d2f18 | note | Standard / Specification - Project ESCP Plans
d5236638-585e-5e7f-9e7a-d7121a304080 | note | Verifying Document - ITP Sign Off
0fc5d5f1-98f8-5eed-b176-57002e3258b9 | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
8366b632-0a70-5798-a741-526e150ce3e0 | note | Verification Activity - M
3f118ed7-6930-568c-a87a-51e8ce7b2afa | note | Verification Activity - By: - PE
| checkpoint | 1.3 - Stakeholder
a909862c-53af-5e97-a577-a7e558fc1387 | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
8b30c912-5308-515f-9011-deff2e5af2d0 | note | Standard / Specification - Project Stakeholder Management Plan
22e61624-58fb-5c44-96e6-7405784989c9 | note | Verifying Document - ITP Sign Off
56b178e3-75aa-52a2-bcd2-286ca395bd16 | note | Frequency - Prior to Construction with continue updates throughout the works
cd042eb1-e4a2-5b7f-acb5-bee68734a58c | note | Verification Activity - M
6760a1e3-a3d9-563b-b0a8-5e043a724492 | note | Verification Activity - By: - PE
| checkpoint | 1.4 - Permits
bd7e3c64-3e2a-5920-be2f-4935d4539398 | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
2fdbe04a-4a53-5122-ad61-f3593e431d12 | note | Standard / Specification - Section 2.2.10 Project Specification
1d39b83d-12b7-5980-af5f-15e7f1351ef1 | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
34edf06c-9560-55bb-ad35-1bd416718184 | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
fd608052-3027-5806-80c0-b9694cfcbeb7 | note | Verification Activity - H
521e991c-018a-531f-b625-69ce492ee8b1 | note | Verification Activity - By: - PE
| section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
| checkpoint | 2.1 - Pipes/Fittings/precast Units
6df1cf8d-1004-5e3d-a742-b98320906274 | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/fittings are correct and in good condition and compliant.
031c0d23-6b74-5de3-9375-5b4fc963eee6 | note | Standard / Specification - Project Specification
149854d4-efea-59df-8950-1b9b3855a0c5 | note | Verifying Document - Delivery Dockets
3a9c473c-e0e8-5ebb-992c-60ade1ec1262 | note | Frequency - Each Delivery to Site
45508343-caa2-5b23-9604-27047d34681d | note | Verification Activity - S
e73d70cb-5a38-5e06-b3c8-827da199cece | note | Verification Activity - By: - PE
| checkpoint | 2.2 - Bedding/Side/Haunch/Overlay
3a420734-f6f5-5210-bd48-c7cf30ddb976 | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material
75f33260-14de-5971-9893-aa995af3205e | note | Standard / Specification - AS/NZS2566
00009c7b-af45-55d2-a046-86613d201e6d | note | Verifying Document - IANZ Lab Test Reports
a99f9c72-9a71-5d7e-a194-447c96233017 | note | Frequency - 1 Test per 1000m3
681c2fad-bfa9-5648-b36c-f6de1429e902 | note | Verification Activity - H
c8944537-7fca-59e6-99ce-a66dad5e2739 | note | Verification Activity - By: - PE
| checkpoint | 2.3 - Backfill Material Compliance
3825299a-25b8-5dca-9c50-d60dda320558 | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material Use selected native soils in berm
f19d87bf-d6e5-5fa9-a4f6-2af14e24867e | note | Standard / Specification - AS/NZS2566
b6a0cd45-5a4a-5990-b006-f25f752d2a22 | note | Verifying Document - IANZ Lab Test Reports
8c338912-06e8-5281-97d2-89075e2694d6 | note | Frequency - 1 Test per 1000m3
5330899a-c227-532d-836c-d2203b881d90 | note | Verification Activity - H
f9a7db0a-0db0-52bb-9e7d-8028f23c799e | note | Verification Activity - By: - PE
| checkpoint | 2.4 - Undercut Backfill Material
5d62f13b-d2e3-5bbe-8ebb-6190edba7f68 | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
67edce20-2cbe-58dd-9fbc-e4a3dc0042fe | note | Standard / Specification - Engineer to Specify
9877596e-c4ed-50c6-a42c-cea5098163f0 | note | Verifying Document - IANZ Lab Test Reports
325f4fc4-0dcf-51e4-b273-c3021feac7ad | note | Frequency - 1 Test per 1000m3
43683a3d-d98b-5349-b20c-8bdb7293c3f8 | note | Verification Activity - HP
49593a74-948e-5827-b1fb-ad1dbd727d6a | note | Verification Activity - By: - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Geotextile/Geogrid
f631587e-0e63-5d52-ae7b-6ffab6e6b11d | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
2fa75ace-6055-55c3-a40c-3d5ec1a96d1e | note | Standard / Specification - Project Specification
32ac1128-ed5e-5ed9-9488-502f284d6511 | note | Verifying Document - Certification Photos of Delivery Dockets
2d807760-f4c3-59a1-a843-389e3e17cb23 | note | Frequency - Material Used
d41ab3eb-8b17-5d1d-b5f2-8814b53290d0 | note | Verification Activity - C
b2953535-89b8-5b39-bdfe-ffa0646ea0d4 | note | Verification Activity - By: - PE
| checkpoint | 2.6 - Warning Tape
da40fc40-9a2f-5faa-b5fb-0c2ca4185b52 | note | Acceptance / Conformance Criteria - Obtain Warning Tape from supplier
1d59ac43-680f-55b0-86a5-141a8a35ca49 | note | Standard / Specification - Project Specification
6d3e8edf-e66b-5f5f-ab2a-78a7e021b887 | note | Verifying Document - Delivery Dockets
1316695c-b14e-56f8-977f-b319f1fc1d28 | note | Frequency - Each Delivery to Site
692ce30d-cceb-518e-8220-c671d05aada5 | note | Verification Activity - S
afd1ceba-7788-5d54-9c23-413cd9057004 | note | Verification Activity - By: - PE
| section | SECTION 3 – CONSTRUCTION ACTIVITY
| checkpoint | 3.1 - Trench Excavation
07477a63-9617-55fe-adb6-e93d735206cf | note | Acceptance / Conformance Criteria - Excavate trench to design height, placing spoil in approved area and benching as required Visual Inspection to any hard stones or rocks to be removed Any archaeological finds to be reported Inspections to any formation of soft spots
f06a3223-84cd-5d5a-9609-ec670899afad | note | Standard / Specification - Project Specification 4.3
5a7fbfbe-688e-5eeb-b7ad-2fc27a97a8fd | note | Verifying Document - Scala test result
e34b1620-5292-5b32-81ad-7a8792e3f85c | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
b0059aa8-b108-581e-b180-24bb3e22c386 | note | Verification Activity - H
fd57b629-7db9-5b42-9417-98d7db9f76de | note | Verification Activity - By: - QE
| checkpoint | 3.2 - Foundation Compliance
a9462c7a-cf46-5d7b-82df-bea3402e54c1 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
6f1a316b-9b79-5dcd-999c-40cdb0a8b150 | note | Standard / Specification - Project Specification 4.3
b1d4f6de-755d-5514-a8cb-7f021fc05aa7 | note | Verifying Document - Scala test result
c28a2bf1-3c70-5baa-b8ce-f3dd98ceaa12 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
c6f79caa-eb63-5d79-b8ac-95e2d42eddc3 | note | Verification Activity - H
4028434b-9d26-5617-9fdd-438d79ac0013 | note | Verification Activity - By: - QE
| checkpoint | 3.3 - Undercut Backfill Compliance
7289baf5-ae7e-54ed-846a-4a2383392ef2 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
36e66f02-4614-53f2-a456-2561cb8cc4ab | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 95% of MDD AS/NZs 3725:2007
44b1bd3c-6feb-5286-881e-7f19a7d026a6 | note | Verifying Document - IANZ Lab Test Report
9f9226ea-523e-5a2b-bc38-72889a5f5bba | note | Frequency - Based on Undercut Section
035f96b5-9059-5337-a1d4-fb0b83a58c03 | note | Verification Activity - H
a2f6e221-4bf9-5a06-ba86-7797617bc26e | note | Verification Activity - By: - QE
| checkpoint | 3.4 - Bedding Compaction Testing
1df4c996-99ab-53f7-942f-6ca7ac2aff57 | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
c28e6dab-f53d-508b-be11-e11c00e05aa9 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
f3d231c1-3db3-5089-8245-ea9d51c272f4 | note | Verifying Document - IANZ Lab Test Report
73ee2aa1-dd52-5ff3-bf59-3d7fa4631d99 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
5db05c3a-ef53-5db7-bc65-5a25040b4841 | note | Verification Activity - H
e0ef5f15-9aea-5074-a24e-658ad51bd8b1 | note | Verification Activity - By: - QE
| checkpoint | 3.5 - Haunch & Side Zone Compaction Testing
5a8cedb3-7758-52f9-ae98-349a03eb9a84 | note | Acceptance / Conformance Criteria - Side zone shall extend from top of haunch zone to 0.5 times the pipe outside diameter 100mm if >75 , <150 150mm if >150 , <300 200mm if >300 , <450 NDM DT Minimum Compaction 92% of MDD
22c67c7a-4f0f-5f27-b916-79dc9fcd70bf | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
e044652c-b18c-5d5c-97ac-f94df5e912de | note | Verifying Document - IANZ Lab Test Report
9fc2191d-c30b-56cd-b959-798fdeb8ab74 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
a7e6fd8b-8b1c-5028-b00d-f5ab364e28b8 | note | Verification Activity - H
55e5af02-e543-5e18-8b81-0f6967bb0813 | note | Verification Activity - By: - QE
| checkpoint | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
73c47ed0-cbf2-5993-934d-120bdd476cee | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
15511fb1-9695-53bd-88f4-1bb6eb4a68eb | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
71d57a91-6ae9-52a3-842f-a526707ddbee | note | Verifying Document - IANZ Lab Test Report
8d60ce92-fb60-5a80-b904-b95a5faaee5b | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
ef0d9e80-b8db-56c6-8afb-6cc3e21ec69d | note | Verification Activity - H
c0779ffe-29b9-5921-b18c-a5822fe94a17 | note | Verification Activity - By: - QE
| checkpoint | 3.7 - Collection of Waipa ITPs
db16c050-4db8-553b-b5ac-c707c111faf3 | note | Acceptance / Conformance Criteria - ITP 02 Manhole and Valves ITP 04 Butt Welding ITP 05 Commissioning
a542d803-defa-5fd1-b771-2d607713ed81 | note | Standard / Specification - PWRBSS Quality Management Plan
407354aa-ee45-5aef-81cc-93cd41c63f9a | note | Verifying Document - Document Review
26782718-d70a-5d80-bd2b-82c07cf499d1 | note | Frequency - Once
0ae112fd-56f4-526f-9070-382d1a63f2a0 | note | Verification Activity - HP
8d2e5d47-b8ba-5d26-a3a6-82ce5b197b84 | note | Verification Activity - By: - ENG
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Backfill Inspection
dc6de0af-115b-5843-b061-6be7817ecf46 | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
675da3b2-fd26-56a3-a501-da6826f06731 | note | Standard / Specification - Project Specification 4.3
6965b7d0-334b-59e2-aa93-25fa3229f737 | note | Verifying Document - Photographs
e95ccae1-d1a3-52a4-9d3b-e564218e2637 | note | Frequency - Continuous
f015779c-9373-5743-a646-802c363d4478 | note | Verification Activity - S
8cf4bc20-61bc-5eeb-a074-a44f5fdd7d96 | note | Verification Activity - By: - PE
| checkpoint | 3.9 - Install Warning Tape
275cc7b9-aa03-59b1-a9ef-15d48a4251a0 | note | Acceptance / Conformance Criteria - For open trenching, detector tape shall be placed approximately 200mm below final ground level and metallic ‘detector’ tape coloured blue, stipulating ‘Danger – Water Main Below’ (or similar) shall be laid.
89fe7a2a-2b50-544d-bdad-97e00f5130ea | note | Standard / Specification - RITS
f6fa2374-a03a-5ce2-bf54-c4c85325f636 | note | Verifying Document - Photographs
afddf2df-94e0-505b-8909-48f846096047 | note | Frequency - Continuous
84edf32f-7f89-51cf-ae66-6b1336689710 | note | Verification Activity - S
f36fa6dc-2bba-5148-8f6f-6e84f2679186 | note | Verification Activity - By: - PE
| checkpoint | 3.1 - Survey
a294f9b0-4c02-5c4d-a1a3-5fc5966b04b4 | note | Acceptance / Conformance Criteria - All Water Mains shall be laid in a straight line or following street layout. The deviation from approved design alignment permitted either in plan or elevation shall be: Open Cut – ± 50mm on straight and 100mm in curves All pipes, fitting and thrust blocks to be as built prior to backfilling
bd943e00-f1ef-5548-9855-abc4a6da9574 | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
e578e240-102e-52d9-8bf4-4b212aa765eb | note | Verifying Document - Survey Data
7162641a-4e07-5fd2-b4a5-1f9598843f3a | note | Frequency - Continuous
715dba86-0507-520f-9d7c-b7ff9bba058f | note | Verification Activity - C
03bed1e0-d9a5-5761-9444-e30df7766f80 | note | Verification Activity - By: - SV
| checkpoint | 3.11 - Backfill Compaction Testing
dcb0cf94-74d4-51d1-8687-dfbb3bd0606b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC Average of 98%
3655ad07-7eb9-5add-99a7-f46a315bd015 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
d6ae28a0-eb28-58ef-82ea-58ef1e0541c9 | note | Verifying Document - IANZ Lab Test Report
860a494c-b3af-53b1-be11-fdc81ccaed51 | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
85d03948-9207-55e4-9ec0-aeae0b9cf4a2 | note | Verification Activity - H
d5659d13-9af2-564d-b799-0641cdf4eb19 | note | Verification Activity - By: - QE
| checkpoint | 3.12 - Manhole Foundation Compliance
d2bb9c59-ced0-5fcb-b60d-aba2e6b81c43 | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
eca8b52f-be49-5686-a1ac-7e03b5cddfd5 | note | Standard / Specification - Section 4.3 PWRBSS Project Specification
cce2838a-eb0a-530a-8a34-51b66141f36c | note | Verifying Document - IANZ Lab Test Report
f0e0bf59-c689-530f-b43b-3271b1b807bd | note | Frequency - 1Test/MH
370ed67e-4d14-5680-bfb7-0014a22de54a | note | Verification Activity - H
5c327065-fbe3-5f72-88e3-56f05f100f09 | note | Verification Activity - By: - QE
| checkpoint | 3.13 - Undercut Backfill Compliance
69d66008-6fab-587a-9ca1-edb57a344028 | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
8989cce0-1ab5-5a3e-8bf4-8902b0256e3c | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 95% of MDD AS/NZs 3725:2007
a7b502ab-05b3-5930-8848-e1bd823626b4 | note | Verifying Document - IANZ Lab Test Report
8f433644-ef93-594d-857d-0df99d6be813 | note | Frequency - Based on Undercut Section
79b84a28-db63-5020-addd-eefa8c943bb8 | note | Verification Activity - H
975e420a-7912-5a09-be21-4e80218f9f86 | note | Verification Activity - By: - QE
| checkpoint | 3.14 - Bedding Compaction Testing
38cf7141-ec8c-5604-942d-b6b72faaabbf | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
a847bebf-1df1-581f-8304-5c4b45e6cdd7 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
1c453333-f6dd-539b-80cc-ae7863c624b9 | note | Verifying Document - IANZ Lab Test Report
1badf2d5-f6bc-57c3-aa6a-c5a45440569a | note | Frequency - 1Test/MH
627ea6e2-0f21-532f-8fe7-6770a74b9623 | note | Verification Activity - H
0d85463d-dab3-51b7-bb97-9b404dff4af2 | note | Verification Activity - By: - QE
| checkpoint | 3.15 - Backfill Inspection
d92fe8a3-ca3a-5430-bfc7-b1328efc2f77 | note | Acceptance / Conformance Criteria - Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. Check for any gaps.
0fcf5aa2-04c1-5473-8ae9-cad3834c3bb4 | note | Standard / Specification - Project Specification 4.3
71a08e1e-9f9e-5735-b9e7-974aca4bf205 | note | Verifying Document - Photographs
e1875c14-0f50-58c6-b6ef-352bf1783dad | note | Frequency - Continuous
9dcc647f-fddb-5773-90ea-778339343ecf | note | Verification Activity - S
addfe930-6991-57da-95c7-300e647696b5 | note | Verification Activity - By: - PE
| checkpoint | 3.16 - Backfill Compaction Testing
0b304461-1592-59ec-8f1c-4adbbf43cc1b | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC Average of 98%
cb84dbae-3878-5efa-8b06-b15858234554 | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
97ac4fea-d9c9-5c8c-baba-96f47f0b7fde | note | Verifying Document - IANZ Lab Test Report
7fc73e23-243b-544c-a192-4cf2db61ca9a | note | Frequency - 4 Density Tests per layer at Quarter Points around structure
01211731-cc47-5c7e-9d96-455d5e38e8d5 | note | Verification Activity - H
f79276d6-10e3-52d0-80a9-20e7c5b178e5 | note | Verification Activity - By: - QE
| checkpoint | 3.17 - Reinstatement
2d63696d-2d33-5c5c-ac3f-78a5a0fb3fbc | note | Acceptance / Conformance Criteria - Quality Check on New Works
a3350074-8599-5295-b334-b07bdf8c4d10 | note | Standard / Specification - Reinstate and Tie into existing surrounds
0b512309-e2c5-51c7-9586-e8a752f5e706 | note | Verifying Document - Photographs
e23e2bb4-89dc-5278-9fad-10048a6d915c | note | Frequency - Continuous
f3a7a097-a0ac-58e8-ae1b-4c6b265514b9 | note | Verification Activity - S
388eeb85-5232-5b2b-a1aa-fa731eb4176e | note | Verification Activity - By: - PE
| section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
| checkpoint | 4.1 - Survey Redline Drawings
fbbf0793-2870-5073-bdad-313d6c053715 | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
49d8634e-c761-5a02-8077-f2be6dbcbed0 | note | Standard / Specification - Project Specification
8f244533-d06f-5885-b00d-17430dbaf917 | note | Verifying Document - Survey Data As Built Drawings Photographs Red Pen As-Builts including Undercuts
a6bf5a44-50bf-558b-b3b2-a54478fc7244 | note | Frequency - Post Works Completion
fb594479-9802-57fc-aeed-4b92904ad9ca | note | Verification Activity - H
72121a75-77cb-536b-88c1-a40ae647a69d | note | Verification Activity - By: - SV
| checklist | Stone Strong Wall Installation Checklist |  | Stone Strong Wall Installation Checklist | c6d03f27-e77e-4918-8777-b48ae7f56392
| checkpoint-no-value | Details
5c56ea41-624d-5f8b-a19d-09dc67614506 | textbox | Project Name:
19e4224b-ed62-5e46-a533-cec42e4dac20 | textbox | Wall Location:
6d6bf996-b548-5dd9-9ee0-d917dd2be190 | textbox | Block Layer:
e07570dd-33f5-585f-8141-e6b9b1e94af6 | textbox | Date:
3453d87e-9319-54a9-acf6-8e0f2f4739a6 | textbox | Inspector:
0692e518-3045-51d8-be5c-39c62e4d3b14 | textbox | RL of current Block/Backfill Layer:
| checkpoint | Level foundation installed as per design. (Base layer only)
| checkpoint | 2 x Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Tramsfer Platform. (Base layer only)
| checkpoint | Blocks Installed within specification tollerances & block pattern as per design drawings
0dd331a6-905b-520f-85e7-1d0e1611df25 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
5e72637e-18b2-53de-82ca-d91284388021 | note | Table 4: MSE Tolerances
807cb619-9421-5d28-ab8c-bf2da6ee9b5c | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
e72d7e9e-6340-547b-aadd-a6cedcd6e744 | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
981f8e13-85e0-5ab8-88d3-a29a943532b7 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
3747f6c4-c6b4-53db-b0a0-918d1038abda | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
02105b15-4ea8-52aa-aa5d-d219414087e5 | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
7fb962c8-aa6b-57e4-980c-845ee2b51feb | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
| checkpoint | The correct number & length of parawebs are to be installed as shown on the construction drawings.
d1b9a8dd-3c74-5dd8-92ee-ba464e7bfa9c | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
cb25453d-184c-5806-8454-04709ba3e357 | note | 24SF1.1 BLOCK PARAWEB SCHEDULE
917cf7ae-3f1c-5095-a6af-1e72e4cc8863 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
8e09984d-6f0d-50f2-abb9-cdcc9fa850cd | note | WALL HEIGHT (H) ¦¦ MINIMUM EMBEDMENT DEPTH (E) ¦¦ GRID LENGTH (L)* ¦¦ CONNECTIONS PER BLOCK
571b4987-9d20-5db7-94d0-56578e113fa8 | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
cc38ae48-88bf-57fa-ba2d-32f679a79148 | note | 8.0-10.0 ¦¦ 0.5 ¦¦ 9.0 ¦¦ 4
a0f36527-892e-5c8d-868f-3b82ab3d24a3 | note | 6.0 - 8.0 ¦¦ 0.5 ¦¦ 7.0 ¦¦ 4
bd88976d-5723-503a-aab2-1dfe67a9ad8c | note | 4.0 - 6.0 ¦¦ 0.5 ¦¦ 5.0 ¦¦ 4
31674d68-f150-5e7a-abb3-b80d5b50c9a3 | note | 2.0 - 4.0 ¦¦ 0.5 ¦¦ 4.0 ¦¦ 4
2ab1aa36-57c5-574a-9159-853a9471fcc3 | note | 0 - 2.0 ¦¦ 0.5 ¦¦ 3.0 ¦¦ 4
| checkpoint | Paraweb is to be placed flat or with a 1% fall toward the rear of the wall.
21d51e76-0781-5346-b566-b7bce9497e97 | note | ○ Paraweb must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
| checkpoint | 150mm of fill cover is required before construction equipment can travel over the area
| checkpoint | Backfill installed in max 250mm lifts
| checkpoint | Proof roll completed on each layer
| checkpoint | NDM testing completed
313e95ff-a74a-5cd3-aca0-96fdfe23b44f | note | ○ Acceptance Criteria: Minimum 95% MDD
18e05c73-4c1f-5444-a747-bda68ed498d4 | note | ○ Frequency: 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
| checkpoint | Clegg testing completed (GAP65 only)
1fa82988-8f1e-568e-9501-5d1fa85b3509 | note | ○ Acceptance Criteria: CIV relationship to be developed by testing alongside NDM tests
6aadb3eb-b399-5f77-82e1-875f5b6abe9a | note | ○ Frequency: 4 tests per NDM
| checkpoint | Scala testing completed (Sand only)
de471c65-92b2-5be9-8242-ab26586fb500 | note | ○ Acceptance Criteria: Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
0d72fa89-8dc8-5a3d-9dd5-e8a34b2db867 | note | ○ Frequency: 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
| checkpoint-no-value | ADDITIONAL NOTES:
81dd5416-d172-51ad-8781-a20c3ac7e029 | textbox