## Master List Templates
Id | Type | Name | Values | Prompting Name
f2fde9e7-9c31-4b6a-b1b5-5c987f27409a | checklist | Contract HoldPoint Checklist |  | Contract HoldPoint Checklist
96a78813-95b0-48fa-9a93-357ec9a1b8cb | checkpoint | Holdpoint Release
e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 | textbox | Enter Name
1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b | textbox | Enter Description
60a1eb35-e850-40c9-a4b9-af7b0196da59 | signoff | Contract Holdpoint Release

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
4955c880-3516-4fa7-bedb-72645765bb4f | checklist | ITP-003 - Stormwater Drainage | itp | ITP-003 - Stormwater Drainage
49b7c6bb-33d9-48a5-956a-7af94567efb3 | section | Preliminary Works
f22ab21f-11e4-4eed-aeba-9ac3f0bd03cb | checkpoint | 1.1 Check for correct documentation
4ed8b356-0e91-568a-add7-f5ada99c6988 | note | FREQUENCY: Prior to commencing any activity
7811b7cf-1ea8-5454-8246-f791425693fd | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
5f3c614d-2a3a-572d-9da5-b88924a683fc | note | – using the correct and complete set of drawings
cef3e785-9c79-5da0-b5b2-d038aa8e50af | note | – all drawings are the latest revision
d8a2e549-eb15-5226-b9a9-fb022ab1ee60 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
24474f8b-68d0-556d-ac47-9eb0ae644799 | note | INSPECTION/TEST METHOD: Document review
1a0d296b-d76f-5046-b98b-f79d812727b1 | note | RECORD OF CONFORMITY: This ITP signed off
3fb21c53-8808-5918-9c60-e51cc740bf75 | note | HP*
b73b60b6-972b-5d82-a32b-c824bde500d9 | note | RESPONSIBILITY: Project Engineer
44e9af11-0dd1-5ee4-b7cb-395e1290c5c2 | textbox | Date Completed:
65291ca2-61e1-40ec-934b-b155cbfcdc75 | checkpoint | 1.2 Implementation of all measures and controls
b91d2cb4-bcb7-5e31-b309-872f0913a5e7 | note | FREQUENCY: Prior to commencing any activity
1665c56c-4b24-56f1-bdec-c9d59a5fd141 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
7405e4b7-0a90-55e9-995e-47a5d7085aeb | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
d6084e08-fb50-59f1-8606-8c09e67b0fe3 | note | INSPECTION/TEST METHOD: Document review
2f07428e-c42d-5ed1-8eae-74222ab247eb | note | RECORD OF CONFORMITY: This ITP signed off
7f69fbe3-4070-578e-957c-51fd0657a1bb | note | HP*
238ce394-4076-5a16-a7b5-c48b385138d5 | note | RESPONSIBILITY: Site Engineer, Site Foreman
1de406f3-4964-54b0-9496-9db1c6fa98e6 | textbox | Date Completed:
c228ce48-5201-457c-83db-77c08cb77128 | checkpoint | 1.3 Precast Materials acceptance
e40786b6-61e5-5c48-bb38-3519ac2b82e3 | note | FREQUENCY: Each Delivery
14e8cff7-a991-56bf-880b-4b4eca381851 | note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
9b7dd538-e847-5050-8aca-f08ac4894efb | note | ○ Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
e2d77a4f-41e1-5eac-9bac-fd693690930b | note | ○ Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058
225ad290-806e-5596-9b9a-2dd058b00023 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
d1443989-e37e-564f-b712-7bd336a916c0 | note | REFERENCE DOCUMENTS: VicRoads Spec.
38e7df9c-587d-5fbc-a76e-5bc6d496d2e3 | note | ○ Cl. 610
d1f54dd9-fa9a-5032-8fc0-0f43d16b2bda | note | ○ Cl.619
5ea4928b-97cb-5296-8ada-c6e78e90826e | note | ○ Cl. 701.04
d196c6e7-23f0-5921-984d-01aef6ea0e40 | note | ○ Cl. 701.05(a) & (e)
09b1b651-3310-5306-8323-50b797612f59 | note | ○ Cl. 705.04
80942aca-61e4-5398-8cb6-31a9bb9f1b20 | note | ○ AS4058
12f3164c-ee7f-55cf-9fd7-c32c948d7ed8 | note | ○ AS4680
a6c5b7f4-82fb-517d-8020-c6a22750da2b | note | ○ AS5100
8de1219b-2f7e-5aae-bd94-3f551956331c | note | ○ City of Melbourne Standard Drawings
a4ae0c9e-8d5f-5fdb-b275-5198c68f03c6 | note | INSPECTION/TEST METHOD: Visual Inspection, Verify
06b4c750-9c3b-5bca-825e-8d82b325ae59 | note | RECORD OF CONFORMITY: This ITP signed, Manufacturer certificate or accreditation
86cb4ca1-ccda-5b8a-bad3-c9b2d3b113dc | note | IP
8ed81959-d497-513e-9f32-83e954c9671b | note | RESPONSIBILITY: Site Engineer
8209e618-5015-5515-b468-5290d735469c | textbox | Date Completed:
0bdbb011-43a1-4f20-b915-398253ce6e3e | checkpoint | 1.6 Bedding material classification
0f48f3cf-d425-5bd8-b17f-436aa1402559 | note | FREQUENCY: Prior to start
62d75304-cb8a-5425-996d-d45929270636 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
b595ece5-d2ac-5ba6-8c0d-5c6399bbd55b | note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
fa44020f-7e88-5200-a2b8-0f6704963a47 | note | INSPECTION/TEST METHOD: Visual Inspection
8caca23d-44dd-5c7e-97b1-6bec4031e1ae | note | RECORD OF CONFORMITY: This ITP signed off
3aece5bf-b55c-5436-b44b-83cffb910130 | note | IP
ddfc90c7-67d6-59be-a7a7-2fbebbf5637b | note | RESPONSIBILITY: Site Engineer
ee9676c6-01bc-5fc1-ae70-430d327de90a | textbox | Date Completed:
a1c57b33-7b64-4bd6-b280-1f93ca5e55a7 | checkpoint | 1.7 Backfill material Classification
4ee4546e-76b2-56c5-a966-c5f0a5c9ba97 | note | FREQUENCY: Prior to start
a4a7f1f0-820f-5b53-be46-1cebc4bdd78b | note | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
687568af-0d9d-576c-83d5-238b546a706a | note | REFERENCE DOCUMENTS: 701.09(d), 701.091
d8670ee4-a0c1-531e-9c05-0ae41f813f54 | note | INSPECTION/TEST METHOD: Visual Inspection
b925cffe-cd23-516e-b091-f2bb6c227970 | note | RECORD OF CONFORMITY: This ITP signed off
8c75870e-14d1-5c91-a5ac-481be6d767b3 | note | IP
48c8f925-ab88-5627-aaea-fa3d9fae515e | note | RESPONSIBILITY: Site Engineer
55dafcd7-6e21-5b75-9c44-44b566eb4020 | textbox | Date Completed:
36337e4e-7b13-49b4-bb0d-04e600b84a18 | checkpoint | 1.8 Mortar material classification
8a652e0a-1df8-50bb-8aca-065b517228e0 | note | FREQUENCY: Prior to start
55feb2b4-837b-5be0-8240-48c7d093d187 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
ed0445f5-4f16-5a27-bff8-3e78eee21fa3 | note | REFERENCE DOCUMENTS: 610.33
bc126712-1f85-5b09-806e-5a5b4d618669 | note | INSPECTION/TEST METHOD: Verify
d3de61de-55bf-5b6d-a7aa-d7642755eda3 | note | RECORD OF CONFORMITY: Test Reports from supplier
97029559-62e1-5845-aa0a-f47deed950d5 | note | HP*
7353e7e7-b8d1-5ab6-bb61-b63eefbdf291 | note | RESPONSIBILITY: Site Engineer
95c40253-733a-5849-beef-b7a76cac05c7 | textbox | Date Completed:
1ca1c267-7cd2-41fa-9f50-3443011b34a9 | section | Construction Works
58fc2697-7b72-43e2-819a-f06ea08dce5a | checkpoint | 2.1 Excavation Permit
c559abda-0504-5fb0-b004-667fec1e6bea | note | FREQUENCY: Weekly, per operator
2046e2b2-25fc-57f7-a961-2e0fb17a78a0 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
0cdd683c-7528-5122-bbd6-e80535b55a18 | note | ○ Plant and equipment shall be appropriate for the task.
a72ac16a-1362-5ebe-8434-673ff3bc137c | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
eb69be60-54e1-56b2-a814-954bd2065ec0 | note | REFERENCE DOCUMENTS: Excavation permit
bda25569-cd4b-5f08-8de3-c8cdc093747c | note | INSPECTION/TEST METHOD: Verify
23a5d540-1fb3-5b6b-8582-403d47069c39 | note | RECORD OF CONFORMITY: ITP Signed
2897ac6e-da11-5840-b17c-d732a80a5f64 | note | HP*
2a819990-43ff-5f0a-938f-0a78d9998f39 | note | RESPONSIBILITY: Site Engineer, Site Foreman
84b545b4-9c9f-5f3a-afe9-f17932f7e5d6 | textbox | Date Completed:
a41851c5-725c-4375-bcc6-30cfec124a57 | checkpoint | 2.2 Set out drainage
765a5dd1-9c24-5c99-bcd9-cc7abe449f7d | note | FREQUENCY: Prior to start
901d810b-8e5f-5189-95d1-9e656104f979 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
903c4723-3404-5b3e-a918-0c843d7922c1 | note | REFERENCE DOCUMENTS: Drawings
08e2efce-c785-5e7c-b087-dec26787abc0 | note | INSPECTION/TEST METHOD: Visual Inspection
1c4a9daf-b596-5b47-9413-fd0f5a7ab732 | note | RECORD OF CONFORMITY: ITP Signed
9b0a724d-43e2-5993-bad1-bb88a328a79e | note | HP
4490ac6c-89ee-57f8-9d37-af80b30292f6 | note | RESPONSIBILITY: Client, Site Engineer
6b79b446-10d7-5730-b1d7-747952f449c1 | textbox | Date Completed:
6b455fee-5de0-4eea-8bcd-12379bdf17ff | signoff | AUTHORITY HOLDPOINT
362f9fc1-ee45-498d-97b9-00c3314e0090 | checkpoint | 2.3 Excavation (pipes)
f63b1a5f-8552-50d7-a356-8e61a9124193 | note | FREQUENCY: Each Trench
d2cf7653-7697-568b-a364-12723c564301 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
d0e6a9f0-47d0-5ed0-bf4e-84c51e755228 | note | Depth of trench:
850d7804-d82e-543d-b866-a4db68215a41 | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
7de377c9-b459-589d-af56-8d17735b3a38 | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
1745f48c-084c-5c92-bc74-8474f3054870 | note | REFERENCE DOCUMENTS: 701.151, 701.15
9d2d07c0-c323-5c0c-ac1c-8a15663ad5cb | note | INSPECTION/TEST METHOD: Visual Inspection
fe0e4229-9227-52e3-af7e-fdbbc6758572 | note | RECORD OF CONFORMITY: ITP Signed
2aea4c94-06e3-56ae-af0d-bd6b98c0b375 | note | IP
3d976ec7-3d39-5108-bffd-2e5bcf29bd72 | note | RESPONSIBILITY: Site Engineer
f0fda3cd-f74d-5f8a-b2a6-5c7d4a74082d | textbox | Date Completed:
7f075558-e62d-4fb1-a335-29cac4a17835 | checkpoint | 2.4 Excavation (pits)
fe09f361-15b0-56b4-a076-6ab0ac5d8f63 | note | FREQUENCY: Each Pit
f25113e7-9a1b-56df-8e99-b90fe536bf5a | note | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
b842ea70-b570-56e5-a557-4ad84f534a51 | note | REFERENCE DOCUMENTS: 705.05b
9f5f6350-d134-5ea0-8c3a-9386fd7dbcfb | note | INSPECTION/TEST METHOD: Visual Inspection
1a3956a3-311b-5f3f-8c5c-8f2295f067e7 | note | RECORD OF CONFORMITY: ITP Signed
9ec9e38c-4958-54f7-aa93-286784057c42 | note | IP
59282186-a655-5a62-a4c1-77f4baca7b98 | note | RESPONSIBILITY: Site Engineer
411eb831-7085-55fc-9434-025dfd06ad6b | textbox | Date Completed:
46712cb1-ca80-434e-b149-ff978e66645f | checkpoint | 2.5 Compact base of trench
a4b3ea9f-b2e6-5637-89f9-18145b5c2cc2 | note | FREQUENCY: Each Trench
74379220-a8bd-5e6a-b9ea-18bb0d5122b4 | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
228c059b-89f4-5163-ba6e-20d4926dfed8 | note | REFERENCE DOCUMENTS: 701.15
3d4b200f-db3b-52be-9acd-db194b768785 | note | INSPECTION/TEST METHOD: Visual Inspection
4ba7d844-2228-544f-a666-879e0536e398 | note | RECORD OF CONFORMITY: ITP Signed
e0996d54-4cf4-55e3-938b-5fe0e3410fcc | note | IP
886eec8d-68e6-58c0-9b54-6e0ae970325d | note | RESPONSIBILITY: Site Engineer
36760000-04c0-5cf4-ad3f-9254851392bc | textbox | Date Completed:
bc73140f-0b9b-4dd1-84cc-160b093e8d6b | checkpoint | 2.6 Place bedding material & compact
d0faa4b1-fb02-5c79-8d01-a55360f1cf62 | note | FREQUENCY: Each Trench
9f5c531f-54d1-5623-bd0c-ed59c77b1a30 | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
c34346fa-4cbd-5a5f-a7ad-471a264bb89c | note | REFERENCE DOCUMENTS: 701.20, 701.20a
9fe476a2-e7e4-5b1f-97ce-2d39acc08622 | note | INSPECTION/TEST METHOD: Visual Inspection
c26adc78-5ef8-55cf-bc8d-7a4612339df3 | note | RECORD OF CONFORMITY: ITP Signed, Photos
8fd79e87-6b34-5f00-a1b1-d05ba6761f53 | note | IP
2ace3192-0509-5d22-82f0-59272a3ee7be | note | RESPONSIBILITY: Site Engineer
96e47302-a372-5136-9dfc-bc3d759c064a | textbox | Date Completed:
0b42140c-9388-4a5b-b61c-74376544876a | checkpoint | 2.7 Place pipes & precast pits
1f64dfac-4a87-5600-af70-27ece6b64e37 | note | FREQUENCY: Each Line/Pit
696847de-4268-5eb4-aad4-21213e9617e5 | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
2595ee97-3da4-56a1-83bb-f2181546ad50 | note | REFERENCE DOCUMENTS: Drawings
fd6a06e3-af17-50e7-9cbe-048757574e65 | note | INSPECTION/TEST METHOD: Visual Inspection
8fccc3f6-659b-56c7-9064-ab06fd1c6020 | note | RECORD OF CONFORMITY: ITP Signed, Photos
25cc181c-8bb0-53a9-ac01-bdfae9ecd2cc | note | IP
3bb0dbce-320b-5447-ba93-6ebd776ab43d | note | RESPONSIBILITY: Site Engineer
31302bc1-0d1d-5f14-9e94-2681eebebde6 | textbox | Date Completed:
f24f2092-e9fe-4e0c-9d70-60aed0194883 | checkpoint | 2.9 Jointing pipe sections
d91cfef0-f051-5ed9-859c-5771ae1874eb | note | FREQUENCY: Each Line
04041cfd-7056-55a3-a8a5-a68df5f3201f | note | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
3a15bd4e-4cfc-5834-8b3b-e415d4f4eaa4 | note | REFERENCE DOCUMENTS: 701.18
ca4b40fe-4fc6-5cc6-b599-447b5ea66b14 | note | INSPECTION/TEST METHOD: Visual Inspection
1dd95c3a-39fa-50c6-9cfc-d8815bf65da3 | note | RECORD OF CONFORMITY: ITP Signed, Photos
317df86c-191e-5d3d-bcad-4160505e9d60 | note | IP
222181cf-de22-54f5-8e1d-f13acf6bbd20 | note | RESPONSIBILITY: Site Engineer
8a8fd494-1ec4-5ca4-8da2-2bbbc7d952cd | textbox | Date Completed:
ac0c70ba-df7c-4514-b7b4-f19ce9688160 | checkpoint | 2.10 Sealing - for joining culvert sections and pipe penetrations in pits
efabf93a-b340-5aee-b7dc-3de253b3c7ee | note | FREQUENCY: Each Pit
fc71f183-4d6d-53c1-abf7-5413c3042d94 | note | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared. The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
26970e50-f46c-5889-8bc7-14557ccd4cff | note | REFERENCE DOCUMENTS: 610.32, 701.17c
8dfb4a74-3ecd-52d8-8652-4526ee490788 | note | INSPECTION/TEST METHOD: Visual Inspection
618b4334-db53-51e8-bf19-d7a308ed4abe | note | RECORD OF CONFORMITY: ITP Signed, Photos
6d5652cb-0876-5f90-aed3-90003e5e469e | note | IP
cc7d912a-1d1f-5b36-b71a-c69c991c4a7d | note | RESPONSIBILITY: Site Engineer
85b3c783-ac92-5ea1-a045-b36edcab28bd | textbox | Date Completed:
cc3ebfde-01a7-4ce5-a89b-993eab22427d | checkpoint | 2.11 Survey of laid pipe or pit
a0fb251b-0018-5618-b7e4-0d1cc7ef2d48 | note | FREQUENCY: Prior to backfilling
8de3b8df-70d4-5d63-99ec-469d41f52459 | note | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances: (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
ad4ff43d-6427-5d51-a73f-e84e0a3404fc | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
6e31fc58-1b19-5e6d-a5f1-2fda575ab095 | note | (c) invert level of pipes at pits ±50 mm
fdb4ba61-d95b-563b-94e7-6eded2c2f124 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
008df440-f27f-5f7f-98f7-517a6516d7e9 | note | REFERENCE DOCUMENTS: 701.1
9b0ca478-00bf-5d3c-a9c0-569954bb555d | note | INSPECTION/TEST METHOD: Survey Conformance Point
0866cc03-901f-559d-a7fb-8a5d2170c122 | note | RECORD OF CONFORMITY: ITP Signed, As-built
a9a72e14-70a8-5be9-aeaa-98b0288c8e5e | note | SCP
93ef252d-c7e9-52ca-88ed-be39512e6741 | note | RESPONSIBILITY: Site Engineer
5f4752d0-7138-58f7-bd4e-0a752f9d1631 | textbox | Date Completed:
e4f1e4fa-e85f-40fb-942f-e8c1ec954c2b | checkpoint | 2.12 Haunching & compaction of bedding material
adf386d7-a2dc-558c-8a55-726ed83fc2b5 | note | FREQUENCY: Each lot
e84a6596-929f-54ba-8374-6257ca672436 | note | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
adb736fb-a55b-5a1d-8935-d378e8d67fa4 | note | ○ Loose layer thickness <=150mm
b0f65799-9424-56b6-ad89-097392cfa0ff | note | ○ Compacted to refusal using hand held mechanical equipment.
eb0162b7-152c-57cb-939e-b17c9162c930 | note | ○ 1 lot = 150mm layer
f8215ecc-6bed-5b30-8f9c-f354326ed4cc | note | REFERENCE DOCUMENTS: 701.16, 701.20
c04f7bc7-cafa-5708-ba63-e6a987778b84 | note | INSPECTION/TEST METHOD: Visual Inspection
9c0dbcb5-f787-5479-8758-430cd7c7ef77 | note | RECORD OF CONFORMITY: ITP Signed, Photos
1e3251bc-17d9-59c6-812b-e595e7458b4e | note | WP
3a2b3472-3e10-5489-bb4c-672cb97ee7a4 | note | RESPONSIBILITY: Client, Site Engineer
fa875c8d-b6a0-5a55-824f-77cca2fc8860 | textbox | Date Completed:
7c101c6a-4c9e-4d69-ae7a-e908a10805a9 | checkpoint | 2.13 Place & compact backfill material over pipes
20f202d9-422b-5a51-9c58-d516fe93da19 | note | FREQUENCY: Each lot
5694b767-282c-5716-a7db-5f8be0b2f293 | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
c26b0f57-69b0-53a7-9af3-9f91f5da413f | note | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
2aaab667-9902-52ef-bac3-0b33e0d49e58 | note | ○ Loose layer thickness <= 150mm.
e04fd46e-974a-5783-bf5d-f1de533225e4 | note | ○ 1 lot = 150mm layer
e158bdb1-459a-5bcc-90c9-74827dc5eb03 | note | REFERENCE DOCUMENTS: 701.19, 701.20
1476a2f7-f8a0-5f54-b26a-7b6e501742e1 | note | INSPECTION/TEST METHOD: Visual Inspection
68ccf5ae-3d01-53bf-a613-5d85a822f288 | note | RECORD OF CONFORMITY: ITP Signed, Photos
6f55f894-f7c7-53e6-b14c-2ca05438c374 | note | IP
fa8690f4-22fc-5053-901c-aa2208834f67 | note | RESPONSIBILITY: Site Enginer
57be3877-4e98-5670-8679-678c8a3f6f7a | textbox | Date Completed:
160e6c39-a096-479c-bc08-3f620a030ed9 | checkpoint | 2.14 Place & compact backfill material around pits
eba08b64-0541-5bdc-b9b7-484d88457577 | note | FREQUENCY: Each Pit
74897127-a93e-5556-9265-3a929b83ca63 | note | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm.
8670a404-0f3c-5a9d-a0b1-4b35a776c269 | note | ○ Compacted to refusal using hand held mechanical equipment.
a00e3806-80fa-5577-b549-d979cebbf1ec | note | REFERENCE DOCUMENTS: 705.18
f23533b0-7973-55e4-9f38-16e899470ed0 | note | INSPECTION/TEST METHOD: Visual Inspection
4bb007c3-8089-5ec9-aa16-a0d20cbf4d54 | note | RECORD OF CONFORMITY: ITP Signed, Photos
7a916837-2398-5307-90a9-39971ea606ba | note | IP
bf869d1e-f4ee-59ae-a0c5-6d83aa79c1b0 | note | RESPONSIBILITY: Site Enginer
b7ee4cce-5142-519c-a639-07d2d1903cb2 | textbox | Date Completed:
38b96236-2356-4aad-b07e-9109939b62c6 | checkpoint | 2.15 Install step irons
7f685318-272f-5bef-9759-940100176d15 | note | FREQUENCY: Each Pit
2b7cc0ab-2813-59b4-abea-080e7cde6851 | note | ACCEPTANCE CRITERIA: For pits > 1m deep.
d52b40e4-5013-598b-a0d3-94a459faf231 | note | REFERENCE DOCUMENTS: 705.12
13ef1e3a-5da9-59d5-880c-8037b00ea6dc | note | INSPECTION/TEST METHOD: Visual Inspection
abff9438-3fe2-517b-bc94-a4a5ef8f611c | note | RECORD OF CONFORMITY: ITP Signed, Photos
94ca5e74-ed3c-505d-8562-74fdd551cc6b | note | IP
eb70a409-d24a-50b1-be52-c7837d6ab8aa | note | RESPONSIBILITY: Site Enginer
ce9071b5-8893-5eb1-a06a-0e9c88b8a76c | textbox | Date Completed:
84cd26dd-984a-42c5-b691-63289fb5f85a | checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
60a8dcc3-d88a-55b8-a109-5ce386eadebf | note | FREQUENCY: Each Pit
453a72e1-96c5-5541-9349-275356899eac | note | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
6331947a-91f6-5523-b055-1683799bd040 | note | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
a9054a76-2e2c-5ff5-b76c-cb49a3041529 | note | INSPECTION/TEST METHOD: Visual Inspection
6ad207ba-2794-52d8-adbc-eb2c0ae437e7 | note | RECORD OF CONFORMITY: ITP Signed, Photos
805d8e34-6d4a-5c5e-9ee8-1cde7d782a9a | note | IP
97efb90a-82d5-5440-8964-ce5c12539636 | note | RESPONSIBILITY: Site Enginer
abd1af0f-cd2d-5d12-9e94-e5bedca6c865 | textbox | Date Completed:
4d5dac5c-defa-4b0d-8ae3-94b2c726c01d | checkpoint | 2.17 Place pit covers
a645d276-a7bd-5d95-bf98-b5d485961535 | note | FREQUENCY: Each Pit
88807edb-f6df-5510-ba46-cdd461026dc2 | note | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
b84e8349-d4e9-5b12-9821-9b210c2dd705 | note | REFERENCE DOCUMENTS: 705.17, CoM Standard Pit Lid Drawing
aa87f5bf-134d-5c55-824d-c0c3f56812e5 | note | INSPECTION/TEST METHOD: Visual Inspection
cb045865-5b5c-5ae8-822a-9d9e6410ce53 | note | RECORD OF CONFORMITY: ITP Signed
71fb8901-4db9-5d75-8c63-1466c9cbeee9 | note | IP
0155516a-dd15-5d42-be3a-c20b32363922 | note | RESPONSIBILITY: Site Enginer
3a774a75-1c69-573a-9bc5-040867e7baca | textbox | Date Completed:
78db9193-3ef2-4256-8f15-8982159c4e25 | section | Testing & Completion
132d72e6-c175-47ac-b4ea-a9d0516507d7 | checkpoint | 3.1 CCTV inspection
55df7285-1094-5f3c-9374-abb5bcf65e09 | note | FREQUENCY: Each new line
ef887266-5f86-5ee8-945a-b70521c90fe4 | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
74f23ab5-4683-57ac-b7d0-da82b6fad747 | note | REFERENCE DOCUMENTS: 701.3
570a9df4-8fb4-5aab-866c-32af80754e2b | note | INSPECTION/TEST METHOD: Visual inspection
58565645-9468-597b-bdf0-0882cd7cb708 | note | RECORD OF CONFORMITY: CCTV Report
1003cc80-c179-5f1f-915b-7e6ab72f6839 | note | HP
fd80212d-1c60-57ee-99c0-19aea65a5c76 | note | RESPONSIBILITY: Client, Site Engineer
bb2e8c59-9381-5d1a-a3db-3f9ac9983aaf | textbox | Date Completed:
1809b21a-f7aa-4f65-8496-e10d6cdd7159 | signoff | AUTHORITY HOLDPOINT
662646cd-95d9-409c-94c7-48f40f30393b | checkpoint | 3.2 Flushing of pipes
f099767a-8b4b-5268-ae4f-3958d6e07b3a | note | FREQUENCY: Each line
7dd9358a-f346-5c56-98ab-2fdde9bfebb3 | note | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
d0184789-d281-5684-bb1b-b14d04544eae | note | REFERENCE DOCUMENTS: 701.28
c88a93b8-d14e-5638-aac5-1b367373014c | note | INSPECTION/TEST METHOD: Verify
8e72c74a-97b1-5de7-85c9-7db4705d54a7 | note | RECORD OF CONFORMITY: ITP Signed
b3b69955-64c4-5c05-ba5e-38a8a958b6e1 | note | IP
9d5231ec-d7b5-5722-99fb-bdc8b39c9b05 | note | RESPONSIBILITY: Site Engineer
04c7c636-f56d-56f3-8fa5-249b808fb9e7 | textbox | Date Completed:
9fa21232-e540-47e9-a9db-1beef5833f74 | checkpoint | 3.3 As-built
b0bc2dd2-df34-51b1-b9b7-bd0486169f8d | note | FREQUENCY: At completion of job
ba4d6b29-ba98-5b5f-9c35-9dd457c30fca | note | ACCEPTANCE CRITERIA: Licensed or competent surveyor to provide plans showing location and cover level of fits, bearing of side entry pits, and pipe inverts.
664bc9ff-ee0d-5de8-abbb-523a0631c2a6 | note | REFERENCE DOCUMENTS: Project tech specs 14.4.3.a
ec292ae1-7efb-5b74-b4e9-19532486e02d | note | INSPECTION/TEST METHOD: Document submission
5daff7ee-995c-5c51-9edb-43e8bd93c763 | note | RECORD OF CONFORMITY: ITP Signed, As-built plan
7a71541c-7aa1-5fae-bf48-6d77eac97cec | note | HP
df8425bf-9b66-5675-9c9e-f066ba43f3de | note | RESPONSIBILITY: Client, Site Engineer
c879c599-3bb1-58aa-b7ea-e26d4ccc0a4c | textbox | Date Completed:
c0f239c1-e611-4a28-9909-4696163a8088 | signoff | AUTHORITY HOLDPOINT
511396ea-5d0e-4b9e-9e4e-9df3290dfeb8 | checkpoint | Final Inspection
e8552735-5c69-5108-aefa-65da90c16be9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
cc97a7a6-9931-5847-90a5-d3d07b77ca49 | textbox | Print Name:
ec3de28e-d953-5489-b7c1-38d494080a5f | textbox | Position:
031587cf-ee4e-5e55-a29e-2c8386226228 | textbox | Date:
253b3841-5a1d-4d26-9dc3-026a9f629286 | checklist | ITP-004 - Subsurface Drainage | itp | ITP-004 - Subsurface Drainage
96768e7e-ec60-4a0f-b9bf-0379406e4107 | section | Preliminary Works
cba90eed-1a6e-4cbc-996a-a8c841ed5686 | checkpoint | 1.1 Check for correct documentation
f2d97ebb-119c-567c-96d7-db0ee8c7b2c4 | note | FREQUENCY: Prior to commencing any activity
9fd36af9-5cf9-5fa4-ac48-33e620053fe4 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
971a52ff-9621-5ebf-8960-b127461878df | note | – using the correct and complete set of drawings
dcb92054-2452-56d5-bbec-5a5ed565a04d | note | – all drawings are the latest revision
d8621f7d-4adb-5f07-9dd9-d9e9881601b4 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
69335422-c195-53ea-8863-8ced0580bde0 | note | INSPECTION/TEST METHOD: Visual inspection
298d3dbf-b2ef-5fc5-a1a8-bd1a11be1a35 | note | RECORD OF CONFORMITY: This ITP signed off
202ead1d-5d05-507f-9fc1-4073a83abb80 | note | HP*
821fab81-4064-5a2e-bb5e-2b018474178a | note | RESPONSIBILITY: Site Engineer / Site Foreman
d996268d-af42-5d42-a96a-2643f8c0ed05 | textbox | Date Completed:
b034bcff-0eec-4a60-9394-2a907af3ceb3 | checkpoint | 1.2 Implementation of all measures and controls
3f2e22bd-ac92-5445-8688-d4d5882e9538 | note | FREQUENCY: Prior to commencing any activity
66a85fcd-294c-56f0-ac67-35b8c4168f68 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
eda8d7fc-8c1e-542c-a230-9417ec330943 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
272e17da-6bca-59a8-8162-e1c083f51747 | note | INSPECTION/TEST METHOD: Document review
426140f5-de9e-5d94-a112-e2b83df228a4 | note | RECORD OF CONFORMITY: This ITP signed off
e765e1f2-f758-5b97-b212-cfd67077b181 | note | HP*
ba07a038-be74-5fd9-b12c-0f6d28a5471f | note | RESPONSIBILITY: Site Engineer, Site Foreman
02dbd386-7827-5d12-b4bc-a9726f6d22ff | textbox | Date Completed:
af1e8bd7-71d7-486f-af8b-de26c2b07d3c | checkpoint | 1.3 Material Classification
bf52396a-bf19-5fd9-9ffa-bfbd888fada1 | note | FREQUENCY: Each Lot
39c73eb7-42cf-5697-bf9d-ad9d922b060f | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes: (behind bluestone wall) 100mm DIA Class 1000kN/m/m corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
cdd0a5b3-a910-54ae-b4f7-25f1426505d4 | note | ○ Subsurface drainage pipes: (in soft landscaping area) 300mm wide megaflo
296f702f-8565-5147-b07f-a28475314ed1 | note | ○ Granular filter material for bedding and backfill: Trench backfilled and bedded with specified material on drawings (clean washed coarse sand for megaflo, 20mm screenings for behind bluestone wall)
9e4c09ad-2999-569d-9a35-823d3bf82f8a | note | ○ Geotextiles: Shall comply with Cl 702.06.
fe9b99c9-2981-52ee-83a0-02fe560da36b | note | ○ Flushout risers: constructed to the detail of SD 1631
9cdc7b8d-68c4-55f8-83dc-dc4224e4b4ec | note | REFERENCE DOCUMENTS: 702.04, 702.05, 702.06
1228ee77-9a04-5f24-9afc-8abfb85ee9dd | note | INSPECTION/TEST METHOD: Verify
f256adef-92b2-50ec-93ba-3bad7e650bc3 | note | RECORD OF CONFORMITY: This ITP signed off, Delivery dockets, product spec sheets etc.
6c95ad8d-1ea2-54b3-a52b-d50c75e31332 | note | WP
cc84038e-e39e-5d28-ab7f-011f86652b33 | note | RESPONSIBILITY: Site Engineer
055b871b-2d8a-5940-8ba3-3884ab0f4723 | textbox | Date Completed:
fa1ae911-a7d9-4f17-8b9c-61fffa0bfc23 | section | Construction Works
afd37089-32c2-4b63-b70c-4a6ff4d9f2cd | checkpoint | 2.1 Excavation Permit
83a3c8ec-232b-586c-9cb2-49def3162f8f | note | FREQUENCY: Weekly, per operator
c2d3dfbb-d0aa-52f5-818c-6192226a0781 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
450d9568-a2cb-5276-a1d8-e43c108c4064 | note | ○ Plant and equipment shall be appropriate for the task.
ec9d2bf8-7f3a-5f6e-a992-f0e6cf837e68 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
9c78bd07-568a-5f6c-99eb-1ef831558fb6 | note | REFERENCE DOCUMENTS: Excavation permit
d8941c61-6d9d-5439-a0ca-85e72dff4928 | note | INSPECTION/TEST METHOD: Verify
383417d3-3736-527f-a157-c14ddc36b591 | note | RECORD OF CONFORMITY: ITP Signed
4421da55-37c8-57ff-a2a5-fc8925c141ba | note | HP*
d6c56673-5ac4-5690-9796-dfbf4f328259 | note | RESPONSIBILITY: Site Engineer, Site Foreman
4ff9bdb5-a0d1-59f7-8fdb-77fb7f1ce510 | textbox | Date Completed:
9b9d5797-effa-4922-a549-b509f4c6257b | checkpoint | 2.2 Excavation of Trench
2a61144d-0e2b-533e-9aea-c9a71a23e0f1 | note | FREQUENCY: Each Lot
40b8cb9f-a993-5dec-8492-2cb5c0a79a31 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed.
5f45cf89-0b79-544f-a035-fcfddc3a6179 | note | REFERENCE DOCUMENTS: 702.08
286bde25-ee36-5b70-9fa4-655832cef9f6 | note | INSPECTION/TEST METHOD: Visual Inspection
1258292e-4e92-52c8-b8e8-4597f31f67ee | note | RECORD OF CONFORMITY: This ITP signed off
c9dad189-91d9-5039-9b77-c140492631c0 | note | HP*
1f4b687a-7cca-5c31-9517-6dd8fb2ca8dd | note | RESPONSIBILITY: Site Engineer
34a08e18-e6b3-51e3-a28f-b28c2ce1592b | textbox | Date Completed:
77abe4f1-f7e7-49ed-a541-b0ce2dca77ac | checkpoint | 2.3 Placement of bedding
de27901d-0d37-5d4a-9c12-12dc4dc3325b | note | FREQUENCY: Each Lot
5d67283a-6fa8-541c-bbdb-97351bab97b8 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material, sand or screenings placed across bottom of trench and screeded or graded to level
7e79472f-bb95-542a-931e-b674c0655a1a | note | REFERENCE DOCUMENTS: 702.09 (c )
6ab10106-c42a-505d-8648-3cca315416ba | note | INSPECTION/TEST METHOD: Visual Inspection
70a84da1-b6be-57d7-8da6-5ea7227ced44 | note | RECORD OF CONFORMITY: ITP Signed, Photos
1f1acec0-70f6-554e-9084-36426eaa7130 | note | IP
374d33c5-160c-56aa-98ec-71236a3fca32 | note | RESPONSIBILITY: Site Engineer
52134def-5faa-50d5-a8ea-19c0c2604616 | textbox | Date Completed:
729ccaa8-11fb-4f61-81d1-aa695244b317 | checkpoint | 2.4 Placing pipes and geofabric (if required)
5d0459eb-3d53-518b-a756-595c4fe673e7 | note | FREQUENCY: Each Lot
17f55c23-a591-50ea-8cba-93d3ebadd578 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
af53b4e4-92af-5e55-86d0-685f04f236a3 | note | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum 150mm lap of geotextile used for wrapping.
ef6e3bc7-b7c0-5cbb-a92d-11a8c8aacb88 | note | REFERENCE DOCUMENTS: 702.09
07782968-0dd0-5402-94ef-bff191104f5f | note | INSPECTION/TEST METHOD: Visual Inspection
60516dee-c0ae-55d4-80df-9c8ad6a1b070 | note | RECORD OF CONFORMITY: ITP Signed, Photos
f6ce6ff4-b08e-5bc1-8660-74387bdcadfb | note | IP
68e2f400-d15b-5db5-8506-533b1287a36b | note | RESPONSIBILITY: Site Engineer
a00519ca-da4b-5ae2-b11c-4d6c3390fcc9 | textbox | Date Completed:
99ec03fb-7074-4712-a3c3-508ce950443c | checkpoint | 2.5 Placement of backfill
a5e1eb90-2cd4-5770-ad79-3e006e05df42 | note | FREQUENCY: Each Lot
466ca703-9c1d-5de2-8e51-0e612ba780c8 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
aec5cf5f-2863-5e27-8e59-41ebfee9c7c2 | note | REFERENCE DOCUMENTS: 702.09 (g)
d1ae6976-9c4c-5824-ba0b-68b24c34067f | note | INSPECTION/TEST METHOD: Visual inspection
21fd776f-e9bb-5c30-b6b4-f228c073901d | note | RECORD OF CONFORMITY: ITP Signed, Photos
8a948a76-5961-573d-993c-69ff370f7402 | note | IP
8f5dc749-dee9-5b52-b292-7b95ff19a402 | note | RESPONSIBILITY: Site Engineer
27c23095-3dc2-5a2d-9995-de5f4a527875 | textbox | Date Completed:
e8f27fdd-c8ab-4d56-9338-1090eaa7e493 | checkpoint | 2.6 Flushout risers
ba2b82cd-7db2-5617-8e30-c2d083c83e35 | note | FREQUENCY: Each Lot
8019dfc9-286e-5e2f-97a9-6efce31d9fe0 | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
cab57183-d61b-530c-ade8-247989294a26 | note | REFERENCE DOCUMENTS: 702.1
53f1b387-7400-50e6-8c8d-27c7814405af | note | INSPECTION/TEST METHOD: Verify
732c180a-e49f-5995-8c4c-91fcd500c922 | note | RECORD OF CONFORMITY: ITP Signed, Photos
eb91a165-041e-5252-9feb-a9b3fee2ba11 | note | HP*
019a167f-60a4-5c43-97d6-c614469ef4b5 | note | RESPONSIBILITY: Site Engineer
a74da8a3-4893-5c0c-8fe3-a8c6ab432b4a | textbox | Date Completed:
28442f0d-2801-45dd-bc43-bff395b5e8fb | section | Testing & Completion
614251fe-16f1-48c4-b5e8-aacdccb5e113 | checkpoint | 3.3 As-built
84e84f6e-ca01-546c-a058-920b225c10a9 | note | FREQUENCY: At completion of job
16d2545e-c86a-5285-b470-bbfb9cc4f223 | note | ACCEPTANCE CRITERIA: Licensed or competent surveyor to provide plans showing location and cover level of fits, bearing of side entry pits, and pipe inverts.
1dcb3e82-b280-59bc-ad1d-622f85def197 | note | REFERENCE DOCUMENTS: Project tech specs 14.4.3.a
7291aee3-5a24-50ec-b900-12590e6f09d9 | note | INSPECTION/TEST METHOD: Document submission
65b54989-d44e-5ea5-ab54-b3496cda4bab | note | RECORD OF CONFORMITY: ITP Signed, As-built plan
0d8d5012-123f-5edc-b3de-9a6b0b579987 | note | HP
1ba2e0e1-40b7-512c-9edb-52dee7a110bc | note | RESPONSIBILITY: Client, Site Engineer
bc214a6e-5d02-531d-8d49-0e17b00c5370 | textbox | Date Completed:
5399b1f3-8988-4884-beda-8a7079c7c1fe | signoff | AUTHORITY HOLDPOINT
c8c71327-c4bf-413e-8534-07f489c44401 | checkpoint | Final Inspection
2f5a3170-87a3-599b-8bcf-634362f8ae32 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1ee1da20-195e-543c-81f0-a2a347e6e582 | textbox | Print Name:
38d739ec-1ba6-5799-a741-8655a7a862b0 | textbox | Position:
d8fdde86-e489-5e89-83d8-26cabc9592f2 | textbox | Date:
246215e0-3db9-4f74-92c3-6f65f4e74bdd | checklist | ITP-005 - Tree Pits | itp | ITP-005 - Tree Pits
a3d1f3b8-a341-46b0-bd3e-de46755ba370 | section | Preliminary Works
db98e7ea-4118-4322-bd07-3b2ac18b6c76 | checkpoint | 1.1 Check for correct documentation
9a7bfa0e-f55e-5179-8732-55fddf88c5a0 | note | FREQUENCY:
4bedb7f2-8b0a-5150-9d17-7c65682dbc22 | note | ACCEPTANCE CRITERIA:
75969f09-08ae-5cdd-8486-9d708ae1650e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
431e8e07-7f42-5a74-ab7a-9337db694184 | note | INSPECTION/TEST METHOD: Document review
8255619f-f804-54b9-807f-0a41a4a42a40 | note | RECORD OF CONFORMITY: This ITP signed off
a4331385-d56b-59ee-bf16-886aa693ad31 | note | HP*
336e651a-cfc5-5799-938c-2f0847aa7221 | note | RESPONSIBILITY: Project Engineer
3207551f-0c48-5acc-8fa4-f672e3189047 | textbox | Date Completed:
5803c277-c161-4434-91ec-ebdb2864e0e1 | checkpoint | 1.2 Implementation of all measures and controls
8d968c26-3cce-5c40-b1d5-cf24d2388cc0 | note | FREQUENCY: Prior to commencing any activity
b7df100c-8612-5b35-9d29-555beacc238a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
71474802-be49-554e-9d98-cd44f348747b | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
4bf9adb2-42c4-5418-836e-d27bb495b407 | note | INSPECTION/TEST METHOD: Document review
8db25d7e-f8b8-532a-b059-4885fe027164 | note | RECORD OF CONFORMITY: This ITP signed off
5ecbd14a-1c08-5240-896b-fb06f8ee0bc4 | note | HP*
0efe8ea3-bbef-502c-b067-fc9abd7b6592 | note | RESPONSIBILITY: Site Engineer, Site Foreman
7c547c88-22a3-5887-8141-c8dc3a00c4a7 | textbox | Date Completed:
fde8887c-ca71-46d8-8de8-975176db2f13 | checkpoint | 1.3 Precast Materials acceptance
535a9c46-eb95-5d8f-9878-228ad0ecefd5 | note | FREQUENCY: Each Delivery
b10d9489-bd05-5601-bff5-89d814f830fe | note | ACCEPTANCE CRITERIA: Precast kerb inlet blocks and pit grates and frames shall comply with Design Standard 304.4, and City of Melbourne drawings 1P 50305 and 1P 50320.
c328dc9f-e037-51ec-89f1-b496613a4bb4 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
f5310983-37e2-5dc7-86a4-f6b82ba5bf1c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 610, City of Melbourne Standard Drawings
2df48d8f-476b-536b-8584-316bf8838a1e | note | INSPECTION/TEST METHOD: Visual Inspection, Verify
bdfcbc1a-96ae-56c7-9173-e48c75b1a98f | note | RECORD OF CONFORMITY: This ITP signed, Manufacturer certificate or accreditation
8f7cef8c-a4e0-5925-a333-a61a3d21c063 | note | IP
27b78785-f0b1-527b-88b4-288b7b12d4f9 | note | RESPONSIBILITY: Site Engineer
16c3a1cb-c585-50ab-8438-ce6978226195 | textbox | Date Completed:
a8f3fec4-227d-4fa1-9f9c-b9488c1cea0d | checkpoint | 1.4 Material Classification
6794a4ce-6908-596b-b1de-2cb7d3fec59a | note | FREQUENCY: Prior to start
a576dd0b-ffa8-5eb4-a9d7-f234596644c5 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
7861317d-7171-501a-ba57-fe1a1fb7381a | note | ○ Drainage Backfill: 5mm screenings
22a85b18-3dfc-51a0-81e0-d5294863b226 | note | ○ Transition Layer: Sand/Coarse Sand
a3c78752-9fcb-5452-aff9-9620bfce906c | note | ○ Filtration Layer: As confirmed by the client (TBC)
f2aa38cb-0ea4-51e5-9267-7252805ad4e7 | note | ○ Drainage pipe: 100mm AGI pipe (no sock)
c77655b7-1713-554d-bd95-a2b4e37105bc | note | ○ Flushout pipe: 100mm PVC solid pipe with screw cap
022a7ce0-b52d-5d7e-ba44-e64152a6c64a | note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092, Project Drawing CI-00080
ebf29736-b1c7-55c5-bb53-6ef604c70d65 | note | INSPECTION/TEST METHOD: Visual Inspection
a3b21196-f356-517d-85b0-22484444d385 | note | RECORD OF CONFORMITY: This ITP signed off, Delivery dockets, product spec sheets etc.
da6af15e-b830-5cad-8fa2-63cbc28c4c06 | note | WP
63bfd2e8-fe34-55c0-acaf-9f8e24523232 | note | RESPONSIBILITY: Site Engineer
3b105e78-fde5-53ac-b820-43b2a9e5229a | textbox | Date Completed:
8829eef9-505d-4046-a3ec-c6728ebd2713 | section | Construction Works
46a14377-4a2d-4251-835c-fef94c038005 | checkpoint | 2.1 Excavation Permit
372273e8-bef1-5b09-9601-81e463dcbf53 | note | FREQUENCY: Weekly, per operator
16baeddb-280e-5106-b6e4-201d6af6e45e | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
004af7e2-e33b-5422-9a67-fd7c125e023e | note | ○ Plant and equipment shall be appropriate for the task.
317dec31-7cfb-58b9-a67c-ec9c3ce2be8a | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
7b96eb8d-3e12-56eb-8a7a-1ea4be0d49e9 | note | REFERENCE DOCUMENTS: Excavation permit
6919beff-d792-5cd3-970b-35e211bdad88 | note | INSPECTION/TEST METHOD: Verify
1b535283-a408-5955-9cee-b4283a1239c9 | note | RECORD OF CONFORMITY: ITP Signed
6bb05dd4-5c98-51d8-aefc-880bf980063a | note | HP*
72a73181-7078-5396-8f1c-43e985c26454 | note | RESPONSIBILITY: Site Engineer, Site Foreman
a18cc168-7883-5cc0-bae6-bd61fe515b34 | textbox | Date Completed:
f19a2c3a-d9ba-43a9-9ae2-36ae048b68a2 | checkpoint | 2.2 Set out pits
f56d03bd-5985-5f18-9cd4-b0dea65dbe9a | note | FREQUENCY: Prior to start
65914eb3-0cbe-5c43-b9bf-7e5fcc9ce747 | note | ACCEPTANCE CRITERIA: The position of all pits are to be confirmed with the superintendent.
24376009-0a11-526b-a235-b30d40454eb2 | note | ○ The inverts of all outlets are to be checked to ensure there is sufficient flow to the downstream system and that there are no service clashes.
74df81d9-38a9-56a9-80d0-632b8c42ee15 | note | REFERENCE DOCUMENTS: Drawings
c57435a0-dad4-5d25-8323-5a8337dba67e | note | INSPECTION/TEST METHOD: Visual Inspection
4b0249b6-0124-58c4-b705-9cb4aeaa0643 | note | RECORD OF CONFORMITY: ITP Signed
6c2be9d2-84fe-58c8-96c8-283f1a20f842 | note | HP
a498a79d-9a3c-5ef7-a75e-13fa76cc46bf | note | RESPONSIBILITY: Client Site Engineer
8840efc1-a724-5493-8f1c-8d45d50bd81f | textbox | Date Completed:
ae155de9-3a5e-4d28-98bb-a60d8a3a45a4 | signoff | AUTHORITY HOLDPOINT
74c2f090-7c9a-4aa2-b204-a81dfeefe70d | checkpoint | 2.3 Excavation
d48fe5ac-3454-5458-8cbe-db7f02345167 | note | FREQUENCY: Each Pit
42523c16-e4dc-58c9-a3d1-d1ce996326d0 | note | ACCEPTANCE CRITERIA: Excavation is to be to sufficient depth to allow for backfill layers to be placed at the required thicknesses.
70eb21ae-9821-5f7f-b4aa-13e2b099c4f8 | note | REFERENCE DOCUMENTS: Drawings
b40c448c-2be4-52a0-84f2-6eb29dfae4a0 | note | INSPECTION/TEST METHOD: Visual Inspection
5d113685-4ada-579c-a892-781a82033e19 | note | RECORD OF CONFORMITY: ITP Signed, Photos
f37f04ee-6c53-5c8c-87b5-ac3125da6bf4 | note | IP
48f4c163-d7a4-522f-8a16-1ff40042f530 | note | RESPONSIBILITY: Site Engineer
f0e7a54e-497d-5930-8043-2651405f226f | textbox | Date Completed:
4a643003-5680-458e-bb30-351b6068a4cc | checkpoint | 2.4 Placing pipes and geofabric (if required)
c381cd78-22f9-58c4-91ee-e3446bdf6a65 | note | FREQUENCY: Each Pit
3e4993f6-4181-5378-89ef-8ad50fdd40fc | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
e920fcce-f14d-582c-a199-707bcc115ef6 | note | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum 150mm lap of geotextile used for wrapping.
4cbdf134-deef-52fd-8047-8daf27c77311 | note | REFERENCE DOCUMENTS: 702.09
24c144b7-95ed-5e21-81b0-4c0177c90acc | note | INSPECTION/TEST METHOD: Visual Inspection
1aba6f21-a9c2-5ec1-87f7-da1d58c81a7c | note | RECORD OF CONFORMITY: ITP Signed, Photos
445c1139-7ca3-578e-aac0-2e48e6220cf2 | note | IP
99ce3b81-f1ba-50cf-8dcf-9530a3d36f6c | note | RESPONSIBILITY: Site Engineer
fcbcaa8f-c1be-5215-bfd6-1fc20ba92346 | textbox | Date Completed:
dfb6e66a-e628-486b-bbda-c7592f41a76c | checkpoint | 2.5 Placing drainage, transition and filtration layers
a005958a-f517-50ca-8201-00abf84af6cd | note | FREQUENCY: Each Pit
5e41d760-0387-503b-bd72-8fdd73eac155 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes.
54cce5ec-3fc6-5459-8a84-a32539ce4f36 | note | REFERENCE DOCUMENTS: 702.09 (g)
01699a3d-9058-5213-863e-0927642efce7 | note | INSPECTION/TEST METHOD: Visual inspection
129418a0-7577-521c-b3f8-5214371bbb05 | note | RECORD OF CONFORMITY: ITP Signed, Photos
8ffdf05f-01fa-5986-beaa-fb8b29820b1e | note | IP
9fef6a86-b877-51a2-ae0c-07ca7e727209 | note | RESPONSIBILITY: Site Engineer
55bbdf46-1d77-5abe-b662-1a8fb322df09 | textbox | Date Completed:
10ddad98-f481-4d87-b752-b1566efcbb09 | checkpoint | 2.6 Placing structural soil (if required)
7eb3e579-f55d-55b8-a891-397ff08f8130 | note | FREQUENCY: Each pit
03f403bd-b61b-5fbe-a51b-cd77c66af360 | note | ACCEPTANCE CRITERIA: Structural soil placed and compacted in layers. Volume as per IFCs.
6f15752d-75cb-52ef-8401-0958f23fdc18 | note | REFERENCE DOCUMENTS: Drawings
11de4cdb-6fe1-5231-b69d-8448910c5bcd | note | INSPECTION/TEST METHOD: Visual Inspection Survey Volume
4fd0d493-9879-5aa2-ad50-daa8434d5526 | note | RECORD OF CONFORMITY: ITP Signed
d5993d47-4a68-5a1f-8ef5-403a2487eb5a | note | IP
ccfef117-b876-5d42-a4af-263c16364ef7 | note | RESPONSIBILITY: Site Engineer
ad912dbd-9566-54f3-b41d-421c5fe52484 | textbox | Date Completed:
99d33c7f-0d7c-4aa8-9418-d78facee47e7 | checkpoint | 2.7 Flushout risers
fe479e14-c4ab-5a41-a3cc-d604a0fd99b1 | note | FREQUENCY: Each Lot
cce9f211-25af-575a-82b9-da2b2d8651cc | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
57f7e311-8aa6-5288-b7e3-4d5626032c41 | note | REFERENCE DOCUMENTS: 702.1
dbad4917-26b4-5d6b-b7af-1027ee2c6a66 | note | INSPECTION/TEST METHOD: Verify
81aa359c-c224-5d3e-a289-347ae154821a | note | RECORD OF CONFORMITY: ITP Signed, Photos
648e6877-12cf-579c-8d20-e0bb7882093c | note | HP*
563bb7ea-b584-5d59-b193-c7c85d682ade | note | RESPONSIBILITY: Site Engineer
710608e8-c6d2-578d-84b0-5f472a9c68a0 | textbox | Date Completed:
172182ab-28c5-4082-a7ca-373b17c76f69 | checkpoint | 2.8 Place and set side entry backing block, grate and frame
5e4d3cdc-9595-539d-aefb-1089889b4efe | note | FREQUENCY: Each Pit
3e281f31-c904-5a5e-b301-61e680d6113f | note | ACCEPTANCE CRITERIA: Entry blocks, grates and frames must be set to within ±10mm of the design levels shown on the drawings and In accordance with the relevant COM standard drawings.
b98fcf1a-0445-5258-93dd-d67d87720b89 | note | REFERENCE DOCUMENTS: City of Melbourne drawings 1P 50305 and 1P 50320.
731ba150-7e71-5335-a1df-269b19baa2a5 | note | INSPECTION/TEST METHOD: Visual Inspection
1c408c4f-2421-5ddf-9d83-6360c0b99ecf | note | RECORD OF CONFORMITY: ITP Signed, Photos
1c8257fb-f96f-5d7e-9f4c-2e4b566c7f8b | note | IP
4105b3b4-bf0c-576b-ac91-e8c0f2f705b5 | note | RESPONSIBILITY: Site Enginer
f4a6fe31-3d91-5e69-8b76-969f1797c3fe | textbox | Date Completed:
c45775e8-7b64-4d79-b17d-68a03dc69d9f | checkpoint | 2.9 Place tree guard and grate for bioretention tree pit
18b071a7-c3a1-5ab7-a280-32f071528e40 | note | FREQUENCY: Each Pit
661154fb-a66b-52e9-8db9-a905ca6e9061 | note | ACCEPTANCE CRITERIA: Guards and grates must be set to within ±10mm of the design levels shown on the drawings and In accordance with the relevant COM standard drawings.
bb9e7e03-6e04-5fb1-b80e-b07c56ca7f81 | note | REFERENCE DOCUMENTS: City of Melbourne design standard 706.03
6aa1f5f7-8c2a-5597-8ca6-ec2ad1e8912a | note | INSPECTION/TEST METHOD: Visual Inspection
3e68b594-9f95-5cb0-983f-c2f9f9b296b9 | note | RECORD OF CONFORMITY: ITP Signed, Photos
585902a6-7207-581b-949c-e6ffafebd102 | note | IP
90258878-564d-5d82-85e0-374e6416924d | note | RESPONSIBILITY: Site Enginer
aaea2d80-803c-5081-9f27-4a9abfb2194b | textbox | Date Completed:
9ce6d845-46e7-44b6-b3d7-fe5804fab849 | section | Testing & Completion
717256e4-5d1d-4506-a536-171176902740 | checkpoint | 3.1 As-built
d497a767-59bb-5eb1-9a0d-f7128e7f1ca6 | note | FREQUENCY: At completion of job
9d4692b6-1f28-568f-be25-6fc8f12f2de3 | note | ACCEPTANCE CRITERIA: Licensed or competent surveyor to provide plans showing location and cover level of fits, bearing of side entry pits, and pipe inverts.
3af83ad4-90eb-52fa-a1bc-71064a726ca3 | note | REFERENCE DOCUMENTS: Project tech specs 14.4.3.a
1d930bd7-20b9-581e-8688-6b2448927c0e | note | INSPECTION/TEST METHOD: Document submission
f3f64aa7-b5df-5d5c-bbd1-52d91ae8ed5e | note | RECORD OF CONFORMITY: ITP Signed, As-built plan
69bf40bf-18d1-56ac-a0bb-7336ef9a7c52 | note | HP
936d80b0-99a9-50ba-8809-8706b306dc4c | note | RESPONSIBILITY: Client, Site Engineer
8a80c841-cd72-53a8-a827-5c8ce27a1e11 | textbox | Date Completed:
442792cf-c7e5-42a2-8137-5a9a0cfb721a | signoff | AUTHORITY HOLDPOINT
a66557d5-99c7-414a-b8c1-bb56128450a2 | checkpoint | Final Inspection
ab7418e4-b1d6-58b0-977b-f6c9a11d6710 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d6200746-3f14-5933-bc81-ba7ce1ba2471 | textbox | Print Name:
d739c3fb-78ad-54d4-89e3-13fdffdb605c | textbox | Position:
95d41f51-2e93-5777-82e3-ef7a43723eac | textbox | Date:
d8c4dcff-83e9-47fd-8693-5f7e9dd6acc7 | checklist | ITP-006 - Bluestone Kerb Installation | itp | ITP-006 - Bluestone Kerb Installation
b5bdd9d8-c97b-4d95-8184-a314094fc938 | section | Preliminary Works
8dcf810c-c991-4c77-a139-68c56eb3bcaf | checkpoint | 1.1 Check for Correct Documentation
3cc6f041-72cc-592a-90c4-8621ac2479e4 | note | FREQUENCY: Prior to Commencing Activity
e1ecc320-c417-5594-bb5e-55a738f5640e | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
8eb50c50-f5d5-56b3-8d1e-ad0e8e259183 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
a81c39c9-334a-59e6-826b-01ac91f53c40 | note | INSPECTION/TEST METHOD: Visual Inspection
016230d7-b21b-51a6-926b-6ede21a7968c | note | RECORD OF CONFORMITY: This ITP Signed off
6a7cff61-28d8-5f6d-86c9-3f7846cdfa98 | note | HP*
0a3d2a5a-11ba-5866-9372-89e5e125d5d3 | note | RESPONSIBILITY: Fulton Hogan Engineer
acccd2bc-0cf5-574a-ad1f-2471022de421 | textbox | Date Completed:
8781a05b-95d4-46f1-ba18-b9cdb12d63a2 | checkpoint | 1.2 Implementation of all measures and controls
a9e086af-d909-57f1-abbd-6a32f7f3fc0a | note | FREQUENCY: Prior to Commencing Activity
99ccce01-7dd2-534a-a129-d191294dc8d4 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
c1b53d4b-ba86-515b-9674-94483a3da8e2 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
7a2a218b-bdc3-5ccd-891d-7c68f9a95bbf | note | INSPECTION/TEST METHOD: Inspection
a5fa2bb3-9c49-5108-a30d-a11ebc31deb3 | note | RECORD OF CONFORMITY: This ITP Signed off
06ea49bd-5f50-5c43-bbca-418fd2da6548 | note | HP*
d4da54fb-6cc9-5d91-b988-a09446f55098 | note | RESPONSIBILITY: Fulton Hogan Engineer
4e76a7e7-ddde-5840-8c06-2be4f767e4ed | textbox | Date Completed:
6b5a9505-1c67-440b-9004-5323c84b962a | checkpoint | 1.3 Existing Bluestone Kerb Demolition
b07bc4b5-bb0c-55f9-aa44-b28bef5c4ce9 | note | FREQUENCY: Each Lot
98816364-e459-5e6f-ba71-3538d2bed79f | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
3f5302ef-2b95-527b-ae57-4903a48d3aea | note | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
007543d3-1888-5381-bbc1-6d87b8e28fe3 | note | ○ Bluestone shall be salvaged and re-used in new kerb alignment
47895b1a-2b22-5348-8a0b-4a1e69e61eab | note | REFERENCE DOCUMENTS: Work Procedure
2e6e129e-6f74-54d8-8a6a-23226aaec5cf | note | INSPECTION/TEST METHOD: Inspection
64e7a0a7-1ec9-5893-864c-50458e8aedd4 | note | RECORD OF CONFORMITY: This ITP Signed off
97326851-c0d6-508d-a25c-1c7676a3056a | note | IP
dd74150a-05e7-51a5-bf75-06ed9fa0fb73 | note | RESPONSIBILITY: Fulton Hogan Engineer
b7523895-0dac-5d01-9c73-4ea538c83cba | textbox | Date Completed:
199dc1b7-cfa8-4186-90d7-39d3607a2eb3 | checkpoint | 1.4 Setting out
238988ec-cd4f-5761-b5fc-f13e5b05ec2b | note | FREQUENCY: Each Lot
24b90d1f-1944-5881-8ac2-f68067893fca | note | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans
f26d14fa-6906-59d6-b7a5-5926a61b5491 | note | ○ Alignment of new kerb shall be marked out using string line
362f6ea6-c9a6-57e0-9dce-480f2281f1a4 | note | REFERENCE DOCUMENTS: Work Procedure
c9b3c859-2a0a-54fc-ad78-f21335ca1679 | note | INSPECTION/TEST METHOD: Inspection
ecf01305-e321-5bde-9a46-78b545ce954b | note | RECORD OF CONFORMITY: This ITP Signed off
ff1745c5-813b-5846-9a3b-f6fc0409ad92 | note | HP*
679e054b-aa13-5fe9-a784-6f5018bdca6f | note | RESPONSIBILITY: Fulton Hogan Engineer
c8364477-1ab0-540c-a21d-ea5988863656 | textbox | Date Completed:
dccf12c5-73a1-41ff-b130-551a4ecc8b0d | section | Construction Works
c1f0e0a5-6de1-4d48-83cf-f62d0f854a9f | checkpoint | 2.1 Saw cut (if required)
aec9b8b9-d2cd-57fb-abb4-6a321f4866f8 | note | FREQUENCY: Each Lot
63281f85-2768-5b79-bd8b-d20a66e08925 | note | ACCEPTANCE CRITERIA: •Saw cuts shall be made to the following depth for existing asphalt pavements:
34da12ea-c671-589b-adb8-3c1abcb6df7a | note | – Footpath: Minimum 75mm
08893e68-db23-5aff-9e99-93a8c1408f5c | note | – Roadway: Minimum 125mm
e9bf8af5-a5e3-5017-8135-d57e75fc0b71 | note | ○ Excavate to allow for design heights
b2587a5c-8d4e-5759-beb4-75398c54c5ca | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 2.0
d72b4dd8-1153-5faf-a421-7b65363fa195 | note | INSPECTION/TEST METHOD: Visual Inspection
14949468-c349-56dc-8d0f-bb93baaf1a62 | note | RECORD OF CONFORMITY: This ITP Signed off
f34c94dd-ca5d-5cb9-b9a1-ade8e1dcf8c2 | note | IP
e177a5f4-72f7-507a-a972-0767323dbdb8 | note | RESPONSIBILITY: Fulton Hogan Engineer
0b02d6f7-2b68-5772-a01c-6281511c0200 | textbox | Date Completed:
70a3697f-13b3-4a50-9835-16a4240b83c9 | checkpoint | 2.2 Concrete Placement and Setting
3491a7b0-59e7-51cd-95af-e76812d1eb4c | note | FREQUENCY: Each Lot
8b30fdb6-7ae7-5864-a821-bf91429bafe5 | note | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness
a986f902-aecd-5efc-8cbe-02bb2a666992 | note | ○ Gaps of >10-30mm< shall be provided and filled with mortar
eac0bf0e-4335-5159-9c5e-5b45a19f3a6a | note | REFERENCE DOCUMENTS: CoM STD 1P 50406
24291d2f-518a-5532-9e91-dc64ace686aa | note | INSPECTION/TEST METHOD: Visual Inspection
0d4f7276-68bf-534d-a970-9f0ae204f55f | note | RECORD OF CONFORMITY: This ITP Signed off
764be82e-3481-58e6-a02f-f9a11df16d21 | note | IP
6b0d4706-7a35-5c77-8609-632ba3a242d3 | note | RESPONSIBILITY: Fulton Hogan Engineer
231f7374-7fe2-5c32-b25d-6eb19479cfcc | textbox | Date Completed:
47344499-5b86-4f7c-925a-58296087866b | checkpoint | 2.3 Mortar Mix
0e482d51-bc64-53f3-adc2-9282df4a6b28 | note | FREQUENCY: Each Lot
ede6d3d0-101f-52ed-bd94-dd1cc526ddac | note | ACCEPTANCE CRITERIA: Joints shall be filled with mixed grout composed of the following:
617c5cb3-fbf1-583c-8a3f-57c5586db055 | note | ○ 16% cement
ebba670f-7f4e-5458-ab70-2ce61e7e8413 | note | ○ 16% stonedust
2c893702-f1a3-5c5d-949a-a31f95f87737 | note | ○ 67% blended wash sand
1b648e85-d031-5c26-a593-85e9dfb03788 | note | ○ 1% lime ready mix grout
99d76d6f-1852-5ee9-8284-c9ce8c8fe97d | note | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 4 AS 3972, CoM SD 1P 50406
6d2c8668-5a90-5d2f-81f3-d8a37660fc57 | note | INSPECTION/TEST METHOD: Verify
0ab6c3ab-14f2-5e4a-8a1a-e397b484afdd | note | RECORD OF CONFORMITY: This ITP Signed off
4bf2bad5-8b58-5fc7-b85d-5bf40349209f | note | IP
ce45c7be-adc4-5bf6-ae79-d286d98e4fc9 | note | RESPONSIBILITY: Fulton Hogan Engineer
30fbc0e9-d3ff-5889-9d05-37e965a5fda6 | textbox | Date Completed:
d75c1c04-326e-4a6f-9a5a-e2c7b11af15b | checkpoint | Final Inspection
0222556f-20dc-5fe6-8a90-830e3cd047df | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
bf64c201-162e-5dcf-b38d-1746566baf36 | textbox | Print Name:
553e7552-8657-552d-b30d-9fe8c72d7c1f | textbox | Position:
ccf41d88-195b-59d4-afb4-3120411961bd | textbox | Date:
7e7ab037-81d5-4be0-9e1b-e71d8e5ff0f0 | checklist | ITP-007 - Bluestone Footpath | itp | ITP-007 - Bluestone Footpath
20aa4a21-bff9-4649-8955-348f52e19b2c | section | Preliminary Works
305232f8-775e-4079-96ec-7c4c4f9b2c5c | checkpoint | 1.1 Check for Correct Documentation
eff28325-2889-5ad2-818a-527aa9ac4a0e | note | FREQUENCY: Prior to Commencing Activity
045d561c-3fbf-5841-9927-1677ca638e9f | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
7f716dbb-85f1-5c18-a210-5006ddfdeee7 | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
37a5f86d-c85a-534e-b1b0-768fc112f271 | note | INSPECTION/TEST METHOD: Visual Inspection
46e324cf-1f4c-5334-a789-f79b9dcb7d1d | note | RECORD OF CONFORMITY: This ITP Signed off
baa21b4a-ce2e-5fb0-8fd5-b4f336432707 | note | HP*
fc4ed4cb-8454-5155-a3e8-3c8fa4c505c0 | note | RESPONSIBILITY: Fulton Hogan Engineer
51a78897-b508-563c-8581-5bfaefebc8da | textbox | Date Completed:
8191669a-f5cc-46cf-aa50-4bcf2f5f01a2 | checkpoint | 1.2 Implementation of all measures and controls
2ce776ad-dc4b-5f0c-ab19-8e8f2b326861 | note | FREQUENCY: Prior to Commencing Activity
c86a95fe-66f6-593c-a25d-72c35d4ef5d2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
ce38b250-8e3f-54e9-a02f-33a0508b307d | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
45b63757-36e0-54e0-b96c-0cfad90f274f | note | INSPECTION/TEST METHOD: Inspection
8d187706-37b5-5dc3-814a-1d6a160a1fac | note | RECORD OF CONFORMITY: This ITP Signed off
7e5bcc38-4083-5f76-b732-ee15e80671cb | note | HP*
42c6bf16-ea82-5a43-80be-dee6ecae3db1 | note | RESPONSIBILITY: Fulton Hogan Engineer
c7425977-5754-5cd6-bd32-097f428e13a9 | textbox | Date Completed:
6b295c6b-f3de-42fa-b916-775d04ac14a6 | checkpoint | 1.3 Existing Bluestone Kerb Demolition
214c8b3b-c45f-5a80-9054-244026dbddd5 | note | FREQUENCY: Each Lot
ec192158-b77e-5e5a-8647-fb4f0ef2732f | note | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
4c77317b-0a8a-53b6-bd05-0f5582bbf3d7 | note | ○ Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
7c306229-7ad5-5b2b-8492-39c102972ec8 | note | ○ Bluestone shall be salvaged and re-used in new kerb alignment where possible
a60a5f47-63a7-5166-b867-4eaa48a477f6 | note | REFERENCE DOCUMENTS: Work Procedure
f46e5817-a675-5f15-8893-2d00fb1aa4c9 | note | INSPECTION/TEST METHOD: Inspection
092df829-0339-5761-8130-318a64472377 | note | RECORD OF CONFORMITY: This ITP Signed off
a064744c-0be2-5d12-824b-3997340718a1 | note | IP
6628fefc-3db7-5122-990a-671f94e4f0ea | note | RESPONSIBILITY: Fulton Hogan Engineer
51abbd62-aa4d-577b-b0aa-dd5b5fb0b818 | textbox | Date Completed:
c47c2075-f5e3-4091-a79b-743c1392d447 | checkpoint | 1.4 Check Materials
8e711003-2647-51f2-b826-9689af56ecd9 | note | FREQUENCY: Prior to Commencing Activity
adddacce-79cf-546e-b40f-e6a2b1e4f260 | note | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
b959d8c5-b180-5d5e-a819-40a2a4f4f586 | note | REFERENCE DOCUMENTS: Receivable Inspection List
228f8f5f-2eae-5f05-ba29-3497317b87a3 | note | INSPECTION/TEST METHOD: Visual Inspection
25db6f14-cc5b-558e-95b3-ad4c365106c5 | note | RECORD OF CONFORMITY: This ITP Signed off
bb66bfe7-2587-5e7f-87f3-d3bffc9689c6 | note | IP
c9ec231f-77af-51ac-abb2-4471895617eb | note | RESPONSIBILITY: Fulton Hogan Engineer
7684a93d-391d-5c7c-b65f-00f3fc6398b3 | textbox | Date Completed:
69b4f510-7d71-4fe6-851e-e22e65ad75eb | checkpoint | 1.5 Setting out
626958ca-bbf0-5030-8b0c-1fbf7d65ea38 | note | FREQUENCY: Each Lot
bca79477-64d6-59a9-809a-5bebe7c81421 | note | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels.
b397a1e6-92cd-54fa-8328-5cba2106ad23 | note | ○ Line and level of bluestone pavers, tactiles and inlay shall be set out according to design levels to suit new kerb heights.
3d61d07b-147e-5eef-935f-49f899c87805 | note | REFERENCE DOCUMENTS: Work Procedure
794b3fba-3064-54c7-b7ac-30c67a70da22 | note | INSPECTION/TEST METHOD: Inspection
d48da228-14dc-5be1-bc0c-c4b3e4017eb1 | note | RECORD OF CONFORMITY: This ITP Signed off
5ccee58a-f8e4-5493-b788-8d428473c945 | note | HP*
c2c033e7-cc05-5124-85bf-ce590b14826b | note | RESPONSIBILITY: Fulton Hogan Engineer
d828a34b-a103-5c52-b0e7-aaef53517c61 | textbox | Date Completed:
92e6d5ef-0abd-4e75-abef-df93612e622e | section | Construction of Access Ramp Bluestone Footpath
cbd92a8f-3040-4e97-89f4-c05731d6320b | checkpoint | 2.1 Re-levelling of bluestone kerbing and ramp
9523f9ff-8309-5a80-80d1-9cd3fc3c5693 | note | FREQUENCY: Each Lot
e2f95ded-8e95-5ce9-9deb-75953c61c745 | note | ACCEPTANCE CRITERIA: Bluestone kerbing to be re-installed to new design levels.
63f4ac53-6d06-51f8-a040-8c5ca0e345d7 | note | ○ Bluestone kerb shall be placed on a bed of low slump, 20 Mpa concrete of 75mm minimum thickness.
936e6043-37cc-53f7-b533-50683ee71c8e | note | REFERENCE DOCUMENTS: IFC Drawings, CoM Bluestone Paving Specification
16bda417-00a4-5410-ba25-507c1b32de3a | note | INSPECTION/TEST METHOD: Visual Inspection
397d97bf-7009-56d4-b3d0-0bd60c089abc | note | RECORD OF CONFORMITY: This ITP Signed off
800d9524-c354-5e1d-bfd0-1bec12a5de96 | note | IP
002a64ed-f3b8-5c2d-a526-391e0b520b8c | note | RESPONSIBILITY: Fulton Hogan Engineer
0956f1d3-4a6b-5395-9d3f-953901e28bd0 | textbox | Date Completed:
c2e541c2-526b-47be-9b23-cb6f0d64aa5d | checkpoint | 2.1 Base preparation
fa4eb2b2-0ab8-56e5-a8d3-a9376aef300c | note | FREQUENCY: Each lot
ca71181d-ae55-5f32-9089-17578bbdb172 | note | ACCEPTANCE CRITERIA: Concrete base shall be inspected to be free of foreign materials and water pooling
7eac3eb7-3beb-5575-9a41-1bc870d4c14e | note | ○ After placing and vibration, the concrete shall be screeded and trowelled to the correct level.
643c98db-5d37-5d1d-b009-425f57ef2eaa | note | REFERENCE DOCUMENTS: CoM Bluestone Paving Specification
ed9ddbc3-b657-57b3-a8ab-686636e43bca | note | INSPECTION/TEST METHOD: Visual Inspection
5b700bb5-4862-5266-be42-da9684891d5e | note | RECORD OF CONFORMITY: This ITP signed off
699005c6-4585-5dd1-8dff-5917605ac4fe | note | IP
f9da659f-97cc-5641-ab5c-753ab310f111 | note | RESPONSIBILITY: Fulton Hogan Engineer
00ac7801-5e39-5bd9-868f-dbe2b5723ed4 | textbox | Date Completed:
0664ff95-645a-43ef-9bbf-3e384406ee2b | checkpoint | 2.3 Mortar Bed
a6610512-8c37-5c69-8e9b-de925c8b0b4f | note | FREQUENCY: Each lot
dcebdcb0-0dfe-59ec-8bd4-de3ad12b911b | note | ACCEPTANCE CRITERIA: Mortar shall be applied at average thickness of 30mm to concrete base
a87888e5-7743-58e8-8da5-ffec3085da0b | note | ○ All pavers shall be coated in mortar slurry on rear face before laying
b2b2eb40-5e5d-5b29-b0b6-24020a5fb3f3 | note | REFERENCE DOCUMENTS: Dwg 1P50201
26aaa4c3-305d-5b23-bb01-3c04a6178fdc | note | INSPECTION/TEST METHOD: Visual Inspection
ae3260b0-f808-58c2-b7fc-523fddf164f6 | note | RECORD OF CONFORMITY: This ITP Signed off
1a842656-44cb-5893-8d47-90a2830a2bc9 | note | IP
ca0f3325-512b-56db-adeb-e634b776523b | note | RESPONSIBILITY: Fulton Hogan Engineer
11984962-cd02-5f88-9c52-ff47c167d392 | textbox | Date Completed:
d5a7617a-8cfc-4169-a9f0-d15e7ef0634b | checkpoint | 2.5 Cutting of Pavers
6f3c0378-da8c-577d-a6da-e853881acc69 | note | FREQUENCY: Each lot
43e35302-e214-5300-8441-e8429b60f0dd | note | ACCEPTANCE CRITERIA: Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points
d81d6825-38b9-56e0-ad1a-c710c3223f2b | note | REFERENCE DOCUMENTS: Manufacturers Specifications
e9efd138-abca-5602-9e39-3054a937cf7d | note | INSPECTION/TEST METHOD: Visual Inspection
7c18431a-229a-5e7c-b8b1-1d5c92083d1c | note | RECORD OF CONFORMITY: This ITP Signed off
e02e9c7a-b7e3-58c2-a1f0-94a2cb088333 | note | IP
e3625591-c2a0-52a6-9a1f-389427c1e7b6 | note | RESPONSIBILITY: Fulton Hogan Engineer
aeca074c-f74a-5050-a98f-dde51855888f | textbox | Date Completed:
f0853469-b138-49b1-acb8-2824c4cdd778 | checkpoint | 2.6 Placement of bluestone pavers
630ceae7-d092-5b80-8fcb-5aad2e9a0425 | note | FREQUENCY: Each lot
3a9ffa41-6710-54b1-87ef-67c06875ddbe | note | ACCEPTANCE CRITERIA: Pavers shall be placed in accordance with Dwg 1P50402.
86335f94-b732-5790-86b5-8d7448d97c71 | note | ○ Kerb access ramp wings shall be at an angle of 45° and the ramp gradient shall not exceed 1:8.
051d0250-05de-5ba1-b097-a5e5701401a3 | note | REFERENCE DOCUMENTS: Dwg 1P50402 Dwg 1P50201
8c9e0d28-e11d-5a11-adb3-55a19aff25b3 | note | INSPECTION/TEST METHOD: Visual Inspection
0e738ee3-754a-549c-a43f-38a9dfbc8c15 | note | RECORD OF CONFORMITY: This ITP Signed off
49153495-b5a6-5c23-8fdd-1ea986d67951 | note | HP*
54bc5f05-32ec-52b0-ad9e-ade94582fc78 | note | RESPONSIBILITY: Fulton Hogan Engineer
aab442c6-4d65-5d20-832e-4725fce58f58 | textbox | Date Completed:
70d9f0f1-4807-431a-937d-3a7ea3efefa1 | checkpoint | 2.7 Curing
1522639b-cb42-5d57-a6d6-716c3a23d511 | note | FREQUENCY: Each lot
e47ea67c-8eb7-5120-b4d6-143669c873a1 | note | ACCEPTANCE CRITERIA: Pavers shall have >24hrs curing time prior to light traffic
a37f9813-48b0-5afa-ac19-a33ba96a44aa | note | ○ Where required, ply shall be laid over area of works
18049cb2-de4b-53b2-aa88-11be36f5858a | note | REFERENCE DOCUMENTS: Manufacturers Specifications
bec1e583-eb77-5a9e-8bd8-2cb304e38042 | note | INSPECTION/TEST METHOD: Visual Inspection
1edbdfe1-395e-5da5-b4a4-94a238dacdf8 | note | RECORD OF CONFORMITY: This ITP Signed off
6be0be4b-e611-5566-8267-dea783edf881 | note | IP
92617f29-c35f-59f2-97e8-6dc85f81e348 | note | RESPONSIBILITY: Fulton Hogan Engineer
9be7201d-1040-5766-bc21-778da15227ec | textbox | Date Completed:
8aa4b206-666b-409a-ac3c-5954ce0aec4b | checkpoint | 2.8 Grouting
480f9369-14b5-5be4-8d21-eadb4ca0e931 | note | FREQUENCY: Each lot
bde3149e-754b-55df-a2ec-f92bd7a0507a | note | ACCEPTANCE CRITERIA: Pavers shall be grouted using agreed colour and mixture
f98358e2-1926-546c-ad18-a18955bf6904 | note | REFERENCE DOCUMENTS: Manufacturers Specifications
83a72b24-a277-5de6-8ae4-f727b90446e1 | note | INSPECTION/TEST METHOD: Visual Inspection
463a3c87-2e5b-5496-a223-46741022b056 | note | RECORD OF CONFORMITY: This ITP Signed off
642047e5-195e-59e7-992e-b03a9a1b76d5 | note | IP
70fd4bd3-98a0-5da7-a32f-36a9eca73d11 | note | RESPONSIBILITY: Fulton Hogan Engineer
cbc9202b-0a0e-5cf7-bc94-3944dd0bb40c | textbox | Date Completed:
6c496ad5-b51b-4889-827d-3108a8e418bc | checkpoint | 2.9 Installation of Versatac Granite Tactiles and Granite Inlay
3dde9f8b-16af-55fd-a398-c293e27333b6 | note | FREQUENCY: Each Lot
fdae0445-9161-5bc1-957d-578e17b4f3d7 | note | ACCEPTANCE CRITERIA: Tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201.
83b59d01-c450-5a70-a4fb-873061cbfe1c | note | REFERENCE DOCUMENTS: Dwg 1P50201
8ae480df-a673-561d-8f8f-6b129051b6b2 | note | INSPECTION/TEST METHOD: Verify
17cdb523-2534-5c66-a288-19987bb406e6 | note | RECORD OF CONFORMITY: This ITP Signed off
9de3efd8-f81d-55b5-a6f9-8261babb23c5 | note | IP
85f8c81a-0eab-57bd-96ac-a04edbca1c6f | note | RESPONSIBILITY: Fulton Hogan Engineer
79310833-53ab-5f6d-8942-b92b8044708a | textbox | Date Completed:
240bb1ad-f9a6-4f3a-9b03-92063eb49472 | section | Completion
ee2ab15a-646f-4ae9-bb2c-7e166bbfff7c | checkpoint | 4.1 Completion
1466bd68-8bff-5d1a-9bfd-253c4cd0248f | note | FREQUENCY: Each lot
56ed3b3c-b589-55e0-8557-a8dd80a81a7d | note | ACCEPTANCE CRITERIA: Pavement area is free of debris and waste
0eed5410-8bd5-54bc-8f44-9ec65b8b4011 | note | ○ Bluestone pavement is free of mortar stains and cleaned to satisfaction
6e670533-7ff3-55e1-8c32-817e6e409261 | note | REFERENCE DOCUMENTS: Visual Inspection
280f5dc1-fc6b-5802-8341-705686c1ecbf | note | INSPECTION/TEST METHOD: Visual Inspection
ee247128-6f12-51bb-b3af-635d3fe85fe6 | note | RECORD OF CONFORMITY: This ITP Signed off
daae1b39-d170-5522-8982-e362ebb39734 | note | HP
b520f708-a05d-58bc-8d50-f65a16147581 | note | RESPONSIBILITY: Fulton Hogan Engineer
ec771ab0-2a9b-5b2b-9008-1ea38a36351a | textbox | Date Completed:
60f03fce-eb72-4515-b80f-5cb8fc9a36e5 | signoff | AUTHORITY HOLDPOINT
2c2ad1b3-eaa5-4abd-a640-49dd24b5500e | checkpoint | Final Inspection
38abde15-7bf6-5cbb-91c7-a66b481f967d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
af5779be-b4ae-570c-a969-3497f1f3cc01 | textbox | Print Name:
8b5f5834-2651-5bc8-a137-114b9751a02e | textbox | Position:
06be736d-b117-5353-88ae-032e01f0ff33 | textbox | Date: