## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
253b3841-5a1d-4d26-9dc3-026a9f629286 | checklist | ITP-004 - Subsurface Drainage | itp | ITP-004 - Subsurface Drainage
96768e7e-ec60-4a0f-b9bf-0379406e4107 | section | Preliminary Works
cba90eed-1a6e-4cbc-996a-a8c841ed5686 | checkpoint | 1.1 Check for correct documentation
f2d97ebb-119c-567c-96d7-db0ee8c7b2c4 | note | FREQUENCY: Prior to commencing any activity
9fd36af9-5cf9-5fa4-ac48-33e620053fe4 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
971a52ff-9621-5ebf-8960-b127461878df | note | – using the correct and complete set of drawings
dcb92054-2452-56d5-bbec-5a5ed565a04d | note | – all drawings are the latest revision
d8621f7d-4adb-5f07-9dd9-d9e9881601b4 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
69335422-c195-53ea-8863-8ced0580bde0 | note | INSPECTION/TEST METHOD: Visual inspection
298d3dbf-b2ef-5fc5-a1a8-bd1a11be1a35 | note | RECORD OF CONFORMITY: This ITP signed off
202ead1d-5d05-507f-9fc1-4073a83abb80 | note | HP*
821fab81-4064-5a2e-bb5e-2b018474178a | note | RESPONSIBILITY: Site Engineer / Site Foreman
d996268d-af42-5d42-a96a-2643f8c0ed05 | textbox | Date Completed:
b034bcff-0eec-4a60-9394-2a907af3ceb3 | checkpoint | 1.2 Implementation of all measures and controls
3f2e22bd-ac92-5445-8688-d4d5882e9538 | note | FREQUENCY: Prior to commencing any activity
66a85fcd-294c-56f0-ac67-35b8c4168f68 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
eda8d7fc-8c1e-542c-a230-9417ec330943 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
272e17da-6bca-59a8-8162-e1c083f51747 | note | INSPECTION/TEST METHOD: Document review
426140f5-de9e-5d94-a112-e2b83df228a4 | note | RECORD OF CONFORMITY: This ITP signed off
e765e1f2-f758-5b97-b212-cfd67077b181 | note | HP*
ba07a038-be74-5fd9-b12c-0f6d28a5471f | note | RESPONSIBILITY: Site Engineer, Site Foreman
02dbd386-7827-5d12-b4bc-a9726f6d22ff | textbox | Date Completed:
af1e8bd7-71d7-486f-af8b-de26c2b07d3c | checkpoint | 1.3 Material Classification
bf52396a-bf19-5fd9-9ffa-bfbd888fada1 | note | FREQUENCY: Each Lot
39c73eb7-42cf-5697-bf9d-ad9d922b060f | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes: (behind bluestone wall) 100mm DIA Class 1000kN/m/m corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
cdd0a5b3-a910-54ae-b4f7-25f1426505d4 | note | ○ Subsurface drainage pipes: (in soft landscaping area) 300mm wide megaflo
296f702f-8565-5147-b07f-a28475314ed1 | note | ○ Granular filter material for bedding and backfill: Trench backfilled and bedded with specified material on drawings (clean washed coarse sand for megaflo, 20mm screenings for behind bluestone wall)
9e4c09ad-2999-569d-9a35-823d3bf82f8a | note | ○ Geotextiles: Shall comply with Cl 702.06.
fe9b99c9-2981-52ee-83a0-02fe560da36b | note | ○ Flushout risers: constructed to the detail of SD 1631
9cdc7b8d-68c4-55f8-83dc-dc4224e4b4ec | note | REFERENCE DOCUMENTS: 702.04, 702.05, 702.06
1228ee77-9a04-5f24-9afc-8abfb85ee9dd | note | INSPECTION/TEST METHOD: Verify
f256adef-92b2-50ec-93ba-3bad7e650bc3 | note | RECORD OF CONFORMITY: This ITP signed off, Delivery dockets, product spec sheets etc.
6c95ad8d-1ea2-54b3-a52b-d50c75e31332 | note | WP
cc84038e-e39e-5d28-ab7f-011f86652b33 | note | RESPONSIBILITY: Site Engineer
055b871b-2d8a-5940-8ba3-3884ab0f4723 | textbox | Date Completed:
fa1ae911-a7d9-4f17-8b9c-61fffa0bfc23 | section | Construction Works
afd37089-32c2-4b63-b70c-4a6ff4d9f2cd | checkpoint | 2.1 Excavation Permit
83a3c8ec-232b-586c-9cb2-49def3162f8f | note | FREQUENCY: Weekly, per operator
c2d3dfbb-d0aa-52f5-818c-6192226a0781 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
450d9568-a2cb-5276-a1d8-e43c108c4064 | note | ○ Plant and equipment shall be appropriate for the task.
ec9d2bf8-7f3a-5f6e-a992-f0e6cf837e68 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
9c78bd07-568a-5f6c-99eb-1ef831558fb6 | note | REFERENCE DOCUMENTS: Excavation permit
d8941c61-6d9d-5439-a0ca-85e72dff4928 | note | INSPECTION/TEST METHOD: Verify
383417d3-3736-527f-a157-c14ddc36b591 | note | RECORD OF CONFORMITY: ITP Signed
4421da55-37c8-57ff-a2a5-fc8925c141ba | note | HP*
d6c56673-5ac4-5690-9796-dfbf4f328259 | note | RESPONSIBILITY: Site Engineer, Site Foreman
4ff9bdb5-a0d1-59f7-8fdb-77fb7f1ce510 | textbox | Date Completed:
9b9d5797-effa-4922-a549-b509f4c6257b | checkpoint | 2.2 Excavation of Trench
2a61144d-0e2b-533e-9aea-c9a71a23e0f1 | note | FREQUENCY: Each Lot
40b8cb9f-a993-5dec-8492-2cb5c0a79a31 | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed.
5f45cf89-0b79-544f-a035-fcfddc3a6179 | note | REFERENCE DOCUMENTS: 702.08
286bde25-ee36-5b70-9fa4-655832cef9f6 | note | INSPECTION/TEST METHOD: Visual Inspection
1258292e-4e92-52c8-b8e8-4597f31f67ee | note | RECORD OF CONFORMITY: This ITP signed off
c9dad189-91d9-5039-9b77-c140492631c0 | note | HP*
1f4b687a-7cca-5c31-9517-6dd8fb2ca8dd | note | RESPONSIBILITY: Site Engineer
34a08e18-e6b3-51e3-a28f-b28c2ce1592b | textbox | Date Completed:
77abe4f1-f7e7-49ed-a541-b0ce2dca77ac | checkpoint | 2.3 Placement of bedding
de27901d-0d37-5d4a-9c12-12dc4dc3325b | note | FREQUENCY: Each Lot
5d67283a-6fa8-541c-bbdb-97351bab97b8 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material, sand or screenings placed across bottom of trench and screeded or graded to level
7e79472f-bb95-542a-931e-b674c0655a1a | note | REFERENCE DOCUMENTS: 702.09 (c )
6ab10106-c42a-505d-8648-3cca315416ba | note | INSPECTION/TEST METHOD: Visual Inspection
70a84da1-b6be-57d7-8da6-5ea7227ced44 | note | RECORD OF CONFORMITY: ITP Signed, Photos
1f1acec0-70f6-554e-9084-36426eaa7130 | note | IP
374d33c5-160c-56aa-98ec-71236a3fca32 | note | RESPONSIBILITY: Site Engineer
52134def-5faa-50d5-a8ea-19c0c2604616 | textbox | Date Completed:
729ccaa8-11fb-4f61-81d1-aa695244b317 | checkpoint | 2.4 Placing pipes and geofabric (if required)
5d0459eb-3d53-518b-a756-595c4fe673e7 | note | FREQUENCY: Each Lot
17f55c23-a591-50ea-8cba-93d3ebadd578 | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
af53b4e4-92af-5e55-86d0-685f04f236a3 | note | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum 150mm lap of geotextile used for wrapping.
ef6e3bc7-b7c0-5cbb-a92d-11a8c8aacb88 | note | REFERENCE DOCUMENTS: 702.09
07782968-0dd0-5402-94ef-bff191104f5f | note | INSPECTION/TEST METHOD: Visual Inspection
60516dee-c0ae-55d4-80df-9c8ad6a1b070 | note | RECORD OF CONFORMITY: ITP Signed, Photos
f6ce6ff4-b08e-5bc1-8660-74387bdcadfb | note | IP
68e2f400-d15b-5db5-8506-533b1287a36b | note | RESPONSIBILITY: Site Engineer
a00519ca-da4b-5ae2-b11c-4d6c3390fcc9 | textbox | Date Completed:
99ec03fb-7074-4712-a3c3-508ce950443c | checkpoint | 2.5 Placement of backfill
a5e1eb90-2cd4-5770-ad79-3e006e05df42 | note | FREQUENCY: Each Lot
466ca703-9c1d-5de2-8e51-0e612ba780c8 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
aec5cf5f-2863-5e27-8e59-41ebfee9c7c2 | note | REFERENCE DOCUMENTS: 702.09 (g)
d1ae6976-9c4c-5824-ba0b-68b24c34067f | note | INSPECTION/TEST METHOD: Visual inspection
21fd776f-e9bb-5c30-b6b4-f228c073901d | note | RECORD OF CONFORMITY: ITP Signed, Photos
8a948a76-5961-573d-993c-69ff370f7402 | note | IP
8f5dc749-dee9-5b52-b292-7b95ff19a402 | note | RESPONSIBILITY: Site Engineer
27c23095-3dc2-5a2d-9995-de5f4a527875 | textbox | Date Completed:
e8f27fdd-c8ab-4d56-9338-1090eaa7e493 | checkpoint | 2.6 Flushout risers
ba2b82cd-7db2-5617-8e30-c2d083c83e35 | note | FREQUENCY: Each Lot
8019dfc9-286e-5e2f-97a9-6efce31d9fe0 | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
cab57183-d61b-530c-ade8-247989294a26 | note | REFERENCE DOCUMENTS: 702.1
53f1b387-7400-50e6-8c8d-27c7814405af | note | INSPECTION/TEST METHOD: Verify
732c180a-e49f-5995-8c4c-91fcd500c922 | note | RECORD OF CONFORMITY: ITP Signed, Photos
eb91a165-041e-5252-9feb-a9b3fee2ba11 | note | HP*
019a167f-60a4-5c43-97d6-c614469ef4b5 | note | RESPONSIBILITY: Site Engineer
a74da8a3-4893-5c0c-8fe3-a8c6ab432b4a | textbox | Date Completed:
28442f0d-2801-45dd-bc43-bff395b5e8fb | section | Testing & Completion
614251fe-16f1-48c4-b5e8-aacdccb5e113 | checkpoint | 3.3 As-built
84e84f6e-ca01-546c-a058-920b225c10a9 | note | FREQUENCY: At completion of job
16d2545e-c86a-5285-b470-bbfb9cc4f223 | note | ACCEPTANCE CRITERIA: Licensed or competent surveyor to provide plans showing location and cover level of fits, bearing of side entry pits, and pipe inverts.
1dcb3e82-b280-59bc-ad1d-622f85def197 | note | REFERENCE DOCUMENTS: Project tech specs 14.4.3.a
7291aee3-5a24-50ec-b900-12590e6f09d9 | note | INSPECTION/TEST METHOD: Document submission
65b54989-d44e-5ea5-ab54-b3496cda4bab | note | RECORD OF CONFORMITY: ITP Signed, As-built plan
0d8d5012-123f-5edc-b3de-9a6b0b579987 | note | HP
1ba2e0e1-40b7-512c-9edb-52dee7a110bc | note | RESPONSIBILITY: Client, Site Engineer
bc214a6e-5d02-531d-8d49-0e17b00c5370 | textbox | Date Completed:
c8c71327-c4bf-413e-8534-07f489c44401 | checkpoint | Final Inspection
2f5a3170-87a3-599b-8bcf-634362f8ae32 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1ee1da20-195e-543c-81f0-a2a347e6e582 | textbox | Print Name:
38d739ec-1ba6-5799-a741-8655a7a862b0 | textbox | Position:
d8fdde86-e489-5e89-83d8-26cabc9592f2 | textbox | Date: