## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
246215e0-3db9-4f74-92c3-6f65f4e74bdd | checklist | ITP-005 - Tree Pits | itp | ITP-005 - Tree Pits
a3d1f3b8-a341-46b0-bd3e-de46755ba370 | section | Preliminary Works
db98e7ea-4118-4322-bd07-3b2ac18b6c76 | checkpoint | 1.1 Check for correct documentation
9a7bfa0e-f55e-5179-8732-55fddf88c5a0 | note | FREQUENCY:
4bedb7f2-8b0a-5150-9d17-7c65682dbc22 | note | ACCEPTANCE CRITERIA:
75969f09-08ae-5cdd-8486-9d708ae1650e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
431e8e07-7f42-5a74-ab7a-9337db694184 | note | INSPECTION/TEST METHOD: Document review
8255619f-f804-54b9-807f-0a41a4a42a40 | note | RECORD OF CONFORMITY: This ITP signed off
a4331385-d56b-59ee-bf16-886aa693ad31 | note | HP*
336e651a-cfc5-5799-938c-2f0847aa7221 | note | RESPONSIBILITY: Project Engineer
3207551f-0c48-5acc-8fa4-f672e3189047 | textbox | Date Completed:
5803c277-c161-4434-91ec-ebdb2864e0e1 | checkpoint | 1.2 Implementation of all measures and controls
8d968c26-3cce-5c40-b1d5-cf24d2388cc0 | note | FREQUENCY: Prior to commencing any activity
b7df100c-8612-5b35-9d29-555beacc238a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
71474802-be49-554e-9d98-cd44f348747b | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
4bf9adb2-42c4-5418-836e-d27bb495b407 | note | INSPECTION/TEST METHOD: Document review
8db25d7e-f8b8-532a-b059-4885fe027164 | note | RECORD OF CONFORMITY: This ITP signed off
5ecbd14a-1c08-5240-896b-fb06f8ee0bc4 | note | HP*
0efe8ea3-bbef-502c-b067-fc9abd7b6592 | note | RESPONSIBILITY: Site Engineer, Site Foreman
7c547c88-22a3-5887-8141-c8dc3a00c4a7 | textbox | Date Completed:
fde8887c-ca71-46d8-8de8-975176db2f13 | checkpoint | 1.3 Precast Materials acceptance
535a9c46-eb95-5d8f-9878-228ad0ecefd5 | note | FREQUENCY: Each Delivery
b10d9489-bd05-5601-bff5-89d814f830fe | note | ACCEPTANCE CRITERIA: Precast kerb inlet blocks and pit grates and frames shall comply with Design Standard 304.4, and City of Melbourne drawings 1P 50305 and 1P 50320.
c328dc9f-e037-51ec-89f1-b496613a4bb4 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
f5310983-37e2-5dc7-86a4-f6b82ba5bf1c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 610, City of Melbourne Standard Drawings
2df48d8f-476b-536b-8584-316bf8838a1e | note | INSPECTION/TEST METHOD: Visual Inspection, Verify
bdfcbc1a-96ae-56c7-9173-e48c75b1a98f | note | RECORD OF CONFORMITY: This ITP signed, Manufacturer certificate or accreditation
8f7cef8c-a4e0-5925-a333-a61a3d21c063 | note | IP
27b78785-f0b1-527b-88b4-288b7b12d4f9 | note | RESPONSIBILITY: Site Engineer
16c3a1cb-c585-50ab-8438-ce6978226195 | textbox | Date Completed:
a8f3fec4-227d-4fa1-9f9c-b9488c1cea0d | checkpoint | 1.4 Material Classification
6794a4ce-6908-596b-b1de-2cb7d3fec59a | note | FREQUENCY: Prior to start
a576dd0b-ffa8-5eb4-a9d7-f234596644c5 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
7861317d-7171-501a-ba57-fe1a1fb7381a | note | ○ Drainage Backfill: 5mm screenings
22a85b18-3dfc-51a0-81e0-d5294863b226 | note | ○ Transition Layer: Sand/Coarse Sand
a3c78752-9fcb-5452-aff9-9620bfce906c | note | ○ Filtration Layer: As confirmed by the client (TBC)
f2aa38cb-0ea4-51e5-9267-7252805ad4e7 | note | ○ Drainage pipe: 100mm AGI pipe (no sock)
c77655b7-1713-554d-bd95-a2b4e37105bc | note | ○ Flushout pipe: 100mm PVC solid pipe with screw cap
022a7ce0-b52d-5d7e-ba44-e64152a6c64a | note | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092, Project Drawing CI-00080
ebf29736-b1c7-55c5-bb53-6ef604c70d65 | note | INSPECTION/TEST METHOD: Visual Inspection
a3b21196-f356-517d-85b0-22484444d385 | note | RECORD OF CONFORMITY: This ITP signed off, Delivery dockets, product spec sheets etc.
da6af15e-b830-5cad-8fa2-63cbc28c4c06 | note | WP
63bfd2e8-fe34-55c0-acaf-9f8e24523232 | note | RESPONSIBILITY: Site Engineer
3b105e78-fde5-53ac-b820-43b2a9e5229a | textbox | Date Completed:
8829eef9-505d-4046-a3ec-c6728ebd2713 | section | Construction Works
46a14377-4a2d-4251-835c-fef94c038005 | checkpoint | 2.1 Excavation Permit
372273e8-bef1-5b09-9601-81e463dcbf53 | note | FREQUENCY: Weekly, per operator
16baeddb-280e-5106-b6e4-201d6af6e45e | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
004af7e2-e33b-5422-9a67-fd7c125e023e | note | ○ Plant and equipment shall be appropriate for the task.
317dec31-7cfb-58b9-a67c-ec9c3ce2be8a | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
7b96eb8d-3e12-56eb-8a7a-1ea4be0d49e9 | note | REFERENCE DOCUMENTS: Excavation permit
6919beff-d792-5cd3-970b-35e211bdad88 | note | INSPECTION/TEST METHOD: Verify
1b535283-a408-5955-9cee-b4283a1239c9 | note | RECORD OF CONFORMITY: ITP Signed
6bb05dd4-5c98-51d8-aefc-880bf980063a | note | HP*
72a73181-7078-5396-8f1c-43e985c26454 | note | RESPONSIBILITY: Site Engineer, Site Foreman
a18cc168-7883-5cc0-bae6-bd61fe515b34 | textbox | Date Completed:
f19a2c3a-d9ba-43a9-9ae2-36ae048b68a2 | checkpoint | 2.2 Set out pits
f56d03bd-5985-5f18-9cd4-b0dea65dbe9a | note | FREQUENCY: Prior to start
65914eb3-0cbe-5c43-b9bf-7e5fcc9ce747 | note | ACCEPTANCE CRITERIA: The position of all pits are to be confirmed with the superintendent.
24376009-0a11-526b-a235-b30d40454eb2 | note | ○ The inverts of all outlets are to be checked to ensure there is sufficient flow to the downstream system and that there are no service clashes.
74df81d9-38a9-56a9-80d0-632b8c42ee15 | note | REFERENCE DOCUMENTS: Drawings
c57435a0-dad4-5d25-8323-5a8337dba67e | note | INSPECTION/TEST METHOD: Visual Inspection
4b0249b6-0124-58c4-b705-9cb4aeaa0643 | note | RECORD OF CONFORMITY: ITP Signed
6c2be9d2-84fe-58c8-96c8-283f1a20f842 | note | HP
a498a79d-9a3c-5ef7-a75e-13fa76cc46bf | note | RESPONSIBILITY: Client Site Engineer
8840efc1-a724-5493-8f1c-8d45d50bd81f | textbox | Date Completed:
ae155de9-3a5e-4d28-98bb-a60d8a3a45a4 | signoff | AUTHORITY HOLDPOINT
74c2f090-7c9a-4aa2-b204-a81dfeefe70d | checkpoint | 2.3 Excavation
d48fe5ac-3454-5458-8cbe-db7f02345167 | note | FREQUENCY: Each Pit
42523c16-e4dc-58c9-a3d1-d1ce996326d0 | note | ACCEPTANCE CRITERIA: Excavation is to be to sufficient depth to allow for backfill layers to be placed at the required thicknesses.
70eb21ae-9821-5f7f-b4aa-13e2b099c4f8 | note | REFERENCE DOCUMENTS: Drawings
b40c448c-2be4-52a0-84f2-6eb29dfae4a0 | note | INSPECTION/TEST METHOD: Visual Inspection
5d113685-4ada-579c-a892-781a82033e19 | note | RECORD OF CONFORMITY: ITP Signed, Photos
f37f04ee-6c53-5c8c-87b5-ac3125da6bf4 | note | IP
48f4c163-d7a4-522f-8a16-1ff40042f530 | note | RESPONSIBILITY: Site Engineer
f0e7a54e-497d-5930-8043-2651405f226f | textbox | Date Completed:
4a643003-5680-458e-bb30-351b6068a4cc | checkpoint | 2.4 Placing pipes and geofabric (if required)
c381cd78-22f9-58c4-91ee-e3446bdf6a65 | note | FREQUENCY: Each Pit
3e4993f6-4181-5378-89ef-8ad50fdd40fc | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
e920fcce-f14d-582c-a199-707bcc115ef6 | note | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum 150mm lap of geotextile used for wrapping.
4cbdf134-deef-52fd-8047-8daf27c77311 | note | REFERENCE DOCUMENTS: 702.09
24c144b7-95ed-5e21-81b0-4c0177c90acc | note | INSPECTION/TEST METHOD: Visual Inspection
1aba6f21-a9c2-5ec1-87f7-da1d58c81a7c | note | RECORD OF CONFORMITY: ITP Signed, Photos
445c1139-7ca3-578e-aac0-2e48e6220cf2 | note | IP
99ce3b81-f1ba-50cf-8dcf-9530a3d36f6c | note | RESPONSIBILITY: Site Engineer
fcbcaa8f-c1be-5215-bfd6-1fc20ba92346 | textbox | Date Completed:
dfb6e66a-e628-486b-bbda-c7592f41a76c | checkpoint | 2.5 Placing drainage, transition and filtration layers
a005958a-f517-50ca-8201-00abf84af6cd | note | FREQUENCY: Each Pit
5e41d760-0387-503b-bd72-8fdd73eac155 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes.
54cce5ec-3fc6-5459-8a84-a32539ce4f36 | note | REFERENCE DOCUMENTS: 702.09 (g)
01699a3d-9058-5213-863e-0927642efce7 | note | INSPECTION/TEST METHOD: Visual inspection
129418a0-7577-521c-b3f8-5214371bbb05 | note | RECORD OF CONFORMITY: ITP Signed, Photos
8ffdf05f-01fa-5986-beaa-fb8b29820b1e | note | IP
9fef6a86-b877-51a2-ae0c-07ca7e727209 | note | RESPONSIBILITY: Site Engineer
55bbdf46-1d77-5abe-b662-1a8fb322df09 | textbox | Date Completed:
10ddad98-f481-4d87-b752-b1566efcbb09 | checkpoint | 2.6 Placing structural soil (if required)
7eb3e579-f55d-55b8-a891-397ff08f8130 | note | FREQUENCY: Each pit
03f403bd-b61b-5fbe-a51b-cd77c66af360 | note | ACCEPTANCE CRITERIA: Structural soil placed and compacted in layers. Volume as per IFCs.
6f15752d-75cb-52ef-8401-0958f23fdc18 | note | REFERENCE DOCUMENTS: Drawings
11de4cdb-6fe1-5231-b69d-8448910c5bcd | note | INSPECTION/TEST METHOD: Visual Inspection Survey Volume
4fd0d493-9879-5aa2-ad50-daa8434d5526 | note | RECORD OF CONFORMITY: ITP Signed
d5993d47-4a68-5a1f-8ef5-403a2487eb5a | note | IP
ccfef117-b876-5d42-a4af-263c16364ef7 | note | RESPONSIBILITY: Site Engineer
ad912dbd-9566-54f3-b41d-421c5fe52484 | textbox | Date Completed:
99d33c7f-0d7c-4aa8-9418-d78facee47e7 | checkpoint | 2.7 Flushout risers
fe479e14-c4ab-5a41-a3cc-d604a0fd99b1 | note | FREQUENCY: Each Lot
cce9f211-25af-575a-82b9-da2b2d8651cc | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
57f7e311-8aa6-5288-b7e3-4d5626032c41 | note | REFERENCE DOCUMENTS: 702.1
dbad4917-26b4-5d6b-b7af-1027ee2c6a66 | note | INSPECTION/TEST METHOD: Verify
81aa359c-c224-5d3e-a289-347ae154821a | note | RECORD OF CONFORMITY: ITP Signed, Photos
648e6877-12cf-579c-8d20-e0bb7882093c | note | HP*
563bb7ea-b584-5d59-b193-c7c85d682ade | note | RESPONSIBILITY: Site Engineer
710608e8-c6d2-578d-84b0-5f472a9c68a0 | textbox | Date Completed:
172182ab-28c5-4082-a7ca-373b17c76f69 | checkpoint | 2.8 Place and set side entry backing block, grate and frame
5e4d3cdc-9595-539d-aefb-1089889b4efe | note | FREQUENCY: Each Pit
3e281f31-c904-5a5e-b301-61e680d6113f | note | ACCEPTANCE CRITERIA: Entry blocks, grates and frames must be set to within ±10mm of the design levels shown on the drawings and In accordance with the relevant COM standard drawings.
b98fcf1a-0445-5258-93dd-d67d87720b89 | note | REFERENCE DOCUMENTS: City of Melbourne drawings 1P 50305 and 1P 50320.
731ba150-7e71-5335-a1df-269b19baa2a5 | note | INSPECTION/TEST METHOD: Visual Inspection
1c408c4f-2421-5ddf-9d83-6360c0b99ecf | note | RECORD OF CONFORMITY: ITP Signed, Photos
1c8257fb-f96f-5d7e-9f4c-2e4b566c7f8b | note | IP
4105b3b4-bf0c-576b-ac91-e8c0f2f705b5 | note | RESPONSIBILITY: Site Enginer
f4a6fe31-3d91-5e69-8b76-969f1797c3fe | textbox | Date Completed:
c45775e8-7b64-4d79-b17d-68a03dc69d9f | checkpoint | 2.9 Place tree guard and grate for bioretention tree pit
18b071a7-c3a1-5ab7-a280-32f071528e40 | note | FREQUENCY: Each Pit
661154fb-a66b-52e9-8db9-a905ca6e9061 | note | ACCEPTANCE CRITERIA: Guards and grates must be set to within ±10mm of the design levels shown on the drawings and In accordance with the relevant COM standard drawings.
bb9e7e03-6e04-5fb1-b80e-b07c56ca7f81 | note | REFERENCE DOCUMENTS: City of Melbourne design standard 706.03
6aa1f5f7-8c2a-5597-8ca6-ec2ad1e8912a | note | INSPECTION/TEST METHOD: Visual Inspection
3e68b594-9f95-5cb0-983f-c2f9f9b296b9 | note | RECORD OF CONFORMITY: ITP Signed, Photos
585902a6-7207-581b-949c-e6ffafebd102 | note | IP
90258878-564d-5d82-85e0-374e6416924d | note | RESPONSIBILITY: Site Enginer
aaea2d80-803c-5081-9f27-4a9abfb2194b | textbox | Date Completed:
9ce6d845-46e7-44b6-b3d7-fe5804fab849 | section | Testing & Completion
717256e4-5d1d-4506-a536-171176902740 | checkpoint | 3.1 As-built
d497a767-59bb-5eb1-9a0d-f7128e7f1ca6 | note | FREQUENCY: At completion of job
9d4692b6-1f28-568f-be25-6fc8f12f2de3 | note | ACCEPTANCE CRITERIA: Licensed or competent surveyor to provide plans showing location and cover level of fits, bearing of side entry pits, and pipe inverts.
3af83ad4-90eb-52fa-a1bc-71064a726ca3 | note | REFERENCE DOCUMENTS: Project tech specs 14.4.3.a
1d930bd7-20b9-581e-8688-6b2448927c0e | note | INSPECTION/TEST METHOD: Document submission
f3f64aa7-b5df-5d5c-bbd1-52d91ae8ed5e | note | RECORD OF CONFORMITY: ITP Signed, As-built plan
69bf40bf-18d1-56ac-a0bb-7336ef9a7c52 | note | HP
936d80b0-99a9-50ba-8809-8706b306dc4c | note | RESPONSIBILITY: Client, Site Engineer
8a80c841-cd72-53a8-a827-5c8ce27a1e11 | textbox | Date Completed:
a66557d5-99c7-414a-b8c1-bb56128450a2 | checkpoint | Final Inspection
ab7418e4-b1d6-58b0-977b-f6c9a11d6710 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d6200746-3f14-5933-bc81-ba7ce1ba2471 | textbox | Print Name:
d739c3fb-78ad-54d4-89e3-13fdffdb605c | textbox | Position:
95d41f51-2e93-5777-82e3-ef7a43723eac | textbox | Date: