## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | External Hebel Wall |  | External Hebel Wall | 72c3cd83-71f9-4fb9-a420-79aa1290ce83
| section | Details
| checkpoint | Angle/sarkingor rab board/top hats in place
| checkpoint | Cut treatment - Hebel and top hats - Zinc Rich 1P, 2 - top hat spacing per Façade eng. Designing Site inspection required befoe panels installation
| checkpoint | Hebel panels Alignment
| checkpoint | Ensure Hebel power panel finish are as per the finishes shown on project drawings and elevations
| checkpoint | All sarking /rad board has been installed as per manufacturers recommendations
| checkpoint | All fixation details should be hot dip galvanized, 2 - All fixing to be sealed, 3 - Air Vapour barrier (Sarking or RAB) joints should be sealed and taped tightly.
| checkpoint | Sarking/RAB overlap flashing by min. 150mm, 2 - flashing-to-flashing overlap by min. 200mm in both sides
| checkpoint | Flashings are installed correctly, are continuous and free of any imperfections
| checkpoint | Ensure hebel installed plumb and level with adjoining surfaces
| checkpoint | Window seal cuts to be neat & consistent
| checkpoint | Hebel Panel cut treatment reiforcement - Zinc Rich 1P
| checkpoint | Ensure hebel panels are in full and not cracked
| checkpoint | Ensure on site routing of panels to be perfectly straight and level
| checkpoint | Enure control joints have been installed in accordance with manufacturers specifications and installation guide
| checkpoint | Hebel expansion joints have been installed and are consistent including slab junctions
| checkpoint | Weep holes have been installed correctly and at correct heights and spacings
| checkpoint | All Hebel walls line up with elements above
| checkpoint | Insulation installed as per AS/BCA (party walls + external)
| checkpoint | Panels finish(patches done)
| checkpoint | Fire-rated caulking and sealing (Junctions should treated with Sealant and backing rod - for both top and bottom junction)
| checkpoint | Satisfaction and sign off from CSR inspection (Provide report to ALAND)
| checklist | Plastering & Internal Hebel |  | Plastering & Internal Hebel | c1ca2b10-51a7-4b58-9335-a3bb85d7df0d
| section | Framing
| checkpoint | All frames/studs set out correctly
| checkpoint | All frames plumb and square
| checkpoint | Fix to structural members
| checkpoint | All window and sliding door openings are as per plan and line up with above elements.
| checkpoint | Nogging all installed correctly
| checkpoint | Plywood installed to all wet areas to adaptable units
| checkpoint | Door frames fixing
| checkpoint | Studco/Rondo Supplier inspection (Provide report to ALAND)
| section | Internal Hebel wall
| checkpoint | Angle/sarking/top hats in place
| checkpoint | Hebel panels Alignment
| checkpoint | Ensure hebel installed plumb and level with adjoining surfaces
| checkpoint | Ensure hebel panels are in full and not cracked
| checkpoint | Enure control joints have been installed in accordance with manufacturers specifications and installation guide
| checkpoint | Hebel expansion joints have been installed and are consistent including slab junctions
| checkpoint | Insulation installed as per AS/BCA (party walls + external)
| checkpoint | Panels finish(patches done)
| checkpoint | Fire-rated caulking and sealing
| checkpoint | Satisfaction and sign off from CSR inspection (Provide report to ALAND)
| section | Plasterboard for Walls
| checkpoint | Ply nogging
| checkpoint | Rough-in sign off
| checkpoint | Insulation installed as per AS/BCA
| checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
| checkpoint | Villaboard to wet areas ONLY
| checkpoint | Plasterboard Lining to be installed at full height (leaving Gaps is not allowed especially in lobbies/common areas)
| section | Plasterboard for Ceiling
| checkpoint | Confirm Ceiling height
| checkpoint | Confirm Access panel location
| checkpoint | Ceiling frame work
| checkpoint | Ceiling bulkheads where required
| checkpoint | Pelmets (use of MDF only)
| checkpoint | Ceiling insulation as per AS/BCA
| checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
| checkpoint | Villaboard to wet areas ONLY
| checkpoint | Ceiling plasterboard Lining
| section | Setting & Sanding
| checkpoint | Angle /LB/P50 install
| checkpoint | First coat setting
| checkpoint | Second coat setting
| checkpoint | Final coat setting
| checkpoint | Sanding
| checkpoint | patching
| checkpoint | Defects
| checkpoint | Final Inspection