## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Plastering & Internal Hebel Progress
| Scope |  |  | plastering & internal hebel
Rows
|  | West Tower - Level 5 | dynamic | level 5 | site qa | plastering & internal hebel | west tower
|  | West Tower - Level 6 | dynamic | level 6 | site qa | plastering & internal hebel | west tower
|  | West Tower - Level 7 | dynamic | level 7 | site qa | plastering & internal hebel | west tower
|  | West Tower - Level 8 | dynamic | site qa | level 8 | plastering & internal hebel | west tower
|  | West Tower - Level 9 | dynamic | site qa | level 9 | plastering & internal hebel | west tower
|  | West Tower - Level 10 | dynamic | level 10 | site qa | plastering & internal hebel | west tower
|  | West Tower - Level 11 | dynamic | site qa | level 11 | plastering & internal hebel | west tower
|  | West Tower - Level 12 | dynamic | site qa | level 12 | plastering & internal hebel | west tower
|  | West Tower - Level 13 | dynamic | site qa | plastering & internal hebel | level 13 | west tower
|  | West Tower - Level 14 | dynamic | site qa | level 14 | plastering & internal hebel | west tower
|  | West Tower - Level 15 | dynamic | level 15 | site qa | plastering & internal hebel | west tower
|  | West Tower - Level 16 | dynamic | level 16 | site qa | plastering & internal hebel | west tower
|  | West Tower - Level 17 | dynamic | level 17 | site qa | plastering & internal hebel | west tower
|  | West Tower - Level 18 | dynamic | level 18 | site qa | plastering & internal hebel | west tower
|  | West Tower - Level 19 | dynamic | site qa | level 19 | plastering & internal hebel | west tower
|  | West Tower - Level 20 | dynamic | level 20 | site qa | plastering & internal hebel | west tower
|  | West Tower - Level 21 | dynamic | level 21 | site qa | plastering & internal hebel | west tower
|  | West Tower - Level 22 | dynamic | site qa | level 22 | plastering & internal hebel | west tower
|  | West Tower - Level 23 | dynamic | site qa | level 23 | plastering & internal hebel | west tower
|  | West Tower - Level 24 | dynamic | site qa | plastering & internal hebel | level 24 | west tower
|  | West Tower - Level 25 | dynamic | site qa | level 25 | plastering & internal hebel | west tower
|  | West Tower - Level 26 | dynamic | level 26 | site qa | plastering & internal hebel | west tower
|  | West Tower - Level 27 | dynamic | level 27 | site qa | plastering & internal hebel | west tower
|  | East Tower - Level 5 | dynamic | level 5 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 6 | dynamic | level 6 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 7 | dynamic | level 7 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 9 | dynamic | site qa | level 9 | east tower | plastering & internal hebel
|  | East Tower - Level 10 | dynamic | level 10 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 11 | dynamic | site qa | level 11 | east tower | plastering & internal hebel
|  | East Tower - Level 12 | dynamic | site qa | level 12 | east tower | plastering & internal hebel
|  | East Tower - Level 13 | dynamic | site qa | east tower | plastering & internal hebel | level 13
|  | East Tower - Level 14 | dynamic | site qa | east tower | level 14 | plastering & internal hebel
|  | East Tower - Level 15 | dynamic | level 15 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 16 | dynamic | level 16 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 17 | dynamic | level 17 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 18 | dynamic | level 18 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 19 | dynamic | site qa | level 19 | east tower | plastering & internal hebel
|  | East Tower - Level 20 | dynamic | level 20 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 21 | dynamic | level 21 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 22 | dynamic | site qa | level 22 | east tower | plastering & internal hebel
|  | East Tower - Level 23 | dynamic | site qa | level 23 | east tower | plastering & internal hebel
|  | East Tower - Level 24 | dynamic | site qa | east tower | plastering & internal hebel | level 24
|  | East Tower - Level 25 | dynamic | site qa | east tower | level 25 | plastering & internal hebel
|  | East Tower - Level 26 | dynamic | level 26 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 27 | dynamic | level 27 | site qa | east tower | plastering & internal hebel
|  | East Tower - Level 28 | dynamic | level 28 | site qa | east tower | plastering & internal hebel
Columns
|  | Framing - All frames/studs set out correctly |  | framing | all frames/studs set out correctly
|  | Framing - All frames plumb and square |  | framing | all frames plumb and square
|  | Framing - Fix to structural members |  | framing | fix to structural members
|  | Framing - All window & sliding door openings as per plan |  | framing | all window and sliding door openings are as per plan and line up with above elements.
|  | Framing - Nogging all installed correctly |  | framing | nogging all installed correctly
|  | Framing - Plywood installed to all wet areas |  | framing | plywood installed to all wet areas to adaptable units
|  | Framing - Door frames fixing |  | framing | door frames fixing
|  | Framing - Studco/Rondo Supplier inspection |  | framing | studco/rondo supplier inspection (provide report to aland)
|  | Internal Hebel wall - Angle/sarking/top hats in place |  | angle/sarking/top hats in place | internal hebel wall
|  | Internal Hebel wall - Hebel panels Alignment |  | hebel panels alignment | internal hebel wall
|  | Internal Hebel wall - Hebel installed plumb & level |  | ensure hebel installed plumb and level with adjoining surfaces | internal hebel wall
|  | Internal Hebel wall - Hebel panels in full & not cracked |  | ensure hebel panels are in full and not cracked | internal hebel wall
|  | Internal Hebel wall - Control joints installed |  | enure control joints have been installed in accordance with manufacturers specifications and installation guide | internal hebel wall
|  | Internal Hebel wall - Hebel expansion joints installed |  | hebel expansion joints have been installed and are consistent including slab junctions | internal hebel wall
|  | Internal Hebel wall - Insulation installed as per AS/BCA |  | insulation installed as per as/bca (party walls + external) | internal hebel wall
|  | Internal Hebel wall - Panels finish (patches done) |  | panels finish(patches done) | internal hebel wall
|  | Internal Hebel wall - Fire-rated caulking & sealing |  | fire-rated caulking and sealing | internal hebel wall
|  | Internal Hebel wall - Satisfaction & sign off from CSR |  | satisfaction and sign off from csr inspection (provide report to aland) | internal hebel wall
|  | Plasterboard for Walls - Ply nogging |  | ply nogging | plasterboard for walls
|  | Plasterboard for Walls - Rough-in sign off |  | rough-in sign off | plasterboard for walls
|  | Plasterboard for Walls - Insulation installed as per AS/BCA |  | insulation installed as per as/bca | plasterboard for walls
|  | Plasterboard for Walls - Correct type of plasterboards |  | correct type of plasterboards and thickness installed as per wall details, project drawings and bca requirements | plasterboard for walls
|  | Plasterboard for Walls - Villaboard to wet areas ONLY |  | villaboard to wet areas only | plasterboard for walls
|  | Plasterboard for Walls - Plasterboard Lining installed |  | plasterboard lining to be installed at full height (leaving gaps is not allowed especially in lobbies/common areas) | plasterboard for walls
|  | Plasterboard for Ceiling - Confirm Ceiling height |  | plasterboard for ceiling | confirm ceiling height
|  | Plasterboard for Ceiling - Confirm Access panel location |  | plasterboard for ceiling | confirm access panel location
|  | Plasterboard for Ceiling - Ceiling frame work |  | plasterboard for ceiling | ceiling frame work
|  | Plasterboard for Ceiling - Ceiling bulkheads where required |  | plasterboard for ceiling | ceiling bulkheads where required
|  | Plasterboard for Ceiling - Pelmets (use of MDF only) |  | pelmets (use of mdf only) | plasterboard for ceiling
|  | Plasterboard for Ceiling - Ceiling insulation as per AS/BCA |  | plasterboard for ceiling | ceiling insulation as per as/bca
|  | Plasterboard for Ceiling - Correct type of plasterboards |  | plasterboard for ceiling | correct type of plasterboards and thickness installed as per wall details, project drawings and bca requirements
|  | Plasterboard for Ceiling - Villaboard to wet areas ONLY |  | plasterboard for ceiling | villaboard to wet areas only
|  | Plasterboard for Ceiling - Ceiling plasterboard Lining |  | plasterboard for ceiling | ceiling plasterboard lining
|  | Setting & Sanding - Angle /LB/P50 install |  | angle /lb/p50 install | setting & sanding
|  | Setting & Sanding - First coat setting |  | setting & sanding | first coat setting
|  | Setting & Sanding - Second coat setting |  | second coat setting | setting & sanding
|  | Setting & Sanding - Final coat setting |  | final coat setting | setting & sanding
|  | Setting & Sanding - Sanding |  | sanding | setting & sanding
|  | Setting & Sanding - patching |  | patching | setting & sanding
|  | Setting & Sanding - Defects |  | setting & sanding | defects
|  | Setting & Sanding - Final Inspection |  | final inspection | setting & sanding