## Table 1
INSPECTION AND TEST PLAN (ITP) ITP No: CC515-ITP-18a
SPWB Ventilation System Pre Construction Works
Complex Co Ǫuality System: ISO 9001:2015 |  | SPWB Ventilation System |  | Revision 1 |  |  | Date: 6/08/2024
Project: | West Belconnen Landfill | Contract No: | PISL0002527 | Principal: | Suburban Land Agency |  | Superintendent: | EGIS
Prepared by: | Lloyd Lucas | Reviewed by:
Reference Standards | [5 empty] | Drawing reference other than Project Designs
Document Name |  | Document No
Transport Canberra and City Services (TCCS) |  | MITS Standard Specifications – 02A
Detailed Design and Construction Ǫuality Assurance Plan |  | R.007.IFC-V0 |  |  |  | Douglas Partners IFC
Verification Key | [6 empty] | Inspection Codes
- HOLD POINT (H): Nominated point beyond which work shall not proceed without verified acceptance by nominee. - WITNESS POINT (W): Points at which the nominee shall be notified and invited to witness an activity, but further work may proceed without the presence of the nominee. - REVIEW (R): Verify by examination of documentary evidence that inspection / tests have been satisfactorily conducted. - SURVEILLANCE (S): Continuing evaluation of the status of methods, analysis of records and monitoring of activities on a random basis to ensure quality requirements will be met. - VISUAL (V): 100% Visual Inspection of work / item to ensure compliance with code / specification. - DIMENSIONAL (D): Measurement of critical dimensions to ensure work / item is within tolerance. | [6 empty] | Project Manager |  | PM
[7 empty] | Project Engineer |  | PE
[7 empty] | Site Manager |  | SM
[7 empty] | Site Supervisor |  | SS
[7 empty] | Superintendent |  | SI
[7 empty] | Surveillance Officer |  | SO
[7 empty] | Authority Representative |  | AR
9/08/2024 Page 1 of 4

## Table 2
Primary | Section Title | Type | Applicable Standard / Specification / Reference | Clause Title | Requirement | Notice for Inspection | Lot Sizes & Test Frequency | Realease by | Request Date of Inspection | Authorised Person for Approval | Approval Status
SPWB Ventalation System
Pre- construction | SPWB Ventalation System
1 | SPWB Ventalation System | Document Submission | Douglas Partners CQA Docs Table 4 | TransGrid approvals | Provide copy of approval to Principal | Prior to work commencment | Contract | Complex Co
2 | SPWB Ventalation System | Surveillance | Douglas Partners CQA Docs Table 4 | Clearing of vegetation along alignment | Provide copy of clearing approval to Principal |  | Contract | Complex Co
3 | SPWB Ventalation System | Survey | Douglas Partners CQA Docs Table 4 | Survey of lateral extents of alignment | Provide copy of survey report to Principal/Environmental Engineer prior to commencement of trench excavation works. |  | Contract | Complex Co
- | SPWB Ventalation System | HP | MITS Specification Clause 1.2.9.1 OA.3 | Utilities and Authorities – Existing services | Before starting earthworks, locate and mark existing underground services in the areas which will be affected by the works including clearing, excavating and trenching. | 1 working day before new work | Site | Authorised Person
- | SPWB Ventalation System | Document Submission | Douglas Partners CQA Docs | Trench excavation woks | Provide trench excavation procedure to Environmental Engineer and LUA for review and approval prior to commencement. Provide copy of trench dimensions/ base survey to Environmental Engineer. Contractor and Environmental Engineer notes. | Prior to work commencment | Contract | Enviromental Engineer
- | SPWB Ventalation System | Document Submission | Douglas Partners CQA Docs | Drilling and Installation procedure | Provide bore drilling/vertical pipe installation procedure to Environmental Engineer and LUA for review and approval prior to commencement. | Prior to work commencment | Contract | Enviromental Engineer
- | SPWB Ventalation System | Document Submission | Douglas Partners CQA Docs | Pipe Connection Procedure | Provide pipe connection procedure to Environmental Engineer and LUA for review and approval prior to commencement. | Prior to work commencment | Contract | Enviromental Engineer
- | SPWB Ventalation System | Document Submission | Douglas Partners CQA Docs | Backfilling Procedure | Provide backfilling procedure to Environmental Engineer and LUA for review and approval prior to commencement. | Prior to work commencment | Contract | Enviromental Engineer
- | SPWB Ventalation System | Document Submission | Douglas Partners CQA Docs Section C3.6.1. | Geotextile Installation Manual | Installation Quality Assurance Manual to be provided by contractor to Environmental Engineer and LUA for review and approval prior to commencement of any | Prior to work commencment | Contract | Enviromental Engineer
- | SPWB Ventalation System | Document Submission | Douglas Partners CQA Docs per Sections C3.6.2 and C3.6.3. | Capping Material | Provide caping material placement procedure to Environmental Engineer and LUA for review and approval prior to commencement. | Prior to work commencment | Contract | Enviromental Engineer
Materials | SPWB Ventalation System
4 | SPWB Ventalation System | HP Document Submission Product Conformance | Douglas Partners CQA Docs C3.3 and C3.5. | Prior to importation of gravel for vertical bores and/or trench backfill | Review manufacturer specifications are in accordance with Sections C3.3 and C3.5. Independent testing of each material as per Sections C3.3 and C3.5. Manufacturer’s data specification sheets. Independent conformance test results at frequencies specified in C3.3 and C3.5. |  | Contract / Material Changed 2 per 5000m3 of material. | Enviromental Engineer
5 | SPWB Ventalation System | HP Document Submission Product Conformance | Douglas Partners CQA Docs Section C3.4 | Prior to delivery of perforated and blank HDPE pipes, joints/elbows/conne ctors, vertical riser and rotating cowls | Manufacturer’s data specification sheets. Independent conformance test results at frequencies specified in C3.4. Prior to importation, review manufacturer specifications are in accordance with Section C3.4. Independent testing of each material as per Section C3.4. |  | Contract | Enviromental Engineer
6 | SPWB Ventalation System | Document Submission Product Conformance | Douglas Partners CQA Docs Section C3.6.1. | Prior to delivery of Separation Geotextile | Review manufacturer specifications are in accordance with Section C3.6.1. Independent testing of each material as per Section C3.6.1. |  | Contract | Enviromental Engineer
7 | SPWB Ventalation System | Visual Inspection | Douglas Partners CQA Docs | Material Delivery, Storage and Handling | Visual inspections during delivery, storage and handling Managed in a manner to avoid damage/deterioration of material. Confirmation of as delivered material properties (each material). Delivery dockets. Contractor and Environmental Engineer notes and observations. | Give Notice of recieved Material | For all Materials and Products recieved | Enviromental Engineer