## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | CC515-ITP-18a - SPWB Ventilation System Pre Construction Works | itp |  |  |  |  | CC515-ITP-18a - SPWB Ventilation System Pre Construction Works Rev1
section | Pre-construction
checkpoint | 01 - SPWB Ventilation System
label | Type - Document Submission
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs Table 4
label | Clause Title - TransGrid approvals
label | Requirement - Provide copy of approval to Principal
label | Notice for Inspection - Prior to work commencment
label | Lot Sizes & Test Frequency - Contract
label | Release by - Complex Co
checkpoint | 02 - SPWB Ventilation System
label | Type - Surveillance
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs Table 4
label | Clause Title - Clearing of vegetation along alignment
label | Requirement - Provide copy of clearing approval to Principal
label | Lot Sizes & Test Frequency - Contract
label | Release by - Complex Co
checkpoint | 03 - SPWB Ventilation System
label | Type - Survey
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs Table 4
label | Clause Title - Survey of lateral extents of alignment
label | Requirement - Provide copy of survey report to Principal/Environmental Engineer prior to commencement of trench excavation works.
label | Lot Sizes & Test Frequency - Contract
label | Release by - Complex Co
checkpoint | SPWB Ventilation System
label | Type - HP
label | Applicable Standard / Specification / Reference - MITS Specification Clause 1.2.9.1 OA.3
label | Clause Title - Utilities and Authorities – Existing services
label | Requirement - Before starting earthworks, locate and mark existing underground services in the areas which will be affected by the works including clearing, excavating and trenching.
label | Notice for Inspection - 1 working day before new work
label | Lot Sizes & Test Frequency - Site
label | Release by - Authorised Person
holdpoint | HOLD POINT
checkpoint | SPWB Ventilation System
label | Type - Document Submission
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs
label | Clause Title - Trench excavation woks
label | Requirement - Provide trench excavation procedure to Environmental Engineer and LUA for review and approval prior to commencement. Provide copy of trench dimensions/ base survey to Environmental Engineer. Contractor and Environmental Engineer notes.
label | Notice for Inspection - Prior to work commencment
label | Lot Sizes & Test Frequency - Contract
label | Release by - Enviromental Engineer
checkpoint | SPWB Ventilation System
label | Type - Document Submission
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs
label | Clause Title - Drilling and Installation procedure
label | Requirement - Provide bore drilling/vertical pipe installation procedure to Environmental Engineer and LUA for review and approval prior to commencement.
label | Notice for Inspection - Prior to work commencment
label | Lot Sizes & Test Frequency - Contract
label | Release by - Enviromental Engineer
checkpoint | SPWB Ventilation System
label | Type - Document Submission
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs
label | Clause Title - Pipe Connection Procedure
label | Requirement - Provide pipe connection procedure to Environmental Engineer and LUA for review and approval prior to commencement.
label | Notice for Inspection - Prior to work commencment
label | Lot Sizes & Test Frequency - Contract
label | Release by - Enviromental Engineer
checkpoint | SPWB Ventilation System
label | Type - Document Submission
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs
label | Clause Title - Backfilling Procedure
label | Requirement - Provide backfilling procedure to Environmental Engineer and LUA for review and approval prior to commencement.
label | Notice for Inspection - Prior to work commencment
label | Lot Sizes & Test Frequency - Contract
label | Release by - Enviromental Engineer
checkpoint | SPWB Ventilation System
label | Type - Document Submission
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs Section C3.6.1.
label | Clause Title - Geotextile Installation Manual
label | Requirement - Installation Quality Assurance Manual to be provided by contractor to Environmental Engineer and LUA for review and approval prior to commencement of any
label | Notice for Inspection - Prior to work commencment
label | Lot Sizes & Test Frequency - Contract
label | Release by - Enviromental Engineer
checkpoint | SPWB Ventilation System
label | Type - Document Submission
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs per Sections C3.6.2 and C3.6.3.
label | Clause Title - Capping Material
label | Requirement - Provide caping material placement procedure to Environmental Engineer and LUA for review and approval prior to commencement.
label | Notice for Inspection - Prior to work commencment
label | Lot Sizes & Test Frequency - Contract
label | Release by - Enviromental Engineer
section | Materials
checkpoint | 04 - SPWB Ventilation System
label | Type - HP, Document Submission Product Conformance
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs C3.3 and C3.5.
label | Clause Title - Prior to importation of gravel for vertical bores and/or trench backfill
label | Requirement - Review manufacturer specifications are in accordance with Sections C3.3 and C3.5. Independent testing of each material as per Sections C3.3 and C3.5.
label | ○ Manufacturer’s data specification sheets. Independent conformance test results at frequencies specified in C3.3 and C3.5.
label | Lot Sizes & Test Frequency - Contract / Material Changed 2 per 5000m3 of material.
label | Release by - Enviromental Engineer
holdpoint | HOLD POINT
checkpoint | 05 - SPWB Ventilation System
label | Type - HP, Document Submission Product Conformance
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs Section C3.4
label | Clause Title - Prior to delivery of perforated and blank HDPE pipes, joints/elbows/conne ctors, vertical riser and rotating cowls
label | Requirement - Manufacturer’s data specification sheets. Independent conformance test results at frequencies specified in C3.4. Prior to importation, review manufacturer specifications are in accordance with Section C3.4. Independent testing of each material as per Section C3.4.
label | Lot Sizes & Test Frequency - Contract
label | Release by - Enviromental Engineer
holdpoint | HOLD POINT
checkpoint | 06 - SPWB Ventilation System
label | Type - Document Submission Product Conformance
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs Section C3.6.1.
label | Clause Title - Prior to delivery of Separation Geotextile
label | Requirement - Review manufacturer specifications are in accordance with Section C3.6.1. Independent testing of each material as per Section C3.6.1.
label | Lot Sizes & Test Frequency - Contract
label | Release by - Enviromental Engineer
checkpoint | 07 - SPWB Ventilation System
label | Type - Visual Inspection
label | Applicable Standard / Specification / Reference - Douglas Partners CQA Docs
label | Clause Title - Material Delivery, Storage and Handling
label | Requirement - Visual inspections during delivery, storage and handling Managed in a manner to avoid damage/deterioration of material.
label | ○ Confirmation of as delivered material properties (each material). Delivery dockets. Contractor and Environmental Engineer notes and observations.
label | Notice for Inspection - Give Notice of recieved Material
label | Lot Sizes & Test Frequency - For all Materials and Products recieved
label | Release by - Enviromental Engineer
checklist | 35.18.1 SPWB Trenching Works | [5 empty] | 35.18.1 SPWB Trenching Works
section | Form 35.18.1 SPWB Trenching
checkpoint-no-status | Details
textbox | Lot
date | Date of Works Commencement
section | Pre Construction
checkpoint | Dial Before you dig completed and understood? This is a Hold Point.
holdpoint | HOLD POINT
checkpoint | Are there any Services
checkpoint | Survey Setout for portion of the works completed. Hold Point
holdpoint | HOLD POINT
checkpoint | Tree Protection in place. Hold Points X3
holdpoint | HOLD POINT
checkpoint | Excavation Permit Completed
section | Construction
checkpoint | Preliminary Approvals Completed. Site Engineer check
checkpoint | Clearing & Grubbing completed. Hold Point to inspect cleared Site
holdpoint | HOLD POINT
checkpoint | Topsoil Removed
checkpoint | Location of Vertical bores marked
checkpoint | Trench Excavation Completed
checkpoint | Depth of Trench Every 10m Over 100m Lot
textbox | 0-10 (Meters)
textbox | 10-20 (Meters)
textbox | 20-30 (Meters)
textbox | 30-40 (Meters)
textbox | 40-50 (Meters)
textbox | 50-60 (Meters)
textbox | 60-70 (Meters)
textbox | 70-80 (Meters)
textbox | 80-90 (Meters)
textbox | 90-100 (Meters)
checkpoint | Excavation Sign Off (Hold Point)
holdpoint | HOLD POINT
checkpoint | Sleeve placed for Vertical Bore
checkpoint | Trench backfilling with coarse gravel (>40mm) to design height of trench pipework? Hold Point (check against Design Height Register)
holdpoint | HOLD POINT
checkpoint | Gravel Sign off prior to pipework (Hold Point)
holdpoint | HOLD POINT
checkpoint | Vertical Bore ITC completed?
checkpoint | Inspection of completed Gas interception Pipework. Hold Point
holdpoint | HOLD POINT
checkpoint | Pipe Work Sign Off (Hold Point)
holdpoint | HOLD POINT
checkpoint | Trench backfilling with coarse gravel (>40mm) to finished design height. Hold Point.
holdpoint | HOLD POINT
checkpoint | Completed Gravel Sign Off (Hold Point)
holdpoint | HOLD POINT
checkpoint | Testing of Coarse gravel. Plan with Site Engineer.
checkpoint | Installation of vertical risers. As per jointing methodology with Site Engineer.
checkpoint | Geotextile installation completed. Hold Point
holdpoint | HOLD POINT
checkpoint | Geotextile Sign Off (Hold Point)
holdpoint | HOLD POINT
checkpoint | Survey completed for top of coarse gravel. Hold Point
holdpoint | HOLD POINT
checkpoint | Survey Sign off
holdpoint | SURVEY Sign off
checkpoint | Placement of capping material completed.
checkpoint | Testing of capping material completed. Refer to Testing Plan.
checkpoint | Survey of capping material.
checkpoint | Capping Sign Off (Hold Point)
holdpoint | HOLD POINT
section | Daily Log and Notes from Trench Work
checkpoint-no-status | Details
number | How Many Days of Excavation per Lot
checkpoint | Was there Weather that affected the trench
checkpoint | Non Conformances
textbox | Details of Non Conformance
textbox | Rectification Measures
holdpoint | Non Conformance Rectification Sign Off
checkpoint | All Works Completed.
textbox | Name of Approver
textbox | Date of Approver