## Balconies
Murray Halberg (Tropicana)
Building Stage 008
Level 2
B69-1
B69-2
B70-1
B70-2
Level 3
C69-1
C69-2
C70-1
C70-2
C71-1
C71-2
C72
C73
C74
C75
C76
C77
C78-1
C78-2
C79-1
C79-2
C80
C81
C82
C83
C84-1
C84-2
C84-3
C85-1
C85-2
C86-1
C86-2
C86-3
C87-1
C87-2
Level 4
D69-1
D69-2
D70-1
D70-2
D71-1
D71-2
D72
D73
D74
D75
D76
D77
D78-1
D78-2
D79-1
D79-2
D80
D81
D82
D83
D84-1
D84-2
D85-1
D85-2
D86-1
D86-2
D87-1
D87-2
Level 5
E69
E70
E71-1
E71-2
E72
E73
E74
E75
E76
E77
E78-1
E78-2
E79-1
E79-2
E80
E81
E82
E83
E84-1
E84-2
E85-1
E85-2
E86-1
E86-2
E87-1
E87-2
Level 6
F69
F70
F71
F72
F74
F75
F76
F77
F78

## Staircases
Staircase 1 | Flight 1 | Handrail / Balustrade
| Mid Landing 1 | Handrail
| Flight 2 | Handrail / Balustrade
| Flight 3 | Handrail / Balustrade
| Mid Landing 2 | Handrail
| Flight 4 | Handrail / Balustrade
| Flight 5 | Handrail / Balustrade
| Mid landing 3 | Handrail
| Flight 6 | Handrail / Balustrade
| Flight 7 | Handrail / Balustrade
| Mid landing 4 | Handrail
| Flight 8 | Handrail / Balustrade
| Landing Closure | Balustrade
Staircase 2 | Flight 1 | Handrail / Balustrade
| Mid Landing 1 | Handrail
| Flight 2 | Handrail / Balustrade
| Flight 3 | Handrail / Balustrade
| Mid Landing 2 | Handrail
| Flight 4 | Handrail / Balustrade
| Flight 5 | Handrail / Balustrade
| Mid Landing 3 | Handrail
| Flight 6 | Handrail / Balustrade
| Landing Closure | Balustrade
Podium staircase | Flight 1 | Balustrade
| Mid Landing | Balustrade
| Flight 2 | Balustrade
| Level Landing Closure | Balustrade

## Roof Area
Roof Access Hatch | Hatch framing complete by others
correct number of fixing screws (8 Min)
Opens to the correct side
Latch is in working order
Gaurdrail bolted into place
Powder coated
Small fixed ladder between hatch and fold down ladder | Sufficient fixing to structure
Brackets fixed to structure
Ladder has end caps
200 mm between the rungs and any solid objects behind the ladder
750 mm between the rungs and any obstruction behind climber
50 mm between stiles and obstruction for hand movement
Rung type fold - down commercial ladder | Celing frame installed by others (1230 (L) x 785 mm (W)
Minimium of 380 mm height clearance from below celing to closest obstruction
Distance from fold down ladder framing to small ladder bracket fixing structure of no less than 350 mm
Minimum clearance for etension of ladder of 1930 mm
Height between celing and floor min 2200mm - Max 3200 mm
Secured to celing framing using 4 x M12 x 50 mm couch screws