## Project Structure
Folder Structure |  |  | Checklists
Site QA
| Prelim Activities | To Contain Preliminary Checklist | Preliminary Activities and Materials Approval
21-J149-1 | Bayswater Longitudinal Headstocks | To Contain Headstocks Checklist | Ability to Add Headstocks Checklists
21-J149-1 | Bayswater Transversal Headstocks | To Contain Headstocks Checklist | Ability to Add Headstocks Checklists

## LHS Resources
type | name | values
checklist-sectioned | Preliminary Activities and Materials Approval
section | Preliminary Activities (Approved by Client)
checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint | Permacast Project Quality Management Plan
checkpoint | Inspection & Test Plan
checkpoint | MDR Index
checkpoint | Work Method Statement (WMS) - Curing
checkpoint | Work Method Statement (WMS) - Concrete Repair Methodology
checkpoint | Work Method Statement (WMS) - Earthing and Bonding
checkpoint | Shop Drawings
checkpoint | Test Panel Prepared and Inspected by Client
checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
section | Concrete
checkpoint | S65GB@180 Concrete Mix Design Approved by Client (MEL-MLCX-ST-SPC-00123[A])
checkpoint | Notify Concrete Supplier of Pour
section | Steel Reinforcement
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
section | Grout tubes
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
section | Cooling pipes
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
section | Lifting Anchors (HOLD POINT FOR PERMACAST TO SIGN OFF)
checkpoint | Lifting Design Approved by Client
checkpoint | Lifting Devices Approved by Client
checkpoint | Inspection of Delivery for Completeness and Quality
section | Cast-in Items and Ferrules
checkpoint | All Cast in Materials Approved
checkpoint | Inspection of Delivery for Completeness and Quality
checklist-sectioned | Headstocks Checklist
section | Pre-Pour Checklist
text | Cast Number
text | Headstock Number
text | Headstock Type Number
checkpoint | Shop Drawings approved for Works
text | File name
text | File revision
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Mould Surface Checked (HOLD POINT FOR PERMACAST TO SIGN OFF)
label | Cleaned
label | Sealed
label | Rubbers in Place
label | Oiled
label | Chamfers in Place
label | Check angle for shutter
checkpoint | Reinforcement in Accordance with Drawings
label | Reinforcement size
label | Lap Length
label | Splicing
label | Bar Chairs
checkpoint | Cover maintained and within tolerance
checkpoint | All Stainless Items are installed in accordance with Drawings
text | Specify
checkpoint | All PT ducts are installed in accordance with Drawings
text | PT duct layout type 1 or type 2
Text | Duct layout orientation
text | No of tubes
text | Tube locators
checkpoint | All Lifting Inserts are installed in accordance with Drawings approved by the client (HOLD POINT FOR PERMACAST TO SIGN OFF)
label | Lifting drawing name
text | 20T Lifters for longitudinal (4x CA20500)
checkpoint | Cast-in Items and Ferrules
label | All Cast in Materials Approved
text | All Couplers are installed in accordance with drawings
text | All ferrules are installed in accordande with drawings
label | Number of couplers
label | Threaded section of coupler installed
checkpoint | Earthing and Bonding is installed in accordance with Drawings (HOLD POINT FOR PERMACAST TO SIGN OFF)
text | Earthing Terminals (FDB-16)
text | Flexi cables
text | Weld locations (not permitted within 75mm of a bend)
text | 100mm single side or 55mm both sides - 6mm fillet welds between bars
text | <20 mOhm across cage Length
text | Checklist Completed (Headstock) (attach results)
checkpoint | Cooling pipes are installed in accordance with Drawings
Label | Approval correspondence
Label | Water circulating temperature monitor
text | Cooling pipes numbers
text | Cooling pipes spacing
text | Hydraulic system in working status (no leaks in mould)
checkpoint | All Temperature Loggers are installed as per Approved WMS (HOLD POINT FOR PERMACAST TO SIGN OFF)
text | Ensure All temperature Loggers are Working
text | Number, location and installation of loggers
text | Temperature logger in cover zone
text | Temperature logger in core zone
text | Temperature logger in tent for ambient temperature
checkpoint | QA Engineer Check Completed by
checkpoint | Client Inspector (if present)
checkpoint | Notify concrete supplier of pour
checkpoint | Notify contractor to arrange NATA testing laboratory of pour
section | Supervisor Release
checkpoint | Supervisor Release to Engineering Team
section | Casting Checklist
checkpoint | Casting Information
text | Cast Date
checkpoint | Concrete Delivery Dockets
text | Concrete Delivery Docket (list all)
checkpoint | Total Concrete Volume
text | Volume (m3)
checkpoint | Mix Design Verified
text | Specify mix used
checkpoint | Ambient Temperature within Limits
label | max 38°C
checkpoint | Concrete Temperature
label | max 32°C
checkpoint | Slump within Allowable Tolerance (180mm +/- 40) First truck and subsequently tested for every 20m3
text | Slump (list all)
checkpoint | Truck Tested for strength
text | Test Report Reference Number (list all)
text | Number of cylinder taken
checkpoint | Vibration adedquate
checkpoint | Time Lag Between Trucks is not exceeded (20 minutes)
checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
checkpoint | Required Finish Applied as per Drawings
checkpoint | Concrete Covered Overnight
checkpoint | Cylinders Stored next to Bed and covered as per AS1012
section | Stripping Checklist
checkpoint | Date Stripped
text | Enter Date
checkpoint | Concrete Cylinders Crushed and Submitted to Client (HOLD POINT FOR PERMACAST TO SIGN OFF)
label | Minimun cylinders (2x1d, 1x7d, 2x28d)
text | 20MPa stripping and curing 45.5MPa
label | Strength = Reading / 7.851
checkpoint | Lifting Strength Achieved
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint | Secondary Curing as per Approved Methodology (Cover with tarp until 45.5MPa is achieved)
label | Temperature 5 degrees less its peak
label | Differential between Core and Ambient within 30 degrees
label | Differential between Core and Cover within 20 degrees
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Specified Finish Achieved
label | Rugasol applied where roughened surfaces are required
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
Label | Couplers
Label | Stainless Items
text | Lifters
text | Blockouts
checkpoint | Earthing and Bonding confirmation of continuity value (HOLD POINT FOR PERMACAST TO SIGN OFF)
text | continuity value
checkpoint | Post-Pour Works Completed (As Required)
text | Couplers are Cleaned,threaded section is fixed and capped
text | Roughened Surfaces are Greencut
text | Water Removed out of Cooling Pipes
text | All Miscellaneous Items are Completed
checkpoint | Temperature Logging Completed and Conforming. Attach Results
section | Any Defect Identified
checkpoint | Punchlisting Completed
checkpoint | Repairs Required (if applicable)
checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint | Crack Map Completed
checkpoint | Any NCR Required (if applicable) (HOLD POINT FOR PERMACAST/CLIENT TO SIGN OFF)
checkpoint | NCR Approved by Client and Repairs Completed (if applicable) (HOLD POINT FOR PERMACAST/CLIENT/PTA TO SIGN OFF)
section | As-Built Drawings
checkpoint | As-Built Drawings Completed, Stamped and Attached
section | Concrete Strength Test Report (HOLD POINT FOR PERMACAST TO SIGN OFF)
checkpoint | Concrete Strength Test Report Received
text | Concrete Test Report (every 20m3)
text | 2x 7 Day Strength (List all)
text | 2x 28 Day Strength (List all)
section | Transportation Requirements
checkpoint | Certificate of Conformance
checkpoint | Inspection Release Certificate
checkpoint | Delivery Notes
checkpoint | Delivery Docket
section | Final Acceptance (HOLD POINT FOR PERMACAST/CLIENT TO SIGN OFF)
checkpoint | Completed by
checkpoint | Reviewed by
checkpoint | Final Inspection Client Representative (HOLD POINT FOR PERMACAST/CLIENT TO SIGN OFF)

## THS Resources
type | name | values
checklist-sectioned | Preliminary Activities and Materials Approval
section | Preliminary Activities (Approved by Client)
checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint | Permacast Project Quality Management Plan
checkpoint | Inspection & Test Plan
checkpoint | MDR Index
checkpoint | Work Method Statement (WMS) - Curing
checkpoint | Work Method Statement (WMS) - Concrete Repair Methodology
checkpoint | Work Method Statement (WMS) - Earthing and Bonding
checkpoint | Shop Drawings
checkpoint | Test Panel Prepared and Inspected by Client
checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
section | Concrete
checkpoint | S65GB@180 Concrete Mix Design Approved by Client (MEL-MLCX-ST-SPC-00123[A])
checkpoint | Notify Concrete Supplier of Pour
section | Steel Reinforcement
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
section | Grout tubes
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
section | Cooling pipes
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
section | Lifting Anchors (HOLD POINT FOR PERMACAST TO SIGN OFF)
checkpoint | Lifting Design Approved by Client
checkpoint | Lifting Devices Approved by Client
checkpoint | Inspection of Delivery for Completeness and Quality
section | Cast-in Items and Ferrules
checkpoint | All Cast in Materials Approved
checkpoint | Inspection of Delivery for Completeness and Quality
checklist-sectioned | Headstocks Checklist
section | Pre-Pour Checklist
text | Cast Number
text | Headstock Number
text | Headstock Type Number
checkpoint | Shop Drawings approved for Works
text | File name
text | File revision
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Mould Surface Checked (HOLD POINT FOR PERMACAST TO SIGN OFF)
label | Cleaned
label | Sealed
label | Rubbers in Place
label | Oiled
label | Chamfers in Place
label | Check angle for shutter
checkpoint | Reinforcement in Accordance with Drawings
label | Reinforcement size
label | Lap Length
label | Splicing
label | Bar Chairs
checkpoint | Cover maintained and within tolerance
checkpoint | All Stainless Items are installed in accordance with Drawings
text | Specify
checkpoint | All PT ducts are installed in accordance with Drawings
text | No of tubes
text | Tube locators
checkpoint | All formed holes for bearings in accordance with Drawings
text | No of holes
checkpoint | All Drainage pipe penetration in accordance with Drawings
label | Penetration for drainage
checkpoint | All Lifting Inserts are installed in accordance with Drawings approved by the client (HOLD POINT FOR PERMACAST TO SIGN OFF)
label | Lifting drawing name
label | Lifters for Transversal HS
text | Lifting loop type and quantity as per lifting design
checkpoint | Cast-in Items and Ferrules
label | All Cast in Materials Approved
text | All Couplers are installed in accordance with drawings
text | All ferrules are installed in accordande with drawings
text | Number of couplers
text | Threaded section of coupler installed
checkpoint | Earthing and Bonding is installed in accordance with Drawings (HOLD POINT FOR PERMACAST TO SIGN OFF)
text | Earthing Terminals (FDB-16)
text | Flexi cables
text | Weld locations (not permitted within 75mm of a bend)
text | 100mm single side or 55mm both sides - 6mm fillet welds between bars
text | <20 mOhm across cage Length
text | Checklist Completed (Headstock) (attach results)
checkpoint | Cooling pipes are installed in accordance with Drawings
Label | Approval correspondence
Label | Water circulating temperature monitor
text | Cooling pipes numbers
text | Cooling pipes spacing
text | Hydraulic system in working status (no leaks in mould)
checkpoint | All Temperature Loggers are installed as per Approved WMS (HOLD POINT FOR PERMACAST TO SIGN OFF)
text | Ensure All temperature Loggers are Working
text | Number, location and installation of loggers
text | Temperature logger in cover zone
text | Temperature logger in core zone
text | Temperature logger in tent for ambient temperature
checkpoint | QA Engineer Check Completed by
checkpoint | Client Inspector (if present)
checkpoint | Notify concrete supplier of pour
checkpoint | Notify contractor to arrange NATA testing laboratory of pour
section | Supervisor Release
checkpoint | Supervisor Release to Engineering Team
section | Casting Checklist
checkpoint | Casting Information
text | Cast Date
checkpoint | Concrete Delivery Dockets
text | Concrete Delivery Docket (list all)
checkpoint | Total Concrete Volume
text | Volume (m3)
checkpoint | Mix Design Verified
text | Specify mix used
checkpoint | Ambient Temperature within Limits
label | max 38°C
checkpoint | Concrete Temperature
label | max 32°C
checkpoint | Slump within Allowable Tolerance (180mm +/- 40) First truck and subsequently tested for every 20m3
text | Slump (list all)
checkpoint | Truck Tested for strength
text | Test Report Reference Number (list all)
text | Number of cylinder taken
checkpoint | Vibration adedquate
checkpoint | Time Lag Between Trucks is not exceeded (20 minutes)
checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
checkpoint | Required Finish Applied as per Drawings
checkpoint | Concrete Covered Overnight (Cover with tarp until 45.5MPa is achieved)
checkpoint | Cylinders Stored next to Bed and covered as per AS1012
section | Stripping Checklist
checkpoint | Date Stripped
text | Enter Date
checkpoint | Concrete Cylinders Crushed and Submitted to Client (HOLD POINT FOR PERMACAST TO SIGN OFF)
label | Minimun cylinders (2x7d, 2x28d)
text | 20MPa stripping and curing 45.5MPa
label | Strength = Reading / 7.851
checkpoint | Lifting Strength Achieved
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint | Secondary Curing as per Approved Methodology (Cover with Tarp until 45.5MPa is achieved)
label | Temperature 5 degrees less its peak
label | Differential between Core and Ambient within 30 degrees
label | Differential between Core and Cover within 20 degrees
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Specified Finish Achieved
label | Rugasol applied where roughened surfaces are required
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
Label | Couplers
Label | Stainless Items
text | Lifters
text | Blockouts
checkpoint | Earthing and Bonding confirmation of continuity value (HOLD POINT FOR PERMACAST TO SIGN OFF)
text | continuity value
checkpoint | Post-Pour Works Completed (As Required)
text | Couplers are Cleaned,threaded section is fixed and capped
text | Roughened Surfaces are Greencut
text | Water Removed out of Cooling Pipes
text | All Miscellaneous Items are Completed
checkpoint | Temperature Logging Completed and Conforming. Attach Results
section | Any Defect Identified
checkpoint | Punchlisting Completed
checkpoint | Repairs Required (if applicable)
checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint | Crack Map Completed
checkpoint | Any NCR Required (if applicable) (HOLD POINT FOR PERMACAST/CLIENT TO SIGN OFF)
checkpoint | NCR Approved by Client and Repairs Completed (if applicable) (HOLD POINT FOR PERMACAST/CLIENT/PTA TO SIGN OFF)
section | As-Built Drawings
checkpoint | As-Built Drawings Completed, Stamped and Attached
section | Concrete Strength Test Report (HOLD POINT FOR PERMACAST TO SIGN OFF)
checkpoint | Concrete Strength Test Report Received
text | Concrete Test Report (every 20m3)
text | 2x 7 Day Strength (List all)
text | 2x 28 Day Strength (List all)
section | Transportation Requirements
checkpoint | Certificate of Conformance
checkpoint | Inspection Release Certificate
checkpoint | Delivery Notes
checkpoint | Delivery Docket
section | Final Acceptance (HOLD POINT FOR PERMACAST/CLIENT TO SIGN OFF)
checkpoint | Completed by
checkpoint | Reviewed by
checkpoint | Final Inspection Client Representative (HOLD POINT FOR PERMACAST/CLIENT TO SIGN OFF)