## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Slab - Concrete Pour ITP |  |  |  |  | Yes | Slab - Concrete Pour ITP | 3c15b7e2-dde9-464c-a6df-5bd051dcbeb3
checkpoint-status |  |  | checkpoint | Cast in pipework/sleeves as per approved engineer detail
checkpoint-status |  |  | checkpoint | Penetrations fire collars and pipework in correct locations as per drawings
checkpoint-status |  |  | checkpoint | Tested & Inspected - test results attached as required below
checkpoint-status |  |  | checkpoint | Jordan Plumbing for info Penetration plan/cast in plan marked off
checkpoint-status |  |  | checkpoint | JP supervisor and Builder Rep signature attached below
checklist-flat |  |  | checklist | Columns - Concrete Pour ITP |  |  |  |  | Yes | Columns - Concrete Pour ITP | 4769bd49-b072-4f71-8541-203c5c6a00c5
checkpoint-status |  |  | checkpoint | HDPE / Raupiano / PVC drainage / penetrations installed as per AS3500
checkpoint-status |  |  | checkpoint | Hydro static test to HDPE / Raupiano / PVC sewer and stormwater stacks
checkpoint-status |  |  | checkpoint | As per AS3500 section 13.2 (No leaks while under test conditions for 15mins)
checkpoint-status |  |  | checkpoint | Cast in pipework/sleeves as per approved engineer detail
checkpoint-status |  |  | checkpoint | Penetrations and pipework in correct locations as per drawings
checkpoint-status |  |  | checkpoint | Book inspection with OTR to undertake visual inspection of each stack as required
checkpoint-status |  |  | checkpoint | Tested & Inspected - test results attached as required below
checkpoint-status |  |  | checkpoint | Ensure all Inspection Openings in columns are capped and flush with external face
checkpoint-status |  |  | checkpoint | Jordan Plumbing for info Penetration plan/cast in plan marked off
checkpoint-status |  |  | checkpoint | JP supervisor and Builder Rep signature attached below
checklist-flat |  |  | checklist | Risers Checklist |  |  |  |  | Yes | Risers Checklist | 9d2108dc-e4f6-4e1f-a52c-51b494ae28f3
checkpoint-status |  |  | checkpoint | Risers complete
checklist-flat |  |  | checklist | Suspended Sewer ITP |  |  |  |  | Yes | Suspended Sewer ITP | deade52a-31cc-40a2-839f-1ea07fe39119
checkpoint-status |  |  | checkpoint | HDPE / Raupiano / PVC drainage installed as per AS3500
checkpoint-status |  |  | checkpoint | Hydro static test to HDPE / Raupiano / PVC suspended drainage and sewer stack
checkpoint-status |  |  | checkpoint | As per AS3500 section 13.2 (No leaks while under test conditions for 15mins)
checkpoint-status |  |  | checkpoint | Book inspection with OTR to undertake visual inspection of each suspended drain / stack
checkpoint-status |  |  | checkpoint | OTR to sign marked up drawing for each suspended drain / stack - drawing and OTR signatureattached below
checkpoint-status |  |  | checkpoint | Tape to be installed to IP cap on sewer stack once test complete - OTR signature attached below
label | d95a86f5-63b9-5af2-9e4d-303e2fce7bfa |  | note | (tape is installed to make sure the IP cap is not removed/loosened by any other trades during construction)
checkpoint-status |  |  | checkpoint | Sign internal walls and ceilings linings handover sheet
checkpoint-status |  |  | checkpoint | Tested & Inspected - test results attached below
checkpoint-status |  |  | checkpoint | JP supervisor and Builder Rep signature attached below