## General
SECTION 1 – GENERAL DETAILS
Project Name: | DCC11014 Water Pump Station Renewals - MT GRAND to WINGATUI | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561483 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council | [5 empty] | B | Report by Breach | CM | Construction Manager | Stephen Vorgers
Contract Number: | 561483 | [5 empty] | C | Check | CR | Cust. Representative | Joff Riley / Mark Todd
Area/ Sub-System: | Commissioning of Pumps |  |  |  | N/A |  | D | Dimension Inspection | IP | Inspection Personnel | Bruce Allan
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | 561483-ITP-011 |  |  | Version: | DRAFT |  | H | Hold Point | OP | Operations Manager
ITP Description: | Commissioning Pumps 1 through 6 | [5 empty] | I | Inspection | PM | Project Manager | Matt Paterson
Discipline: | Pumps | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | C11014 Water Pump Station Renewals Specification 12581908 | [5 empty] | O | Operation | QE | Quality Engineer | Hamish Watson
[7 empty] | R | Review | QM | QA Manager | Grundfos Commissioning Engineer
Drawings: | Construction Issue Drawings as issued by GHD - Mt Grand to Wingatui Project Ref: 12581908-GHD-PS-MG-DRG-GN Drawings: G0001, M0001, M0011,S0001 & S0002 and various other as-built drawings | [5 empty] | S | Subcontractor | SP | Supervisor | Bruce Allan
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Matt Paterson |  |  | Date: | 2024-01-15 |  | W | Witness Point | SV | Surveyor
Quality Specified: | None - As per Specification requirements & refer Commissioning Methodology | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Bruce Allan |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Paterson/Stephen Vorgers |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: | Mark Todd / Iain Partington |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
Note: Pumps have been set to match the existing pump performance temporarily. This ITP is for the final commissioning of the system
3.1 | Pump 1 | Set Pump Flowrate and establish communication with Grundfos Main controller | VFD 1 configured to match existing pump performance | 561483-ITP-009.1 | Once | Visual | I | IP
3.2 | Pump 2 | Set Pump Flowrate and establish communication with Grundfos Main controller | VFD 2 configured to match existing pump performance | 561483-ITP-009.2 | Once | Visual | I | IP
3.3 | Pump 3 | Set Pump Flowrate and establish communication with Grundfos Main controller | VFD 3 configured to match existing pump performance | 561483-ITP-009.3 | Once | Visual | I | IP
3.4 | Pump 4 | Set Pump Flowrate and establish communication with Grundfos Main controller | VFD 4 configured to match existing pump performance | 561483-ITP-009.4 | Once | Visual | I | IP
3.5 | Pump 5 | Set Pump Flowrate and establish communication with Grundfos Main controller | VFD 5 configured to match existing pump performance | 561483-ITP-009.5 | Once | Visual | I | IP
3.6 | Pump 6 | Set Pump Flowrate and establish communication with Grundfos Main controller | VFD 6 configured to match existing pump performance | 561483-ITP-009.6 | Once | Visual | I | IP

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | Pump 1 | Set pump 1 final pressure and flowrates | Pump 1 Delivery head and flowrate is as per specified values (153 Litres/sec combined) | Grundfos controller display/Commissioning sheet | Once | Visual / Photograph | O/W | Grundfos Commissioning Engineer
4.2 | Pump 2 | Set pump 2 final pressure and flowrates | Pump 2 Delivery head and flowrate is as per specified values (153 Litres/sec combined) | Grundfos controller display/Commissioning sheet | Once | Visual / Photograph | O/W | Grundfos Commissioning Engineer
4.3 | Pump 3 | Set pump 3 final pressure and flowrates | Pump 3 Delivery head and flowrate is as per specified values (153 Litres/sec combined) | Grundfos controller display/Commissioning sheet | Once | Visual / Photograph | O/W | Grundfos Commissioning Engineer
4.4 | Pump 4 | Set pump 4 final pressure and flowrates | Pump 4 Delivery head and flowrate is as per specified values (153 Litres/sec combined) | Grundfos controller display/Commissioning sheet | Once | Visual / Photograph | O/W | Grundfos Commissioning Engineer
4.5 | Pump 5 | Set pump 5 final pressure and flowrates | Pump 5 Delivery head and flowrate is as per specified values (153 Litres/sec combined) | Grundfos controller display/Commissioning sheet | Once | Visual / Photograph | O/W | Grundfos Commissioning Engineer
4.6 | Pump 6 | Set pump 6 final pressure and flowrates | Pump 6 Delivery head and flowrate is as per specified values (153 Litres/sec combined) | Grundfos controller display/Commissioning sheet | Once | Visual / Photograph | O/W | Grundfos Commissioning Engineer

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1 | Pumps 1 through 6 | Full pumping duty is restored from Mt Grand to Wingatui Reservoir | Flow rates equal the specified design value (130 L/sec High flow) | View on Grundfos Controller | Once | Visual / Photograph | W / H | CR
5.2 | Pumps 1 through 6 | Pumping duty is restored to Stoney Knowe Reservoir | Flow rates equal the specified design value (70 L/sec High flow) | View on Grundfos Controller | Once | Visual / Photograph | W / H | CR
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: