## General
SECTION 1 – GENERAL DETAILS
Project Name: | DCC11014 Water Pump Station Renewals - MT GRAND to WINGATUI | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561483 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council | [5 empty] | B | Report by Breach | CM | Construction Manager | Stephen Vorgers
Contract Number: | DCC11014-WPS004 | [5 empty] | C | Check | CR | Cust. Representative | Joff Riley / Mark Todd
Area/ Sub-System: | Pipe Spool & Control Valve 1 - Mt Grand to Wingatui |  |  | Lot ID Number: | N/A |  | D | Dimension Inspection | IP | Inspection Personnel | Jason Bell
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | 561483-ITP-012.1 |  |  | Version: | DRAFT |  | H | Hold Point | OP | Operations Manager
ITP Description: | Pipe Spool & Control Valve - Inspection Test Plan | [5 empty] | I | Inspection | PM | Project Manager | Matt Paterson
Discipline: | Wingatui Valve Chamber | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | C11014 Water Pump Station Renewals Specification 12581908 | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager
Drawings: | Construction Issue Drawings as issued by GHD - Mt Grand to Wingatui Project Ref: 12581908-GHD-PS-MG-DRG-GN Drawings: G0001, M0001, M0002, M0011, S0001 & S0002 | [5 empty] | S | Subcontractor | SP | Supervisor | Bruce Allan
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Matt Paterson |  |  | Date: | 2024-01-15 |  | W | Witness Point | SV | Surveyor
Quality Specified: | None - As per Specification | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Matt Paterson/Aaron Sutherland |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Paterson/Stephen Vorgers |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: | Mark Todd / Iain Partington |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
3.1 | Pipe Spool Installation | Installation completion. All bolts are tightened and torqued to their correct values | Completion of ITP | ITP-002.1 | Once | Visual + Inspection + Photograph | I | IP
3.2 | Control Valve 1 Installation | Installation completion. All bolts are tightened and torqued to their correct values | Completion of ITP | ITP-002.1 | Once | Visual + Inspection + Photograph | I | IP
3.3 | Control Valve 2 & ancillaries | Installation completion. All bolts are tightened and torqued to their correct values | Completion of ITP | ITP-002.2 | Once | Visual + Inspection + Photograph | I | IP
3.4 | Pumps 1 through 6 are installed and commissioned | Verify commissioning is complete via Grundfos | Completion of Commissioning | Grundfos report | Once | Inspection + Documentation | I | IP

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | Commission Control Valve 1 | Set to achieve correct flow rate | 130 litres/sec achieved | Commissioning Methodology/Claval Commissioning sheet | once | Visual + Photographs + document | I | IP
Note: Valve chamber will need to be assessed by Downer HS&E to determine as to whether is a confined space

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1 | Record Value | At completion of valve commissioning | When consistent results are achieved | Commissioning record sheet / Operation & Maintenance Manual | once | Visual + Document + Photograph | I | IP
5.2 | Set Lock nut on pilot valve | At completion of valve commissioning | When consistent results are achieved | Commissioning record sheet / Operation & Maintenance Manual | once | Visual + Document + Photograph | I | IP
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: