## General
SECTION 1 – GENERAL DETAILS
Project Name: | DCC11014 Water Pump Station Renewals - MT GRAND to WINGATUI | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561483 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council | [5 empty] | B | Report by Breach | CM | Construction Manager | Stephen Vorgers
Contract Number: | DCC11014-WPS004 | [5 empty] | C | Check | CR | Cust. Representative | Joff Riley / Mark Todd
Area/ Sub-System: | Pilot Valve Installation. Wingatui Control Valve 2 |  |  | Lot ID Number: | N/A |  | D | Dimension Inspection | IP | Inspection Personnel | Jason Bell
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | 561483-ITP-002.2 |  |  | Version: | DRAFT |  | H | Hold Point | OP | Operations Manager
ITP Description: | Pilot Valve - Delivery & Inatallation | [5 empty] | I | Inspection | PM | Project Manager | Matt Paterson
Discipline: | Pilot Valve | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | C11014 Water Pump Station Renewals Specification 12581908 | [5 empty] | O | Operation | QE | Quality Engineer
[7 empty] | R | Review | QM | QA Manager
Drawings: | Construction Issue Drawings as issued by GHD - Mt Grand to Wingatui Project Ref: 12581908-GHD-PS-MG-DRG-GN Drawings: G0001, M0001, M0002, M0011, S0001 & S0002 | [5 empty] | S | Subcontractor | SP | Supervisor | Bruce Allan
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Matt Paterson |  |  | Date: | 19-12-24 |  | W | Witness Point | SV | Surveyor
Quality Specified: | None - As per Specification | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Matt Paterson/Aaron Sutherland |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Paterson/Stephen Vorgers |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: | Mark Todd / Iain Partington |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
3.1 | Take delivery of pilot valve assembly | Check that Make/Model/Dimensions are correct and all components are delivered and are damage free | Matches Design Drawings/Documents | Drawings & Specifications. Advice from ClaVal | Once | Visual + electronic | I | IP/PM
3.2 | Take Delivery of Valve position indicator | Check that Make/Model/Dimensions are correct and all components are delivered and are damage free | Matches Design Drawings/Documents | Drawings & Specifications. Advice from ClaVal | Once | Visual + electronic | I | IP/PM
3.3 | Take Delivery of Air Release Valve | Check that Make/Model/Dimensions are correct and all components are delivered and are damage free | Matches Design Drawings/Documents | Drawings & Specifications. Advice from ClaVal | Once | Visual + electronic | I | IP/PM
3.4 | Valve Assessment | Internal valve component inspection | ClaVal Assessment | Claval report and verification | Once | Visual + electronic | H | IP/PM
Note: Downer HS&E to assess as to whether Valve chamber is Confined Space.

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | Shutdown preparation | Arrange with Client & Engineer for shutdown | Acceptance from client & Engineer | Written, via email or NTC | once | Written + Inspection | I | IP
4.2 | Pilot Valve | Install new pilot valve and ancillary items | As per manufacturers installation instructions. ClaVal technician | ClaVal Technician sign off | once | Visual + Document + Photographs | I | IP
4.3 | Valve Position indicator | Correct installation of valve position indicator and fittings | As per manufacturers installation instructions. No leaks and orientation is correct | This ITP | once | Visual + Document + Photographs | I | IP
4.4 | Air Release Valve | Correct installation of air release valve and fittings | As per ClaVal installation instructions | This ITP | once | Visual + Document + Photographs | I | IP
4.5 | System reinstatement | Open main valve to reinstate water supply | Completion of item 4.2 | Inspection and this ITP | once | Visual + Inspection + Photographs | I | IP
4.6 | Adjust | Adjust the pilot valve to obtain the correct flow 8.5m Head & 130L/sec | Obtain specified flow rate ClaVal technician | Specification flowrate | once | Visual + Document + Photographs | I | IP/CR

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1 | Red pen Mark up | At completion of all items on this ITP. Document upgrade and recored new flow rate & pilot valve position setting | As per specified pressure & flow or client requirements | Red line mark up drawing. This ITP | once | Visual + Document + Photograph | I | IP
SECTION 6 – COMMENTS
| Specified | Recorded | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Head | 8.5m
Flow | 130L/sec |  | Certificate Number: