## General
SECTION 1 – GENERAL DETAILS
Project Name: | DCC11014 Water Pump Station Renewals - MT GRAND to WINGATUI | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561483 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council | [5 empty] | B | Report by Breach | CM | Construction Manager | Stephen Vorgers
Contract Number: | DCC11014 - WPS004 | [5 empty] | C | Check | CR | Cust. Representative | Joff Riley Mark Todd
Area/ Sub-System: | Stoney Knowe Pipeline |  |  | Lot ID Number: | N/A |  | D | Dimension Inspection | IP | Inspection Personnel | Bruce Allan
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | 561483-ITP-003 |  |  | Version: | DRAFT |  | H | Hold Point | OP | Operations Manager
ITP Description: | Pipeline Flushing | [5 empty] | I | Inspection | PM | Project Manager | Matt Paterson
Discipline: | Pre Pressure Test & Disinfection | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Aaron Sutherland
Specification: | C11014 Water Pump Station Renewals Specification 12581908 | [5 empty] | O | Operation | QE | Quality Engineer | Bruce Buxton
[7 empty] | R | Review | QM | QA Manager
Drawings: | Construction Issue Drawings as issued by GHD - Mt Grand to Wingatui Project Ref: 12581908-GHD-PS-MG-DRG-GN Drawings: G0001, M0001, M0002, M0011, S0001 & S0002 plus various other as-built drawings | [5 empty] | S | Subcontractor | SP | Supervisor | Bruce Allan
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Matt Paterson |  |  | Date: | 19-12-24 |  | W | Witness Point | SV | Surveyor
Quality Specified: | NZS4402:2010 | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Bruce Allan |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Paterson/Stephen Vorgers |  |  | Signature: |  | Matt Paterson |  |  | Date:
Customer Approval |  | Name: | Mark Todd / Iain Partington |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
3.1 | Adaptor to pipeline | Manufacture adapter spool to connect Downer pumping equipment onto pipe | All air valves installed and isolating valves on off position | None | Once | Specification - Water Main Pressure Test Record | I | IP
3.2 | Excavate to expose | Break existing flange and connect temporary spool | HS&E documentation. Traffic Management Plan Shoring (iff applicable) Ground disturbance | Downer HS&E Documentation | Once | Permit issuer | I | IP

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | Flushing | Flush pipeline to remove any loose material | Flush line until water runs clean | This ITP. Client Engineer witness. | once | Visual - monitor any excess debris | A / E / I | SP / PM / CR

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1 | Pipeline Flushed to Engineer approval | Pipeline Flush - Pass | Engineer / Client Approval | This ITP | once | Action/Visual/Issued document containing results/ Photograph | O | IP / CR
Timestamped photographs of flushing & short video clip as evidence - Engineer to Approve
5.2 | reinstatement | Disconnect Temporary Flushing Spool | Flushing acceptance. Engineer / Client Approval | This ITP | once | Verbal / Visual | O | IP / CR
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: