## General
SECTION 1 – GENERAL DETAILS
Project Name: | DCC11014 Water Pump Station Renewals - MT GRAND to WINGATUI | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561483 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council | [5 empty] | B | Report by Breach | CM | Construction Manager | Stephen Vorgers
Contract Number: | DCC11014 - WPS004 | [5 empty] | C | Check | CR | Cust. Representative | Joff Riley Mark Todd
Area/ Sub-System: | Re-Commissioned Water main Stoney Knowe Pipeline - Pressure testing |  |  | Lot ID Number: | N/A |  | D | Dimension Inspection | IP | Inspection Personnel | Bruce Allan
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | Inspection Test Plan 4 |  |  | Version: | DRAFT |  | H | Hold Point | OP | Operations Manager
ITP Description: | Pressure testing to re-commissioned water main | [5 empty] | I | Inspection | PM | Project Manager | Matt Paterson
Discipline: | Pressure test (Pre test & Final Test) | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Aaron Sutherland
Specification: | C11014 Water Pump Station Renewals Specification 12581908 | [5 empty] | O | Operation | QE | Quality Engineer | Callum Gillies
[7 empty] | R | Review | QM | QA Manager
Drawings: | Construction Issue Drawings as issued by GHD - Mt Grand to Wingatui Project Ref: 12581908-GHD-PS-MG-DRG-GN Drawings: G0001, M0001, M0002, M0011, S0001 & S0002 plus various other as-built drawings | [5 empty] | S | Subcontractor | SP | Supervisor | Bruce Allan
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Matt Paterson |  |  | Date: | 19-12-24 |  | W | Witness Point | SV | Surveyor
Quality Specified: | As Per Specification - Section 4.6 Acceptance Testing, Disinfection & Commissioning | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Bruce Allan |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Paterson/Stephen Vorgers |  |  | Signature: |  | Matt Paterson |  |  | Date:
Customer Approval |  | Name: | Mark Todd / Iain Partington |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
3.1 | System Primary Flush | Completion of system flush | Completion of ITP 3 | ITP3 | once | Visual + Photo + Document | I | IP
3.2 | System Pressure Pre -Test | Ball valves to air vents are in the closed position | 4.6.6 of Specification | Appendix E Specification | Once | Specification - Water Main Pressure Test Record | I | IP / CR
3.3 | System Pressure Test | Ball valves to air vents are in the closed position | 4.6.6 of Specification | Appendix E Specification | Once | Specification - Water Main Pressure Test Record | I | IP / CR

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | System Pre- test | Pre pressure test | Pressure test - Pass. Pressure test value be determined by Engineer. Use method as outlined in specification section 4.6.6.1 | Watermain Pressure test record - Attached | once | Visual - monitor any pressure drop/time. Report any issues or concerns to Engineer | A | PS / CR
4.2 | System Pressure Test | Pressure test | Pressure test - Pass. Pressure test value be determined by Engineer. Use method as outlined in specification section 4.6.6.1 | Watermain Pressure test record - Attached | once | Visual - monitor any pressure drop/time | A | PS / CR
Note: Client or Clients Representative to be present to witness pressure testing. Test pressure to be confirmed by the Engineer

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1 | System Pressure Testing | System Pressure Test - Pass | Pressure drop is less than specified value | Watermain Pressure Test Record - Submitted | once | Action/Visual/Issued document containing results/ Photograph | A | IP / QE / CR
Timestamped photographs of pressure gauge at critical stages to be submitted as evidence - Engineer to Approve
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: