## General
SECTION 1 – GENERAL DETAILS
Project Name: | DCC11014 Water Pump Station Renewals - MT GRAND to WINGATUI | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561483 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council | [5 empty] | B | Report by Breach | CM | Construction Manager | Stephen Vorgers
Contract Number: | DCC11014 - WPS004 | [5 empty] | C | Check | CR | Cust. Representative | Joff Riley Mark Todd
Area/ Sub-System: | Stoney Knowe Pipeline - Disinfection |  |  | Lot ID Number: | N/A |  | D | Dimension Inspection | IP | Inspection Personnel | Bruce Allan
[7 empty] | E | Examine | MC | Material Controller
ITP Number: | 561483-ITP-005 |  |  | Version: | DRAFT |  | H | Hold Point | OP | Operations Manager
ITP Description: | Re-Commissioned Water Main Disinfection | [5 empty] | I | Inspection | PM | Project Manager | Matt Paterson
Discipline: | Testing | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | Aaron Sutherland
Specification: | C11014 Water Pump Station Renewals Specification 12581908 | [5 empty] | O | Operation | QE | Quality Engineer | Bruce Buxton
[7 empty] | R | Review | QM | QA Manager
Drawings: | Construction Issue Drawings as issued by GHD - Mt Grand to Wingatui Pump Replacement Project Ref: 12581908-GHD-PS-MG-DRG-GN Drawings: G0001, M0001 to M0011, S0001 & S0002 | [5 empty] | S | Subcontractor | SP | Supervisor | Bruce Allan
[7 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Matt Paterson |  |  | Date: | 19-12-24 |  | W | Witness Point | SV | Surveyor
Quality Specified: | As Per Specification - Section 4.6 Acceptance Testing, Disinfection & Commissioning | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Bruce Allan |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: | Matt Paterson/Stephen Vorgers |  |  | Signature: |  | Matt Paterson |  |  | Date:
Customer Approval |  | Name: | Mark Todd / Iain Partington |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
3.1 | System Pressure Test | Completed installation Check all unions & Fittings are tight and leak free | 4.6.7 of Specification | Appendix E Specification | Once - After Pre system commission checks have been observed | Specification - Water Main Pressure Test Record | I | IP
3.2 | Drain pipeline of pressure test water | Upon completion of pressure test | 4.6.7 of Specification | Appendix E Specification | Post Pressure testing | Visual + Photograph | I | IP
3.3 | Arrange for client attendance/witness | During Disinfection process | Client representative availability | DCC Approved Flushing & Disinfection of Water Mains - Document | Once - After completed checks | Attached Flushing & Disinfection Document | I | IP

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | Ensure all pipe fittings, valves & other connections are tight and leak free (as per pressure test) | At completiion of installation and prior to pressure testing | Installation complete | Check list. Initial & Verification on the Schematic drawing | once | Visual - monitor any pressure drop/time | A | IP / SP
4.2 | Prepare to flush and disinfect new pipe, Fittings & pump | Post pressure testing | Pressure test - Pass | Pressure test - Pass Flushing & Disinfection of Water Mains Document | once | Closed loop circulation as installed by Bruce Allan | A | IP / SP
4.3 | Calculate system volume to determine required chemical quantity. | Pre-disinfect process | Watermeter or calculation | NZS4404:2010 | once | Visual - Document volumes on client provided tdocumentation | A | IP / SP
4.4 | Undertake disinfection process | Monitor circulation | Monitor values (this may need done more than once due to age) to achieve acceptable level | Client FLUSHING & DISINFECTION OF WATERMAIN DOCUMENT | once - or more as required | Visual, Document and photograph | A | IP / SP

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
5.1 | System Flush & Disinfect | Upon successful pressure test | NZS4404:2010 | DCC Standard Flushing & Disinfection of Watermain document | once | Action/ Visual/ Time/ Photograph | O | QE / CR
Video footage of pump and disinfection process in action - Engineer to Approve
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: