## Sheet1
3.1 | Control Pilot Valve Installation | Installation completion. All valves CHAR(AMP) Unions installed | Completion of ITP | ITP-002.3 | Once | Visual + Inspection + Photograph | I | IP | 3.1 - Control Pilot Valve Installation | Inspection Point: Quality Control Activity - Installation completion. All valves CHAR(AMP) Unions installed | Acceptance Criteria - Completion of ITP | Verifying Document - ITP-002.3 | Frequency - Once | Inspection Type (Visual, other) - Visual + Inspection + Photograph | Inspection: Key - I | Inspection: By - IP | 3.1 - Control Pilot Valve Installation
3.2 | Stoney Knowe Pipeline | Pressure testing | Pressure test pass | ITP-004 | Once | Visual + Inspection + Photograph | I | IP | 3.2 - Stoney Knowe Pipeline | Inspection Point: Quality Control Activity - Pressure testing | Acceptance Criteria - Pressure test pass | Verifying Document - ITP-004 | Frequency - Once | Inspection Type (Visual, other) - Visual + Inspection + Photograph | Inspection: Key - I | Inspection: By - IP | Inspection Point: Quality Control Activity - Installation completion. All valves CHAR(AMP) Unions installed
3.3 | Stoney Knowe Pipeline | Pipeline disinfection | Pipeline disinfection pass | ITP-005 | Once | Visual + Inspection + Photograph | I | IP | 3.3 - Stoney Knowe Pipeline | Inspection Point: Quality Control Activity - Pipeline disinfection | Acceptance Criteria - Pipeline disinfection pass | Verifying Document - ITP-005 | Frequency - Once | Inspection Type (Visual, other) - Visual + Inspection + Photograph | Inspection: Key - I | Inspection: By - IP | Acceptance Criteria - Completion of ITP
3.4 | Pumps 1 through 6 are installed and commissioned | Verify commissioning is complete via Grundfos | Completion of Commissioning | Grundfos report | Once | Inspection + Documentation | I | IP | 3.4 - Pumps 1 through 6 are installed and commissioned | Inspection Point: Quality Control Activity - Verify commissioning is complete via Grundfos | Acceptance Criteria - Completion of Commissioning | Verifying Document - Grundfos report | Frequency - Once | Inspection Type (Visual, other) - Inspection + Documentation | Inspection: Key - I | Inspection: By - IP | Verifying Document - ITP-002.3
4.1 | Commission Stoney Knowe Control Valve | Set to achieve correct flow rate | 70 litres/sec achieved | Commissioning Methodology/Clavel Commissioning sheet | once | Visual + Photographs + document | I | IP | 4.1 - Commission Stoney Knowe Control Valve | Inspection Point: Quality Control Activity - Set to achieve correct flow rate | Acceptance Criteria - 70 litres/sec achieved | Verifying Document - Commissioning Methodology/Clavel Commissioning sheet | Frequency - once | Inspection Type (Visual, other) - Visual + Photographs + document | Inspection: Key - I | Inspection: By - IP | Frequency - Once
4.2 | Solenoid function test | Test function of solenoid shut-off | Shut off when reservoir is full | Reservoir levels | once | Visual + Photographs + document | I | IP | 4.2 - Solenoid function test | Inspection Point: Quality Control Activity - Test function of solenoid shut-off | Acceptance Criteria - Shut off when reservoir is full | Verifying Document - Reservoir levels | Frequency - once | Inspection Type (Visual, other) - Visual + Photographs + document | Inspection: Key - I | Inspection: By - IP | Inspection Type (Visual, other) - Visual + Inspection + Photograph
5.1 | Record Value | At completion of valve commissioning | When consistent results are achieved | Commissioning record sheet / Operation CHAR(AMP) Maintenance Manual | once | Visual + Document + Photograph | I | IP | 5.1 - Record Value | Inspection Point: Quality Control Activity - At completion of valve commissioning | Acceptance Criteria - When consistent results are achieved | Verifying Document - Commissioning record sheet / Operation CHAR(AMP) Maintenance Manual | Frequency - once | Inspection Type (Visual, other) - Visual + Document + Photograph | Inspection: Key - I | Inspection: By - IP | Inspection: Key - I
5.2 | Record solenoid valve feedback values | At completion of valve commissioning | When consistent results are achieved | Commissioning record sheet / Operation CHAR(AMP) Maintenance Manual | once | Visual + Document + Photograph | I | IP | 5.2 - Record solenoid valve feedback values | Inspection Point: Quality Control Activity - At completion of valve commissioning | Acceptance Criteria - When consistent results are achieved | Verifying Document - Commissioning record sheet / Operation CHAR(AMP) Maintenance Manual | Frequency - once | Inspection Type (Visual, other) - Visual + Document + Photograph | Inspection: Key - I | Inspection: By - IP | Inspection: By - IP
3.2 - Stoney Knowe Pipeline
Inspection Point: Quality Control Activity - Pressure testing
Acceptance Criteria - Pressure test pass
Verifying Document - ITP-004
Frequency - Once
Inspection Type (Visual, other) - Visual + Inspection + Photograph
Inspection: Key - I
Inspection: By - IP
3.3 - Stoney Knowe Pipeline
Inspection Point: Quality Control Activity - Pipeline disinfection
Acceptance Criteria - Pipeline disinfection pass
Verifying Document - ITP-005
Frequency - Once
Inspection Type (Visual, other) - Visual + Inspection + Photograph
Inspection: Key - I
Inspection: By - IP
3.4 - Pumps 1 through 6 are installed and commissioned
Inspection Point: Quality Control Activity - Verify commissioning is complete via Grundfos
Acceptance Criteria - Completion of Commissioning
Verifying Document - Grundfos report
Frequency - Once
Inspection Type (Visual, other) - Inspection + Documentation
Inspection: Key - I
Inspection: By - IP
4.1 - Commission Stoney Knowe Control Valve
Inspection Point: Quality Control Activity - Set to achieve correct flow rate
Acceptance Criteria - 70 litres/sec achieved
Verifying Document - Commissioning Methodology/Clavel Commissioning sheet
Frequency - once
Inspection Type (Visual, other) - Visual + Photographs + document
Inspection: Key - I
Inspection: By - IP
4.2 - Solenoid function test
Inspection Point: Quality Control Activity - Test function of solenoid shut-off
Acceptance Criteria - Shut off when reservoir is full
Verifying Document - Reservoir levels
Frequency - once
Inspection Type (Visual, other) - Visual + Photographs + document
Inspection: Key - I
Inspection: By - IP
5.1 - Record Value
Inspection Point: Quality Control Activity - At completion of valve commissioning
Acceptance Criteria - When consistent results are achieved
Verifying Document - Commissioning record sheet / Operation CHAR(AMP) Maintenance Manual
Frequency - once
Inspection Type (Visual, other) - Visual + Document + Photograph
Inspection: Key - I
Inspection: By - IP
5.2 - Record solenoid valve feedback values
Inspection Point: Quality Control Activity - At completion of valve commissioning
Acceptance Criteria - When consistent results are achieved
Verifying Document - Commissioning record sheet / Operation CHAR(AMP) Maintenance Manual
Frequency - once
Inspection Type (Visual, other) - Visual + Document + Photograph
Inspection: Key - I
Inspection: By - IP