## Enabling Works
ITP - The Strand
Enabling Works - Footpath, Kerb and channel
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
| Site Set out | Surveyor | Surveyor | Every site | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
Kerb and Channel
| Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Every 10m for Scalar | Subgrade CBR > 5 | In process Inspection | Scalar Sheet | Site Engineer
| Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Every 10m for Clegg | Kerb & Channel to be laid using basalt kerb hand-laid on compacted GAP40. Thickness - 100mm on Footpath / 300mm on roads CVI > 25 | In process Inspection | Clegg Sheet Photos | Site Engineer
| Kerb Setout | QA FORM | TDM Technical Standards - KC0001 | Every site | Site Setout as per construction drawings and heights and falls verified | Mandatory HOLD POINT - | K&C Pre-pour Checklist | Site Engineer / MSQA
| Channel Material | QA FORM | TDM Technical Standards - KC0001 | Every site | Concrete Strength 20MPa @28 Days | In process Inspection | Concrete Docket | Site Engineer
| Channel Level | QA FORM | TDM Technical Standards - KC0001 | Every site | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level | In process Inspection | Photos | Site Engineer
Footpath
| Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m intervals | Subgrade CBR > 3 | In process Inspection | Scalar Sheet | Site Engineer
| Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m Intervals | Basecourse - 100mm min. thickness Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX) Concrete Strength 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing) Standard Footpath - 100mm thick Heavy Duty - 150mm thick | Inprocess Inspection | Clegg Sheet, photos. Concrete Plant Docket | Site Engineer
| AC Footpaths | QA FORM | TDM Technical Standards - FP0003 | 10m Intervals | Subgrade -(CBR > 3) Basecourse - 150mm min. thickness GAP40 Clegg CIV > 27 DG10/Fine asphalt mix used | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer
Bus Shelter Pad
| Bus shelter pad (oOh!media) | QA FORM | ITP | Each pad | 4.65m x 1.6m total pqd area Basecourse to be 50-100mm thick 2 Layers of SE72 mesh within 200mm 25MPa thick concrete Clegg CIV > 12 Bolting the bus shelter on top of the concrete Pour an additional 100mm thick 20Mpa concrete over the bus shelter feet to match existing footpath | Inprocess Inspection | Clegg Sheet, photos. Concrete Plant Docket | Site Engineer
Pram Crossing
| Pram Crossing | Visual | TDM Technical Standards - FP006 | Each Crossing | Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. Tactiles Directional & warning - 60mm; 600mm flares;width as per design; Slope no greater than 1:12 where practicably possible Clegg CIV > 12 | Mandatory HOLD POINT - | Photos | Site Engineer
| Service Covers and Street Furniture | Visual | AT Contract Specification 14000 | Everysite | Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works. | Inprocess Inspection | Nil | Site Engineer
Asbuilts
| As built information | Drawings | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | As built drawings | In Process Inspection | Asbuilt records | Site Engineer & PM
| RAMM DATA | RAMM DATA SHEET | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | RAMM SHEET | In Process Inspection | RAMM Sheet | Site Engineer & PM
ITP APPROVAL
Prepared By |  | Asith Gunaratna | Initial | AG |  | Date: | 2025-01-16
Approving Delegate |  | Daeyoung Jeong | Initial | DJ |  | Date: | 2025-01-16
0

## Traffic Islands
ITP - The Strand
Traffic Island
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Materials
1 | Kerb | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Every site | Kerb to be laid using precast hand-laid | In process Inspection | FH Concrete QA sheet Photos | Site Engineer
Construction
2 | Survey Setout | Survey | Setout Kerb Alignment required to construct to design | Prior to commencement. | Survey | In process Inspection | Survey Receipt. | Site Engineer
3A | In-Situ Concrete Island | QA FORM | TDM Technical Standards - IS0001 | Each Site | Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm CVI > 12 | In process Inspection | Photos | Site Engineer
4 | Concrete Infill | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | 150/180mm depth of 20MPa Concrete Surface finish to confirm with Engineer's Rep Cross Fall of 2% or max rise in centre of 180mm | In process Inspection | FH Concrete QA sheet. Concrete Delivery Dockets | Site Engineer
As-builts
7 | As built information | Drawings | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | As built drawings | In Process Inspection | As-built records | Supervisor and Engineer
7 | RAMM DATA | RAMM DATA SHEET | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | RAMM SHEET | In Process Inspection | As-built records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Asith Gunaratna | Initial | AG |  | Date: | 2025-01-16
Approving Delegate |  | Daeyoung Jeong | Initial | DJ |  | Date: | 2025-01-16

## Ducting and Traffic Signals
|  |  |  | ITP |  |  | Approved |  | Signature
|  |  |  | Contract Name: | The Strand |  | FH Engineer |  | AG
|  |  |  | Procedure: | Traffic signal ducting and Pole erection |  | FH PM |  | DJ
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | Potholing and traffic signal installation |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
Ducting
1 | Permits | H | Obtain Permits | As required | Document Review | Authorisation to work, dig permit and service provider permits | This ITP signed | Site Engineer
2 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
3 | Survey Setout | H | Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor. | Prior to commencement | Survey | Consistency with Drawings and Specifiactions | Survey Records | Site Engineer
|  | H | Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation. | Prior to commencement | Visual Inspection | Consistency with Drawings and Specifiactions | Photos / Engineers approval documentation | Site Engineer
4 | Locate existing services by hand digging/ hydrovac | W | Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation | Prior to Installation | Potholing | All conflicts have been located and survey as built recorded | Digging/Excavating Control Checklist | Site Engineer
5 | Material Compliance | H | Ensure duct pipes and poles are as per drawings and specification | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | Site Engineer
|  | H | Ensure all concrete used is 20MPa mix | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | Site Engineer
6 | Trenching | H | Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 1000mm cover to duct when under berm/footpath (1500mm cover when under road crossing - non motorway/expressway) | 10m Intervals | Visual Inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
6.1 |  | H | Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs | 10m Intervals | Measure | Ensure trench alignment and levels match the design drawings | Dipsheet & Photos | Site Engineer
7 | Duct Installation | W | Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct. | Prior to Installation | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
7.1 |  | H | Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
7.2 |  | H | Asbuilt Survey | 20m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Survey Records | Site Engineer
8 | Bedding | H | Lay min. 100mm pit sand or finer for bedding and haunching | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
9 | Warning Tape | H | Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines. | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | Site Engineer
10 | Traffic signal pole erection | H | Ensure Design engineer as inspected pole locations prior to proceeding | Per pole | Visual Inspection | Sign off by design engineer | Engineer sign off
10.1 |  | H | Ensure Pot hole is as per design with required depths and widths | Per pole | Measure | Consistency with Drawings and Specifiactions | Dipsheet & Photos
10.2 |  | H | Ensure Poles are plumb and within design tolerances | Per pole | Visual Inspection | Consistency with Drawings and Specifiactions | Photos
11 | As-builts & C&I Diagram | H | As-built as per ATOC requirements | At the completion of the Lot of work | Drawings | As-built as per ATOC requirements | Asbuilt Drawing | Site Engineer
Comments:
Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Project manager |  |  |  |  | Signature: |  |  | Date:
QA checked By Contract Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design/AT Engineer: |  |  |  |  | Signature: |  |  | Date: