## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - The Strand - Enabling Works - Footpath, Kerb and channel | itp |  |  |  |  | ITP - The Strand - Enabling Works - Footpath, Kerb and channel REV1
section | Site Set out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | HOLD POINT
section | Kerb and Channel
checkpoint | 2 - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every 10m for Scalar
label | ACCEPTANCE CRITERIA: Subgrade CBR > 5
label | HOLD POINT: In process Inspection
label | RECORDS: Scalar Sheet
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every 10m for Clegg
label | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using basalt kerb hand-laid on compacted GAP40.
label | ○ Thickness - 100mm on Footpath / 300mm on roads
label | ○ CVI > 25
label | HOLD POINT: In process Inspection
label | RECORDS: Clegg Sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Kerb Setout
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Site Setout as per construction drawings and heights and falls verified
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: K&C Pre-pour Checklist
label | ONSITE RESPONSIBILITY: Site Engineer / MSQA
holdpoint | HOLD POINT
checkpoint | 5 - Channel Material
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days
label | HOLD POINT: In process Inspection
label | RECORDS: Concrete Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6 - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Footpath
checkpoint | 7 - Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m intervals
label | ACCEPTANCE CRITERIA: Subgrade CBR > 3
label | HOLD POINT: In process Inspection
label | RECORDS: Scalar Sheet
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 8 - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness
label | ○ Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX)
label | ○ Concrete Strength 20 MPa @ 28 days.
label | ○ 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing)
label | ○ Standard Footpath - 100mm thick
label | ○ Heavy Duty - 150mm thick
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 9 - AC Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0003
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
label | ○ Basecourse - 150mm min. thickness GAP40
label | ○ Clegg CIV > 27
label | ○ DG10/Fine asphalt mix used
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
section | Pram Crossing
checkpoint | 10 - Pram Crossing
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FP006
label | FREQUENCY: Each Crossing
label | ACCEPTANCE CRITERIA: Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | ○ Tactiles Directional & warning - 60mm; 600mm flares;width as per design;
label | ○ Slope no greater than 1:12 where practicably possible
label | ○ Clegg CIV > 12
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | HOLD POINT
checkpoint | 11 - Service Covers and Street Furniture
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AT Contract Specification 14000
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Nil
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 12 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Site Engineer & PM
checkpoint | 13 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: RAMM Sheet
label | ONSITE RESPONSIBILITY: Site Engineer & PM
section | ITP APPROVAL
checkpoint | Approvals
label | Prepared By: Asith Gunaratna
label | Approving Delegate: Daeyoung Jeong
checklist | ITP - The Strand - Traffic Islands | itp |  |  |  |  | ITP - The Strand - Traffic Islands REV1
section | Materials
checkpoint | 1 - Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 2 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: In process Inspection
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3A - In-Situ Concrete Island
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm
label | ○ CVI > 12
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Infill
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 150/180mm depth of 20MPa Concrete
label | ○ Surface finish to confirm with Engineer's Rep
label | ○ Cross Fall of 2% or max rise in centre of 180mm
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet, Concrete Delivery Dockets
label | ONSITE RESPONSIBILITY: Site Engineer
section | As-builts
checkpoint | 7 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 7 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | Approvals
label | Prepared By: Asith Gunaratna
label | Approving Delegate: Daeyoung Jeong
checklist | ITP - The Strand - Traffic signal ducting and Pole erection | itp |  |  |  |  | ITP - The Strand - Traffic signal ducting and Pole erection REV1
section | Ducting
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Obtain Permits
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits
label | RECORDS: This ITP signed
holdpoint | HOLD POINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA:
label | RECORDS: Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 3 - Survey Setout (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Survey Records
holdpoint | HOLD POINT
checkpoint | 3 - Survey Setout (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos / Engineers approval documentation
holdpoint | HOLD POINT
checkpoint | 4 - Locate existing services by hand digging/ hydrovac
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
label | FREQUENCY: Prior to Installation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
label | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
label | RECORDS: Digging/Excavating Control Checklist
checkpoint | 5 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure duct pipes and poles are as per drawings and specification
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
label | CONFORMANCE CRITERIA:
label | RECORDS: Delivery Docket
holdpoint | HOLD POINT
checkpoint | 5 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all concrete used is 20MPa mix
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
label | CONFORMANCE CRITERIA:
label | RECORDS: Delivery Docket
holdpoint | HOLD POINT
checkpoint | 6 - Trenching
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 1000mm cover to duct when under berm/footpath (1500mm cover when under road crossing - non motorway/expressway)
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | HOLD POINT
checkpoint | 6.1 - Trenching
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
label | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
label | RECORDS: Dipsheet & Photos
holdpoint | HOLD POINT
checkpoint | 7 - Duct Installation
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
label | FREQUENCY: Prior to Installation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
checkpoint | 7.1 - Duct Installation
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | HOLD POINT
checkpoint | 7.2 - Duct Installation
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Asbuilt Survey
label | FREQUENCY: 20m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Survey Records
holdpoint | HOLD POINT
checkpoint | 8 - Bedding
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Lay min. 100mm pit sand or finer for bedding and haunching
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | HOLD POINT
checkpoint | 9 - Warning Tape
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | HOLD POINT
checkpoint | 10 - Traffic signal pole erection
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Design engineer as inspected pole locations prior to proceeding
label | FREQUENCY: Per pole
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Sign off by design engineer
label | RECORDS: Engineer sign off
holdpoint | HOLD POINT
checkpoint | 10.1 - Traffic signal pole erection
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Pot hole is as per design with required depths and widths
label | FREQUENCY: Per pole
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Dipsheet & Photos
holdpoint | HOLD POINT
checkpoint | 10.2 - Traffic signal pole erection
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Poles are plumb and within design tolerances
label | FREQUENCY: Per pole
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
label | RECORDS: Photos
holdpoint | HOLD POINT
checkpoint | 11 - As-builts & C&I Diagram
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: As-built as per ATOC requirements
label | FREQUENCY: At the completion of the Lot of work
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
label | CONFORMANCE CRITERIA: As-built as per ATOC requirements
label | RECORDS: Asbuilt Drawing
holdpoint | HOLD POINT