## Seperate
Type | Name | Values | Prompting Name | Usage Count | Resource Id
CHECKLIST | 00. PRELIMINARY ACTIVITIES |  | 00. PRELIMINARY ACTIVITIES
SECTION | PRODUCTION PLANNING REQUIREMENTS FOR EACH PRECAST UNIT TYPE
checkpoint | Contractor's Construction / Installation Programme
tickbox | Verify Production Lot System / Precast Unit identification accepted by Contractor
tickbox | Verify programme details are current
tickbox | Verify programme dates are achievable
tickbox | Verify Casting Programme finalised
checkpoint | Production Area
tickbox | Verify work area identified including storage of raw materials
tickbox | Easy access for concrete agitator trucks / craneage / forklift
tickbox | Curing facilities available
checkpoint | Storage Area
tickbox | Adequate area for potential long term storage
tickbox | Bearing capacity of storage area will meet loading of precast units
tickbox | Unit Layout plan developed
tickbox | Adequate area for craneage operation and access by heavy haulage
SECTION | Plant / Equipment / Procurements
checkpoint | Verify moulding received and dimensions checked
tickbox | Curing facility available as required
tickbox | Jigs / working platform (rebar) available as required
tickbox | Verify Curing Methodology signed off
tickbox | Verify Curing System functional
checkpoint | Verify Stressing System / bed signed off by member of MIAustE as required
checkpoint | Craneage available as required
checkpoint | Procurements
tickbox | Verify Reinforcement ordered and delivery commenced
tickbox | Verify concrete order process agreed with concrete supplier
tickbox | Verify Strand / Couplers ordered and delivery commenced
tickbox | Verify Contractor Supplied Product ordered and delivery commenced
tickbox | Verify cast-in items ordered and delivery commenced
tickbox | Verify lifting systems in precast unit signed off
tickbox | Verify lifting equipment available and signed off by Authority as required
tickbox | Verify production consumables ordered and delivery commenced
textbox | specify others
CHECKLIST | 01. MDR COMMON BOOK |  | 01. MDR COMMON BOOK
SECTION | A - PERMACAST CERTIFICATE OF CONFORMANCE
checkpoint | A1 - Certificate of Conformance for all Precast Concrete Items
checkpoint | A2 - Permacast ISO 9001 Certification
SECTION | B - PERMACAST'S DOCUMENTATION (approved and signed off)
checkpoint | B1 - Register for Quality Plan, Inspection & Test Plans, Work Method Statements, Manufacturer's Data Reports
checkpoint | B2 - Project Quality Management Plan and Work Method Statement
checkpoint | B3 - Inspection & Test Plans (Approved copies)
SECTION | C - DRAWINGS - IFC and SHOP
checkpoint | C1 - Register of IFC drawings
checkpoint | C2 - Register of Shop Drawings
checkpoint | C3 - Register of Lifting Designs
SECTION | D - CHANGE MANAGEMENT
checkpoint | D1 - Technical Query Register
checkpoint | D2 - Completed Technical Queries
checkpoint | D3 - Non-Conformance Register
checkpoint | D4 - Closed Out Non-Conformance Reports
checkpoint | D5 - Defects Register
checkpoint | D6 - Defects to be carried through to Defects Liability Period
SECTION | E - CONCRETE
checkpoint | E1 - Concrete Supplier: ISO 9001 Certificate
checkpoint | E2 - Aggregate Supplier: ISO 9001 Certificate
checkpoint | E3 - Concrete Mix Designs
checkpoint | E4 - CMRS Cement Certificate
checkpoint | E5 - Concrete Aggregate Reports
SECTION | F - REINFORCEMENT
checkpoint | F1 - Reinforcement Supplier: ISO 9001 Certificate
checkpoint | F2 - ACRS Certificate
checkpoint | F3 - Register of Mill Certificates
checkpoint | F4 - Mill Certificates
SECTION | G - STRESSING (if applicable)
checkpoint | G1 - Strand Supplier: ISO 9001 Certificate
checkpoint | G2 - Register of Stressing Coils
checkpoint | G3 - Mill Certificates
checkpoint | G4 - Stressing Calculations
SECTION | H - CAST IN ITEMS
checkpoint | H1 - Cast-in Items Compliance Records
SECTION | I - REINFORCEMENT WELDING (if applicable)
checkpoint | I1 - Weld Procedure Specifications / WPQR
checkpoint | I2 - Welder Qualification Register
checkpoint | I3 - Welder Qualifications
SECTION | J - CALIBRATION OF INSPECTION, MEASURING AND TEST EQUIPMENT
checkpoint | J1 - Register of NATA Laboratories Used for the Precast Project
checkpoint | J2 - In-house Concrete Crusher Calibration Certificate
checkpoint | J3 - Calibration of Jacks / Gauges (if applicable)
checkpoint | J4 - Other Calibration Records
SECTION | K - DELIVERY OF PRECAST UNITS
checkpoint | K1 - Register of Permacast IRC Certificates
checkpoint | K2 - Permacast IRC Certificates
checkpoint | K3 - Register of Permacast Conformance Certificates
checkpoint | K4 - Permacast Conformance Certificates
checkpoint | K5 - Register of Deliveries
checkpoint | K6 - Delivery Dockets
SECTION | L - AUDITS
checkpoint | L1 - Register of Audits
checkpoint | L2 - Audit Reports
CHECKLIST | 02. PRE-POUR CHECKLIST-STAGE 1 |  | 02. PRE-POUR CHECKLIST-STAGE 1
SECTION | PRE-POUR CHECKLIST-STAGE 1
checkpoint-no-value | Details
textbox | Cast Number
textbox | Specify Precast ID (separating each with a comma):
textbox | Strand Arrangement Type (If Required)
checkpoint | Shop Drawings approved for Works
Date | IFC Date
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
tickbox | Mould set-out drawing provided
tickbox | Length
tickbox | Width
tickbox | Height
tickbox | Straightness
tickbox | Cross-section
checkpoint | Mould Surface Checked
tickbox | Cleaned
tickbox | Sealed
tickbox | Rubbers in Place
tickbox | Oiled
tickbox | Chamfers / Drip Groove in Place
tickbox | shutters angle checked
tickbox | Temporary props / Push-pull spreader in place and secured
checkpoint | Reinforcement in Accordance with Drawings
tickbox | Reinforcement size
tickbox | Reinforcement Quantity
tickbox | Lap Length
tickbox | Splicing
tickbox | Blockout recess around lifting Hoops (If Required)
tickbox | Additional reinforcement around Lifters (If Required)
tickbox | Bar Chairs / Deck rails
tickbox | Cover maintained and within tolerance
checkpoint | All Cast-in Items are installed in accordance with Drawings and Tolerances
tickbox | All Ferrules are installed in accordance with Drawings and Tolerances
textbox | Ferrules Type / Quantity
tickbox | All Stainless Items are installed in accordance with Drawings and Tolerances
textbox | Items:
tickbox | All Blockout Conduits / PT ducts / Stressbar are installed in accordance with Drawings and Tolerances
textbox | Temporary Works Conduits
textbox | Transport Holes Conduits
textbox | Bearings
textbox | PT ducts
textbox | Stress Bars
tickbox | All Lifting Inserts are installed in accordance with Drawings and Tolerances
dropdown | Lifting System
textbox | Others (Specify)
tickbox | Additional reinforcement around Lifters (If Required)
tickbox | All Couplers are installed in accordance with Drawings
textbox | Couplers Type and Quantity
tickbox | Other Casting Items are installed in accordance with Drawings
textbox | Type and Quantity
checkpoint | Earthing and Bonding is installed in accordance with Drawings
tickbox | Earthing Terminals Specify Type and Quantity
tickbox | Flexi cables
tickbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
tickbox | <20 mOhm across cage Length
tickbox | Checklist Completed (attach results)
signoff | Client Hold / Withness Point
checkpoint | Post-Tensioning Equipment is installed in accordance with Drawings and Tolerances
label | Verify
textbox | Tendon Types
tickbox | Profile
tickbox | Firmly secured to rebar
tickbox | Grout tubes, Breathing Tubes and Grout Vents secure / sealed
textbox | Anchors installed / secured
tickbox | Temporary blockouts in Tendons
signoff | Client Hold / Withness Point
checkpoint | Prestressing Strands
label | Verify
textbox | No of strands
textbox | Debonded strands encased to correct length
textbox | Enter Coil Number Used for this Cast
tickbox | Sag Load all Strand
tickbox | Full Load: Multi-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
tickbox | Full Load: Singel-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
signoff | Prepare Stressing Records and Submit to Client for Review (HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint | QA Engineer Check Completed by
signoff | Pre-lifting cage inspection (Client present)
signoff | Pre-Pour Mould inspection (Client present)
CHECKLIST | 03. EARTHING AND BONDING CHECKLIST |  | 03. EARTHING AND BONDING CHECKLIST
SECTION | EARTHING AND BONDING DETAILS
checkpoint | Earthing and Bonding is installed in accordance with Drawings
tickbox | Earthing Terminals Specify Type and Quantity
tickbox | Flexi cables
tickbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
tickbox | <20 mOhm across cage Length
tickbox | Checklist Completed (attach results)
signoff | Client Hold / Withness Point
CHECKLIST | 04. POST-TENSIONING CHECKLIST |  | 04. POST-TENSIONING CHECKLIST
SECTION | POST-TENSIONING DETAILS
checkpoint | Post-Tensioning Equipment is installed in accordance with Drawings and Tolerances
label | Verify
textbox | Tendon Types
tickbox | Profile
tickbox | Firmly secured to rebar
tickbox | Grout tubes, Breathing Tubes and Grout Vents secure / sealed
textbox | Anchors installed / secured
tickbox | Temporary blockouts in Tendons
signoff | Client Hold / Withness Point
CHECKLIST | 05. PRESTRESSING CHECKLIST |  | 05. PRESTRESSING CHECKLIST
SECTION | PRESTRESSING DETAILS
checkpoint | Prestressing Strands
label | Verify
textbox | No of strands
textbox | Debonded strands encased to correct length
textbox | Enter Coil Number Used for this Cast
tickbox | Sag Load all Strand
tickbox | Full Load: Multi-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
tickbox | Full Load: Singel-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
CHECKLIST | 06. TUBS / BOATS CHECKLIST |  | 06. TUBS / BOATS CHECKLIST
SECTION | INSTALLATION OF TUBS / BOATS
checkpoint | Installation Details
tickbox | Tubs are tightened and positioned correctly
tickbox | All Sliding arms are locked in position
tickbox | All accrow props are locked in position
tickbox | Dimensions of Tub and Webb are correct
tickbox | All feet for tubs resting on mould & bolted down
tickbox | Tubs have release agent
CHECKLIST | 07. COOLING PIPES CHECKLIST |  | 07. COOLING PIPES CHECKLIST
SECTION | INSTALLATION OF COOLING PIPES
checkpoint | Water Cooling Pipes
label | Verify
textbox | Number, location and installation of water cooling pipes as per approved WMS
CHECKLIST | 08. TEMPERATURE CONTROL (LOGGERS) CHECKLIST |  | 08. TEMPERATURE CONTROL (LOGGERS) CHECKLIST
SECTION | TEMPERATURE LOGGERS
checkpoint | All Temperature Loggers are installed as per Approved WMS
tickbox | Ensure All temperature Loggers are Working (Check Maturix)
tickbox | Number, location and installation of loggers matches WMS
tickbox | Every 25m
tickbox | 1 x Core (If Required)
tickbox | 1 x Within Cover Zone
tickbox | 1 x Within Tent/Tarp Enclosure (Outside concrete)
tickbox | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
textbox | Specify Extra Loggers If Required
CHECKLIST | 09. SUPERVISOR / SUBCONTRACTOR CHECKLIST |  | 09. SUPERVISOR / SUBCONTRACTOR CHECKLIST
SECTION | SUPERVISOR / SUBCONTRACTOR CHECK
checkpoint | Supervisor Release to Engineering Team
tickbox | Verify all concrete placement plant / equipment available
tickbox | Concrete Supplier of pour Notified
tickbox | NATA Testing Laboratory of pour Notified
signoff | Supervisor Hold / Withness Point
CHECKLIST | 10. CASTING AND STRIPPING CHECKLIST |  | 10. CASTING AND STRIPPING CHECKLIST
SECTION | CASTING DETAILS
checkpoint | Pour Detail
date | Cast Date
textbox | Concrete Delivery Docket (list All And Attach Dockets)
textbox | Total Concrete Volume (m3)
textbox | Specify Mix Design Verified/Used
textbox | Ambient Temperature within Limits (max 38°C)
textbox | Concrete Temperature within Limits (max 32°C)
tickbox | Slump within Allowable Tolerance (First truck and every 20m3)
textbox | Slump (list all)
checkpoint | Truck Tested for strength
tickbox | If volume <=20m3, 2 sets min required
tickbox | If volume >20m3 & <= 40m3, 2 sets min required (every 20m3 tested)
tickbox | If volume >40m3, sample every 20m3
tickbox | 1 * 7 Days and 3 * 28 Days per test (Total 4 Per Test)
tickbox | Cast 2-4 Cylinders for Destressing / Stripping / Lifting / Curing (PMC Internal)
textbox | Test Report Reference Number (list all)
checkpoint | Concreting
tickbox | Vibration adedquate
tickbox | Time Lag Between Trucks is not exceeded
tickbox | Concrete Placed within allowable time from Batching Plant
tickbox | No Free Fall During Pour
tickbox | Required Finish Applied as per Drawings
checkpoint | Curing
tickbox | Concrete Covered Overnight and Tent sealed
tickbox | Cylinders Stored next to Bed and covered as per AS1012
tickbox | Verify (if used) Temperature loggers are connected and recording and set the temperature alarm to 65°C.
tickbox | Verify (if used) Pipes connected, pump working, no leaks in mould
tickbox | Verify (if used) Steam Temperature Monitors installed and connected
SECTION | STRIPPING DETAILS
checkpoint | STRIPPING DETAILS
date | Date Stripped
checkpoint | Minimum Required Strength for Stripping, Destressing, Lifting, and Curing Achieved
dropdown | Strength Determined by | Curing Strength: 70% of fc (Characteristic design strength)
textbox | Specify Min Stripping Strength and Record Strength MPa (Mpa: Reading / 7.851)
textbox | Specify Min Destressing Strength and Record Strength MPa (Mpa: Reading / 7.851)
textbox | Specify Min Lifting Strength and Record Strength MPa (Mpa: Reading / 7.851)
textbox | Specify Min Curing Strength and Record Strength MPa (Mpa: Reading / 7.851)
textbox | Specify Strength by Maturity if available
tickbox | Mould and Steam Cured until the curing strength achieved
tickbox | Curing Strength: 70% of fc (Characteristic design strength)
signoff | Client Hold / Withness Point
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
tickbox | Product ID, Weight, Cast Date, Job Number
checkpoint | Storage as per Approved Temporary Works Drawings
tickbox | Verify supports complies with approved storage drawings and Orientation and Location matches with delivery Orientation and Schedule
checkpoint | Secondary Curing as per Approved Methodology
tickbox | Temperature 5 degrees past its peak
tickbox | Differential between Core and Ambient As Per Spec i.e., within 30 degrees
tickbox | Differential between Core and Cover As Per Spec i.e., within 25 degrees
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
tickbox | Length
tickbox | Width
tickbox | Height
tickbox | Straightness
tickbox | Cross-section
tickbox | Check all critical dimensions comply (Bearing Location)
checkpoint | Specified Finish Achieved
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
tickbox | Ferrules
tickbox | Couplers
tickbox | Stainless Items
tickbox | Lifters
tickbox | Blockouts
tickbox | Earthing and Bonding
tickbox | Post-Tensioning Equipment
checkpoint | Post-Pour Works Completed (As Required)
tickbox | Strands have been cut flush and epoxied.
tickbox | Strands are properly bulbed.
tickbox | Nailplates, recesses, and other obstructions have been removed.
tickbox | Couplers and ferrules are cleaned and capped.
tickbox | Earthing and bonding terminals are cleaned, with bolts securely screwed.
tickbox | Chamfers are clean, neat, and present on all required edges.
tickbox | Cooling pipes are drained of water and filled with grout as per the Work Method Statement (WMS).
tickbox | All drain holes, service ducts, and blockouts are cleaned and cut as required.
tickbox | Temperature logging wires are cut flush with the surface.
tickbox | Starter bars are cleaned and bent as specified.
tickbox | Surfaces requiring roughening are greencut according to the drawings.
tickbox | The top concrete surface is free of loose concrete.
tickbox | Areas requiring U2/U3 finish do not have a roughened surface.
tickbox | Bug holes and air bubbles have been identified, with sizes and distribution compared to AS Standards.
tickbox | All blemishes (dry concrete) have been removed and patched.
tickbox | Any discoloration on external/visible surfaces has been removed by sanding.
tickbox | All generic post-pour works are completed as required.
checkpoint | Temperature Logging Completed and Conforming. Attach Results
CHECKLIST | 11. PRECAST SURVAY |  | 11. PRECAST SURVAY
SECTION | HOG/BOW DETAILS
checkpoint | Survey Hog of Beams
textbox | First Reading (mm) (Once Stripped)
date | First Reading date
textbox | Second Reading (mm) (After casting stage 2 And / Or atleast 7days after stage 1 casting) (if required)
date | Second Reading date
textbox | Third Reading (mm) (At 28 days after stage 1 casting)(if required)
date | Third Reading date
textbox | Final Reading (mm) (7 days prior to scheduled delivery)
date | Final Reading date
SECTION | GENERAL SURVAY
checkpoint | Survey Details
tickbox | Geometry Survay (Attach the files)
tickbox | Stress bars
tickbox | Ferrules
tickbox | Bearings
textbox | Others (specify)
CHECKLIST | 12.CHECKLIST-STAGE 2 |  | 12.CHECKLIST-STAGE 2
SECTION | PRE-POUR CHECKLIST
checkpoint-no-value | Details
textbox | Cast Number
textbox | Specify Precast ID:
checkpoint | Shop Drawings approved for Works
Date | IFC Date
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
tickbox | Length
tickbox | Width
tickbox | Height
tickbox | Straightness
tickbox | Cross-section
checkpoint | Mould Surface Checked
tickbox | Cleaned
tickbox | Sealed
tickbox | Rubbers in Place
tickbox | Oiled
tickbox | Chamfers in Place
tickbox | shutters angle checked
tickbox | Temporary props / Push-pull spreader in place and secured
checkpoint | Reinforcement in Accordance with Drawings
tickbox | Reinforcement size
tickbox | Reinforcement Quantity
tickbox | Lap Length
tickbox | Splicing
tickbox | Stitch pour reinforcement lapping bars spacing maintained (If Required)
tickbox | Blockout recess around lifting Hoops (If Required)
tickbox | Reinforcement bars with couplers (If Required)
tickbox | Additional reinforcement around Lifters (If Required)
tickbox | Bar Chairs / Deck rails
tickbox | Cover maintained and within tolerance
checkpoint | All Cast-in Items are installed in accordance with Drawings and Tolerances
tickbox | All Ferrules are installed in accordance with Drawings and Tolerances
textbox | Specify Ferrules Type and Quantity
tickbox | All Stainless Items are installed in accordance with Drawings and Tolerances
textbox | Items:
tickbox | All Blockout Conduits / PT ducts / Stressbar are installed in accordance with Drawings and Tolerances
textbox | Temporary Works Conduits
textbox | Transport Holes Conduits
textbox | Bearings
textbox | PT ducts
textbox | Stress Bars
textbox | Other type, specify
tickbox | All Lifting Inserts are installed in accordance with Drawings and Tolerances
dropdown | Lifting System
textbox | Items:
tickbox | Additional reinforcement around Lifters (If Required)
tickbox | All Couplers are installed in accordance with Drawings
textbox | Specify Couplers Type and Quantity
tickbox | Other Casting Items are installed in accordance with Drawings
textbox | Specify Type and Quantity
checkpoint | Earthing and Bonding is installed in accordance with Drawings
textbox | Earthing Terminals Specify Type and Quantity
textbox | Flexi cables
textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
textbox | <20 mOhm across cage Length
tickbox | Checklist Completed (attach results)
signoff | Client Hold / Withness Point
checkpoint | Pre-lifting cage inspection (Client present)
checkpoint | Installation of tubs
tickbox | Tubs are tightened and positioned correctly
tickbox | All Sliding arms are locked in position
tickbox | All accrow props are locked in position
tickbox | Dimensions of Tub and Webb are correct
tickbox | All feet for tubs resting on mould & bolted down
tickbox | Tubs have release agent
checkpoint | Water Cooling Pipes
label | Verify (if used):
tickbox | Number, location and installation of water cooling pipes as per approved WMS
checkpoint | All Temperature Loggers are installed as per Approved WMS
tickbox | Ensure All temperature Loggers are Working (Check Maturix)
tickbox | Number, location and installation of loggers matches WMS
tickbox | Every 25m
tickbox | 1 x Core (If Required)
tickbox | 1 x Within Cover Zone
tickbox | 1 x Within Tent/Tarp Enclosure (Outside concrete)
tickbox | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
textbox | Specify Extra Loggers If Required
checkpoint | QA Engineer Check Completed by
checkpoint | Pre-Pour Mould inspection (Client present)
signoff | Client Hold / Withness Point
SECTION | SUPERVISOR / SUBCONTRACTOR CHECK COMPLETED OF MOULD & CAGE FOR CONCRETE PLACEMENT
checkpoint | Supervisor Release to Engineering Team
tickbox | Verify all concrete placement plant / equipment available
tickbox | Concrete Supplier of pour Notified
tickbox | NATA Testing Laboratory of pour Notified
signoff | Supervisor Hold / Withness Point
SECTION | CASTING DETAILS
checkpoint | Pour Detail
date | Cast Date
textbox | Concrete Delivery Docket (list All And Attach Dockets)
textbox | Total Concrete Volume (m3)
textbox | Specify Mix Design Verified/Used
textbox | Ambient Temperature within Limits (max 38°C)
textbox | Concrete Temperature within Limits (max 32°C)
tickbox | Slump within Allowable Tolerance (First truck and every 20m3)
textbox | Slump (list all)
checkpoint | Truck Tested for strength
tickbox | If volume <=20m3, 2 sets min required
tickbox | If volume >20m3 & <= 40m3, 2 sets min required (every 20m3 tested)
tickbox | If volume >40m3, sample every 20m3
tickbox | 1 * 7 Days and 3 * 28 Days per test (Total 4 Per Test)
tickbox | Cast 2-4 Cylinders for Destressing / Stripping / Lifting / Curing (PMC Internal)
textbox | Test Report Reference Number (list all)
checkpoint | Concreting
tickbox | Vibration adedquate
tickbox | Time Lag Between Trucks is not exceeded
tickbox | Concrete Placed within allowable time from Batching Plant
tickbox | No Free Fall During Pour
tickbox | Required Finish Applied as per Drawings
checkpoint | Curing
tickbox | Concrete Covered Overnight and Tent sealed
tickbox | Cylinders Stored next to Bed and covered as per AS1012
tickbox | Verify (if used) Temperature loggers are connected and recording and set the temperature alarm to 65°C.
tickbox | Verify (if used) Pipes connected, pump working, no leaks in mould
tickbox | Verify (if used) Steam Temperature Monitors installed and connected
SECTION | STRIPPING CHECKLIST
checkpoint | Date Stripped
date | Date Stripped
checkpoint | Minimum Required Strength for Stripping, Lifting, and Curing Achieved
dropdown | Strength Determined by | Curing Strength: 70% of fc (Characteristic design strength)
textbox | Specify Min Stripping Strength and Record Strength MPa (Mpa: Reading / 7.851)
textbox | Specify Min Lifting Strength and Record Strength MPa (Mpa: Reading / 7.851)
textbox | Specify Min Curing Strength and Record Strength MPa (Mpa: Reading / 7.851)
textbox | Specify Strength by Maturity if available
tickbox | Mould and Steam Cured until the curing strength achieved
tickbox | Curing Strength: 70% of fc (Characteristic design strength)
signoff | Client Hold / Withness Point
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
tickbox | Product ID, Weight, Cast Date, Job Number
checkpoint | Storage as per Approved Temporary Works Drawings
tickbox | Verify supports comply and Orientation and Location match with delivery Orientation and Schedule
checkpoint | Secondary Curing as per Approved Methodology
tickbox | Temperature 5 degrees past its peak
tickbox | Differential between Core and Ambient As Per Spec i.e., within 30 degrees
tickbox | Differential between Core and Cover As Per Spec i.e., within 25 degrees
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
tickbox | Length
tickbox | Width
tickbox | Height
tickbox | Straightness
tickbox | Cross-section
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
tickbox | Ferrules
tickbox | Couplers
tickbox | Stainless Items
tickbox | Lifters
tickbox | Blockouts
tickbox | Earthing and Bonding
tickbox | Post-Tensioning Equipment
checkpoint | Post-Pour Works Completed (As Required)
tickbox | Strands have been cut flush and epoxied.
tickbox | Strands are properly bulbed.
tickbox | Nailplates, recesses, and other obstructions have been removed.
tickbox | Couplers and ferrules are cleaned and capped.
tickbox | Earthing and bonding terminals are cleaned, with bolts securely screwed.
tickbox | Chamfers are clean, neat, and present on all required edges.
tickbox | Cooling pipes are drained of water and filled with grout as per the Work Method Statement (WMS).
tickbox | All drain holes, service ducts, and blockouts are cleaned and cut as required.
tickbox | Temperature logging wires are cut flush with the surface.
tickbox | Starter bars are cleaned and bent as specified.
tickbox | Surfaces requiring roughening are greencut according to the drawings.
tickbox | The top concrete surface is free of loose concrete.
tickbox | Areas requiring U2/U3 finish do not have a roughened surface.
tickbox | Bug holes and air bubbles have been identified, with sizes and distribution compared to AS Standards.
tickbox | All blemishes (dry concrete) have been removed and patched.
tickbox | Any discoloration on external/visible surfaces has been removed by sanding.
tickbox | All generic post-pour works are completed as required.
tickbox | Specified Finish Achieved
checkpoint | Temperature Logging Completed and Conforming. Attach Results
SECTION | CONCRETE STRENGTH TEST REPORT
checkpoint | Concrete Strength Test Report Received
textbox | Concrete Test Report Number
textbox | 7 Day Strength (List all) (separating each with a comma)
textbox | 28 Day Strength (List all) (separating each with a comma)
CHECKLIST | 13. POST POUR CHECK LIST |  | 13. POST POUR CHECK LIST
SECTION | ANY DEFECT IDENTIFIED
checkpoint | Punchlisting Completed for all Units / Attached
textbox | Precast IDs (More Than One Unit)
checkpoint | Crack Map Completed (If Applicable) / Attached
textbox | Precast IDs (More Than One Unit)
checkpoint | NCR Approved by Client and Repairs Completed (If Applicable)
textbox | Precast IDs (More Than One Unit)
checkpoint | Client Inspected Precast and Accepted Visual Condition
textbox | Specify Precast ID (separating each with a comma)
signoff | Client Hold / Withness Point
checkpoint | Precasts are free of Defects and QC Stamp Placed
textbox | Precast IDs (More Than One Unit)
SECTION | AS-BUILT DRAWINGS
checkpoint | As-Built Drawings Completed, Stamped and Attached
SECTION | CONCRETE STRENGTH TEST REPORT
checkpoint | Concrete Strength Test Report Received
textbox | Concrete Test Report Number
textbox | 7 Day Strength (List all) (separating each with a comma)
textbox | 28 Day Strength (List all) (separating each with a comma)
SECTION | TRANSPORTATION REQUIREMENTS
checkpoint | Transport Strength / Age
tickbox | Verify unit(s) have achieved 28 day concrete strength
tickbox | Verify unit(s) is at least 7 days old
signoff | If 28-day strength is not achieved by the delivery time, obtain client approval for a minimum of 95% of the 28-day strength before delivery.
checkpoint | Certificate of Conformance
checkpoint | Inspection Release Certificate
checkpoint | Delivery Notes
checkpoint | Delivery Docket
tickbox | Lashing, chains, frames, bolts, supports, and orientation of precast elements as per approved drawings.
tickbox | Attach Final photos prior to delivery (on Truck)
SECTION | FINAL ACCEPTANCE
checkpoint | Completed by
checkpoint | Reviewed by
checkpoint | Client Representative (if applicable)
signoff | Client Hold / Withness Point
CHECKLIST | 14. PRECAST UNIT CHECKLIST- COMBINED |  | 14. PRECAST UNIT CHECKLIST- COMBINED
SECTION | PRE-POUR CHECKLIST
checkpoint-no-value | Details
textbox | Cast Number
textbox | Specify Precast ID (separating each with a comma):
textbox | Strand Arrangement Type (If Required)
checkpoint | Shop Drawings approved for Works
Date | Shop Drawings approved for Works
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
tickbox | Mould set-out drawing provided
tickbox | Length
tickbox | Width
tickbox | Height
tickbox | Straightness
tickbox | Cross-section
checkpoint | Mould Surface Checked
tickbox | Cleaned
tickbox | Sealed
tickbox | Rubbers in Place
tickbox | Oiled
tickbox | Chamfers / Drip Groove in Place
tickbox | shutters angle checked
tickbox | Temporary props / Push-pull spreader in place and secured
checkpoint | Reinforcement in Accordance with Drawings
tickbox | Reinforcement size
tickbox | Reinforcement Quantity
tickbox | Lap Length
tickbox | Splicing
tickbox | Blockout recess around lifting Hoops (If Required)
tickbox | Additional reinforcement around Lifters (If Required)
tickbox | Bar Chairs / Deck rails
tickbox | Cover maintained and within tolerance
checkpoint | All Cast-in Items are installed in accordance with Drawings and Tolerances
tickbox | All Ferrules are installed in accordance with Drawings and Tolerances
textbox | Specify Ferrules Type and Quantity
tickbox | All Stainless Items are installed in accordance with Drawings and Tolerances
textbox | Items:
tickbox | All Blockout Conduits / PT ducts / Stressbar are installed in accordance with Drawings and Tolerances
textbox | Temporary Works Conduits
textbox | Transport Holes Conduits
textbox | Bearings
textbox | PT ducts
textbox | Stress Bars
tickbox | All Lifting Inserts are installed in accordance with Drawings and Tolerances
dropdown | Lifting System
textbox | Others (Specify)
tickbox | Additional reinforcement around Lifters (If Required)
tickbox | All Couplers are installed in accordance with Drawings
textbox | Couplers Type and Quantity
tickbox | Other Casting Items are installed in accordance with Drawings
textbox | Type and Quantity
checkpoint | Earthing and Bonding is installed in accordance with Drawings
tickbox | Earthing Terminals Specify Type and Quantity
tickbox | Flexi cables
tickbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
tickbox | <20 mOhm across cage Length
tickbox | Checklist Completed (attach results)
signoff | Client Hold / Withness Point (If Required)
checkpoint | Post-Tensioning Equipment is installed in accordance with Drawings and Tolerances
label | Verify:
textbox | Tendon Types
tickbox | Profile
tickbox | Firmly secured to rebar
tickbox | Grout tubes, Breathing Tubes and Grout Vents secure / sealed
textbox | Anchors installed / secured
tickbox | Temporary blockouts in Tendons
signoff | Client Hold / Withness Point
checkpoint | Prestressing Strands
label | Verify
textbox | No of strands
textbox | Debonded strands encased to correct length
textbox | Enter Coil Number Used for this Cast
tickbox | Sag Load all Strand
tickbox | Full Load: Multi-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
tickbox | Full Load: Singel-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
signoff | Prepare Stressing Records and Submit to Client for Review (HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint | Pre-lifting cage inspection (Client present)
checkpoint | Installation of tubs
tickbox | Tubs are tightened and positioned correctly
tickbox | All Sliding arms are locked in position
tickbox | All accrow props are locked in position
tickbox | Dimensions of Tub and Webb are correct
tickbox | All feet for tubs resting on mould & bolted down
tickbox | Tubs have release agent
checkpoint | Water Cooling Pipes
label | Verify (if used):
tickbox | Number, location and installation of water cooling pipes as per approved WMS
checkpoint | All Temperature Loggers are installed as per Approved WMS
tickbox | Ensure All temperature Loggers are Working (Check Maturix)
tickbox | Number, location and installation of loggers matches WMS
tickbox | Every 25m
tickbox | 1 x Core (If Required)
tickbox | 1 x Within Cover Zone
tickbox | 1 x Within Tent/Tarp Enclosure (Outside concrete)
tickbox | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
textbox | Specify Extra Loggers If Required
checkpoint | QA Engineer Check Completed by
checkpoint | Pre-Pour Mould inspection (Client present)
signoff | Client Hold / Withness Point
SECTION | SUPERVISOR / SUBCONTRACTOR CHECK COMPLETED OF MOULD & CAGE FOR CONCRETE PLACEMENT
checkpoint | Supervisor Release to Engineering Team
tickbox | Verify all concrete placement plant / equipment available
tickbox | Concrete Supplier of pour Notified
tickbox | NATA Testing Laboratory of pour Notified
signoff | Supervisor Hold / Withness Point
SECTION | CASTING DETAILS
checkpoint | Pour Detail
date | Cast Date
textbox | Concrete Delivery Docket (list All And Attach Dockets)
textbox | Total Concrete Volume (m3)
textbox | Specify Mix Design Verified/Used
textbox | Ambient Temperature within Limits (max 38°C)
textbox | Concrete Temperature within Limits (max 32°C)
tickbox | Slump within Allowable Tolerance (First truck and every 20m3)
textbox | Slump (list all)
checkpoint | Truck Tested for strength
tickbox | If volume <=20m3, 2 sets min required
tickbox | If volume >20m3 & <= 40m3, 2 sets min required (every 20m3 tested)
tickbox | If volume >40m3, sample every 20m3
tickbox | 1 * 7 Days and 3 * 28 Days per test (Total 4 Per Test)
tickbox | Cast 2-4 Cylinders for Destressing / Stripping / Lifting / Curing (PMC Internal)
textbox | Test Report Reference Number (list all)
checkpoint | Concreting
tickbox | Vibration adedquate
tickbox | Time Lag Between Trucks is not exceeded
tickbox | Concrete Placed within allowable time from Batching Plant
tickbox | No Free Fall During Pour
tickbox | Required Finish Applied as per Drawings
checkpoint | Curing
tickbox | Concrete Covered Overnight and Tent sealed
tickbox | Cylinders Stored next to Bed and covered as per AS1012
tickbox | Verify (if used) Temperature loggers are connected and recording and set the temperature alarm to 65°C.
tickbox | Verify (if used) Pipes connected, pump working, no leaks in mould
tickbox | Verify (if used) Steam Temperature Monitors installed and connected
SECTION | STRIPPING CHECKLIST
checkpoint | Date Stripped
date | Date Stripped
checkpoint | Minimum Required Strength for Stripping, Destressing, Lifting, and Curing Achieved
dropdown | Strength Determined by | Curing Strength: 70% of fc (Characteristic design strength)
textbox | Specify Min Stripping Strength and Record Strength MPa (Mpa: Reading / 7.851)
textbox | Specify Min Destressing Strength and Record Strength MPa (Mpa: Reading / 7.851)
textbox | Specify Min Lifting Strength and Record Strength MPa (Mpa: Reading / 7.851)
textbox | Specify Min Curing Strength and Record Strength MPa (Mpa: Reading / 7.851)
textbox | Specify Strength by Maturity if available
tickbox | Mould and Steam Cured until the curing strength achieved
tickbox | Curing Strength: 70% of fc (Characteristic design strength)
signoff | Client Hold / Withness Point
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
tickbox | Product ID, Weight, Cast Date, Job Number
checkpoint | Storage as per Approved Temporary Works Drawings
tickbox | Verify supports complies with approved storage drawings and Orientation and Location matches with delivery Orientation and Schedule
checkpoint | Secondary Curing as per Approved Methodology
tickbox | Temperature 5 degrees past its peak
tickbox | Differential between Core and Ambient As Per Spec i.e., within 30 degrees
tickbox | Differential between Core and Cover As Per Spec i.e., within 25 degrees
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
tickbox | Length
tickbox | Width
tickbox | Height
tickbox | Straightness
tickbox | Cross-section
checkpoint | Specified Finish Achieved
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
tickbox | Ferrules
tickbox | Couplers
tickbox | Stainless Items
tickbox | Lifters
tickbox | Blockouts
tickbox | Earthing and Bonding
tickbox | Post-Tensioning Equipment
checkpoint | Post-Pour Works Completed (As Required)
tickbox | Strands have been cut flush and epoxied.
tickbox | Strands are properly bulbed.
tickbox | Nailplates, recesses, and other obstructions have been removed.
tickbox | Couplers and ferrules are cleaned and capped.
tickbox | Earthing and bonding terminals are cleaned, with bolts securely screwed.
tickbox | Chamfers are clean, neat, and present on all required edges.
tickbox | Cooling pipes are drained of water and filled with grout as per the Work Method Statement (WMS).
tickbox | All drain holes, service ducts, and blockouts are cleaned and cut as required.
tickbox | Temperature logging wires are cut flush with the surface.
tickbox | Starter bars are cleaned and bent as specified.
tickbox | Surfaces requiring roughening are greencut according to the drawings.
tickbox | The top concrete surface is free of loose concrete.
tickbox | Areas requiring U2/U3 finish do not have a roughened surface.
tickbox | Bug holes and air bubbles have been identified, with sizes and distribution compared to AS Standards.
tickbox | All blemishes (dry concrete) have been removed and patched.
tickbox | Any discoloration on external/visible surfaces has been removed by sanding.
tickbox | All generic post-pour works are completed as required.
checkpoint | Temperature Logging Completed and Conforming. Attach Results
checkpoint | Survey Hog of Beams
textbox | First Reading (mm) (Once Stripped)
date | First Reading date
textbox | Second Reading (mm) (After casting stage 2 And / Or atleast 7days after stage 1 casting) (if required)
date | Second Reading date
textbox | Third Reading (mm) (At 28 days after stage 1 casting)(if required)
date | Third Reading date
textbox | Final Reading (mm) (7 days prior to scheduled delivery)
date | Final Reading date
SECTION | ANY DEFECT IDENTIFIED
checkpoint | Punchlisting Completed for all Units / Attached
textbox | Precast IDs (More Than One Unit)
checkpoint | Crack Map Completed (If Applicable) / Attached
textbox | Precast IDs (More Than One Unit)
checkpoint | NCR Approved by Client and Repairs Completed (If Applicable)
textbox | Precast IDs (More Than One Unit)
checkpoint | Client Inspected Precast and Accepted Visual Condition
textbox | Specify Precast ID (separating each with a comma)
signoff | Client Hold / Withness Point
checkpoint | Precasts are free of Defects and QC Stamp Placed
textbox | Precast IDs (More Than One Unit)
SECTION | AS-BUILT DRAWINGS
checkpoint | As-Built Drawings Completed, Stamped and Attached
SECTION | CONCRETE STRENGTH TEST REPORT
checkpoint | Concrete Strength Test Report Received
textbox | Concrete Test Report Number
textbox | 7 Day Strength (List all) (separating each with a comma)
textbox | 28 Day Strength (List all) (separating each with a comma)
SECTION | TRANSPORTATION REQUIREMENTS
checkpoint | Transport Strength / Age
tickbox | Verify unit(s) have achieved 28 day concrete strength
tickbox | Verify unit(s) is at least 7 days old
signoff | If 28-day strength is not achieved by the delivery time, obtain client approval for a minimum of 95% of the 28-day strength before delivery.
checkpoint | Certificate of Conformance
checkpoint | Inspection Release Certificate
checkpoint | Delivery Notes
checkpoint | Delivery Docket
tickbox | Lashing, chains, frames, bolts, supports, and orientation of precast elements as per approved drawings.
tickbox | Attach Final photos prior to delivery (on Truck)
SECTION | FINAL ACCEPTANCE
checkpoint | Completed by
checkpoint | Reviewed by
checkpoint | Client Representative (if applicable)
signoff | Client Hold / Withness Point

## Rev history
Revision | Date | Reason for Issue
3 | 2025-01-13 | Update CB as per Stans revision