## Master List Templates
Id | Type | Name | Values | Prompting Name
51a12ec0-5226-4c6b-8497-16296f16e1ad | checklist | 00. PRELIMINARY ACTIVITIES |  | 00. PRELIMINARY ACTIVITIES
f75da0a7-783b-4df0-b50c-1bd4ce99f315 | section | PRODUCTION PLANNING REQUIREMENTS FOR EACH PRECAST UNIT TYPE
01eca3f9-6c62-4ca6-954c-fdb56730f09b | checkpoint | Contractor's Construction / Installation Programme
3c117198-bff4-502a-a395-b5cfa598588a | tickbox | Verify Production Lot System / Precast Unit identification accepted by Contractor
1e57a8b8-d083-5d17-8d04-f1ec8079ebda | tickbox | Verify programme details are current
6a0ed510-e2df-519e-929d-4efafe8ff290 | tickbox | Verify programme dates are achievable
d37d335f-cbc7-5579-b3c5-643666248b38 | tickbox | Verify Casting Programme finalised
8bc3685d-9ca5-434c-9e5e-b284b290265c | checkpoint | Production Area
ba635813-23d9-5233-84d0-91d4dbb06503 | tickbox | Verify work area identified including storage of raw materials
e2ab616c-2426-54ec-bcff-8825f8b34189 | tickbox | Easy access for concrete agitator trucks / craneage / forklift
8b798f5a-a393-5fa6-bb41-81ee33256bb5 | tickbox | Curing facilities available
daa9c7de-f0d6-4d6f-a22a-44359540be2c | checkpoint | Storage Area
7f8889c7-31f0-50f9-bd33-056414225493 | tickbox | Adequate area for potential long term storage
1e706273-80a1-5c2a-be15-d5fdb9153e3f | tickbox | Bearing capacity of storage area will meet loading of precast units
ec8b16af-f10b-5100-ac4b-a0361ee7630e | tickbox | Unit Layout plan developed
8f459817-84db-5fba-9fcb-12add0ae62bc | tickbox | Adequate area for craneage operation and access by heavy haulage
47ed13fb-ca69-4c3f-87b4-73eacf5efa13 | checkpoint | Plant / Equipment / Procurements
357b4819-4846-5a14-aeaa-201a4f7aa657 | tickbox | Verify moulding received and dimensions checked
967c9772-1cf0-52de-89bf-dcad88730a9a | tickbox | Curing facility available as required
49a51fb1-2e6d-57e6-99d1-082e4b845bf9 | tickbox | Verify Stressing System / bed signed off by member of MIAustE as required
f60ba44e-cd11-54b1-a3a4-2fb624ca9629 | tickbox | Craneage available as required
aeaa54aa-42ce-5cfa-aa75-4be0f205dacb | tickbox | Jigs / working platform (rebar) available as required
8da262a9-476c-5be0-b591-f98020dd8122 | tickbox | Verify Reinforcement ordered and delivery commenced
56d4e2bf-37ed-52ee-a91c-4a51b64519fa | tickbox | Verify concrete order process agreed with concrete supplier
951c415e-fb9b-51a6-aaaf-1c989769beb3 | tickbox | Verify Strand / Couplers ordered and delivery commenced
9b9b32ad-9d16-5a34-aa68-4c451dae7149 | tickbox | Verify Contractor Supplied Product ordered and delivery commenced
d861f489-ecf7-580c-aca8-f3bb1e4e448a | tickbox | Verify cast-in items ordered and delivery commenced
5875024c-5574-5f59-895b-238a173f5e45 | tickbox | Verify lifting systems in precast unit signed off
01f4458b-2555-5860-90ce-d0d124853f28 | tickbox | Verify Curing Methodology signed off
12544b16-41d9-5fc1-8d57-64e9e03dad39 | tickbox | Verify Curing System functional
cc879505-acb7-57b1-a6b2-9b85666e0318 | tickbox | Verify lifting equipment available and signed off by Authority as required
6febfe26-2838-5e24-aa4e-a9f9a271aa3d | tickbox | Verify production consumables ordered and delivery commenced
1ab768e3-5191-5fe6-8a7a-0784ac0d211a | textbox | specify others
da870fe2-3e5c-4737-8241-32c9c13b46d0 | checklist | 01. MDR COMMON BOOK |  | [object Object]
67b12e8d-90f3-43e5-83b0-5221c0867c20 | section | A - PERMACAST CERTIFICATE OF CONFORMANCE
96347ddd-8245-4867-8aa7-3a94b589ad34 | checkpoint | A1 - Certificate of Conformance for all Precast Concrete Items
7d7dab19-a425-4780-a294-dc906838f38c | checkpoint | A2 - Permacast ISO 9001 Certification
d143b522-6f5e-4a93-aedc-a700e1c9917f | section | B - PERMACAST'S DOCUMENTATION (approved and signed off)
1213f436-e6e4-496c-bf27-f6d23f2af379 | checkpoint | B1 - Register for Quality Plan, Inspection & Test Plans, Work Method Statements, Manufacturer's Data Reports
5158067c-ada3-47b8-a514-035d291b2955 | checkpoint | B2 - Project Quality Management Plan (Cover page and table of contents only)
ce854014-9b5d-4651-9821-22a10db5c758 | checkpoint | B3 - Inspection & Test Plans (Approved copies)
2e708310-cf3a-5293-a46e-9848f1dd0369 | tickbox | ITP: Preparation for Precast Unit Production
cd5f9428-303e-57e7-994d-476d2f824eb0 | tickbox | ITP: General Precast Units
575e476a-da6d-5cc7-9086-c35c39a5b52b | tickbox | ITP: Prestress Precast Units
00a38175-0948-516a-88ad-59de5272c5f9 | tickbox | ITP: Prestress / Post Tension Precast Units
501b549a-afb3-41e7-bfa9-ae0c9582ad98 | checkpoint | B4 - Work Method Statements (Approved copies)
423fb2a2-34fe-54ba-ad8c-8beb9e1a216c | tickbox | 501 WMS General Precast Units
a86da12a-a680-56b4-be79-1c7fcda21e63 | tickbox | 502 WMS Prestress Precast Units
b76d31bf-0bfa-51dd-9b1b-f28c398c6177 | tickbox | 503 WMS Curing Methodology
ab4804c7-443b-5ecb-a1ea-30f335ee22a9 | tickbox | 504 WMS Concrete Repair
745460a9-a32d-5684-9aae-8c972f112eae | tickbox | 505 WMS Prestress - Post Tension Precast Units
710d92d7-69d6-5aa7-ad37-0d9a9840443b | tickbox | 506 WMS Earthing and Bonding
19d33987-9c9e-4b1e-9554-91b1344e66d0 | section | C - HEAVY LIFTING
0f82d65d-cb3d-43eb-8a80-bbf9e6718413 | checkpoint | C1 - Lifting Design
53a127dd-5169-4c6a-8a92-7662006b9d93 | checkpoint | C2 - Lifting Study
625999f7-3f53-4034-961d-0727cf9cce29 | checkpoint | C3 - Lifting Plant / Equipment / Material Requiring Statutory Documentation
9efce6e8-670a-4bbf-aa4c-5d3fad7e16ff | checkpoint | C4 - Temporary Works Drawings 'Storage' (If Required)
dc9d414b-93b4-4beb-8380-e63befae8244 | section | D - DRAWINGS - IFC and SHOP
a613c38e-0b78-4704-9da2-3a70ac9ed4cc | checkpoint | D1 - Register of IFC drawings
6c77c7ed-bbda-4a1a-8773-f8f032245e56 | checkpoint | D2 - Register of Shop Drawings
d098fec5-209b-4e84-9142-b47e7ea5ddbd | section | E - CHANGE MANAGEMENT
de0f3e1b-a296-4805-b4af-4092e6a94be7 | checkpoint | E1 - Technical Query Register
2a2bd0f3-7831-4c44-9607-fb175fd8f1c5 | checkpoint | E2 - Completed Technical Queries
5684fd71-880a-43ba-84a4-e3b421c84a3c | checkpoint | E3 - Non-Conformance Register
dd5f5e47-d2d1-4614-8ef3-328fc28b521e | checkpoint | E4 - Closed Out Non-Conformance Reports
5ad8cfe1-c6a3-4b89-8e00-ff953a942aa6 | checkpoint | E5 - Defects Register
62e56bf7-1c2f-42e7-bb39-fd6ef8d1afd3 | checkpoint | E6 - Completed / Closed Out Defects
2ff1ac45-0cbc-49fb-84f1-7db988afa150 | checkpoint | E7 - Defects to be carried through to Defects Liability Period
40bbc83e-6771-42ea-b421-18f600c9fde7 | section | F - CONCRETE
32ff9cc6-eb77-4d12-82c6-df3fe9a97769 | checkpoint | F1 - Approved concrete Mix Design
048ff3b9-021b-54c8-820e-96388f8cc782 | tickbox | Develop Mix Design
376d6935-4c7d-5d98-9ca0-0df0977f5fa2 | tickbox | Conduct Trial Mix
526515b9-2f0e-5ae4-9fe6-aa854dcc1362 | tickbox | Compile Concrete Mix Compliance Report Including Test Data
9ba16fe8-fc01-5ebe-963f-27afddb02360 | tickbox | Submit Details To Main Roads For Acceptance And Approving The Concrete Mix Design
12e51ef4-424c-5fb5-9cac-ad6ad7036c7e | tickbox | Submit Mix Design Report And MRWA Mix Design Number To Contractor For Acceptance
33b660af-399f-47bc-92db-a76395453b1d | checkpoint | F2 - Concrete Supplier: ISO 9000 Certificate
29df82c2-65d2-4fad-8dee-97868c0b734c | checkpoint | F3 - Aggregate Supplier: ISO 9000 Certificate (Coarse and Fine)
3ce2990a-e3d7-4ddb-a034-9b4f1755beca | checkpoint | F4 - CMRS Cement Certificate
08a3aac5-6b93-5062-a8e1-f2387f943d82 | tickbox | Complies with ATIC – Specification SP43
753e96f8-dd9d-4b2a-b011-c08c93e552fd | checkpoint | F5 - Admixtures
f04cf58a-40ef-43d0-8d39-d9d7241340c8 | checkpoint | F6 - Concrete Supplier’s Letter of Compliance
36628688-7e94-4b60-9897-260c770bb68a | checkpoint | F7 - Concrete Production Report Grade 65 GB
9f683a2c-fd8d-5e2f-896a-d818d1a7ab7a | tickbox | Grade 65
74675b20-beeb-5ad4-ad35-08425d5b76c2 | tickbox | Grade 50
0bf74b83-a98b-5a07-8942-63454025b14c | tickbox | Grade 40
581b89a1-e90b-4faa-89d6-ae45cde3d4df | checkpoint | F8 - Concrete Curing: First precast element - Verification Testing for the maturity curve
aedf98ec-43bc-4f3e-b3c6-ef0163133bfa | checkpoint | F9 - Contractor's (via Independent Durability Consultant’s) acceptance of Maturity Curve
88ee2524-cacd-4628-acf0-e8cabb2a6946 | checkpoint | F10 - Test Panel Prepared and Inspected by Client
c782d152-31db-4645-87e0-d599c7d6342e | section | G - REINFORCEMENT
f2091b7d-b33d-4a42-96d5-394acff7ef89 | checkpoint | G1 - Reinforcement Supplier: ISO 9000 Certificate
43c1f778-a6a6-4f8f-805f-ebe8bbe7424f | checkpoint | G2 - ACRS Certificate
b9094dde-0749-4c06-8ce8-bedee76cd0f3 | checkpoint | G3 - Steel Reinforcement: Supplier’s Letter of Compliance
2552cd04-2fd0-4b9e-9d3a-1cfa49a4da97 | checkpoint | G4 - Register of Mill Certificates
82d6cd26-9c51-400f-a1ce-47492a2dbc66 | checkpoint | G5 - Mill Certificates
167af766-4d17-4eeb-86f3-0f6a6946e92d | section | H - STRESSING
03440071-6052-4cd3-b0a8-d8bf5f3c401b | checkpoint | H1 - Stressing Calculations (including force, extension, gauge pressure)
a28c8c99-7493-51ce-ac1f-248b3bb1c8f3 | tickbox | Stressing Procedure
09e3ce9c-668a-4e2c-b70c-ef0fa8b072d3 | checkpoint | H2 - Calibration of Jacks / gauges Certificates (refer section L below)
9fcd8b7b-aa52-461f-b0a4-e2bd3e3adc1f | checkpoint | H3 - Register of Coils and Allocation to Precast Units
d276a7c0-7931-486a-81af-147aeb3b35e5 | checkpoint | H4 - Strand material certificates
19d2291a-891c-4411-befa-4d1d90f7bf1f | section | J - CAST IN ITEMS (Supplier’s Letter of Compliance)
225ae5bc-b524-475a-8086-1eae63ab99de | checkpoint | J1 - Anchors / Lifters
13bd5503-9243-4eda-9d83-0a692466e3d0 | checkpoint | J2 - Ferrules
d8ffe1e9-051a-4cb3-84ec-8c2b0f0c992b | checkpoint | J3 - Earthing and Bonding materials (Terminals / Cables)
ec4388a4-7951-422d-9475-d23e19046c38 | checkpoint | J4 - Grout / Breather Tubes
5024d6a3-bddc-4a57-b06e-93ca38c95c56 | checkpoint | J5 - Debonding Tubes
422f4521-85cd-49b0-beb8-fe9792ad7654 | checkpoint | J6 - PVC Ducts (Sacrificial)
87bd2183-ecba-496b-859b-aa6b28367f2e | checkpoint | J7 - Condek (Sacrificial)
4c111549-efb7-4657-9384-2a67f588c39f | checkpoint | J8 - PT Duct
e51054be-1c5e-41c0-ada6-398e146752fc | checkpoint | J9 - Cooling Pipe
3de9bf81-53ba-423d-938f-078a22359892 | checkpoint | J10 - Grout
2e208be5-e43f-4857-8acd-fa1c26bb7f1f | checkpoint | J11 - Post Tension Ducts / Anchors / Bedding Plates
fb4381fd-a7a5-467b-95ba-a34c002cf42b | checkpoint | J12 - Other Items
154247ce-1a0f-5f7c-ba72-177336219fa9 | textbox | Specify items
96d9ce91-c52a-42aa-b453-2a06b5069286 | section | K - WELDING (in situ)
8f071b63-2fdb-4a86-8449-3a75d499bedb | checkpoint | K1 - Weld Procedure Specifications / WPQR
f31428fc-1b0b-4f1b-b247-c7c2000f1ae1 | checkpoint | K2 - Welder Qualification Register
86f245d2-5ee1-49da-b58a-4981031a88a9 | checkpoint | K3 - Welder Qualifications
cd099bea-b0fd-4f47-bc15-f11ac62eb1c3 | section | L - CALIBRATION OF INSPECTION, MEASURING AND TEST EQUIPMENT
51309ce7-24ed-41e6-b447-b8299d1fed8f | checkpoint | L1 - Register of NATA laboratories used for the precast project
dce3972f-f8f6-4a1d-b367-6b7d0f338ed1 | checkpoint | L2 - In-house concrete crusher calibration Certificates
4225249f-a1cd-4957-b63d-9f6401f77c06 | checkpoint | L3 - On Site Batch Plant Calibration Certificates
fb58e222-d6fb-4a58-b643-7142de91c2bb | checkpoint | L4 - Conductivity Tester (Earthing & Bonding) Certificates
6a7c86d4-087f-4e73-a7f0-2cf413d70777 | checkpoint | L5 - Calibration of Jacks / gauges Certificates
20f589f3-3396-4493-a049-e0b7100110f6 | checkpoint | L6 - Calibration of Load Cells Certificates
cac22572-16e3-4480-b0ea-4420e698e314 | section | M - DELIVERY OF PRECAST UNITS
70a1b7bd-3590-43f0-b456-47104129394d | checkpoint | M1 - Register of Permacast IRC Certificates
6867bbf8-2284-4727-840f-99317d6c8304 | checkpoint | M2 - Permacast IRC Certificates
063856db-313f-484d-8276-a595ec6af2c7 | checkpoint | M3 - Register of Permacast Conformance Certificates
ae0ce36f-eb42-4974-9c7d-20ee73c49686 | checkpoint | M4 - Permacast Conformance Certificates
b54721a7-a7c1-4682-9e60-4643d8a68c0f | checkpoint | M5 - Register of deliveries
d3003a6f-07cf-4c02-805e-0ad3c0ec85e9 | checkpoint | M6 - Delivery Docket (sent to Contractor requesting acceptance of loaded precast items)
70bcafdb-369f-4823-9cd6-b284db405a35 | section | N - AUDITS
655ef3c8-22c8-4742-af85-14a0e6c07b3b | checkpoint | N1 - Register of Audits
f3781826-5c84-4cef-911f-868c888a382e | checkpoint | N2 - Audit Reports
857251c3-b042-41c1-9cce-99a51f990358 | checklist | 02. PRE-POUR CHECKLIST-STAGE 1 |  | [object Object]
5f58bb04-0ac7-4b00-a701-325e40b364c7 | section | PRE-POUR CHECKLIST-STAGE 1
fa5d2c6e-e0b9-4ba7-86c0-7936532d767a | checkpoint-no-value | Details
6c69bb8a-7ab5-56ed-a847-b666b4850bc3 | textbox | Cast Number
46422424-bf21-58de-9874-cb2df9b9ba6d | textbox | Specify Precast ID (separating each with a comma):
935c300c-9a13-5ca7-8aef-1e5f920fa3a7 | textbox | Strand Arrangement Type (If Required)
e990782b-844c-492d-847b-f16207e79814 | checkpoint | Shop Drawings approved for Works
a8c386cc-951a-5ba1-b11f-a5bfb8d77f36 | date | IFC Date
60e0d779-8814-4f37-aa8f-aacef7996904 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
f040da53-f7d7-55f3-b80a-aa6fbdca7948 | tickbox | Mould set-out drawing provided
07885dd3-1a42-52ae-bc35-97beb1b132ff | tickbox | Length
d02da1eb-be22-55eb-9630-b25a131eb3f9 | tickbox | Width
d7e0e20c-3656-552e-a4c6-78972072af75 | tickbox | Height
5974fd95-a84d-5fed-b873-81afb9879349 | tickbox | Straightness
2a367b9e-511d-5800-85b3-b2d7c785ecb7 | tickbox | Cross-section
ff2fd0b8-f981-4abe-82f0-996a3cdf8601 | checkpoint | Mould Surface Checked
d4bbc9ac-2bf7-5014-ad78-62296dff2612 | tickbox | Cleaned
490f6c37-397f-5cf9-9fdd-e4e297b7dd77 | tickbox | Sealed
10d83b64-01f1-507b-8bb5-01fb2472e6fb | tickbox | Rubbers in Place
2337f462-4a65-5c16-a75d-2b4b7d83d1d5 | tickbox | Oiled
a79a299a-1e4c-5430-800b-9553b50f170d | tickbox | Chamfers / Drip Groove in Place
c58bea86-d9e9-5dee-a3e8-f762e31edcf0 | tickbox | shutters angle checked
abec3e4d-080e-55bc-ac72-e15f22632b2e | tickbox | Temporary props / Push-pull spreader in place and secured
ed251e5e-98a0-420f-94bc-d19c78fd467f | checkpoint | Reinforcement in Accordance with Drawings
b426138e-9aa6-5765-a728-8ad327d1c77e | tickbox | Reinforcement size
0d1a6046-cd1b-51de-a426-e2d9c0ea6f2b | tickbox | Reinforcement Quantity
487f0b14-07cd-5978-ae84-d178df01d443 | tickbox | Lap Length
54de0207-c2d5-5bb7-b313-981f9319bdec | tickbox | Splicing
3da43414-2467-5066-a5b2-9fdd22048f42 | tickbox | Blockout recess around lifting Hoops (If Required)
0449a9bb-e3bd-5a09-94f0-c62934b6becd | tickbox | Additional reinforcement around Lifters (If Required)
a1d72892-b351-5d50-ac18-782e0c5ce344 | tickbox | Bar Chairs / Deck rails
30e4bbaf-d007-5872-9624-4ee055830ec7 | tickbox | Cover maintained and within tolerance
8dc9d538-8239-4877-9079-286704b77fc5 | checkpoint | All Cast-in Items are installed in accordance with Drawings and Tolerances
a8ff62b4-04e8-501a-a868-27d5bd4c8abe | tickbox | All Ferrules are installed in accordance with Drawings and Tolerances
8c4b3916-3bf5-5e92-adef-4c15bdda9528 | textbox | Ferrules Type / Quantity
c161e4b5-afb0-5c8f-a92b-1a06aff072cd | tickbox | All Stainless Items are installed in accordance with Drawings and Tolerances
70eb8a43-b5c5-5182-9b84-90e9061894df | textbox | Items:
aca02a2a-422d-526f-9673-b28e5acccdd0 | tickbox | All Blockout Conduits / PT ducts / Stressbar are installed in accordance with Drawings and Tolerances
f58a8c00-ef17-5bcd-bbd6-3dc13b391469 | textbox | Temporary Works Conduits
a692e9ba-30e1-5544-ad3e-478c3bf1be06 | textbox | Transport Holes Conduits
5fbf1f91-95ef-5453-b79a-b9b6483752bf | textbox | Bearings
639a4f2f-bd59-5f46-99f3-fca3e74a462e | textbox | PT ducts
eabc0c6c-73cf-5473-a449-90996a5abbf1 | textbox | Stress Bars
b135e145-e40a-5b3b-892f-724869100639 | tickbox | All Lifting Inserts are installed in accordance with Drawings and Tolerances
16093bce-4b1a-5b5d-b6ec-35898095880f | dropdown | Lifting System | Lifting Loops, Lifting Anchors, Edge Lifters, VLGB Load Ring, VSL Bars (Stress Bars / Cors Nuts / Lock Nuts / Bearing Plate / Washer) Others (Specify)
8e4c7da7-6b2b-5a02-9676-81564ac32894 | textbox | Others (Specify)
967fd563-07ad-5be2-8012-49a453da59da | tickbox | Additional reinforcement around Lifters (If Required)
116cf655-268a-5c9c-91a1-1e37f57d5266 | tickbox | All Couplers are installed in accordance with Drawings
ef366132-7f72-5ad6-95fd-bfd7d6111826 | textbox | Couplers Type and Quantity
4ea6e68d-02dc-5bb7-b676-3b14a369e474 | tickbox | Other Casting Items are installed in accordance with Drawings
f5c8bd08-5465-57b9-8508-465c90a3f07e | textbox | Type and Quantity
9547df62-986a-4e52-accb-8a59772adcfc | checkpoint | Earthing and Bonding is installed in accordance with Drawings
ed45fa19-99ae-59cf-a478-bceb46e0275c | tickbox | Earthing Terminals Specify Type and Quantity
ce9862ca-e082-5fe9-abc7-de7b5a9bf0e0 | tickbox | Flexi cables
d6f6bdfb-5f6c-5570-bd8e-2e9e4a91c28f | tickbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
1133b98d-af6b-5703-9aca-5895e305f57c | tickbox | <20 mOhm across cage Length
245b40c2-f27e-576e-845e-e3299922a0b7 | tickbox | Checklist Completed (attach results)
55c26dff-cbe5-4e4e-8523-810fd641562c | signoff | Client Hold / Withness Point
3dbda0f9-7f7b-4799-bc17-acf9cf94d49b | checkpoint | Post-Tensioning Equipment is installed in accordance with Drawings and Tolerances
f954c845-688a-5c60-a86c-a803a51e186b | note | Verify
37277c50-acad-5a38-aa87-5f2196fe5fa5 | textbox | Tendon Types
b8fbbdf0-bf17-5330-adb3-32f41d275b27 | tickbox | Profile
2c72f38c-ab6d-5854-a792-c759b5e8346b | tickbox | Firmly secured to rebar
4571fd59-65d7-5040-9242-1b5c41d85987 | tickbox | Grout tubes, Breathing Tubes and Grout Vents secure / sealed
1081e767-207a-56a7-9657-2765cd5b1032 | textbox | Anchors installed / secured
ab7f8e63-688b-5b69-b02d-afb4de6f4d28 | tickbox | Temporary blockouts in Tendons
41a0ef04-8ef3-4ad0-91df-7b2b4dab704f | signoff | Client Hold / Withness Point
52932e12-afbb-4df7-8ea5-366b52bae6ab | checkpoint | Prestressing Strands
13f07c60-e3df-5c67-ac16-29c54908d2e0 | note | Verify
9246e222-6719-5e68-a31e-18e6e4575541 | textbox | No of strands
7cd9c758-8e97-5080-a9af-d84061d2e23a | textbox | Debonded strands encased to correct length
65770d88-de29-5393-a76e-e7e23f429744 | textbox | Enter Coil Number Used for this Cast
35f1d800-314b-5955-9b3c-848151464c9e | tickbox | Sag Load all Strand
dd2c4042-6eec-559e-9156-8bdb999028b9 | tickbox | Full Load: Multi-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
5cbd42f0-b25a-5026-b560-73fbd9746faf | tickbox | Full Load: Singel-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
2142f2db-356c-48a8-b907-f038b1139b87 | signoff | Prepare Stressing Records and Submit to Client for Review (HOLD POINT FOR CLIENT TO SIGN OFF)
dd2ebacf-e090-4ec6-9d40-bf5e9c484fa1 | checkpoint | QA Engineer Check Completed by
c0f50e47-c0cb-41b3-be25-bab6b2bb50c9 | signoff | Pre-lifting cage inspection (Client present)
5345fdd8-abda-4cb9-bdfa-6c69c539d550 | checkpoint | QA Engineer Check Completed by
2efb977f-0143-486c-8ae9-90b947c106aa | signoff | Pre-Pour Mould inspection (Client present)
176e9f20-232e-44a8-99f2-be1f56ad7ee6 | checklist | 03. EARTHING AND BONDING CHECKLIST |  | [object Object]
0715e136-f927-47f2-a563-a5fea94b1b58 | section | EARTHING AND BONDING DETAILS
07eaa810-4a99-4678-8525-e1f4a5abeaf1 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
7ce6bb22-bf9e-5914-b87a-2a594210034f | tickbox | Earthing Terminals Specify Type and Quantity
7f7f3ba0-510d-59e7-aefb-af24f5afa28f | tickbox | Flexi cables
e75fef62-af8c-5614-9388-bd84d618e4a1 | tickbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
04453ed1-a5ea-53bd-bfe2-d037a5f57b76 | tickbox | <20 mOhm across cage Length
4d061799-868b-5177-b289-454dbafcb2ec | tickbox | Checklist Completed (attach results)
6b8cdffe-3264-44fc-b9a7-f846ce4f25a5 | signoff | Client Hold / Withness Point
be6b9dfb-2898-4d32-8cfc-289e29b1facd | checklist | 04. POST-TENSIONING CHECKLIST |  | [object Object]
87c1cd30-b9b3-4584-ad09-50b2c5fcfee9 | section | POST-TENSIONING DETAILS
8d1a4d5f-d182-4264-b89f-bd44787c940a | checkpoint | Post-Tensioning Equipment is installed in accordance with Drawings and Tolerances
5cf2e112-19e8-5390-bbb6-2c1621dc58be | note | Verify
d004acf0-bfd6-5647-a8c1-f7e2a777bb48 | textbox | Tendon Types
c2993635-7f3b-51ae-b517-deb254172790 | tickbox | Profile
360d42c1-d622-53e8-8288-01b30f0a94ef | tickbox | Firmly secured to rebar
86b67513-e84d-535e-8f48-ef26d18b3c8f | tickbox | Grout tubes, Breathing Tubes and Grout Vents secure / sealed
5101c99d-7222-5354-a421-806834d73e4b | textbox | Anchors installed / secured
d1f94899-66b4-5dc5-8f4b-0e8a745f8310 | tickbox | Temporary blockouts in Tendons
10eb2669-3e31-447e-8431-74c1a524c5a5 | signoff | Client Hold / Withness Point
006f6de8-d9b2-4e64-a454-e54323f20ef0 | checklist | 05. PRESTRESSING CHECKLIST |  | [object Object]
3ab59075-98bc-4ee0-ab42-b1976bc82fff | section | PRESTRESSING DETAILS
9dfe944f-57cf-4f31-9801-fd5c2138c751 | checkpoint | Prestressing Strands
b383005b-a4bb-5246-a1cb-17d65524007c | note | Verify
5af10872-30a2-5a74-991f-c56c2765e701 | textbox | No of strands
cdd425f9-6d57-5cc3-aeea-7e1afa1c5d9d | textbox | Debonded strands encased to correct length
77cded8e-d23d-5946-9e60-f56d43e59bff | textbox | Enter Coil Number Used for this Cast
3ee65468-9101-5a0a-a2b4-1ff10da8f137 | tickbox | Sag Load all Strand
9d971636-4f35-5036-bfa7-6a4e64755589 | tickbox | Full Load: Multi-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
183d5110-ac09-5c20-82f7-5ee3bb7b5cf3 | tickbox | Full Load: Singel-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
bc1f6702-78d8-4bbe-819e-d99895e17b90 | checklist | 06. TUBS / BOATS CHECKLIST |  | [object Object]
4b1b9663-c429-4f2a-a6a3-4040a8bb9c2c | section | INSTALLATION OF TUBS / BOATS
91455804-dad9-401f-9115-3d4ece07f07e | checkpoint | Installation Details
6c448aba-3496-50a3-bbdb-8059a3fec070 | tickbox | Tubs are tightened and positioned correctly
80ac8a49-8bef-571d-b322-20209aec7430 | tickbox | All Sliding arms are locked in position
537393e7-1a0e-583a-97f5-906a3f867561 | tickbox | All accrow props are locked in position
0121b5cb-e682-5e98-a1ab-59ac29c6ee50 | tickbox | Dimensions of Tub and Webb are correct
93354a7e-7c7f-569b-8725-e030b44e49df | tickbox | All feet for tubs resting on mould & bolted down
eae895ff-467b-5d68-8d3e-f6151814c530 | tickbox | Tubs have release agent
574b9862-382d-4eaa-8fdd-bf976b34c6a9 | checklist | 07. COOLING PIPES CHECKLIST |  | [object Object]
86a07b26-42e9-4de8-be0d-0383b2d2e023 | section | INSTALLATION OF COOLING PIPES
fabb973f-d8e1-440e-b069-1acafdb51ce7 | checkpoint | Water Cooling Pipes
0694bcfd-70fc-5c19-a505-5df4043858a2 | note | Verify
54d5ff3e-c012-5910-98f2-73acf2923db6 | textbox | Number, location and installation of water cooling pipes as per approved WMS
39f218aa-1f26-4b2f-9d21-3f826335b26f | checklist | 08. TEMPERATURE CONTROL (LOGGERS) CHECKLIST |  | [object Object]
d541ad92-28f9-4b80-a9ed-5ec35dcccdd9 | section | TEMPERATURE LOGGERS
ee0e7ef0-42ac-4694-9a7c-c06f5c535413 | checkpoint | All Temperature Loggers are installed as per Approved WMS
345d29a3-7dce-5a21-95f0-041581bafe22 | tickbox | Ensure All temperature Loggers are Working (Check Maturix)
4e2d5a97-ab14-5d01-9dcd-ed517be3bd3c | tickbox | Number, location and installation of loggers matches WMS
7178fff8-8193-5bc0-9b1c-e58968f2ff71 | tickbox | Every 25m
9ecdf5da-79f8-59b3-9c9e-49e2d1e39b5d | tickbox | 1 x Core (If Required)
32aff360-2f25-55b6-944f-80e56a11eb2b | tickbox | 1 x Within Cover Zone
cecc5a9f-2689-5e1f-9016-2413afe4ae57 | tickbox | 1 x Within Tent/Tarp Enclosure (Outside concrete)
3b51ddf6-8a88-5378-abc5-fb4897368f07 | tickbox | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
5bc70331-17a3-5f85-b4d1-52003feffc49 | textbox | Specify Extra Loggers If Required
2b766f83-4c56-46c9-8785-9f73a8875728 | checklist | 09. SUPERVISOR / SUBCONTRACTOR CHECKLIST |  | [object Object]
0807ad3e-ef97-4033-a159-7ab4572e9daa | section | SUPERVISOR / SUBCONTRACTOR CHECK
e3677b1c-f2bb-4796-a65c-629bf5d9f609 | checkpoint | Supervisor Release to Engineering Team
def7d631-c8eb-5503-be8d-59f13fcdfcb7 | tickbox | Verify all concrete placement plant / equipment available
10d91e8f-4f74-5fb3-ad45-29acb6b4b5ec | tickbox | Concrete Supplier of pour Notified
b2c9e418-5fda-5945-9a24-87ba4a8a1c3c | tickbox | NATA Testing Laboratory of pour Notified
b73e67f0-fc6c-40fd-8764-b3ce9ad35ce7 | signoff | Supervisor Hold / Withness Point
84e2fe58-0c38-4703-8b02-7b5fe9934d30 | checklist | 10. CASTING AND STRIPPING CHECKLIST |  | [object Object]
cec76016-ca67-43f9-8ed1-a0d306ee9585 | section | CASTING DETAILS
f945c7be-511a-4394-afdf-4551ca56cf37 | checkpoint | Pour Detail
f42f7780-cecb-505f-a9d9-0904914fcb8b | date | Cast Date
84297fee-1cab-528d-a164-8a0626058e27 | textbox | Concrete Delivery Docket (list All And Attach Dockets)
d1835901-0807-5fb0-a244-473cd0b75b58 | textbox | Total Concrete Volume (m3)
379e9d6e-c195-550d-b86e-7d7cda28043f | textbox | Specify Mix Design Verified/Used
0ad8642c-fae0-5e82-a72f-24c8ea0f9b80 | textbox | Ambient Temperature within Limits (max 38°C)
c4e7582a-97a5-5017-bd2c-4e00a577c53b | textbox | Concrete Temperature within Limits (max 32°C)
e091bb48-f19b-599f-97ac-11c1bb472bef | tickbox | Slump within Allowable Tolerance (First truck and every 20m3)
9af4795b-92f8-5ee8-88ad-fe0a31f4a593 | textbox | Slump (list all)
d197ea09-2f8d-4681-8768-7189575ebd39 | checkpoint | Truck Tested for strength
4e2c3236-7a5f-5913-aab0-491c2778e9e2 | tickbox | If volume <=20m3, 2 sets min required
8b5e2328-1829-5c23-982c-e374b2939383 | tickbox | If volume >20m3 & <= 40m3, 2 sets min required (every 20m3 tested)
c09bea15-d8e4-5766-94e7-a4e73467a2a3 | tickbox | If volume >40m3, sample every 20m3
80f12246-e86c-5162-b0b2-90141850cb77 | tickbox | 1 * 7 Days and 3 * 28 Days per test (Total 4 Per Test)
4f3c23a5-2ae9-5454-9fdb-f5166efdb222 | tickbox | Cast 2-4 Cylinders for Destressing / Stripping / Lifting / Curing (PMC Internal)
00bb189e-acf0-5a94-9070-38062966fdc7 | textbox | Test Report Reference Number (list all)
9f3afe7f-220c-4cc8-821e-3b7476781e7b | checkpoint | Concreting
bc83adcf-547a-554a-8832-45b807b041ec | tickbox | Vibration adedquate
9c64e365-538f-502e-a7b3-821ab1e8026e | tickbox | Time Lag Between Trucks is not exceeded
7a49c5c2-2d7b-5c98-85a0-86aedeff3bf3 | tickbox | Concrete Placed within allowable time from Batching Plant
14f75ae6-6cd9-505d-a9f2-06da1be24fef | tickbox | No Free Fall During Pour
4423455f-c10f-54ca-aade-d779d4916c1a | tickbox | Required Finish Applied as per Drawings
8751d84b-eb61-44a3-80d4-5d8826dadf2b | checkpoint | Curing
840f74da-85f6-5e8f-b016-2a0f27dad9c0 | tickbox | Concrete Covered Overnight and Tent sealed
c07c8b01-b56e-52f3-8613-e884c05e57cd | tickbox | Cylinders Stored next to Bed and covered as per AS1012
b4a2cc7e-ec26-54a7-ab2e-63debb157e7b | tickbox | Verify (if used) Temperature loggers are connected and recording and set the temperature alarm to 65°C.
f53bd25b-bcc3-59fd-82d7-9dc70df7242f | tickbox | Verify (if used) Pipes connected, pump working, no leaks in mould
3bd63fbe-f8dd-5aaa-97b9-4e5d12462318 | tickbox | Verify (if used) Steam Temperature Monitors installed and connected
3fb63c2c-7e91-4521-8b5e-1b4a6c530da8 | section | STRIPPING DETAILS
2d067a9e-8e34-4caa-a710-7a063ed09526 | checkpoint | STRIPPING DETAILS
2b426fce-884c-5373-b9cf-47c8559ca8be | date | Date Stripped
e31b157a-cbe7-45f4-832f-f021f6044a4e | checkpoint | Minimum Required Strength for Stripping, Destressing, Lifting, and Curing Achieved
6a1cf701-a12c-5108-9fe0-c9470bdfe468 | dropdown | Strength Determined by | Crushing Cylinders, Maturity Report
1514a90a-c1ec-505a-9a60-8c09efcd74a3 | textbox | Specify Min Stripping Strength and Record Strength MPa (Mpa: Reading / 7.851)
af44740d-805c-543c-bd43-9f34aaab421f | textbox | Specify Min Destressing Strength and Record Strength MPa (Mpa: Reading / 7.851)
7ee9b0ed-e0ac-5f2d-82b2-8034a6668d8f | textbox | Specify Min Lifting Strength and Record Strength MPa (Mpa: Reading / 7.851)
21bfc05c-1dce-5685-a52f-e848f3c87255 | textbox | Specify Min Curing Strength and Record Strength MPa (Mpa: Reading / 7.851)
fea69f5d-8112-5376-bca3-9ce2140ab37d | textbox | Specify Strength by Maturity if available
260fc9ef-4f5a-574a-8fc5-55730350d256 | tickbox | Mould and Steam Cured until the curing strength achieved
6e73e6ab-9d97-5d52-a761-00872542d719 | tickbox | Curing Strength: 70% of fc (Characteristic design strength)
da07f8da-9bfe-45ca-a0c3-c5a13b11409f | signoff | Client Hold / Withness Point
862acedc-775f-4157-9cf4-d8c9783c90ff | checkpoint | Lifted and Handled as per Drawings
d5731aa0-1fc5-4e47-9d94-82d819d2ee68 | checkpoint | Product Clearly Labelled
95efa7b4-fdd7-5e1b-81cc-a7b3f19048a2 | tickbox | Product ID, Weight, Cast Date, Job Number
a5963a25-9d4f-4aa1-87a3-98c02346a508 | checkpoint | Storage as per Approved Temporary Works Drawings
2b2b9632-87c7-5002-adb2-02c42a3d0d89 | tickbox | Verify supports complies with approved storage drawings and Orientation and Location matches with delivery Orientation and Schedule
d4ac5dc6-a6b3-4c71-8aec-f90060adb38e | checkpoint | Secondary Curing as per Approved Methodology
37e89761-64ee-5bbb-a2f1-9c36d3341c98 | tickbox | Temperature 5 degrees past its peak
b8d2a475-78bb-5f4b-8e60-49c5a56db7ff | tickbox | Differential between Core and Ambient As Per Spec i.e., within 30 degrees
d66db876-4555-5f46-974b-8d89e0c1b678 | tickbox | Differential between Core and Cover As Per Spec i.e., within 25 degrees
c2984c9f-e25a-45f2-9eb6-2c11ac8cacdb | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
f665a54f-fd95-5fb2-9ffd-0f0418fd4cf7 | tickbox | Length
babf1c7b-48d3-56a6-9902-1d6732f660b4 | tickbox | Width
c6b22bc3-96b6-5214-9138-4cb92addfada | tickbox | Height
b94f3e0e-2b64-505d-8fa1-75faa041a40f | tickbox | Straightness
3cc51bd9-f95b-51a9-b9a9-9be13f346d16 | tickbox | Cross-section
2073f460-9594-5d2a-9aa1-7767c72092a6 | tickbox | Check all critical dimensions comply (Bearing Location)
7b98a17b-46fe-4fe5-b911-86a639b0c203 | checkpoint | Specified Finish Achieved
0d6f9f0f-e060-47a2-86b9-7a17be6be21a | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
3869c0e7-a6d6-55a6-9674-8e20fe67a67f | tickbox | Ferrules
bc4e476b-4afd-560e-ba01-16a42565cc6f | tickbox | Couplers
365ccd26-f2a6-5404-9bc9-9d4e6283c47e | tickbox | Stainless Items
4061d645-927d-511f-9bfc-3c65635f8f65 | tickbox | Lifters
e2ec123c-87d1-5650-beec-bff9bd436efa | tickbox | Blockouts
ace00dcf-5396-532b-9f2a-09337a431784 | tickbox | Earthing and Bonding
3d057abd-3dc3-5e0e-b5ef-ae56b1f3089b | tickbox | Post-Tensioning Equipment
7a7dcfcc-99d1-4e58-87e1-68895a5074cd | checkpoint | Post-Pour Works Completed (As Required)
f2b0c6c6-7a4c-5b7a-8c99-00d409c6a555 | tickbox | Strands have been cut flush and epoxied.
1021c974-3946-5b3b-925d-a22fc65d0d39 | tickbox | Strands are properly bulbed.
26016113-806c-5feb-b64f-1db620d9e687 | tickbox | Nailplates, recesses, and other obstructions have been removed.
029b8acc-73d8-5c12-b253-cf7d0a6e3922 | tickbox | Couplers and ferrules are cleaned and capped.
75da6244-4a9a-58f0-9113-ad94873cde83 | tickbox | Earthing and bonding terminals are cleaned, with bolts securely screwed.
85f9be96-7587-5bf3-9e2a-8a1f75d3e768 | tickbox | Chamfers are clean, neat, and present on all required edges.
b4d3651e-11c7-5d9d-8a09-a22afe562421 | tickbox | Cooling pipes are drained of water and filled with grout as per the Work Method Statement (WMS).
cf33d765-d640-5e3b-9969-813bd8e0dffc | tickbox | All drain holes, service ducts, and blockouts are cleaned and cut as required.
c9e76e87-9427-585e-9a1e-20490e4c863d | tickbox | Temperature logging wires are cut flush with the surface.
06625071-dc3a-551b-b8bf-005069d07f8d | tickbox | Starter bars are cleaned and bent as specified.
7b138042-6139-53e5-8b41-d8d628322836 | tickbox | Surfaces requiring roughening are greencut according to the drawings.
209e7e70-9889-59f0-9f85-00e0404ff213 | tickbox | The top concrete surface is free of loose concrete.
4d30da38-f5fd-5ecb-b920-41f54cb5232a | tickbox | Areas requiring U2/U3 finish do not have a roughened surface.
b2a45234-d63e-5f00-b7ad-ff7e4352c4f2 | tickbox | Bug holes and air bubbles have been identified, with sizes and distribution compared to AS Standards.
343f48b9-a3ab-5c0c-a8a3-60cc2a30ad3d | tickbox | All blemishes (dry concrete) have been removed and patched.
113cbaf3-63cc-58bc-88ce-e071636496a1 | tickbox | Any discoloration on external/visible surfaces has been removed by sanding.
2d5fd840-99f4-572b-a5fd-c10ee44951b5 | tickbox | All generic post-pour works are completed as required.
60e25e57-7414-4792-8334-d33a2d6b86c9 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
dedae1e1-b22e-4d0d-bbb1-2791bf6b797f | checklist | 11. PRECAST SURVAY |  | [object Object]
bf4d87da-8b9d-406b-802b-462502d9a2ad | section | HOG/BOW DETAILS
80dbcdf6-71a7-4513-913a-bdc5180efa84 | checkpoint | Survey Hog of Beams
b9879238-98e1-59c9-8eb9-d0721a70b59f | textbox | First Reading (mm) (Once Stripped)
bd3d0d35-1e7d-5811-b3e1-a1741f54216d | date | First Reading date
1d0ae6d5-01ff-504a-84c0-3a51687c7cd0 | textbox | Second Reading (mm) (After casting stage 2 And / Or atleast 7days after stage 1 casting) (if required)
c66af43e-8afd-52f4-91bb-decd5925de63 | date | Second Reading date
9a37f45a-db9f-5aaf-b7eb-9fbe7ad959b7 | textbox | Third Reading (mm) (At 28 days after stage 1 casting)(if required)
b3acb8ea-e6c5-51bf-9866-7751b806f4cc | date | Third Reading date
b575fd8d-094c-59c7-9527-cce61dbecaa8 | textbox | Final Reading (mm) (7 days prior to scheduled delivery)
55172cb1-aa63-54f8-8f01-a505dde829f3 | date | Final Reading date
469de381-c4cc-4d53-8743-50d274408bbf | section | GENERAL SURVAY
c19e985f-6ab6-4e3a-b612-ef7594cc5f88 | checkpoint | Survey Details
bccfa221-0935-5d36-b913-87c8dee3dab3 | tickbox | Geometry Survay (Attach the files)
bcf5c231-1cd0-5ce4-8a95-117ed84e082e | tickbox | Stress bars
898fcd6f-cfea-5ca2-89b4-1f51483d04b5 | tickbox | Ferrules
c1286140-b823-5e93-a838-6d5bfd44da06 | tickbox | Bearings
a09b26c5-246b-54a5-a138-cb0071a33ed7 | textbox | Others (specify)
bcdb07bb-8c18-4bbc-aab7-fae190a87cb7 | checklist | 12.CHECKLIST-STAGE 2 |  | [object Object]
b361a97f-c9e5-49cc-9645-8ff4e4cff1f0 | section | PRE-POUR CHECKLIST
03e4f3ad-7feb-48ad-a948-8827de32d122 | checkpoint-no-value | Details
9f0e9e99-8316-52f5-936e-51bf7dd937fe | textbox | Cast Number
8b0d3764-fe36-5981-a0ba-e7f0e3d398c7 | textbox | Specify Precast ID:
92f5b112-4694-4f79-909b-25a6e0e5698d | checkpoint | Shop Drawings approved for Works
0b3d1c82-1fbc-5a0a-a117-139318274443 | date | IFC Date
cb95c90d-f69b-44db-9cb9-9b770cd5d878 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
11c9cd97-9673-5cdb-ab28-ae1d0d107c56 | tickbox | Length
5b784ac6-cd11-52a3-9742-1d9717fd6977 | tickbox | Width
e35cdf7d-b875-59a9-85d5-c7bbde139622 | tickbox | Height
f5f750e5-bb29-5543-ab21-507648dc91dd | tickbox | Straightness
949ca7a8-2d4f-5fe7-912e-c821831e4d10 | tickbox | Cross-section
35ba85b8-13f1-4432-9f7d-459614c5f8bc | checkpoint | Mould Surface Checked
a43d38bc-ad2e-5009-98fd-4f9f45c87747 | tickbox | Cleaned
c24d869f-057a-5a18-8d38-2cd58e3d45c4 | tickbox | Sealed
3b0dfa1d-65f2-5b43-be4f-ff04d2d30afc | tickbox | Rubbers in Place
63c74c30-42a9-50cf-a4e4-ed9032223a18 | tickbox | Oiled
5e619914-8f6c-576b-a15d-b3f7b5ec61a0 | tickbox | Chamfers in Place
a109d478-0955-5fb5-b48a-b12c5ab98beb | tickbox | shutters angle checked
0e8bf17c-ed37-56bb-865a-9b9d167da934 | tickbox | Temporary props / Push-pull spreader in place and secured
bd81d7c1-5e25-4345-a9b3-afe91c0a1f90 | checkpoint | Reinforcement in Accordance with Drawings
fa9b856b-f8b8-5135-a97d-6c363b31c2c9 | tickbox | Reinforcement size
2f4f5f92-e197-5f2f-9b43-08fa109b6fe3 | tickbox | Reinforcement Quantity
81ac48f3-1d65-5231-a203-2426ac83937b | tickbox | Lap Length
8bf19184-4341-572f-9899-ef0b444912b5 | tickbox | Splicing
a9e3d935-31e3-52be-a0c5-f7adb8cca5fd | tickbox | Stitch pour reinforcement lapping bars spacing maintained (If Required)
3023a652-75ad-53dd-97da-132cc3572d8a | tickbox | Blockout recess around lifting Hoops (If Required)
b472b02c-8e5f-594b-baaa-213f1a835bf6 | tickbox | Reinforcement bars with couplers (If Required)
dc734b34-3508-5d40-9a74-5fdd4d7d7d36 | tickbox | Additional reinforcement around Lifters (If Required)
85ab804b-132d-5f9e-8ede-39f23a50476b | tickbox | Bar Chairs / Deck rails
59028b56-b5a7-525a-95c0-a923955ecd1e | tickbox | Cover maintained and within tolerance
8a9951db-2f19-4f4d-a033-2ddb23a02a85 | checkpoint | All Cast-in Items are installed in accordance with Drawings and Tolerances
991aa870-e527-55df-b9e7-a42f6faa9d81 | tickbox | All Ferrules are installed in accordance with Drawings and Tolerances
8597c8f4-9aef-5bc5-bd55-253997dbd9fb | textbox | Specify Ferrules Type and Quantity
ac3f3621-bd8c-5589-8ec5-11dc459eb09a | tickbox | All Stainless Items are installed in accordance with Drawings and Tolerances
239a5f0c-9766-56de-bf7f-0066f2826009 | textbox | Items:
b7cce523-056d-5f84-9b89-8fd83dc27b9f | tickbox | All Blockout Conduits / PT ducts / Stressbar are installed in accordance with Drawings and Tolerances
73e196c5-2926-5096-88e6-358d9365d4ad | textbox | Temporary Works Conduits
c10be822-9e34-55a0-8a7a-73c8ff6596f1 | textbox | Transport Holes Conduits
826c2734-7de8-55f4-8f29-d7389855cf59 | textbox | Bearings
f2d1e711-8e14-566b-8b94-922ece29e4ea | textbox | PT ducts
29ab7959-5da1-57ca-84af-87c75a4f00d6 | textbox | Stress Bars
636b59cb-9a89-5d97-983b-26b30b01b776 | textbox | Other type, specify
0a43c230-2c5a-5d7a-9ef6-eca5a2f5ef08 | tickbox | All Lifting Inserts are installed in accordance with Drawings and Tolerances
50785aec-164e-51d0-a1c0-241b2f416c2e | dropdown | Lifting System | Lifting Loops, Lifting Anchors, Edge Lifters, VLGB Load Ring, VSL Bars (Stress Bars / Cors Nuts / Lock Nuts / Bearing Plate / Washer) Others (Specify)
9732f007-5fd4-5465-a8d1-3c7b6f0f9739 | textbox | Items:
32244b35-e09f-5ad0-9d71-6e67adc4669b | tickbox | Additional reinforcement around Lifters (If Required)
a3f811c4-2fdf-5e36-86f7-cefd9ac5baca | tickbox | All Couplers are installed in accordance with Drawings
1ef4a3e1-d09e-53e1-851c-edbe4bf7b0ac | textbox | Specify Couplers Type and Quantity
fd76aa09-a5cc-5305-a1a0-99c79cc50d2f | tickbox | Other Casting Items are installed in accordance with Drawings
8840f70c-ec8a-58fb-93f2-c840a901cf73 | textbox | Specify Type and Quantity
3789be93-0381-4f79-9042-3496883cd6c7 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
c9a4c704-b5bd-5cd4-976f-9b954e48a932 | textbox | Earthing Terminals Specify Type and Quantity
29efb438-30ec-53f5-b88c-3833f8007079 | textbox | Flexi cables
56b527d5-0f18-5e57-86bd-6f2ba5fbda59 | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
af6658b3-eb20-5a60-afd2-510b2beb6fa6 | textbox | <20 mOhm across cage Length
fc97ab05-8225-5b01-b91d-96f9b93cd3e1 | tickbox | Checklist Completed (attach results)
9ed9b5bf-15b6-4399-8c6f-0d568326e90c | signoff | Client Hold / Withness Point
30f0df5c-f99a-4264-9480-93bef48d3c6f | checkpoint | Pre-lifting cage inspection (Client present)
c7e697bb-8136-43d0-8218-e186f3f5316c | checkpoint | Installation of tubs
2a1e6230-920b-572e-bc5e-1cc6ce2bc216 | tickbox | Tubs are tightened and positioned correctly
ce438532-e8fa-57a1-8af1-566e1da999e2 | tickbox | All Sliding arms are locked in position
f8c910d5-f218-5a93-bdce-868d7f099823 | tickbox | All accrow props are locked in position
630032af-f723-579c-a9c5-26db16776e10 | tickbox | Dimensions of Tub and Webb are correct
dd937ce0-e738-57e7-8b45-1c94e45d0d70 | tickbox | All feet for tubs resting on mould & bolted down
6ebb0a68-8ed9-5ef8-b46a-4a89d0006b59 | tickbox | Tubs have release agent
0f73d548-d15d-4ae1-8283-3921cb20d22d | checkpoint | Water Cooling Pipes
c32b4e6e-4f92-5e8d-a112-ce89e473730b | note | Verify (if used):
fb4bb7f5-93d9-5e19-957e-53e2c25f59f3 | tickbox | Number, location and installation of water cooling pipes as per approved WMS
294bf859-7873-421a-8bbc-e63125213e18 | checkpoint | All Temperature Loggers are installed as per Approved WMS
fef5712b-3eca-5503-930a-56655851c238 | tickbox | Ensure All temperature Loggers are Working (Check Maturix)
c7d1ca00-2d4e-58cf-8718-49edc7b3db2e | tickbox | Number, location and installation of loggers matches WMS
3a4e41a6-17b9-5137-9d6b-53c5d9f3d4ee | tickbox | Every 25m
b212e29f-0b18-57bb-8e30-f667a90c5086 | tickbox | 1 x Core (If Required)
b3c6a265-a0e9-5d98-acc6-1a678156758c | tickbox | 1 x Within Cover Zone
b7133d39-d382-58cf-929a-80428d4671ac | tickbox | 1 x Within Tent/Tarp Enclosure (Outside concrete)
3a5a675a-1ee0-5610-a553-17ce654e4c7a | tickbox | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
ea517cc6-bfc9-573d-80ee-1417cdb2e8d7 | textbox | Specify Extra Loggers If Required
8d2970f9-dd4d-45ea-bd2b-5f338d119c40 | checkpoint | QA Engineer Check Completed by
8b4f97ef-da94-4c76-90d5-7f7763a91b85 | checkpoint | Pre-Pour Mould inspection (Client present)
791d630d-839f-42de-8c59-f5f4410480aa | signoff | Client Hold / Withness Point
783ecc72-0e74-4593-a7a4-cb6575393065 | section | SUPERVISOR / SUBCONTRACTOR CHECK COMPLETED OF MOULD & CAGE FOR CONCRETE PLACEMENT
4b289063-ebb4-4e96-8b63-2bdad2003617 | checkpoint | Supervisor Release to Engineering Team
89ed2bc8-2d61-542e-bafd-dcead03c4ccd | tickbox | Verify all concrete placement plant / equipment available
0ce09959-b389-5b6f-9bf2-dc3ba886d92d | tickbox | Concrete Supplier of pour Notified
cd9cd1dc-f2b2-5dfe-a5d1-ff738102bfbd | tickbox | NATA Testing Laboratory of pour Notified
13f00c57-3e63-4818-8641-270d5498d7bf | signoff | Supervisor Hold / Withness Point
004e8efb-66fb-4a7d-aa6f-45bb448b75ba | section | CASTING DETAILS
f301287c-29b8-4254-b02e-d9f6e8619f9d | checkpoint | Pour Detail
f82790ea-a706-5212-aaad-df456c58d233 | date | Cast Date
fcfa5678-e7ea-5af9-be8a-1c02c68f9aec | textbox | Concrete Delivery Docket (list All And Attach Dockets)
38ba7fb7-0c35-5502-9632-75f9a09a512d | textbox | Total Concrete Volume (m3)
8b4fec13-a024-5e5f-96d4-8f8bf5bc2d71 | textbox | Specify Mix Design Verified/Used
02bef180-0c2a-5a5d-9479-391cd7bc4f98 | textbox | Ambient Temperature within Limits (max 38°C)
1c9faa4d-75de-5426-9ee2-58a9aec5208f | textbox | Concrete Temperature within Limits (max 32°C)
a6660e46-679f-5558-99d8-4380ce0a5157 | tickbox | Slump within Allowable Tolerance (First truck and every 20m3)
ce064523-54d8-5bbb-857c-4c44d66d8d0e | textbox | Slump (list all)
d8e9f653-d4fa-474e-92e9-7f6c5269e6ab | checkpoint | Truck Tested for strength
397613b8-36b1-56ec-9802-64e277b1b6b0 | tickbox | If volume <=20m3, 2 sets min required
d31a5548-b7d7-5452-bd55-12cb12eb0ddc | tickbox | If volume >20m3 & <= 40m3, 2 sets min required (every 20m3 tested)
37082075-ee2b-5ef2-a529-89bc0ddcc922 | tickbox | If volume >40m3, sample every 20m3
09fb05a7-dd66-5edf-b3b5-75da50e05ba2 | tickbox | 1 * 7 Days and 3 * 28 Days per test (Total 4 Per Test)
7b54b34d-3117-517e-94b2-79ddf46dbf3f | tickbox | Cast 2-4 Cylinders for Destressing / Stripping / Lifting / Curing (PMC Internal)
1a7e0072-3fac-5bae-9380-7a3970ac9812 | textbox | Test Report Reference Number (list all)
67b8e22b-915c-4dc2-9366-6d7636f73425 | checkpoint | Concreting
70326ab8-389b-5f2b-a259-e10c695c6384 | tickbox | Vibration adedquate
a5ba3335-18d5-511b-aad2-2d032c653863 | tickbox | Time Lag Between Trucks is not exceeded
8bab3df6-c029-541c-ad93-b31b69fa9fe1 | tickbox | Concrete Placed within allowable time from Batching Plant
88f36ed6-ccf0-593c-b2fd-98c4507060ac | tickbox | No Free Fall During Pour
d5b861c9-7ba2-59dc-a61c-0c51512c6bce | tickbox | Required Finish Applied as per Drawings
1147d21a-0a58-41cb-aa9b-911caa27e100 | checkpoint | Curing
7211db0f-370c-599b-ab01-4a04afa13393 | tickbox | Concrete Covered Overnight and Tent sealed
7a12766d-dfad-5140-b9dd-2480e57103cf | tickbox | Cylinders Stored next to Bed and covered as per AS1012
a19b2af1-4c45-5337-bc9b-b8b3fd286cf3 | tickbox | Verify (if used) Temperature loggers are connected and recording and set the temperature alarm to 65°C.
9c688c35-4b37-5ee3-b27a-717fc8ee091c | tickbox | Verify (if used) Pipes connected, pump working, no leaks in mould
56fefcf0-97c0-5953-8484-398720880360 | tickbox | Verify (if used) Steam Temperature Monitors installed and connected
43e4ab73-8291-4b8f-a95f-6c466ccfcec2 | section | STRIPPING CHECKLIST
de1007bb-6477-4b54-8a22-661a576085c0 | checkpoint | Date Stripped
898525b0-4443-5363-a028-8f012eb3984a | date | Date Stripped
d6dd3896-ff7b-4bbd-ba6a-093c3b9a88f6 | checkpoint | Minimum Required Strength for Stripping, Lifting, and Curing Achieved
d8cc68ac-4a1f-5b3b-9482-ec30f693514f | dropdown | Strength Determined by | Crushing Cylinders, Maturity Report
afaf5c6e-9925-5aab-b050-89bb0bc798e6 | textbox | Specify Min Stripping Strength and Record Strength MPa (Mpa: Reading / 7.851)
caeff3eb-2f71-5599-aeec-707aec63d32a | textbox | Specify Min Lifting Strength and Record Strength MPa (Mpa: Reading / 7.851)
27ce5e77-31a9-5bdd-bb52-14be8e4e1ba2 | textbox | Specify Min Curing Strength and Record Strength MPa (Mpa: Reading / 7.851)
0ab03ce7-24d7-51af-b179-023e66a3786d | textbox | Specify Strength by Maturity if available
d5cbcca8-6274-5b3c-bc36-0071fbee62c6 | tickbox | Mould and Steam Cured until the curing strength achieved
29287b31-80b6-5e17-83d7-503f874d096d | tickbox | Curing Strength: 70% of fc (Characteristic design strength)
457250a4-696f-4b54-9e5d-fd055eee81c8 | signoff | Client Hold / Withness Point
aa228f29-8d57-4716-87a0-1c1a09dd3f2a | checkpoint | Lifted and Handled as per Drawings
49992e6c-564a-4d88-b6ca-8452809526ce | checkpoint | Product Clearly Labelled
d2eec5c5-ba35-5f82-8804-7a029fa980f9 | tickbox | Product ID, Weight, Cast Date, Job Number
0060417b-7c5e-4226-a51f-e29e396e89a8 | checkpoint | Storage as per Approved Temporary Works Drawings
93d6551e-6ab7-5303-89b2-63d8a47364a6 | tickbox | Verify supports comply and Orientation and Location match with delivery Orientation and Schedule
a433d982-c1e0-49fb-8386-f9a0d020441a | checkpoint | Secondary Curing as per Approved Methodology
cf01856d-5492-5cb5-a63d-cc6481f0e5a0 | tickbox | Temperature 5 degrees past its peak
e146da65-d4ff-5f16-9191-73e3c2708a40 | tickbox | Differential between Core and Ambient As Per Spec i.e., within 30 degrees
7e02f5e8-3257-575d-b400-758caf13f35b | tickbox | Differential between Core and Cover As Per Spec i.e., within 25 degrees
d708de6b-7d3d-44e5-bb45-efd2a3026883 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
9f7c1361-be3b-5f9f-867e-7b79c09ab2e3 | tickbox | Length
1c1ac710-f857-591d-81b2-60c5fed53a69 | tickbox | Width
5db5d58a-3bbe-513a-80b4-9a7fab794bb1 | tickbox | Height
361c9ca4-bfce-5ac8-b53f-404f345c7990 | tickbox | Straightness
f3d6c00c-db18-5f2e-bf94-8d10c2d1c359 | tickbox | Cross-section
1784cc08-ce2f-4e78-b380-a8f1e7c79f39 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
2a463640-33b8-501a-ae63-75fdc3e573c0 | tickbox | Ferrules
8d785afc-d25d-5e08-845b-1ec9b069a28b | tickbox | Couplers
66aa1112-2149-5eb8-8425-5ebf90024f15 | tickbox | Stainless Items
a920c776-6975-5b7d-aeff-3fd113eb7b3f | tickbox | Lifters
f18007b5-d903-579e-91b0-294255d91113 | tickbox | Blockouts
592c2eb8-f26b-5dde-bb9e-23c8d4f154e0 | tickbox | Earthing and Bonding
d227688a-0ecb-56aa-9559-8e4e305c91ac | tickbox | Post-Tensioning Equipment
a102d273-9f73-4f1c-a3c8-6b24249616a4 | checkpoint | Post-Pour Works Completed (As Required)
a0145470-6116-5443-bf7a-9baecaaa68af | tickbox | Strands have been cut flush and epoxied.
25d4927c-1ace-5e25-b786-455382ad9343 | tickbox | Strands are properly bulbed.
faa8d30f-a635-5b86-8087-708652765047 | tickbox | Nailplates, recesses, and other obstructions have been removed.
38cf029a-f542-5ef5-82d1-a716d4d47a92 | tickbox | Couplers and ferrules are cleaned and capped.
6a2fda68-8ee2-5cf1-adcc-4b58f97c341c | tickbox | Earthing and bonding terminals are cleaned, with bolts securely screwed.
3cc9a579-4c9d-5cef-870c-3da85c06ea2e | tickbox | Chamfers are clean, neat, and present on all required edges.
79e57536-fdde-5494-a45c-82ad320ea77c | tickbox | Cooling pipes are drained of water and filled with grout as per the Work Method Statement (WMS).
cd60d997-d35e-57cc-8a7c-3679aab138cb | tickbox | All drain holes, service ducts, and blockouts are cleaned and cut as required.
e48d6c5b-dda2-5095-9d65-6660bdbf9135 | tickbox | Temperature logging wires are cut flush with the surface.
20174a5d-2654-5567-b6e5-ff23fb30de8a | tickbox | Starter bars are cleaned and bent as specified.
87906db0-d9d7-5d50-95eb-6164f5540326 | tickbox | Surfaces requiring roughening are greencut according to the drawings.
43dec4db-8567-5b51-b2de-954b84c9599a | tickbox | The top concrete surface is free of loose concrete.
c7d80fdd-585b-5848-b4f3-0c45e3118024 | tickbox | Areas requiring U2/U3 finish do not have a roughened surface.
a5c9d536-bd94-5fd9-83fc-9061d00d9afe | tickbox | Bug holes and air bubbles have been identified, with sizes and distribution compared to AS Standards.
448931be-ce30-53d0-9372-dd31c2905ddd | tickbox | All blemishes (dry concrete) have been removed and patched.
fd058ab6-44be-5446-adbe-aa17c299f5c6 | tickbox | Any discoloration on external/visible surfaces has been removed by sanding.
2eea5460-7aee-51c4-a941-366a9fbe3f4e | tickbox | All generic post-pour works are completed as required.
74a7325b-16f4-5dad-baf4-1fe870f1b029 | tickbox | Specified Finish Achieved
46f0980d-ddd5-4827-91d5-a0f03f3ea3f0 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
499e506b-0f2c-410e-b768-a26ad6700ca4 | section | CONCRETE STRENGTH TEST REPORT
51d31563-fc81-4bf2-bef0-f79da921ae15 | checkpoint | Concrete Strength Test Report Received
350b401e-bbc0-57fc-afdb-abbaf76c95ec | textbox | Concrete Test Report Number
8cbfabad-6b98-5bfe-9f98-23e4bf3f0d72 | textbox | 7 Day Strength (List all) (separating each with a comma)
4eaa9841-c12d-5f25-91f0-3e5eee656bfc | textbox | 28 Day Strength (List all) (separating each with a comma)
85ace93f-b44f-4524-9154-57f28d77770e | checklist | 13. POST POUR CHECK LIST |  | [object Object]
f456a1ad-1387-4707-ac3d-de66909efdcb | section | ANY DEFECT IDENTIFIED
bf7c6075-cee9-4575-8d4d-90b13c134150 | checkpoint | Punchlisting Completed for all Units / Attached
5edad631-ae83-5a93-a19d-94b30ff02723 | textbox | Precast IDs (More Than One Unit)
07d7c9a1-3c6d-494b-ade4-66f5e938b8e7 | checkpoint | Crack Map Completed (If Applicable) / Attached
d510870a-eea5-5405-a354-70911d350397 | textbox | Precast IDs (More Than One Unit)
cd914ff4-a76c-4a3b-ac96-9dea4679e884 | checkpoint | NCR Approved by Client and Repairs Completed (If Applicable)
97ee1a33-7f46-58fa-8ec9-29480adca045 | textbox | Precast IDs (More Than One Unit)
68d81d52-de51-446d-8be4-e8db95b2df1d | checkpoint | Client Inspected Precast and Accepted Visual Condition
68ee04bf-9da3-58b4-bb1d-c376f5b26f10 | textbox | Specify Precast ID (separating each with a comma)
5edce80f-793f-469b-9664-00115ebaf00b | signoff | Client Hold / Withness Point
91a870ac-9022-4c19-abaa-160a456188ff | checkpoint | Precasts are free of Defects and QC Stamp Placed
4c26b251-3cf1-58ec-8821-831476c135e5 | textbox | Precast IDs (More Than One Unit)
053ceda5-6c7f-4ab5-81b6-a09ff7d4260e | section | AS-BUILT DRAWINGS
0829f354-be80-4c04-b84a-36fd2841a5bf | checkpoint | As-Built Drawings Completed, Stamped and Attached
c3d19c94-6fd5-4ca8-8e36-b29fcb8b3fd3 | section | CONCRETE STRENGTH TEST REPORT
c68970de-edf4-497a-8f84-f1d41e4ceef5 | checkpoint | Concrete Strength Test Report Received
d0ee4965-9db5-5ecf-8c05-3c4ced47ef3c | textbox | Concrete Test Report Number
5e2feb95-44a5-5b94-aae5-50905a19da21 | textbox | 7 Day Strength (List all) (separating each with a comma)
4d9df370-5376-55d1-8e57-53f771e848a6 | textbox | 28 Day Strength (List all) (separating each with a comma)
3f87a390-0239-440c-9de1-9a653939ac15 | section | TRANSPORTATION REQUIREMENTS
6ac09494-dff9-447a-8d81-6d885bf12c73 | checkpoint | Transport Strength / Age
d2df4cf2-93df-5764-b5ab-fe0b381ab5d5 | tickbox | Verify unit(s) have achieved 28 day concrete strength
6d32f000-5138-59f7-9c70-19e1ce46d661 | tickbox | Verify unit(s) is at least 7 days old
1ca005ab-e2f0-49cd-be1d-ce4386cbc634 | signoff | If 28-day strength is not achieved by the delivery time, obtain client approval for a minimum of 95% of the 28-day strength before delivery.
27af60bc-636f-4e60-886c-cfb73669ce5e | checkpoint | Certificate of Conformance
611188dc-6617-4148-a376-edea189a3071 | checkpoint | Inspection Release Certificate
79ebb25c-5e93-4d7d-b099-9b7889e44f15 | checkpoint | Delivery Notes
f71171ff-d506-4e7f-9a52-92cd6c75d552 | checkpoint | Delivery Docket
b3b03f3b-fe01-53a6-8dfa-0dbb0a5eb66a | tickbox | Lashing, chains, frames, bolts, supports, and orientation of precast elements as per approved drawings.
f7061603-79af-5a2a-929f-28c616221c80 | tickbox | Attach Final photos prior to delivery (on Truck)
708a2e8e-5275-4ce6-9ba1-7e3273fa0a2e | section | FINAL ACCEPTANCE
0003d44b-8ea2-4203-813b-f61e53e2de77 | checkpoint | Completed by
55688a03-ecb3-40d6-bdce-e8ef08325868 | checkpoint | Reviewed by
77fa9a17-5069-4126-86ef-3e7fbe86d8f4 | checkpoint | Client Representative (if applicable)
876ba526-3084-4c5b-9793-98e303309318 | signoff | Client Hold / Withness Point
1a50bb77-c632-45a5-b5e1-fe10dca5de73 | checklist | 14. PRECAST UNIT CHECKLIST- COMBINED |  | 14. PRECAST UNIT CHECKLIST- COMBINED
0713e52b-b29d-4e0b-b43c-b3c33b37f7f6 | section | PRE-POUR CHECKLIST
5c57768d-af6c-4aa8-a4d9-977828634fe7 | checkpoint-no-value | Details
b24b80db-0096-50f2-882d-4dd53f6c6690 | textbox | Cast Number
53e1297d-4d94-551a-9abe-83a2d95b4331 | textbox | Specify Precast ID (separating each with a comma):
f030d3b5-9c23-5aa0-bcf0-acb15f0b3228 | textbox | Strand Arrangement Type (If Required)
20316608-58f0-4f09-9558-03545ad75783 | checkpoint | Shop Drawings approved for Works
825d3e4f-3777-53ae-940b-3216aea31088 | date | Shop Drawings approved for Works
7e6bf3fc-443c-4aa5-9996-4f9e06815903 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
fc2decf0-a8e1-50ba-8be0-1deeb72ef8ff | tickbox | Mould set-out drawing provided
3a4d61ee-5ade-5142-80af-4fd4bb575e50 | tickbox | Length
65cfe034-e345-5d92-9012-e7ae5f0e594d | tickbox | Width
2ab6a27d-e34f-51a2-82e0-698765858a05 | tickbox | Height
9a122bd7-5173-5969-ae12-c718da6480ec | tickbox | Straightness
77b2e8be-ad10-5370-88a2-fef4a4da8110 | tickbox | Cross-section
06bf0f00-f13f-45b3-9a67-ebacd9a7ec37 | checkpoint | Mould Surface Checked
938246b8-b070-59e9-a261-7340e973e084 | tickbox | Cleaned
e91c4b91-d47f-5a9c-8d38-b7e864857eae | tickbox | Sealed
f04408d5-0f1e-5029-97fa-b917df1362e0 | tickbox | Rubbers in Place
013ba197-acf3-5328-80f1-dfa558fec0ee | tickbox | Oiled
ac4af697-1e62-5b70-9a15-abc12325922d | tickbox | Chamfers / Drip Groove in Place
5b9f0eb2-837d-5544-aa59-deeba05c4030 | tickbox | shutters angle checked
0fdcd2a5-d46d-5f3e-a55b-6691311b4e85 | tickbox | Temporary props / Push-pull spreader in place and secured
8349a6b8-dfdb-4b5f-a7e2-f743a3a24cfc | checkpoint | Reinforcement in Accordance with Drawings
fc707278-ede0-517a-9313-5ef04db9765d | tickbox | Reinforcement size
b2aa4d32-2aee-5a2e-bab8-83684ae528a8 | tickbox | Reinforcement Quantity
0c8554b1-b145-5dff-897a-2d07d5ddde0d | tickbox | Lap Length
7db7c5a8-e683-5c1c-8c2b-8f4128db8234 | tickbox | Splicing
73d18704-8603-5588-bf13-6c5281dab456 | tickbox | Blockout recess around lifting Hoops (If Required)
3b45e2c0-ff4f-5750-bb16-0c37665219a9 | tickbox | Additional reinforcement around Lifters (If Required)
45b51328-70a5-5cb5-9549-55e3eeee6eef | tickbox | Bar Chairs / Deck rails
09d66f4e-3103-5d82-bb0c-a1232897e04f | tickbox | Cover maintained and within tolerance
20c8d3c1-8119-4a10-bd82-2915660cb15a | checkpoint | All Cast-in Items are installed in accordance with Drawings and Tolerances
3c750ff9-2881-56f7-bca9-ca59ce15fc27 | tickbox | All Ferrules are installed in accordance with Drawings and Tolerances
7ea80980-986d-5145-847d-2789bf523982 | textbox | Specify Ferrules Type and Quantity
d1ee5ccc-6566-5773-bb89-328ca282ded1 | tickbox | All Stainless Items are installed in accordance with Drawings and Tolerances
fc25bd79-e712-5b90-a67d-73ec3c3f4fbc | textbox | Items:
924b225c-013c-577a-977a-cec7b5fb61dc | tickbox | All Blockout Conduits / PT ducts / Stressbar are installed in accordance with Drawings and Tolerances
6607d171-f2f9-51b0-91b3-892691b27c36 | textbox | Temporary Works Conduits
3edf30b4-2845-58ad-b870-63f41150c222 | textbox | Transport Holes Conduits
5ec7c023-2570-5d69-95ce-893dd0347bc4 | textbox | Bearings
4ffa91f2-4f8a-567d-a06e-342426d0c1b6 | textbox | PT ducts
82672e2a-321f-599f-ae59-6eabfec010aa | textbox | Stress Bars
5ca07be5-0233-5fa7-87c1-747a8bb91576 | tickbox | All Lifting Inserts are installed in accordance with Drawings and Tolerances
b3d72cb1-7df3-53dd-bb0e-8c2a6d017896 | dropdown | Lifting System | Lifting Loops, Lifting Anchors, Edge Lifters, VLGB Load Ring, VSL Bars (Stress Bars / Cors Nuts / Lock Nuts / Bearing Plate / Washer) Others (Specify)
0068bc02-3ef1-5cea-a46a-3bf2888de499 | textbox | Others (Specify)
a0331e37-992d-581b-9e95-559a8b7b86a9 | tickbox | Additional reinforcement around Lifters (If Required)
8c123e31-399b-56ac-afe4-3f30c934eed6 | tickbox | All Couplers are installed in accordance with Drawings
d1925633-c1b3-5495-be1a-b8d6948e92f7 | textbox | Couplers Type and Quantity
91df6178-6925-5dec-996f-f9567a58e3fa | tickbox | Other Casting Items are installed in accordance with Drawings
67d23308-442b-5dcc-8eb1-a08247aa9f14 | textbox | Type and Quantity
af1fb13b-9d09-414f-b2af-4b07477e2c40 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
c4388b32-982c-51e7-bd4b-6c7e815d5734 | tickbox | Earthing Terminals Specify Type and Quantity
d66b5a91-cb7b-54f8-a09e-7b26c2fee27d | tickbox | Flexi cables
fb271d30-31bd-5306-a84d-b13e5f803b56 | tickbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
ad9e5151-48ad-5846-b750-e4f16b9f9da7 | tickbox | <20 mOhm across cage Length
b0c82d2f-67dd-5c94-b7c6-67276010a12d | tickbox | Checklist Completed (attach results)
0b293ad8-7653-4072-b3a3-e9f5840c0858 | signoff | Client Hold / Withness Point (If Required)
3ef854cc-bf36-4e46-bb00-875e76117fa8 | checkpoint | Post-Tensioning Equipment is installed in accordance with Drawings and Tolerances
4a8da3fc-81ab-5327-a5c4-bd01e89ecef9 | note | Verify:
123c4cf3-814c-5ac7-9fef-d40928c24f6b | textbox | Tendon Types
70b6a9d0-2585-55a2-be86-83a3519f2a2c | tickbox | Profile
cab4a874-16d2-5ef1-81bb-c4ff4afc269f | tickbox | Firmly secured to rebar
88ee8892-bd08-503a-a057-d77d56e90036 | tickbox | Grout tubes, Breathing Tubes and Grout Vents secure / sealed
a3477fb2-1654-5256-a861-2fe70ac004bb | textbox | Anchors installed / secured
bd40fb7a-c32f-511f-bbc5-65e1629a3c86 | tickbox | Temporary blockouts in Tendons
e48eec06-2579-40a1-986e-80bd44902abd | signoff | Client Hold / Withness Point
37d0a13f-928b-4276-b1c0-f17baeebca91 | checkpoint | Prestressing Strands
d511bdb5-9991-5c9b-817e-f8dd70f82b9a | note | Verify
c8b8557c-00a3-5813-80c5-1c28fbd1e3d1 | textbox | No of strands
70c34e83-a8cb-5e84-9ad6-f8b4d3e8cd6e | textbox | Debonded strands encased to correct length
4b396c84-939e-596b-9a76-47b453a2e4d1 | textbox | Enter Coil Number Used for this Cast
660f76db-2f15-5e8c-8b5f-b75d56ed1ed7 | tickbox | Sag Load all Strand
3a228dc1-68fc-5294-b72b-2f52f12494c9 | tickbox | Full Load: Multi-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
fdd712d1-6244-5039-8c4b-2630d31a8510 | tickbox | Full Load: Singel-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
a56f60e5-b092-4431-9a18-1885d48b55d8 | signoff | Prepare Stressing Records and Submit to Client for Review (HOLD POINT FOR CLIENT TO SIGN OFF)
555529a9-cbeb-46d9-85f4-b15cbe78cbf3 | checkpoint | Pre-lifting cage inspection (Client present)
2ddd9b6d-5b75-470c-be52-2954597ae0d2 | checkpoint | Installation of tubs
5426041a-f9ca-57b7-9298-cf3204d368c3 | tickbox | Tubs are tightened and positioned correctly
3b793e3c-afa5-544b-ace8-91fc567b554d | tickbox | All Sliding arms are locked in position
47ac13ed-6b13-57e2-af1b-a018a9a88f72 | tickbox | All accrow props are locked in position
d5756507-d4f2-514c-8bfa-e74f8341c1ec | tickbox | Dimensions of Tub and Webb are correct
7b31496a-0aa4-5429-ad34-9462b0b28df6 | tickbox | All feet for tubs resting on mould & bolted down
1a103c27-9baa-54c0-bd8a-89fee9922de4 | tickbox | Tubs have release agent
0b38d9c4-4fd1-42ac-8ca7-56b6ccb6fb92 | checkpoint | Water Cooling Pipes
28227867-35d8-5cb0-ad16-f69b4f96d81a | note | Verify (if used):
bd566169-8122-5f2e-9a47-1ba74440263c | tickbox | Number, location and installation of water cooling pipes as per approved WMS
60301485-1833-423a-a79b-211656979e41 | checkpoint | All Temperature Loggers are installed as per Approved WMS
6c2e861f-a6e1-5805-a378-b61274b7b9fc | tickbox | Ensure All temperature Loggers are Working (Check Maturix)
394bccf1-b6c3-5646-9fc4-6b33bd40ccde | tickbox | Number, location and installation of loggers matches WMS
2c2ea927-36ac-52ba-8af5-3801ea04b21b | tickbox | Every 25m
72fb952c-00cd-56ed-be29-fc5ad150cd7a | tickbox | 1 x Core (If Required)
8a0889bf-2b44-5b4a-9331-25581f80db75 | tickbox | 1 x Within Cover Zone
8058adf5-d427-5544-9351-80f77849f61e | tickbox | 1 x Within Tent/Tarp Enclosure (Outside concrete)
acbb3a12-df03-5cde-bebc-3ad503eb1c42 | tickbox | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
ec5f579a-18b0-5ca0-be3b-7ea91b4eba63 | textbox | Specify Extra Loggers If Required
d2f0ccb0-bcca-4a08-bb8d-0780115f29c7 | checkpoint | QA Engineer Check Completed by
2725f722-f1b3-48ca-b1b1-4811f05feb9e | checkpoint | Pre-Pour Mould inspection (Client present)
9140d14d-1ebd-460d-a2cb-e73af706b0d9 | signoff | Client Hold / Withness Point
67e1f4ea-9a09-4909-b1e9-65cdbda8d4e3 | section | SUPERVISOR / SUBCONTRACTOR CHECK COMPLETED OF MOULD & CAGE FOR CONCRETE PLACEMENT
57e74153-1ba7-4070-8e1f-30a208a70c29 | checkpoint | Supervisor Release to Engineering Team
2458dc2f-5244-54b6-a091-3df03148bba3 | tickbox | Verify all concrete placement plant / equipment available
cc8d6641-7ded-51dd-8af8-584be2cadd62 | tickbox | Concrete Supplier of pour Notified
5536b3c0-6804-5d7e-b670-07ed5ff4cdc3 | tickbox | NATA Testing Laboratory of pour Notified
47383fc6-fc09-446c-a7b8-b90257afff22 | signoff | Supervisor Hold / Withness Point
28ce6b4f-0bb3-448b-a87a-08ea10aceb50 | section | CASTING DETAILS
14603eb8-d885-42ab-b27e-2c888153977f | checkpoint | Pour Detail
b8cae436-8596-59ad-8a3d-ca4817d9dca4 | date | Cast Date
1f5384ba-ae49-584a-bdcd-586d3989aa50 | textbox | Concrete Delivery Docket (list All And Attach Dockets)
5f383b8b-03ee-5b68-b7b9-a5299938f7b9 | textbox | Total Concrete Volume (m3)
60b5a2b4-a546-575f-a532-3b411e05543b | textbox | Specify Mix Design Verified/Used
bfe989df-839b-5dc7-bc41-c7cc46940555 | textbox | Ambient Temperature within Limits (max 38°C)
c1f0718c-f108-5bf6-9bd4-3caec6b700cf | textbox | Concrete Temperature within Limits (max 32°C)
b6230f87-7fde-550c-9595-5d421424f007 | tickbox | Slump within Allowable Tolerance (First truck and every 20m3)
806c4ab1-43de-5d73-ba53-90a8144e5f06 | textbox | Slump (list all)
833a35a2-c2f7-49bf-93d8-802c3b9459e5 | checkpoint | Truck Tested for strength
e109839c-938c-54fe-9eab-50cb8b8fb6d6 | tickbox | If volume <=20m3, 2 sets min required
d0a7531f-4ab4-5d62-9e70-18057b439b44 | tickbox | If volume >20m3 & <= 40m3, 2 sets min required (every 20m3 tested)
49c43334-fdc6-5b14-b82e-97c7c090f89b | tickbox | If volume >40m3, sample every 20m3
aafe37fe-c097-5ce1-8579-a48f016e353f | tickbox | 1 * 7 Days and 3 * 28 Days per test (Total 4 Per Test)
65080bce-f204-5e84-a502-df0172c5a4f5 | tickbox | Cast 2-4 Cylinders for Destressing / Stripping / Lifting / Curing (PMC Internal)
401161a7-deee-52bb-80ee-0922ae52fcfd | textbox | Test Report Reference Number (list all)
356f5f95-928a-4876-8902-7c5f3e11e434 | checkpoint | Concreting
db717803-4179-5036-b5cc-70de97135bb2 | tickbox | Vibration adedquate
45b530f3-bc8a-5fd6-95e2-e8488af82fe0 | tickbox | Time Lag Between Trucks is not exceeded
855b7cfa-e076-5ed6-8398-d5467d9f8652 | tickbox | Concrete Placed within allowable time from Batching Plant
2ac9e16f-5da8-559b-8aca-0bce84ad0982 | tickbox | No Free Fall During Pour
792d6004-aab8-5178-8c5f-20c1091d2786 | tickbox | Required Finish Applied as per Drawings
c83c3955-6e77-42f1-afb7-6259deb54ddb | checkpoint | Curing
fd6af66f-db96-596d-908a-d366958eb11a | tickbox | Concrete Covered Overnight and Tent sealed
0d34e3e2-d59c-5716-9aab-79bfaa7b44fd | tickbox | Cylinders Stored next to Bed and covered as per AS1012
4d188ee6-48f0-5c5a-8a62-940db65d2785 | tickbox | Verify (if used) Temperature loggers are connected and recording and set the temperature alarm to 65°C.
1a66798b-8576-5a41-bb02-06b50c7d813d | tickbox | Verify (if used) Pipes connected, pump working, no leaks in mould
0945bdc8-0336-50c0-be52-3142a8bee080 | tickbox | Verify (if used) Steam Temperature Monitors installed and connected
5c71b37d-1d7b-4ed4-a25a-7a5500006fff | section | STRIPPING CHECKLIST
685e4b14-935a-4c38-b0fa-c3c8c7c51c34 | checkpoint | Date Stripped
07fb3ab0-3d5a-564d-b728-bb91806685ec | date | Date Stripped
1ddeb403-46cb-4efa-9cd5-445e1abd2365 | checkpoint | Minimum Required Strength for Stripping, Destressing, Lifting, and Curing Achieved
9333de2c-f623-5335-81d1-6c9fddf5bf22 | dropdown | Strength Determined by | Crushing Cylinders, Maturity Report
de20fb02-b2bf-5f50-9643-752abf99b763 | textbox | Specify Min Stripping Strength and Record Strength MPa (Mpa: Reading / 7.851)
79c09c47-031b-5673-b28e-13527fe4396f | textbox | Specify Min Destressing Strength and Record Strength MPa (Mpa: Reading / 7.851)
012e076c-52f2-5baa-893c-57dc423c59fd | textbox | Specify Min Lifting Strength and Record Strength MPa (Mpa: Reading / 7.851)
a246371a-68f1-52bf-a51b-372545193ee0 | textbox | Specify Min Curing Strength and Record Strength MPa (Mpa: Reading / 7.851)
34a46fe5-8818-5848-acdf-89bfa32a5c49 | textbox | Specify Strength by Maturity if available
ef413462-02e0-5dc5-ad1f-738fdc36795e | tickbox | Mould and Steam Cured until the curing strength achieved
ab33fdad-d4b2-5a94-8d2b-2bd7679c97bc | tickbox | Curing Strength: 70% of fc (Characteristic design strength)
08eb7d49-c0f8-4e4b-b319-eb92756a2090 | signoff | Client Hold / Withness Point
d7f2ece2-3553-4ed2-965d-8ae6da45c8dd | checkpoint | Lifted and Handled as per Drawings
5d436d90-815a-4962-9ccb-a294d5baa710 | checkpoint | Product Clearly Labelled
0b8dee5b-1277-58b2-ab30-e3dcf8b75ec7 | tickbox | Product ID, Weight, Cast Date, Job Number
9dcb8d55-a661-4bca-a0d8-a5bf663d8e8c | checkpoint | Storage as per Approved Temporary Works Drawings
a7ca56d0-36e9-54f3-b16d-035e440a980a | tickbox | Verify supports complies with approved storage drawings and Orientation and Location matches with delivery Orientation and Schedule
dd7ba9a3-970f-4d06-a0f3-4dbb56ad8fbc | checkpoint | Secondary Curing as per Approved Methodology
0787e3e1-4432-5b5e-8f53-cfbe769b30f1 | tickbox | Temperature 5 degrees past its peak
f9ade2b5-a1da-5f3f-9378-5607c04e50a6 | tickbox | Differential between Core and Ambient As Per Spec i.e., within 30 degrees
5b09f76e-dfee-5e5d-aec5-d86b1ff7a0a2 | tickbox | Differential between Core and Cover As Per Spec i.e., within 25 degrees
08ca23ac-f1e0-49ae-bbed-65e0de59fd26 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
c03a112e-242d-5a18-b513-d1b2c890cda6 | tickbox | Length
f2a6b042-02ae-5d39-b774-9b6991d4db3e | tickbox | Width
cbe1e5e6-ef46-5435-ab3f-c5d2ec244b71 | tickbox | Height
eb28d0ce-6016-5f23-a69c-2b2c447dcb36 | tickbox | Straightness
1725355b-acad-572c-83b2-f00518779179 | tickbox | Cross-section
bc33de54-75d4-4648-8692-8662c5476f51 | checkpoint | Specified Finish Achieved
72b412d9-f32f-44d0-b38b-91e56e47972f | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
37d1df15-071d-5cd7-b81c-ad357c2f82f5 | tickbox | Ferrules
6a64b94f-6a6b-5328-8955-57cd60869a39 | tickbox | Couplers
c42e3db1-3448-598a-afe3-26eb016afef4 | tickbox | Stainless Items
48822101-fd73-5ffc-9378-33fb819336e6 | tickbox | Lifters
9f13321c-33dc-5b4c-94ab-835a3d20b72a | tickbox | Blockouts
028dc839-1da6-5c4a-820e-cce29f0411af | tickbox | Earthing and Bonding
4c33cbf4-0bd7-5fe2-b552-13b47760f448 | tickbox | Post-Tensioning Equipment
1c91f69a-c5cc-49fd-a86b-5e158683177a | checkpoint | Post-Pour Works Completed (As Required)
a57e1c3d-c47c-5ca4-ac0c-b61a82827265 | tickbox | Strands have been cut flush and epoxied.
f2b1cfa2-fd90-5275-ab7d-7dd625c3424a | tickbox | Strands are properly bulbed.
63ae0adf-eb83-5232-8c53-f4dfc945ebaf | tickbox | Nailplates, recesses, and other obstructions have been removed.
05f54b4d-1130-5d40-9111-3cfaa0aa9879 | tickbox | Couplers and ferrules are cleaned and capped.
84035b4c-f598-53f8-b663-13a247248df7 | tickbox | Earthing and bonding terminals are cleaned, with bolts securely screwed.
74d41e6a-f0e9-5a22-8819-7d503119f75b | tickbox | Chamfers are clean, neat, and present on all required edges.
afd65c28-a4b0-5918-b4bd-820553e26711 | tickbox | Cooling pipes are drained of water and filled with grout as per the Work Method Statement (WMS).
a465e7c8-bdb1-5375-bf85-47159625a5a4 | tickbox | All drain holes, service ducts, and blockouts are cleaned and cut as required.
7b555a36-daa2-5c1c-85ce-d68575577593 | tickbox | Temperature logging wires are cut flush with the surface.
4ee848cd-8cb1-5ed2-bbc1-5b5042f9e04d | tickbox | Starter bars are cleaned and bent as specified.
018a0610-821f-5631-adf9-f0b9022ef890 | tickbox | Surfaces requiring roughening are greencut according to the drawings.
1df82490-6752-5a91-bda5-660a6b511716 | tickbox | The top concrete surface is free of loose concrete.
40eec08a-9c43-575a-8df1-501546e772b3 | tickbox | Areas requiring U2/U3 finish do not have a roughened surface.
5e9757b5-6c55-5ba9-947b-b5ba915ea200 | tickbox | Bug holes and air bubbles have been identified, with sizes and distribution compared to AS Standards.
9ecb1e8f-8aec-5d3b-87ad-ffbc535c4569 | tickbox | All blemishes (dry concrete) have been removed and patched.
218f471f-974d-5e42-9218-04b459f1f5fd | tickbox | Any discoloration on external/visible surfaces has been removed by sanding.
2bc7f389-ba2b-56a4-9b21-e1afa19ab3e0 | tickbox | All generic post-pour works are completed as required.
bfe90614-e869-4ce8-baa6-33ffb321a902 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
a0eb8a3d-ecec-4705-a2d4-096b17a29954 | checkpoint | Survey Hog of Beams
b0827207-6cf3-584b-b183-37edc415c6ab | textbox | First Reading (mm) (Once Stripped)
d3dc6789-c26d-57ce-868b-ecaa4a01525a | date | First Reading date
8fb1843f-87b9-5559-aa26-e8383fc9f463 | textbox | Second Reading (mm) (After casting stage 2 And / Or atleast 7days after stage 1 casting) (if required)
df5c980e-fb62-5e4d-a1aa-e997aed27fb8 | date | Second Reading date
ed6cf66d-7deb-5a96-99f7-765671236bc1 | textbox | Third Reading (mm) (At 28 days after stage 1 casting)(if required)
b3306e61-f717-5755-8900-a5597c5cacfb | date | Third Reading date
957e4f47-1335-5d98-8bba-322723d554af | textbox | Final Reading (mm) (7 days prior to scheduled delivery)
1daa3f80-ae1e-51d9-aaae-79951f522d91 | date | Final Reading date
ba80ef08-5c1f-4a04-aa8f-a049df1fa8ef | section | ANY DEFECT IDENTIFIED
81c0b640-4e1a-40d1-858e-fde7e77b61db | checkpoint | Punchlisting Completed for all Units / Attached
2172f117-10ab-5072-a74f-7aa40fc48887 | textbox | Precast IDs (More Than One Unit)
ea14f02b-8657-4470-980f-273b72fa435b | checkpoint | Crack Map Completed (If Applicable) / Attached
c2ba4d38-ac16-5133-b801-78f2dea01821 | textbox | Precast IDs (More Than One Unit)
6fe07d2b-f651-484c-ac73-110a52821c38 | checkpoint | NCR Approved by Client and Repairs Completed (If Applicable)
b5c9f7c4-97e0-52de-8b9e-f332cddfbabf | textbox | Precast IDs (More Than One Unit)
e571e159-b4a7-4a97-a7a8-6067597ff8cd | checkpoint | Client Inspected Precast and Accepted Visual Condition
8f0ced2d-1688-5bbb-8c74-4b3e8b9f7431 | textbox | Specify Precast ID (separating each with a comma)
5c6fd29c-c477-4d47-9c18-5b3e23d312c0 | signoff | Client Hold / Withness Point
e6ee8aae-4d82-4324-b419-177a93039f4a | checkpoint | Precasts are free of Defects and QC Stamp Placed
b6cc5b21-f884-5b9b-aedd-e496b911727d | textbox | Precast IDs (More Than One Unit)
313518fd-5b87-4605-b4a2-155a60592c2b | section | AS-BUILT DRAWINGS
bb61108b-3ec3-42f1-abbe-164320e1f027 | checkpoint | As-Built Drawings Completed, Stamped and Attached
642a71ca-e473-4acc-bd73-074afd8444e3 | section | CONCRETE STRENGTH TEST REPORT
cb578869-19e1-469b-b75f-9102880f962b | checkpoint | Concrete Strength Test Report Received
9145f656-ab47-585d-9a92-f9344cf6548e | textbox | Concrete Test Report Number
ab5e8bf6-190d-5d77-939c-77250b02bfcd | textbox | 7 Day Strength (List all) (separating each with a comma)
55369a9a-faa2-5cd3-86c2-87173ef70193 | textbox | 28 Day Strength (List all) (separating each with a comma)
ceffccf0-6950-40e4-8803-3906f3807107 | section | TRANSPORTATION REQUIREMENTS
3084df4f-d8d4-4fc5-a00b-c628bc07ef93 | checkpoint | Transport Strength / Age
21e9bf21-9449-55aa-86fa-15ea83206611 | tickbox | Verify unit(s) have achieved 28 day concrete strength
5030083c-d1c3-58d9-9372-608b1bcba1b9 | tickbox | Verify unit(s) is at least 7 days old
8f37bcfb-4357-44c5-ba98-3c4c99fe45c8 | signoff | If 28-day strength is not achieved by the delivery time, obtain client approval for a minimum of 95% of the 28-day strength before delivery.
786cb5fc-bc32-4715-a2a3-c349b4166740 | checkpoint | Certificate of Conformance
89e75904-08f9-4c26-87c1-75d82a07737d | checkpoint | Inspection Release Certificate
4b11af3d-e3c6-49de-9c2e-c87ff8845d91 | checkpoint | Delivery Notes
a5d1ffc2-0b70-4df0-a9a1-5e575f4196c5 | checkpoint | Delivery Docket
90fe47dd-f1e0-57df-b22d-7985623d647d | tickbox | Lashing, chains, frames, bolts, supports, and orientation of precast elements as per approved drawings.
66314b2a-b882-5db8-b952-3b9eb8f6129e | tickbox | Attach Final photos prior to delivery (on Truck)
f3ce2e3f-8068-40a0-8638-931c2652afce | section | FINAL ACCEPTANCE
68907f6e-7e4d-4f77-a3de-c412af2870b3 | checkpoint | Completed by
17997d9b-76ad-47e9-af57-bccd801b9714 | checkpoint | Reviewed by
48e802e1-c468-4bc1-b2a7-bbbd18f6057f | checkpoint | Client Representative (if applicable)
6cfe3816-b28f-4b8f-b627-55041d953833 | signoff | Client Hold / Withness Point

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
7a614cda-7922-4d8e-b11d-0b208a404a9f | checklist | Precast Beams |  | Precast Beams
0e814078-3806-4ab7-812c-c59865817988 | section | Pre-Pour Checklist
63e9aec2-5f47-4b2f-999f-571edf69e32e | checkpoint | Details
6af10176-2eb8-57fb-b122-0d4963dba9ca | textbox | Cast Number | 1
21332056-2a73-560c-be9f-0cf5ce2351be | textbox | Project Name | 3
b7cb55a0-b73e-585e-bf9b-233eccac2870 | textbox | Precast Concrete Roof Unit 2 | 4
1e3730c6-1710-4cd8-ad8b-7a97ed37a92f | checkpoint | Shop Drawings approved for Works
44e33da0-fa52-4543-aa4d-d055718c7eff | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
6d94f182-a6cc-54f6-8b73-216c95d214fa | note | Length
0240ff71-62dd-5128-930a-2a586af86b90 | note | Width
3cc20daa-b344-5b8b-b544-15b8b6b07800 | note | Height
48b7256c-9416-51ff-9993-bb83a25e69b9 | note | Straightness
f8f5b1b7-03a0-54e2-8356-14b3b8191e42 | note | Cross-section
d1e311f4-eed4-4068-8142-a4395ed4d622 | checkpoint | Mould Surface Checked
e34ca181-2deb-53da-910a-9e17bb4f8950 | note | Cleaned
b44dd801-b4ae-5d36-ae8d-1ee134f3b580 | note | Sealed
75439750-7d42-5a75-882a-e75db1d174bb | note | Rubbers in Place
283e6634-441d-5acf-b7b0-3f0865acaa57 | note | Oiled
15eb39d6-cd14-53ff-add3-c80e127d4464 | note | Chamfers in Place
155d5fe0-f0fa-4160-a3d6-991f749b1604 | checkpoint | Reinforcement in Accordance with Drawings
b4654cec-9c4d-5887-9422-e43853643ac0 | note | Reinforcement size
181d3b28-62a0-5244-b2f3-ce54708203c9 | note | Lap Length
e34c988c-9559-5f24-8108-3d5028e5b4df | note | Splicing
6d42c60d-313a-528c-aa3d-f62874664485 | note | Bar Chairs
9e9a5b2d-9d17-4d4f-930f-00c07875f832 | checkpoint | Cover maintained and within tolerance
6f2bccc4-e1a4-4389-89a9-02c5bbacaf69 | checkpoint | All Cast-in Items are installed in accordance with Drawings
ed2cd275-9232-5df0-9dfe-40e721850378 | note | Cast-in Items
471cf251-87cb-54f2-9541-728d624e4ed8 | note | Fittings
33931a6a-df0f-53ea-9236-083a8cc0de7b | note | Lifters Position and Type
cdac2a72-9ab7-43d8-bdda-fd34f6b80111 | checkpoint | QA Engineer Check Completed by
1f8866b2-0b64-401e-a217-ab616edaa1b2 | checkpoint | Client Inspector (if present)
75d48435-8132-4d92-84e5-73fab2d7fa20 | section | Supervisor Release
501f27bb-cf2d-4ce3-afe1-b71a0947f24e | checkpoint | Supervisor Release to Engineering Team
5e4738bb-1644-4c5a-a9e9-cd5effeb76b3 | section | Casting Checklist
4a0215b2-e6bd-44e8-b4c7-6243f99926ae | checkpoint | Casting Information
a9258353-4f7c-55ac-990e-39c081e395d5 | textbox | Cast Date | 2
fdb5770e-b790-4141-8ac5-4548cf198f21 | checkpoint | Concrete Delivery Dockets
d8dbce70-69c0-52a4-a633-8266f56bab90 | textbox | Concrete Delivery Dockets | 8
eea378d4-ec3f-4e8e-b42d-e1bdaf14ed3a | checkpoint | Total Concrete Volume
e76dc85c-6962-562f-82ac-2f288f433768 | textbox | Volume (m3) | 7
b4afff45-f5ed-4f2b-bd0e-899e04668a9e | checkpoint | Mix Design Verified: WS504MB09 (S50/14/200)
7c7c4818-1a6c-57e0-8291-13ea8676c99f | note | Concrete Mix Strength (Mpa) | 6
1380a18b-814b-4b4b-8c55-421f0c228e08 | checkpoint | Ambient Temperature within Limits
c1d0fb5a-f449-5622-b94d-7628f8c5bbc6 | note | 5 - 38°C
766a6c25-27d0-4245-a466-084ff3cb8b4c | checkpoint | Concrete Temperature
3cf83273-244a-57cd-a3c6-630166c16e43 | note | max 32°C
a0a2cacf-63e8-4600-b960-156c36deca1c | checkpoint | Slump within Allowable Tolerance
97b4670d-2d69-532b-a127-7d17f31539d3 | textbox | Slump 1 | 14
053055d5-382b-5321-932d-7fc3c8ef6de0 | textbox | Slump 2 | 15
0f598fd5-5200-5c8c-8851-719228c490a2 | note | Holcim S50/14/200(Design Slump 200)
c1cc1ff7-66f3-4e73-9703-8f69b2bea551 | checkpoint | Truck Tested for strength
b5667b53-d8cf-5260-9749-2a3fdd04bac9 | textbox | Test Report Reference Number 1
182e90b4-1ece-5686-9bf9-81b2e2b8f45c | textbox | Test Report Reference Number 2
8155ad70-a412-4fc0-bb28-01e309cab0b1 | checkpoint | Time Lag Between Trucks (< 20min)
f24eddc1-faa0-41db-91da-3a7bc8c69ad0 | checkpoint | Concrete Placed within 90min from Batching Plant
9af8e959-23f7-44fc-b43c-8246819597c0 | checkpoint | No Free Fall During Pour (< 2m)
772c94d2-2c81-4331-ba37-5adb86987e84 | checkpoint | Required Finish Applied as per Drawings
504a4877-2131-4654-b1a1-e99f2bb05a6b | checkpoint | Concrete Covered Overnight
86826854-6887-4bb2-b857-045ac5197b80 | checkpoint | Cylinders Stored next to Bed
d0b187e9-3cd6-4f28-aff0-164ee7d21411 | section | Stripping Checklist
8c8d4cea-8ca6-4cab-8adf-cb8af2c6ea93 | checkpoint | Date Stripped
9c5f692e-34c8-5b67-a1fc-b41a4845d4ca | textbox | Enter Date
f443ca73-d224-56f8-bdd0-63a95b305cf7 | textbox | Stripping Strength | 16
d0300f0c-4795-5c92-b978-1062d68ce5a6 | note | Strength = Reading / 7.851
4b708246-ccfa-41f4-a0cc-12607570e585 | signoff | Concrete Cylinders Crushed and Submitted to Client
2c560b29-2ff9-48e9-8f63-c230616aeabf | checkpoint | Lifting Strength Achieved
3e1e7477-4af4-441a-a482-b89ab566faa5 | checkpoint | Product Clearly Labelled
3b72ec65-3121-48a6-8213-8928845bc6b3 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
d9c5027b-bb59-5c0d-bf24-822f04f8fa42 | note | Length
76e4dcdd-58d6-5a39-bb5f-63c6d99e8e6d | note | Width
63caca50-2dd0-59e5-861b-4f455ec8c1d9 | note | Height
86cb0245-d53b-5a05-afdf-48c54de4ab05 | note | Straightness
3fc6074f-a49b-5730-a56f-68312f8b8d88 | note | Cross-section
539934e4-d8e2-45a7-a09c-3b66e66bb659 | checkpoint | Specified Finish Achieved
f186c771-1900-4f63-ae48-7bfea2498c00 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
c3de5e9c-484b-58f8-9fb9-1cb9c964ac3c | note | Cast-in Items
bbb95424-9c0f-54cc-89d7-7607b939ca9e | note | Fittings
ba76d287-3e75-5fa2-a494-c8b91a63bec7 | note | Lifters Position and Type
699aa502-8373-4fee-9086-1029a79aeecf | checkpoint | Lifted and Handled as per Drawings
27df9a92-0e4d-4cd7-b6c8-c13ddc47dc6b | checkpoint | Storage/Stacking as per Approved Plan
93010855-09a5-426b-a573-e0ff89160b19 | checkpoint | Curing as per Approved Methodology
821ba6e0-97f7-4150-b5b5-0a73195b1810 | checkpoint | Post-Pour Works Completed (As Required)
f75d6ffb-2b4f-555e-852a-cb66317b4822 | textbox | All Miscellaneous Items are Completed
f0ecbe73-3bac-4681-9057-62dde16fbd51 | section | Any Defect Identified
526ce212-6346-4db5-b2b4-670706b8934d | checkpoint | Punchlisting Completed
ff668800-f142-4912-96af-64c3305024ae | checkpoint | Repairs Required (if applicable)
d1ca474b-c695-48a4-a980-9dfef05495d2 | checkpoint | Repairs Completed as per approved WMS (if applicable)
5dc305b6-15b3-422c-9122-4bf5165a2275 | checkpoint | Any NCR Required (if applicable)
3e702dfc-945c-4439-903f-077bc2108d05 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
66820e01-d460-46f8-8a2b-9540501c55c1 | section | As-Built Drawings
8dfe9fb6-7587-428b-964e-1cc9399b9104 | checkpoint | As-Built Drawings Completed, Stamped and Attached
2c9b6225-3d24-4d45-88b5-bb046510b64e | section | Concrete Strength Test Report
b6cf7c7c-2d4d-4b5b-b795-b5b90e00b1f0 | checkpoint | Concrete Strength Test Report Received
6950862e-5461-577d-afd5-9342aaa6b254 | textbox | Concrete Test Report Number 1
bd82c25e-fd2e-5eb3-b0c0-2c2da1a72222 | textbox | 7 Day Strength (1) | 17
b46a1fbb-ea7d-56a7-a104-d5c0b1878de4 | textbox | 7 Day Strength (2) | 18
89ccc599-ad72-54c1-896d-29c2e5a5b544 | textbox | 28 Day Strength (3) | 19
3bdd66d6-d70b-596e-993a-2e23dfabddb2 | textbox | 28 Day Strength (4) | 20
76e4ad02-425d-532f-bc00-faf646a358de | textbox | 28 Day Strength (5) | 21
651b2ec6-ef82-5886-a78e-1c5bce1c7d56 | textbox | 28 Day Strength (6) | 22
faf5c625-9b59-488b-9a58-5c7a947af1a9 | section | Transportation Requirements
55e0ce1b-b88c-42d6-8cdc-b49b26d7631a | checkpoint | Certificate of Conformance
085ea3d4-d8fb-446c-a388-3b1874d3a09f | checkpoint | Inspection Release Certificate
b1b5fdf3-9a74-45de-b6d4-c17c53391ac4 | checkpoint | Delivery Notes
7ecd3659-f4e1-4e11-b6ff-53dd6ecb4284 | checkpoint | Delivery Dockets
c1b1b0a7-78c4-4a56-9c75-e84c8ca50256 | section | Final Acceptance (Conforming to all Requirements and is Ready for Transport)
0d706ff0-0e07-4bc8-a716-b605b830fd5e | checkpoint | Completed by
5d5a4776-5be0-41f1-875f-2c049337f667 | checkpoint | Reviewed by
36508d00-c63d-4556-bc7a-7e3fe81429d7 | signoff | (INTERNAL HOLD POINT)
5df99bbd-eebb-460e-826a-fbe30fbcc6aa | checkpoint | Client Representative (if applicable)
3799e0cb-7cab-4ec2-a238-5353d3088901 | signoff | (EXTERNAL HOLD POINT)
272c798d-b29e-4dc9-8845-0b64a7967840 | checklist | Preliminary Activities and Materials Approval |  | Preliminary Activities and Materials Approval
6141d9a6-4e73-4cb5-a578-c1a11fb22480 | section | Preliminary Activities (Approved by Client)
afd45702-e9b9-4a5d-8cf3-f28ea87c2d28 | checkpoint | Compliance to AS/NZ ISO 9001:2015
632a1b87-1291-4626-928c-a26b45a8b783 | checkpoint | HSE Management Plan
ad2016f5-d11a-42e7-9f65-a8816149a119 | checkpoint | Permacast Project Quality Management Plan
aeffff30-d59f-4672-8ebb-48f56fc0f875 | checkpoint | Inspection & Test Plan
df187feb-7c7b-48f9-8a15-7bf05ee03382 | checkpoint | MDR Index
cdc30570-e109-4ab7-b861-9fe1d1c75303 | checkpoint | Work Method Statement (WMS)
47ee7ded-7fbe-416c-ae52-d9715071ef75 | checkpoint | Work Method Statement (WMS) - Curing
6d1fecfa-d72e-4f3c-8a40-e3fd112889e8 | checkpoint | Concrete Repair Methodology
2b3bfd48-2b15-4cf9-a8a1-b1c8fca00606 | checkpoint | Shop Drawings
925c4674-11d9-41db-942c-b7682970cdc7 | checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
3b7a83af-41e6-47df-bbbf-356d1ed8ebdb | section | Concrete
5f0b6544-4de6-4d38-b786-520c19d25988 | checkpoint | S50 Concrete Mix Design Approved by Client
4dd894a1-a3d5-5338-87fd-35e45d9d4d10 | note | Supplier : Holcim
18681c05-6cc1-53d4-9e29-790464710c8a | note | Mix Code: WS504MB09 (S50/14/200)
b084d0d5-8e5c-57e4-b907-0a62f723a1eb | note | Slump : 200 ± 40
8d02d5fb-def5-4111-976e-01639e3701bb | section | Steel Reinforcement
e74bef77-ed73-4843-a447-e050384c8327 | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
babdf3e8-c355-4781-98bf-7f3091b73f46 | checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
ed7cd395-cad2-4fe2-8515-4691121aa0b0 | section | Lifting Anchors
49cda1a4-cd4c-414b-bdb6-7a1d04632df6 | checkpoint | Lifting Design Approved by Client
887e0e50-8d04-4103-8696-c24fc0a39280 | checkpoint | Lifting Devices Approved by Client
79e9c4c7-e7d1-4639-bc50-2f1cba5fb0ce | checkpoint | Inspection of Delivery for Completeness and Quality
78a34852-cee7-4cab-b70c-c0ce2f088982 | section | Cast-in Items and Ferrules
a4f25f67-5252-448d-97c7-5fa524fc2325 | checkpoint | All Cast in Materials Approved
c3ea3eb8-f780-4cb0-a6fa-ce9d3efe6741 | checkpoint | Inspection of Delivery for Completeness and Quality