## Sheet1
Customer: |  |  |  | Lot No:
Project : |  |  |  | Job Location:
Project No: |  |  |  | Date:
Zafa Job No:
Inspection Code | [5 empty] | Inspection Initials
H - Hold Point [Direction from Nominated Authority] |  |  | R - Record/Report | W - Witness Point | FM - Foreman PM - Project Manager | O - Observation
No | Process | Inspection Type | Test Method | Acceptance Criteria | Frequency | Action | Report Ref.
1 | PRIOR TO WORKS COMMENCING
1 | Set Out Limits to be Inspected by the administrator prior to excavation | H | Direction | Site Marked Up Prior to Works Commencing | As Required | PM | Authority to ProceedVisual
1.1 | Extent of Crack Filling | H | Direction | All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form | As Required | PM | Authority to Proceed
1.2 | Extent of Strain Alleviating Fabric Strips | H | Direction | All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form | As Required | PM | Authority to Proceed
1.3 | Areas for Corrector Course | H | Direction | All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form | AS Required | PM | Authority to Proceed
2 | ASPHALT WORKS
2.1 | Weather Conditions | O | Visual | Surface dry and free of surface water. Paving not to take place during rain | Continuous | FM | Authority to Proceed
2.2 | Asphalt placement and compaction (1) | O | Visual | Sufficient notice given to enable inspection of: Materials or areas ready for tests. | Each Shift | FM | Visual
2.2 | Asphalt placement and compaction (2) | O | Visual | Testing (incl. rolling pattern trials) | Each Shift | FM | Visual
2.2 | Asphalt placement and compaction (3) | O | Visual | Each pavement layer placed & compacted. | Each Shift | FM | Visual
2.2 | Asphalt placement and compaction (4) | O | Visual | Surfaces prepared for tack coating, sealing, surfacing. | Each Shift | FM | Visual
2.2 | Asphalt placement and compaction (5) | O | Visual | Asphalt surfacing | Each Shift | FM | Visual
2.3 | Pavement Surface Temperature | W | Measure | Supply additional roller if below 25 degrees celcius and /or high AC temperature when winds are > 25km/h | Continuous | FM | Authority to Proceed
2.4 | Preparation of the Existing Surface | W | Visual | Surface is Dry and Clean Prior to Commencement of Paving | Each Shift | FM | Authority to Proceed
2.5 | Excavation Depth | R | Record | Measurement of the profiled depth from existing surface level. | Each Shift | FM | Dip Sheet
2.6 | Strain Alleviating Fabric | W | Witness Point | Applied to the penultimate joint below the final surfacing layer, where shown on drawings or as directed. | As Required | FM | Visual
2.7 | Application of Tack Coat | W | Observed | Tack Coat Applied to Clean Surface Prior to Placing Asphalt [0.1 - 0.3L/m2] | As Required | FM | Qty Agreement
2.8 | Joining of New Work to Existing | W | Visual | Provide smooth riding surface across junction. | As Required | FM | Visual
2.9 | Asphalt Loading Temperature | W | Observed | Max 185°C [Bitumen Binders] | As Required | FM | Delivery Docket
2.1 | Asphalt Temperature at Discharge to Hopper | R | Record | Max 175°C [Bitumen Binders] | Continuous | FM | Laying Record
2.11 | Layer Thickness - probing (loose thickness) | R | Measure | 3 points across paving run | 1/20m | FM | Laying Record
2.12 | Rolling Temperature | O | Measure | Asphalt Laying for Minimum Temperatures | Continuous | FM | Laying Record
| Construction Joints (1) |  |  | Hot join < 15 min | Continuous | FM | Visual
| Construction Joints (2) |  |  | Cold Joins to be luted with edge compaction wheel | Continuous | FM | Visual
2.14 | Edge Ramps | W | Observed | Level differences >30mm ramps with asphalt wedge Longitudinal < 1on5. Transverse (slow) <1on10. Transverse (>75kmh) , 1on20. | As Required | FM | Visual
2.15 | Apperance Quality | W | Observed | Uniform appearance with no evidence of segregation | Each Shift | FM | Visual
3 | Compaction Testing
3.1 | Compaction Testing: Relative [Core Density] | R | Record | Density testing carried out asap on customer request | As Required | PM | Asphalt Summary Test Report
3.2 | Thickness Tests | R | Record | Measure all core samples cut for densities; and Record thickness when laying 1/20 (min. 3 points). | As Required | PM/FM | Compaction Test report Dip sheet
3 | ADDITIONAL INFORMATION
I certify that the works have been contructed in accordance with Australian standards and the Inspection and Test Plan. All requirements have been met.
Zafa Contracting Pty Ltd Representative: |  |  |  |  | Signature:
Client Representative: |  |  |  |  | Signature: