## Sheet1
1 | Set Out Limits to be Inspected by the administrator prior to excavation | H | Direction | Site Marked Up Prior to Works Commencing | As Required | PM | Authority to ProceedVisual | 1 - Set Out Limits to be Inspected by the administrator prior to excavation | Inspection Type - H | Test Method - Direction | Acceptance Criteria - Site Marked Up Prior to Works Commencing | Frequency - As Required | Action - PM | Report Ref. - Authority to ProceedVisual | 1 - Set Out Limits to be Inspected by the administrator prior to excavation
1.1 | Extent of Crack Filling | H | Direction | All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form | As Required | PM | Authority to Proceed | 1.1 - Extent of Crack Filling | Inspection Type - H | Test Method - Direction | Acceptance Criteria - All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form | Frequency - As Required | Action - PM | Report Ref. - Authority to Proceed | Inspection Type - H
1.2 | Extent of Strain Alleviating Fabric Strips | H | Direction | All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form | As Required | PM | Authority to Proceed | 1.2 - Extent of Strain Alleviating Fabric Strips | Inspection Type - H | Test Method - Direction | Acceptance Criteria - All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form | Frequency - As Required | Action - PM | Report Ref. - Authority to Proceed | Test Method - Direction
1.3 | Areas for Corrector Course | H | Direction | All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form | AS Required | PM | Authority to Proceed | 1.3 - Areas for Corrector Course | Inspection Type - H | Test Method - Direction | Acceptance Criteria - All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form | Frequency - AS Required | Action - PM | Report Ref. - Authority to Proceed | Acceptance Criteria - Site Marked Up Prior to Works Commencing
2.1 | Weather Conditions | O | Visual | Surface dry and free of surface water. Paving not to take place during rain | Continuous | FM | Authority to Proceed | 2.1 - Weather Conditions | Inspection Type - O | Test Method - Visual | Acceptance Criteria - Surface dry and free of surface water. Paving not to take place during rain | Frequency - Continuous | Action - FM | Report Ref. - Authority to Proceed | Frequency - As Required
2.2 | Asphalt placement and compaction (1) | O | Visual | Sufficient notice given to enable inspection of: Materials or areas ready for tests. | Each Shift | FM | Visual | 2.2 - Asphalt placement and compaction (1) | Inspection Type - O | Test Method - Visual | Acceptance Criteria - Sufficient notice given to enable inspection of: Materials or areas ready for tests. | Frequency - Each Shift | Action - FM | Report Ref. - Visual | Action - PM
2.2 | Asphalt placement and compaction (2) | O | Visual | Testing (incl. rolling pattern trials) | Each Shift | FM | Visual | 2.2 - Asphalt placement and compaction (2) | Inspection Type - O | Test Method - Visual | Acceptance Criteria - Testing (incl. rolling pattern trials) | Frequency - Each Shift | Action - FM | Report Ref. - Visual | Report Ref. - Authority to ProceedVisual
2.2 | Asphalt placement and compaction (3) | O | Visual | Each pavement layer placed CHAR(AMP) compacted. | Each Shift | FM | Visual | 2.2 - Asphalt placement and compaction (3) | Inspection Type - O | Test Method - Visual | Acceptance Criteria - Each pavement layer placed CHAR(AMP) compacted. | Frequency - Each Shift | Action - FM | Report Ref. - Visual | 1.1 - Extent of Crack Filling
2.2 | Asphalt placement and compaction (4) | O | Visual | Surfaces prepared for tack coating, sealing, surfacing. | Each Shift | FM | Visual | 2.2 - Asphalt placement and compaction (4) | Inspection Type - O | Test Method - Visual | Acceptance Criteria - Surfaces prepared for tack coating, sealing, surfacing. | Frequency - Each Shift | Action - FM | Report Ref. - Visual | Inspection Type - H
2.2 | Asphalt placement and compaction (5) | O | Visual | Asphalt surfacing | Each Shift | FM | Visual | 2.2 - Asphalt placement and compaction (5) | Inspection Type - O | Test Method - Visual | Acceptance Criteria - Asphalt surfacing | Frequency - Each Shift | Action - FM | Report Ref. - Visual | Test Method - Direction
2.3 | Pavement Surface Temperature | W | Measure | Supply additional roller if below 25 degrees celcius and /or high AC temperature when winds are > 25km/h | Continuous | FM | Authority to Proceed | 2.3 - Pavement Surface Temperature | Inspection Type - W | Test Method - Measure | Acceptance Criteria - Supply additional roller if below 25 degrees celcius and /or high AC temperature when winds are > 25km/h | Frequency - Continuous | Action - FM | Report Ref. - Authority to Proceed | Acceptance Criteria - All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form
2.4 | Preparation of the Existing Surface | W | Visual | Surface is Dry and Clean Prior to Commencement of Paving | Each Shift | FM | Authority to Proceed | 2.4 - Preparation of the Existing Surface | Inspection Type - W | Test Method - Visual | Acceptance Criteria - Surface is Dry and Clean Prior to Commencement of Paving | Frequency - Each Shift | Action - FM | Report Ref. - Authority to Proceed | Frequency - As Required
2.5 | Excavation Depth | R | Record | Measurement of the profiled depth from existing surface level. | Each Shift | FM | Dip Sheet | 2.5 - Excavation Depth | Inspection Type - R | Test Method - Record | Acceptance Criteria - Measurement of the profiled depth from existing surface level. | Frequency - Each Shift | Action - FM | Report Ref. - Dip Sheet | Action - PM
2.6 | Strain Alleviating Fabric | W | Witness Point | Applied to the penultimate joint below the final surfacing layer, where shown on drawings or as directed. | As Required | FM | Visual | 2.6 - Strain Alleviating Fabric | Inspection Type - W | Test Method - Witness Point | Acceptance Criteria - Applied to the penultimate joint below the final surfacing layer, where shown on drawings or as directed. | Frequency - As Required | Action - FM | Report Ref. - Visual | Report Ref. - Authority to Proceed
2.7 | Application of Tack Coat | W | Observed | Tack Coat Applied to Clean Surface Prior to Placing Asphalt [0.1 - 0.3L/m2] | As Required | FM | Qty Agreement | 2.7 - Application of Tack Coat | Inspection Type - W | Test Method - Observed | Acceptance Criteria - Tack Coat Applied to Clean Surface Prior to Placing Asphalt [0.1 - 0.3L/m2] | Frequency - As Required | Action - FM | Report Ref. - Qty Agreement | 1.2 - Extent of Strain Alleviating Fabric Strips
2.8 | Joining of New Work to Existing | W | Visual | Provide smooth riding surface across junction. | As Required | FM | Visual | 2.8 - Joining of New Work to Existing | Inspection Type - W | Test Method - Visual | Acceptance Criteria - Provide smooth riding surface across junction. | Frequency - As Required | Action - FM | Report Ref. - Visual | Inspection Type - H
2.9 | Asphalt Loading Temperature | W | Observed | Max 185°C [Bitumen Binders] | As Required | FM | Delivery Docket | 2.9 - Asphalt Loading Temperature | Inspection Type - W | Test Method - Observed | Acceptance Criteria - Max 185°C [Bitumen Binders] | Frequency - As Required | Action - FM | Report Ref. - Delivery Docket | Test Method - Direction
2.1 | Asphalt Temperature at Discharge to Hopper | R | Record | Max 175°C [Bitumen Binders] | Continuous | FM | Laying Record | 2.1 - Asphalt Temperature at Discharge to Hopper | Inspection Type - R | Test Method - Record | Acceptance Criteria - Max 175°C [Bitumen Binders] | Frequency - Continuous | Action - FM | Report Ref. - Laying Record | Acceptance Criteria - All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form
2.11 | Layer Thickness - probing (loose thickness) | R | Measure | 3 points across paving run | 1/20m | FM | Laying Record | 2.11 - Layer Thickness - probing (loose thickness) | Inspection Type - R | Test Method - Measure | Acceptance Criteria - 3 points across paving run | Frequency - 1/20m | Action - FM | Report Ref. - Laying Record | Frequency - As Required
2.12 | Rolling Temperature | O | Measure | Asphalt Laying for Minimum Temperatures | Continuous | FM | Laying Record | 2.12 - Rolling Temperature | Inspection Type - O | Test Method - Measure | Acceptance Criteria - Asphalt Laying for Minimum Temperatures | Frequency - Continuous | Action - FM | Report Ref. - Laying Record | Action - PM
| Construction Joints (1) |  |  | Hot join CHAR(LESS) 15 min | Continuous | FM | Visual | - Construction Joints (1) | Inspection Type - | Test Method - | Acceptance Criteria - Hot join CHAR(LESS) 15 min | Frequency - Continuous | Action - FM | Report Ref. - Visual | Report Ref. - Authority to Proceed
| Construction Joints (2) |  |  | Cold Joins to be luted with edge compaction wheel | Continuous | FM | Visual | - Construction Joints (2) | Inspection Type - | Test Method - | Acceptance Criteria - Cold Joins to be luted with edge compaction wheel | Frequency - Continuous | Action - FM | Report Ref. - Visual | 1.3 - Areas for Corrector Course
2.14 | Edge Ramps | W | Observed | Level differences >30mm ramps with asphalt wedge Longitudinal CHAR(LESS) 1on5. Transverse (slow) CHAR(LESS)1on10. Transverse (>75kmh) , 1on20. | As Required | FM | Visual | 2.14 - Edge Ramps | Inspection Type - W | Test Method - Observed | Acceptance Criteria - Level differences >30mm ramps with asphalt wedge Longitudinal CHAR(LESS) 1on5. Transverse (slow) CHAR(LESS)1on10. Transverse (>75kmh) , 1on20. | Frequency - As Required | Action - FM | Report Ref. - Visual | Inspection Type - H
2.15 | Apperance Quality | W | Observed | Uniform appearance with no evidence of segregation | Each Shift | FM | Visual | 2.15 - Apperance Quality | Inspection Type - W | Test Method - Observed | Acceptance Criteria - Uniform appearance with no evidence of segregation | Frequency - Each Shift | Action - FM | Report Ref. - Visual | Test Method - Direction
3.1 | Compaction Testing: Relative [Core Density] | R | Record | Density testing carried out asap on customer request | As Required | PM | Asphalt Summary Test Report | 3.1 - Compaction Testing: Relative [Core Density] | Inspection Type - R | Test Method - Record | Acceptance Criteria - Density testing carried out asap on customer request | Frequency - As Required | Action - PM | Report Ref. - Asphalt Summary Test Report | Acceptance Criteria - All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form
3.2 | Thickness Tests | R | Record | Measure all core samples cut for densities; and Record thickness when laying 1/20 (min. 3 points). | As Required | PM/FM | Compaction Test report Dip sheet | 3.2 - Thickness Tests | Inspection Type - R | Test Method - Record | Acceptance Criteria - Measure all core samples cut for densities; and Record thickness when laying 1/20 (min. 3 points). | Frequency - As Required | Action - PM/FM | Report Ref. - Compaction Test report Dip sheet | Frequency - AS Required
Action - PM
Report Ref. - Authority to Proceed
2.1 - Weather Conditions
Inspection Type - O
Test Method - Visual
Acceptance Criteria - Surface dry and free of surface water. Paving not to take place during rain
Frequency - Continuous
Action - FM
Report Ref. - Authority to Proceed
2.2 - Asphalt placement and compaction (1)
Inspection Type - O
Test Method - Visual
Acceptance Criteria - Sufficient notice given to enable inspection of: Materials or areas ready for tests.
Frequency - Each Shift
Action - FM
Report Ref. - Visual
2.2 - Asphalt placement and compaction (2)
Inspection Type - O
Test Method - Visual
Acceptance Criteria - Testing (incl. rolling pattern trials)
Frequency - Each Shift
Action - FM
Report Ref. - Visual
2.2 - Asphalt placement and compaction (3)
Inspection Type - O
Test Method - Visual
Acceptance Criteria - Each pavement layer placed CHAR(AMP) compacted.
Frequency - Each Shift
Action - FM
Report Ref. - Visual
2.2 - Asphalt placement and compaction (4)
Inspection Type - O
Test Method - Visual
Acceptance Criteria - Surfaces prepared for tack coating, sealing, surfacing.
Frequency - Each Shift
Action - FM
Report Ref. - Visual
2.2 - Asphalt placement and compaction (5)
Inspection Type - O
Test Method - Visual
Acceptance Criteria - Asphalt surfacing
Frequency - Each Shift
Action - FM
Report Ref. - Visual
2.3 - Pavement Surface Temperature
Inspection Type - W
Test Method - Measure
Acceptance Criteria - Supply additional roller if below 25 degrees celcius and /or high AC temperature when winds are > 25km/h
Frequency - Continuous
Action - FM
Report Ref. - Authority to Proceed
2.4 - Preparation of the Existing Surface
Inspection Type - W
Test Method - Visual
Acceptance Criteria - Surface is Dry and Clean Prior to Commencement of Paving
Frequency - Each Shift
Action - FM
Report Ref. - Authority to Proceed
2.5 - Excavation Depth
Inspection Type - R
Test Method - Record
Acceptance Criteria - Measurement of the profiled depth from existing surface level.
Frequency - Each Shift
Action - FM
Report Ref. - Dip Sheet
2.6 - Strain Alleviating Fabric
Inspection Type - W
Test Method - Witness Point
Acceptance Criteria - Applied to the penultimate joint below the final surfacing layer, where shown on drawings or as directed.
Frequency - As Required
Action - FM
Report Ref. - Visual
2.7 - Application of Tack Coat
Inspection Type - W
Test Method - Observed
Acceptance Criteria - Tack Coat Applied to Clean Surface Prior to Placing Asphalt [0.1 - 0.3L/m2]
Frequency - As Required
Action - FM
Report Ref. - Qty Agreement
2.8 - Joining of New Work to Existing
Inspection Type - W
Test Method - Visual
Acceptance Criteria - Provide smooth riding surface across junction.
Frequency - As Required
Action - FM
Report Ref. - Visual
2.9 - Asphalt Loading Temperature
Inspection Type - W
Test Method - Observed
Acceptance Criteria - Max 185°C [Bitumen Binders]
Frequency - As Required
Action - FM
Report Ref. - Delivery Docket
2.1 - Asphalt Temperature at Discharge to Hopper
Inspection Type - R
Test Method - Record
Acceptance Criteria - Max 175°C [Bitumen Binders]
Frequency - Continuous
Action - FM
Report Ref. - Laying Record
2.11 - Layer Thickness - probing (loose thickness)
Inspection Type - R
Test Method - Measure
Acceptance Criteria - 3 points across paving run
Frequency - 1/20m
Action - FM
Report Ref. - Laying Record
2.12 - Rolling Temperature
Inspection Type - O
Test Method - Measure
Acceptance Criteria - Asphalt Laying for Minimum Temperatures
Frequency - Continuous
Action - FM
Report Ref. - Laying Record
- Construction Joints (1)
Inspection Type -
Test Method -
Acceptance Criteria - Hot join CHAR(LESS) 15 min
Frequency - Continuous
Action - FM
Report Ref. - Visual
- Construction Joints (2)
Inspection Type -
Test Method -
Acceptance Criteria - Cold Joins to be luted with edge compaction wheel
Frequency - Continuous
Action - FM
Report Ref. - Visual
2.14 - Edge Ramps
Inspection Type - W
Test Method - Observed
Acceptance Criteria - Level differences >30mm ramps with asphalt wedge Longitudinal CHAR(LESS) 1on5. Transverse (slow) CHAR(LESS)1on10. Transverse (>75kmh) , 1on20.
Frequency - As Required
Action - FM
Report Ref. - Visual
2.15 - Apperance Quality
Inspection Type - W
Test Method - Observed
Acceptance Criteria - Uniform appearance with no evidence of segregation
Frequency - Each Shift
Action - FM
Report Ref. - Visual
3.1 - Compaction Testing: Relative [Core Density]
Inspection Type - R
Test Method - Record
Acceptance Criteria - Density testing carried out asap on customer request
Frequency - As Required
Action - PM
Report Ref. - Asphalt Summary Test Report
3.2 - Thickness Tests
Inspection Type - R
Test Method - Record
Acceptance Criteria - Measure all core samples cut for densities; and Record thickness when laying 1/20 (min. 3 points).
Frequency - As Required
Action - PM/FM
Report Ref. - Compaction Test report Dip sheet