## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 01 - Site Specific Induction & Toolbox Meeting | [5 empty] | 01 - Site Specific Induction & Toolbox Meeting
section | Details
checkpoint-no-status | Details
textbox | Site Details:
textbox | Activity:
textbox | SWMS:
date | Date:
textbox | Supervisor:
label | Weather Conditions:
bool | Clear Sky
bool | Dull Sky
bool | Bright Sun
bool | No Wind
bool | Very Windy
bool | No Rain
bool | Light Rain
bool | Heavy Rain
section | SITE SPECIFIC INDUCTION & TOOLBOX MEETING RECORD
checkpoint | Site plant/equipment
label | RISK CONTROL MEASURE - All plant pre-start checks completed.
checkpoint | External/Internal vehicular and pedestrian traffic
label | RISK CONTROL MEASURE - Work site to be clearly defined.
label | ○ Use appropriate traffic control as required - separate trafficable areas.
label | ○ Plant/equipment with operational flashing amber lights & audible reversing beepers.
label | ○ All workers wear hi visibility safety vest/clothing.
checkpoint | Operating powered plant or equipment & working around mobile plant
label | RISK CONTROL MEASURE - Only competently trained persons to operate plant or equipment.
label | ○ Operator wears seatbelts.
label | ○ Check area behind before reversing.
checkpoint | Reversing trucks with restricted rear vision
label | RISK CONTROL MEASURE - A ‘truck controller’ is appointed to guide reversing trucks on job site.
checkpoint | Entanglement
label | RISK CONTROL MEASURE - Appropriate machine guarding.
label | ○ Don’t enter paver hopper if operating
checkpoint | Mobile phones
label | RISK CONTROL MEASURE - Crew - Use Only in Lunch Break
label | ○ Foreman/Supervisor to step AWAY from work area when using phone.
checkpoint | Plant roll over and contact with rotating / slewing plant
label | RISK CONTROL MEASURE - Approach embankments/trenches from a 90 degree angle.
label | ○ Operator to complete visual assessment of ground conditions.
label | ○ Operator wears seatbelts when ROPS are fitted to plant.
checkpoint | Low overhead power lines
label | RISK CONTROL MEASURE - Permit applied for if required.
label | ○ A “spotter” is appointed to guide plant safely under low power lines.
label | ○ Tiger tails fitted as required.
checkpoint | Using power tools
label | RISK CONTROL MEASURE - Use battery powered tools first.
label | ○ Use correct tool for task
label | ○ Electric power tools tested & tagged.
checkpoint | Ultra violet exposure
label | RISK CONTROL MEASURE - Sun hats and sunscreen.
checkpoint | Bitumen Burns
label | RISK CONTROL MEASURE - Operator to wear all required PPE.
label | ○ Long pants, long sleeves, safety boots, safety gloves, face shield & balaclava as a minimum.
checkpoint | Emulsion product contact with eyes
label | RISK CONTROL MEASURE - Operator to wear safety glasses when operating hand lance.
checkpoint | Asphalt burns
label | RISK CONTROL MEASURE - Operator to wear all required PPE.
checkpoint | Underground assets
label | RISK CONTROL MEASURE - “Dial Before You Dig”
checkpoint | Persons falling or tripping on site. Ground condition. Open excavation. Excavation cave in
label | RISK CONTROL MEASURE - Maintain good housekeeping.
label | ○ Barricade off unsafe areas & all battered excavations.
label | ○ Clearly mark protruding objects using paint, cones or hazard tape.
label | ○ Benching/shoring if 1500mm+.
checkpoint | Inhalation of dust
label | RISK CONTROL MEASURE - Face protection worn as required.
label | ○ Suppress dust using water truck.
checkpoint | Chemical or fume exposure. Welding or concrete burns
label | RISK CONTROL MEASURE - Store and handle chemicals in accordance with relevant SDS.
label | ○ PPE provided should be worn.
checkpoint | Noise
label | RISK CONTROL MEASURE - Wear hearing protection where equipment is signed.
checkpoint | Manual handling
label | RISK CONTROL MEASURE - Request assistance where required.
label | ○ Correct manual handling techniques.
checkpoint | Heat stress
label | RISK CONTROL MEASURE - Sufficient cool water/regular breaks.
checkpoint | Bites & stings
label | RISK CONTROL MEASURE - Watch for spiders, snakes & wasps.
checkpoint | Falls from heights (above 2 metres)
label | RISK CONTROL MEASURE - Use approved ladder on level ground & tied off appropriately.
label | ○ Wear safety harness.
label | ○ Use scaffolding. Use scissor lift.
checkpoint | Worker Site Specific Induction & Toolbox Meeting Sign Off
holdpoint | Add Signatures:
checklist | 02 - SF-51 Quantity Agreement Sheet | [5 empty] | 02 - SF-51 Quantity Agreement Sheet Rev3
section | MISCELLANEOUS
checkpoint | Surface Preparation
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
checkpoint | Tack coat [0.2] litres/m2, residual bitumen
label | UNITS - Litres
textbox | QUANTITY SUPPLIED: |  |  | Litres
textbox | DEDUCTIONS RETURN MIX: |  |  | Litres
textbox | DEDUCTIONS RAMPS: |  |  | Litres
textbox | QUANTITY AGREED: |  |  | Litres
checkpoint | Paved Area
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
checkpoint | Handwork (Tonnes)
label | UNITS - Tonnes
textbox | QUANTITY SUPPLIED: |  |  | Tonnes
textbox | DEDUCTIONS RETURN MIX: |  |  | Tonnes
textbox | DEDUCTIONS RAMPS: |  |  | Tonnes
textbox | QUANTITY AGREED: |  |  | Tonnes
checkpoint | Handwork (Minutes)
label | UNITS - Minutes
textbox | QUANTITY SUPPLIED: |  |  | Minutes
textbox | DEDUCTIONS RETURN MIX: |  |  | Minutes
textbox | DEDUCTIONS RAMPS: |  |  | Minutes
textbox | QUANTITY AGREED: |  |  | Minutes
section | ASPHALT
checkpoint | Asphalt (1)
textbox | Asphalt used:
textbox | Depth:
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
checkpoint | Asphalt (2)
textbox | Asphalt used:
textbox | Depth:
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
checkpoint | Asphalt (3)
textbox | Asphalt used:
textbox | Depth:
label | UNITS - Tons
textbox | QUANTITY SUPPLIED: |  |  | Tons
textbox | DEDUCTIONS RETURN MIX: |  |  | Tons
textbox | DEDUCTIONS RAMPS: |  |  | Tons
textbox | QUANTITY AGREED: |  |  | Tons
section | PROFILING
checkpoint | Cold planing existing pavement 50mm below finished surface (Refer CTS05 Jan 15).
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
checkpoint | Cold planing an additional 200mm below surface plane (Refer CTS05 Jan 15). Chainages 170 - 430m: All Lanes.
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
checkpoint | Cold planing an additional 200mm below surface plane (Refer CTS05 Jan 15). Chainages 0 - 170m, chainages 0 - 130m (slip lane), chainage 430 - 1064m; All lanes.
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
section | CIVILS
checkpoint | Roadbase
textbox | Roadbase used:
textbox | Depth:
label | UNITS -
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
section | VARIATIONS
checkpoint | Additional Profiling(Rock/lean mix treatment areas)
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
checkpoint | Excavation of un suitable subgrade
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
checkpoint | Ballast Rock
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
checkpoint | Lean Mix
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
checkpoint | Corrector
label | UNITS - Tonnes
textbox | QUANTITY SUPPLIED: |  |  | Tonnes
textbox | DEDUCTIONS RETURN MIX: |  |  | Tonnes
textbox | DEDUCTIONS RAMPS: |  |  | Tonnes
textbox | QUANTITY AGREED: |  |  | Tonnes
checkpoint | Tensar Triax [Fabric]
label | UNITS - m2
textbox | QUANTITY SUPPLIED: |  |  | m2
textbox | DEDUCTIONS RETURN MIX: |  |  | m2
textbox | DEDUCTIONS RAMPS: |  |  | m2
textbox | QUANTITY AGREED: |  |  | m2
checkpoint | Traffic control
textbox | QUANTITY SUPPLIED:
textbox | DEDUCTIONS RETURN MIX:
textbox | DEDUCTIONS RAMPS:
textbox | QUANTITY AGREED:
section | CUSTOMER'S ACCEPTANCE
checkpoint | CUSTOMER'S ACCEPTANCE:
textbox | CUSTOMER REPRESENTATIVE:
holdpoint | CUSTOMER SIGNATURE:
checklist | 03 - SF 52 Site Operation Environmental Checklist | [5 empty] | 03 - SF 52 Site Operation Environmental Checklist Rev3
section | GENERAL ITEMS
checkpoint | Kerb and Channel Clean
button | PRE SURFACING | Yes,No,N/A
button | POST SURFACING | Yes,No,N/A
checkpoint | Gully Pits Clean
button | PRE SURFACING | Yes,No,N/A
button | POST SURFACING | Yes,No,N/A
checkpoint | Edge Profiling Complete [If Required]
button | PRE SURFACING | Yes,No,N/A
button | POST SURFACING | Yes,No,N/A
checkpoint | Job Site Swept and Clean
button | PRE SURFACING | Yes,No,N/A
button | POST SURFACING | Yes,No,N/A
checkpoint | After Care Signs in Place
button | PRE SURFACING | Yes,No,N/A
button | POST SURFACING | Yes,No,N/A
checkpoint | Temporary Line Marking Complete - Stick 'n' Stomp, Stop/Give Way Bars, Ped-Crossing
button | PRE SURFACING | Yes,No,N/A
button | POST SURFACING | Yes,No,N/A
checkpoint | Tack on Gutters / Driveways / Footpaths
button | PRE SURFACING | Yes,No,N/A
button | POST SURFACING | Yes,No,N/A
checkpoint | Principal Assets Damaged
button | PRE SURFACING | Yes,No,N/A
button | POST SURFACING | Yes,No,N/A
checkpoint | Resident Complaints
button | PRE SURFACING | Yes,No,N/A
button | POST SURFACING | Yes,No,N/A
checkpoint | Mobile Plant Parking Area Designated
button | PRE SURFACING | Yes,No,N/A
button | POST SURFACING | Yes,No,N/A
checkpoint | Mobile Plant Clean
button | PRE SURFACING | Yes,No,N/A
button | POST SURFACING | Yes,No,N/A
section | EROSION & SEDIMENTATION
checkpoint | Was Milled Material Removed
checkpoint-no-status | Where was it stockpiled?
section | AIR QUALITY
checkpoint | Was Dust Monitored?
checkpoint | Was Excess Dust Generated?
checkpoint-no-status | What was done to supress excess dust?
section | NOISE
checkpoint | Was Any Excess Noise Generated?
section | LIGHTING
checkpoint | Was lighting positioned not to shine at houses or cars?
section | VIBRATION
checkpoint | Was Any Unnecessary Vibration Used?
section | WATER QUALITY
checkpoint | Were there any Fuel, Oil, Bitumen, Emulsions spills in close proximity to water ways or drains?
checkpoint | Was The Spill Contained?
checkpoint-no-status | How Was The Spill Contained?
checkpoint-no-status | What was Done with the Contaminated Material?
section | GULLY PITS / STORM WATER
checkpoint | Are Gully's and Pits Protected?
checkpoint | Is the Storm water outlet protected?
checkpoint | Has any Contaminant entered the storm water?
section | DANGEROUS GOODS & FUELS
checkpoint | Was Equipment Fuelled On A Seal Platform?
checkpoint | Was Any Fuel Or Cutter Spilled?
checkpoint | Were the spills clean up?
checkpoint | What was done with the contaiminated material?
section | END OF SHIFT SITE CLEAN UP
checkpoint-no-status | Where was Waste Asphalt Disposed of?
checkpoint-no-status | What is the state of the site?
button | State: | CLEAN,SAFE,TIDY
section | FLORA & FAUNA
checkpoint | Was Any Flora & Fauna Disturbed?
section | WEATHER
checkpoint | Was Weather an Issue?
checklist | 04 - SF 39 Authority to Proceed | [5 empty] | 04 - SF 39 Authority to Proceed Rev3
section | MILESTONE DESCRIPTION [Pre-Construction]
checkpoint | Description:
textbox | Specification / YR:
textbox | Layer:
textbox | Mix Design Reference:
textbox | Thickness:
date | Mix Certificate Dated:
textbox | Asphalt Temperature of Delivery: Range -
textbox | Asphalt Temperature of Delivery: Comment -
section | HOLD POINT DESCRIPTION [ON SITE]
checkpoint | Crack Filling
label | SPECIFICATION REFERENCE - CTS30 CI 1.2.2
label | COMMENTS - As Directed By Client
textbox | RELEASED BY:
checkpoint | Strain Alleviating Fabric Strips
label | SPECIFICATION REFERENCE - CTS30 CI 1.2.2
label | COMMENTS - As Directed By Client
textbox | RELEASED BY:
checkpoint | Area for Corrector Course
label | SPECIFICATION REFERENCE - CTS30 CI 1.2.2
label | COMMENTS - As Directed By Client
textbox | RELEASED BY:
checkpoint | Tolerance on Corrector Course
label | SPECIFICATION REFERENCE - CTS30 CI 1.2.2
label | COMMENTS - As Directed By Client
textbox | RELEASED BY:
section | Details
checkpoint | What is the Underlying Pavement?
button | RELEASE REQUIRED | Zafa,Asset Owners Pavement
checkpoint | Is the Condition of the Underlying Pavement Acceptable?
button | RELEASE REQUIRED | Yes,No
checkpoint | Is Lamination of Existing Pavement Occurring?
button | RELEASE REQUIRED | Yes,No
checkpoint | Is there any Movement in the Underlying Pavement?
button | RELEASE REQUIRED | Yes,No
checkpoint | Has a Proof Roll been Carried Out?
button | RELEASE REQUIRED | Yes,No
checkpoint | Will Zafa Compaction Standard be Affected?
button | RELEASE REQUIRED | Yes,No
checkpoint | Will Zafa Average Spread Rate be Affected?
button | RELEASE REQUIRED | Yes,No
checkpoint | Will Zafa Surface Evenness / Geometrics be Affected?
button | RELEASE REQUIRED | Yes,No
checklist | 05 - SF 54 Zafa ITP | itp |  |  |  |  | 05 - SF 54 Zafa ITP
section | 1.0 - PRIOR TO WORKS COMMENCING
checkpoint | 1.0 - Set Out Limits to be Inspected by the administrator prior to excavation
label | Inspection Type - H
label | Test Method - Direction
label | Acceptance Criteria - Site Marked Up Prior to Works Commencing
label | Frequency - As Required
label | Action - PM
label | Report Ref. - Authority to ProceedVisual
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 1.1 - Extent of Crack Filling
label | Inspection Type - H
label | Test Method - Direction
label | Acceptance Criteria - All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form
label | Frequency - As Required
label | Action - PM
label | Report Ref. - Authority to Proceed
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 1.2 - Extent of Strain Alleviating Fabric Strips
label | Inspection Type - H
label | Test Method - Direction
label | Acceptance Criteria - All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form
label | Frequency - As Required
label | Action - PM
label | Report Ref. - Authority to Proceed
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 1.3 - Areas for Corrector Course
label | Inspection Type - H
label | Test Method - Direction
label | Acceptance Criteria - All Underlying Lots conform and necessary/extra works required prior to paving agreed to and signed off by the client on the Hold Point Release Form
label | Frequency - AS Required
label | Action - PM
label | Report Ref. - Authority to Proceed
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | 2.0 - ASPHALT WORKS
checkpoint | 2.1 - Weather Conditions
label | Inspection Type - O
label | Test Method - Visual
label | Acceptance Criteria - Surface dry and free of surface water. Paving not to take place during rain
label | Frequency - Continuous
label | Action - FM
label | Report Ref. - Authority to Proceed
checkpoint | 2.2 - Asphalt placement and compaction (1)
label | Inspection Type - O
label | Test Method - Visual
label | Acceptance Criteria - Sufficient notice given to enable inspection of:
label | ○ Materials or areas ready for tests.
label | Frequency - Each Shift
label | Action - FM
label | Report Ref. - Visual
checkpoint | 2.2 - Asphalt placement and compaction (2)
label | Inspection Type - O
label | Test Method - Visual
label | Acceptance Criteria - Testing (incl. rolling pattern trials)
label | Frequency - Each Shift
label | Action - FM
label | Report Ref. - Visual
checkpoint | 2.2 - Asphalt placement and compaction (3)
label | Inspection Type - O
label | Test Method - Visual
label | Acceptance Criteria - Each pavement layer placed & compacted.
label | Frequency - Each Shift
label | Action - FM
label | Report Ref. - Visual
checkpoint | 2.2 - Asphalt placement and compaction (4)
label | Inspection Type - O
label | Test Method - Visual
label | Acceptance Criteria - Surfaces prepared for tack coating, sealing, surfacing.
label | Frequency - Each Shift
label | Action - FM
label | Report Ref. - Visual
checkpoint | 2.2 - Asphalt placement and compaction (5)
label | Inspection Type - O
label | Test Method - Visual
label | Acceptance Criteria - Asphalt surfacing
label | Frequency - Each Shift
label | Action - FM
label | Report Ref. - Visual
checkpoint | 2.3 - Pavement Surface Temperature
label | Inspection Type - W
label | Test Method - Measure
label | Acceptance Criteria - Supply additional roller if below 25 degrees celcius and /or high AC temperature when winds are > 25km/h
label | Frequency - Continuous
label | Action - FM
label | Report Ref. - Authority to Proceed
checkpoint | 2.4 - Preparation of the Existing Surface
label | Inspection Type - W
label | Test Method - Visual
label | Acceptance Criteria - Surface is Dry and Clean Prior to Commencement of Paving
label | Frequency - Each Shift
label | Action - FM
label | Report Ref. - Authority to Proceed
checkpoint | 2.5 - Excavation Depth
label | Inspection Type - R
label | Test Method - Record
label | Acceptance Criteria - Measurement of the profiled depth from existing surface level.
label | Frequency - Each Shift
label | Action - FM
label | Report Ref. - Dip Sheet
checkpoint | 2.6 - Strain Alleviating Fabric
label | Inspection Type - W
label | Test Method - Witness Point
label | Acceptance Criteria - Applied to the penultimate joint below the final surfacing layer, where shown on drawings or as directed.
label | Frequency - As Required
label | Action - FM
label | Report Ref. - Visual
checkpoint | 2.7 - Application of Tack Coat
label | Inspection Type - W
label | Test Method - Observed
label | Acceptance Criteria - Tack Coat Applied to Clean Surface Prior to Placing Asphalt [0.1 - 0.3L/m2]
label | Frequency - As Required
label | Action - FM
label | Report Ref. - Qty Agreement
checkpoint | 2.8 - Joining of New Work to Existing
label | Inspection Type - W
label | Test Method - Visual
label | Acceptance Criteria - Provide smooth riding surface across junction.
label | Frequency - As Required
label | Action - FM
label | Report Ref. - Visual
checkpoint | 2.9 - Asphalt Loading Temperature
label | Inspection Type - W
label | Test Method - Observed
label | Acceptance Criteria - Max 185°C [Bitumen Binders]
label | Frequency - As Required
label | Action - FM
label | Report Ref. - Delivery Docket
checkpoint | 2.10 - Asphalt Temperature at Discharge to Hopper
label | Inspection Type - R
label | Test Method - Record
label | Acceptance Criteria - Max 175°C [Bitumen Binders]
label | Frequency - Continuous
label | Action - FM
label | Report Ref. - Laying Record
checkpoint | 2.11 - Layer Thickness - probing (loose thickness)
label | Inspection Type - R
label | Test Method - Measure
label | Acceptance Criteria - 3 points across paving run
label | Frequency - 1/20m
label | Action - FM
label | Report Ref. - Laying Record
checkpoint | 2.12 - Rolling Temperature
label | Inspection Type - O
label | Test Method - Measure
label | Acceptance Criteria - Asphalt Laying for Minimum Temperatures
label | Frequency - Continuous
label | Action - FM
label | Report Ref. - Laying Record
checkpoint | Construction Joints (1)
label | Acceptance Criteria - Hot join < 15 min
label | Frequency - Continuous
label | Action - FM
label | Report Ref. - Visual
checkpoint | Construction Joints (2)
label | Acceptance Criteria - Cold Joins to be luted with edge compaction wheel
label | Frequency - Continuous
label | Action - FM
label | Report Ref. - Visual
checkpoint | 2.14 - Edge Ramps
label | Inspection Type - W
label | Test Method - Observed
label | Acceptance Criteria - Level differences >30mm ramps with asphalt wedge Longitudinal < 1on5. Transverse (slow) <1on10. Transverse (>75kmh) , 1on20.
label | Frequency - As Required
label | Action - FM
label | Report Ref. - Visual
checkpoint | 2.15 - Apperance Quality
label | Inspection Type - W
label | Test Method - Observed
label | Acceptance Criteria - Uniform appearance with no evidence of segregation
label | Frequency - Each Shift
label | Action - FM
label | Report Ref. - Visual
section | 3.0 - Compaction Testing
checkpoint | 3.1 - Compaction Testing: Relative [Core Density]
label | Inspection Type - R
label | Test Method - Record
label | Acceptance Criteria - Density testing carried out asap on customer request
label | Frequency - As Required
label | Action - PM
label | Report Ref. - Asphalt Summary Test Report
checkpoint | 3.2 - Thickness Tests
label | Inspection Type - R
label | Test Method - Record
label | Acceptance Criteria - Measure all core samples cut for densities; and Record thickness when laying 1/20 (min. 3 points).
label | Frequency - As Required
label | Action - PM/FM
label | Report Ref. - Compaction Test report, Dip sheet
checkpoint | I certify that the works have been contructed in accordance with Australian standards and the Inspection and Test Plan. All requirements have been met.
textbox | Zafa Contracting Pty Ltd Representative:
textbox | Client Representative:
holdpoint | Add Signature:
checklist | 06 - SF-50 Laying Record | [5 empty] | 06 - SF-50 Laying Record Rev3
section | Details
checkpoint | Details
textbox | DOCKET NUMBER:
textbox | TRUCK REGO:
textbox | TIME IN:
textbox | TEMP [Truck Discharge]:
textbox | TEMP [Initial Rolling]:
textbox | TONNES:
textbox | PROGRESSIVE TOTAL:
textbox | CHAINAGE - START:
textbox | CHAINAGE - FINISH:
textbox | RUN NO:
textbox | LAYER NO:
textbox | RUN WIDTH:
textbox | RUN LOCATION/DIRECTION CONTROL LINE:
checklist | 07 - Site Diagram | [5 empty] | 07 - Site Diagram
section | Details
checkpoint | Upload Site Diagram