## Sheet1
- | VERIFICATION ACTIVITY: | METHODS OR REFERENCE: | FREQUENCY: | ACCEPTANCE CRITERIA: | HOLD POINT: | RECORDS: | - | 1 | Permits | H | Obtain Permits | As required | Document Review | Authorisation to work, dig permit and service provider permits | This ITP signed | 1 - Permits | ACTION (Hold, Monitor, Witness): H | DETAIL: Obtain Permits | FREQUENCY: As required | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits | RECORDS: This ITP signed | 1 - Permits | Site Set out | Surveyor | Surveyor | Every site | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer | Site Set out | VERIFICATION ACTIVITY: Surveyor | METHODS OR REFERENCE: Surveyor | FREQUENCY: Every site | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. | HOLD POINT: Mandatory HOLD POINT - | RECORDS: Onsite records/photos | ONSITE RESPONSIBILITY: Site Engineer | Site Set out | 1 | Kerb | QA FORM | TDM Technical Standards - IS0001 CHAR(AMP) IS0002 | Every site | Kerb to be laid using precast hand-laid | In process Inspection | FH Concrete QA sheet Photos | Site Engineer | 1 - Kerb | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - IS0001 CHAR(AMP) IS0002 | FREQUENCY: Every site | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid | HOLD POINT: In process Inspection | RECORDS: FH Concrete QA sheet Photos | ONSITE RESPONSIBILITY: Site Engineer | 1 - Kerb
[7 empty] | VERIFICATION ACTIVITY: | 2 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | 2 - Design | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure that Design is approved and Drawings are of the latest revision | FREQUENCY: Prior to commencement | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review | CONFORMANCE CRITERIA: | RECORDS: Check Drawing Register | ACTION (Hold, Monitor, Witness): H | Kerb CHAR(AMP) Channel | QA FORM | TDM Technical Standards - KC0001 | Every 10m for Scalar | Subgrade CBR > 5 | In process Inspection | Scalar Sheet | Site Engineer | Kerb CHAR(AMP) Channel | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - KC0001 | FREQUENCY: Every 10m for Scalar | ACCEPTANCE CRITERIA: Subgrade CBR > 5 | HOLD POINT: In process Inspection | RECORDS: Scalar Sheet | ONSITE RESPONSIBILITY: Site Engineer | VERIFICATION ACTIVITY: Surveyor | 2 | Survey Setout | Survey | Setout Kerb Alignment required to construct to design | Prior to commencement. | Survey | In process Inspection | Survey Receipt. | Site Engineer | 2 - Survey Setout | VERIFICATION ACTIVITY: Survey | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design | FREQUENCY: Prior to commencement. | ACCEPTANCE CRITERIA: Survey | HOLD POINT: In process Inspection | RECORDS: Survey Receipt. | ONSITE RESPONSIBILITY: Site Engineer | VERIFICATION ACTIVITY: QA FORM
[7 empty] | METHODS OR REFERENCE: | 3 | Survey Setout (1) | H | Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor. | Prior to commencement | Survey | Consistency with Drawings and Specifiactions | Survey Records | 3 - Survey Setout (1) | ACTION (Hold, Monitor, Witness): H | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor. | FREQUENCY: Prior to commencement | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | RECORDS: Survey Records | DETAIL: Obtain Permits | Kerb CHAR(AMP) Channel | QA FORM | TDM Technical Standards - KC0001 | Every 10m for Clegg | Kerb CHAR(AMP) Channel to be laid using basalt kerb hand-laid on compacted GAP40. Thickness - 100mm on Footpath / 300mm on roads CVI > 25 | In process Inspection | Clegg Sheet Photos | Site Engineer | Kerb CHAR(AMP) Channel | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - KC0001 | FREQUENCY: Every 10m for Clegg | ACCEPTANCE CRITERIA: Kerb CHAR(AMP) Channel to be laid using basalt kerb hand-laid on compacted GAP40. Thickness - 100mm on Footpath / 300mm on roads CVI > 25 | HOLD POINT: In process Inspection | RECORDS: Clegg Sheet Photos | ONSITE RESPONSIBILITY: Site Engineer | METHODS OR REFERENCE: Surveyor | 3A | In-Situ Concrete Island | QA FORM | TDM Technical Standards - IS0001 | Each Site | Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm CVI > 12 | In process Inspection | Photos | Site Engineer | 3A - In-Situ Concrete Island | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - IS0001 | FREQUENCY: Each Site | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm CVI > 12 | HOLD POINT: In process Inspection | RECORDS: Photos | ONSITE RESPONSIBILITY: Site Engineer | METHODS OR REFERENCE: TDM Technical Standards - IS0001 CHAR(AMP) IS0002
[7 empty] | FREQUENCY: | 3 | Survey Setout (2) | H | Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation. | Prior to commencement | Visual Inspection | Consistency with Drawings and Specifiactions | Photos / Engineers approval documentation | 3 - Survey Setout (2) | ACTION (Hold, Monitor, Witness): H | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation. | FREQUENCY: Prior to commencement | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | RECORDS: Photos / Engineers approval documentation | FREQUENCY: As required | Kerb Setout | QA FORM | TDM Technical Standards - KC0001 | Every site | Site Setout as per construction drawings and heights and falls verified | Mandatory HOLD POINT - | KCHAR(AMP)C Pre-pour Checklist | Site Engineer / MSQA | Kerb Setout | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - KC0001 | FREQUENCY: Every site | ACCEPTANCE CRITERIA: Site Setout as per construction drawings and heights and falls verified | HOLD POINT: Mandatory HOLD POINT - | RECORDS: KCHAR(AMP)C Pre-pour Checklist | ONSITE RESPONSIBILITY: Site Engineer / MSQA | FREQUENCY: Every site | 4 | Concrete Infill | QA FORM | TDM Technical Standards - IS0001 CHAR(AMP) IS0002 | Each Site | 150/180mm depth of 20MPa Concrete Surface finish to confirm with Engineer's Rep Cross Fall of 2% or max rise in centre of 180mm | In process Inspection | FH Concrete QA sheet. Concrete Delivery Dockets | Site Engineer | 4 - Concrete Infill | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - IS0001 CHAR(AMP) IS0002 | FREQUENCY: Each Site | ACCEPTANCE CRITERIA: 150/180mm depth of 20MPa Concrete Surface finish to confirm with Engineer's Rep Cross Fall of 2% or max rise in centre of 180mm | HOLD POINT: In process Inspection | RECORDS: FH Concrete QA sheet. Concrete Delivery Dockets | ONSITE RESPONSIBILITY: Site Engineer | FREQUENCY: Every site
[7 empty] | ACCEPTANCE CRITERIA: | 4 | Locate existing services by hand digging/ hydrovac | W | Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation | Prior to Installation | Potholing | All conflicts have been located and survey as built recorded | Digging/Excavating Control Checklist | 4 - Locate existing services by hand digging/ hydrovac | ACTION (Hold, Monitor, Witness): W | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation | FREQUENCY: Prior to Installation | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded | RECORDS: Digging/Excavating Control Checklist | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review | Channel Material | QA FORM | TDM Technical Standards - KC0001 | Every site | Concrete Strength 20MPa @28 Days | In process Inspection | Concrete Docket | Site Engineer | Channel Material | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - KC0001 | FREQUENCY: Every site | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days | HOLD POINT: In process Inspection | RECORDS: Concrete Docket | ONSITE RESPONSIBILITY: Site Engineer | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. | 7 | As built information | Drawings | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | As built drawings | In Process Inspection | As-built records | Supervisor and Engineer | 7 - As built information | VERIFICATION ACTIVITY: Drawings | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | FREQUENCY: Every Site | ACCEPTANCE CRITERIA: As built drawings | HOLD POINT: In Process Inspection | RECORDS: As-built records | ONSITE RESPONSIBILITY: Supervisor and Engineer | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
[7 empty] | HOLD POINT: | 5 | Material Compliance (1) | H | Ensure duct pipes and poles are as per drawings and specification | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | 5 - Material Compliance (1) | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure duct pipes and poles are as per drawings and specification | FREQUENCY: Upon delivery to site | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials | CONFORMANCE CRITERIA: | RECORDS: Delivery Docket | CONFORMANCE CRITERIA: Authorisation to work, dig permit and service provider permits | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Every site | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level | In process Inspection | Photos | Site Engineer | Channel Level | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - KC0001 | FREQUENCY: Every site | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level | HOLD POINT: In process Inspection | RECORDS: Photos | ONSITE RESPONSIBILITY: Site Engineer | HOLD POINT: Mandatory HOLD POINT - | 7 | RAMM DATA | RAMM DATA SHEET | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | RAMM SHEET | In Process Inspection | As-built records | Supervisor and Engineer | 7 - RAMM DATA | VERIFICATION ACTIVITY: RAMM DATA SHEET | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | FREQUENCY: Every Site | ACCEPTANCE CRITERIA: RAMM SHEET | HOLD POINT: In Process Inspection | RECORDS: As-built records | ONSITE RESPONSIBILITY: Supervisor and Engineer | HOLD POINT: In process Inspection
[7 empty] | RECORDS: | 5 | Material Compliance (2) | H | Ensure all concrete used is 20MPa mix | Upon delivery to site | Ensure delivery docket matches materials |  | Delivery Docket | 5 - Material Compliance (2) | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure all concrete used is 20MPa mix | FREQUENCY: Upon delivery to site | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials | CONFORMANCE CRITERIA: | RECORDS: Delivery Docket | RECORDS: This ITP signed | Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m intervals | Subgrade CBR > 3 | In process Inspection | Scalar Sheet | Site Engineer | Footpaths | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - FP0001 | FREQUENCY: 10m intervals | ACCEPTANCE CRITERIA: Subgrade CBR > 3 | HOLD POINT: In process Inspection | RECORDS: Scalar Sheet | ONSITE RESPONSIBILITY: Site Engineer | RECORDS: Onsite records/photos | [17 empty] | RECORDS: FH Concrete QA sheet Photos
[8 empty] | 6 | Trenching | H | Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 1000mm cover to duct when under berm/footpath (1500mm cover when under road crossing - non motorway/expressway) | 10m Intervals | Visual Inspection | Consistency with Drawings and Specifiactions | Photos | 6 - Trenching | ACTION (Hold, Monitor, Witness): H | DETAIL: Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 1000mm cover to duct when under berm/footpath (1500mm cover when under road crossing - non motorway/expressway) | FREQUENCY: 10m Intervals | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | RECORDS: Photos | 2 - Design | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m Intervals | Basecourse - 100mm min. thickness Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX) Concrete Strength 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing) Standard Footpath - 100mm thick Heavy Duty - 150mm thick | Inprocess Inspection | Clegg Sheet, photos. Concrete Plant Docket | Site Engineer | Concrete Footpaths | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - FP0001 | FREQUENCY: 10m Intervals | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX) Concrete Strength 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing) Standard Footpath - 100mm thick Heavy Duty - 150mm thick | HOLD POINT: Inprocess Inspection | RECORDS: Clegg Sheet, photos. Concrete Plant Docket | ONSITE RESPONSIBILITY: Site Engineer | ONSITE RESPONSIBILITY: Site Engineer | [17 empty] | ONSITE RESPONSIBILITY: Site Engineer
[8 empty] | 6.1 | Trenching | H | Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs | 10m Intervals | Measure | Ensure trench alignment and levels match the design drawings | Dipsheet CHAR(AMP) Photos | 6.1 - Trenching | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs | FREQUENCY: 10m Intervals | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings | RECORDS: Dipsheet CHAR(AMP) Photos | ACTION (Hold, Monitor, Witness): H | AC Footpaths | QA FORM | TDM Technical Standards - FP0003 | 10m Intervals | Subgrade -(CBR > 3) Basecourse - 150mm min. thickness GAP40 Clegg CIV > 27 DG10/Fine asphalt mix used | Inprocess Inspection | FH concrete QA sheet. Concrete delivery Dockets kept as record | Site Engineer | AC Footpaths | VERIFICATION ACTIVITY: QA FORM | METHODS OR REFERENCE: TDM Technical Standards - FP0003 | FREQUENCY: 10m Intervals | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3) Basecourse - 150mm min. thickness GAP40 Clegg CIV > 27 DG10/Fine asphalt mix used | HOLD POINT: Inprocess Inspection | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record | ONSITE RESPONSIBILITY: Site Engineer | Kerb CHAR(AMP) Channel | [17 empty] | 2 - Survey Setout
[8 empty] | 7 | Duct Installation | W | Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct. | Prior to Installation | Visual inspection | Consistency with Drawings and Specifiactions | Photos | 7 - Duct Installation | ACTION (Hold, Monitor, Witness): W | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct. | FREQUENCY: Prior to Installation | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | RECORDS: Photos | DETAIL: Ensure that Design is approved and Drawings are of the latest revision | Pram Crossing | Visual | TDM Technical Standards - FP006 | Each Crossing | Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. Tactiles Directional CHAR(AMP) warning - 60mm; 600mm flares;width as per design; Slope no greater than 1:12 where practicably possible Clegg CIV > 12 | Mandatory HOLD POINT - | Photos | Site Engineer | Pram Crossing | VERIFICATION ACTIVITY: Visual | METHODS OR REFERENCE: TDM Technical Standards - FP006 | FREQUENCY: Each Crossing | ACCEPTANCE CRITERIA: Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. Tactiles Directional CHAR(AMP) warning - 60mm; 600mm flares;width as per design; Slope no greater than 1:12 where practicably possible Clegg CIV > 12 | HOLD POINT: Mandatory HOLD POINT - | RECORDS: Photos | ONSITE RESPONSIBILITY: Site Engineer | VERIFICATION ACTIVITY: QA FORM | [17 empty] | VERIFICATION ACTIVITY: Survey
[8 empty] | 7.1 | Duct Installation | H | Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | 7.1 - Duct Installation | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables | FREQUENCY: 10m Intervals | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | RECORDS: Photos | FREQUENCY: Prior to commencement | Service Covers and Street Furniture | Visual | AT Contract Specification 14000 | Everysite | Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works. | Inprocess Inspection | Nil | Site Engineer | Service Covers and Street Furniture | VERIFICATION ACTIVITY: Visual | METHODS OR REFERENCE: AT Contract Specification 14000 | FREQUENCY: Everysite | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works. | HOLD POINT: Inprocess Inspection | RECORDS: Nil | ONSITE RESPONSIBILITY: Site Engineer | METHODS OR REFERENCE: TDM Technical Standards - KC0001 | [17 empty] | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
[8 empty] | 7.2 | Duct Installation | H | Asbuilt Survey | 20m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Survey Records | 7.2 - Duct Installation | ACTION (Hold, Monitor, Witness): H | DETAIL: Asbuilt Survey | FREQUENCY: 20m Intervals | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | RECORDS: Survey Records | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review | As built information | Drawings | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | As built drawings | In Process Inspection | Asbuilt records | Site Engineer CHAR(AMP) PM | As built information | VERIFICATION ACTIVITY: Drawings | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | FREQUENCY: Every Site | ACCEPTANCE CRITERIA: As built drawings | HOLD POINT: In Process Inspection | RECORDS: Asbuilt records | ONSITE RESPONSIBILITY: Site Engineer CHAR(AMP) PM | FREQUENCY: Every 10m for Scalar | [17 empty] | FREQUENCY: Prior to commencement.
[8 empty] | 8 | Bedding | H | Lay min. 100mm pit sand or finer for bedding and haunching | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | 8 - Bedding | ACTION (Hold, Monitor, Witness): H | DETAIL: Lay min. 100mm pit sand or finer for bedding and haunching | FREQUENCY: 10m Intervals | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | RECORDS: Photos | CONFORMANCE CRITERIA: | RAMM DATA | RAMM DATA SHEET | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | RAMM SHEET | In Process Inspection | RAMM Sheet | Site Engineer CHAR(AMP) PM | RAMM DATA | VERIFICATION ACTIVITY: RAMM DATA SHEET | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | FREQUENCY: Every Site | ACCEPTANCE CRITERIA: RAMM SHEET | HOLD POINT: In Process Inspection | RECORDS: RAMM Sheet | ONSITE RESPONSIBILITY: Site Engineer CHAR(AMP) PM | ACCEPTANCE CRITERIA: Subgrade CBR > 5 | [17 empty] | ACCEPTANCE CRITERIA: Survey
[8 empty] | 9 | Warning Tape | H | Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines. | 10m Intervals | Visual inspection | Consistency with Drawings and Specifiactions | Photos | 9 - Warning Tape | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines. | FREQUENCY: 10m Intervals | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | RECORDS: Photos | RECORDS: Check Drawing Register | [16 empty] | HOLD POINT: In process Inspection | [17 empty] | HOLD POINT: In process Inspection
[8 empty] | 10 | Traffic signal pole erection | H | Ensure Design engineer as inspected pole locations prior to proceeding | Per pole | Visual Inspection | Sign off by design engineer | Engineer sign off | 10 - Traffic signal pole erection | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure Design engineer as inspected pole locations prior to proceeding | FREQUENCY: Per pole | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection | CONFORMANCE CRITERIA: Sign off by design engineer | RECORDS: Engineer sign off | 3 - Survey Setout (1) | [16 empty] | RECORDS: Scalar Sheet | [17 empty] | RECORDS: Survey Receipt.
[8 empty] | 10.1 | Traffic signal pole erection | H | Ensure Pot hole is as per design with required depths and widths | Per pole | Measure | Consistency with Drawings and Specifiactions | Dipsheet CHAR(AMP) Photos | 10.1 - Traffic signal pole erection | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure Pot hole is as per design with required depths and widths | FREQUENCY: Per pole | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | RECORDS: Dipsheet CHAR(AMP) Photos | ACTION (Hold, Monitor, Witness): H | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer | [17 empty] | ONSITE RESPONSIBILITY: Site Engineer
[8 empty] | 10.2 | Traffic signal pole erection | H | Ensure Poles are plumb and within design tolerances | Per pole | Visual Inspection | Consistency with Drawings and Specifiactions | Photos | 10.2 - Traffic signal pole erection | ACTION (Hold, Monitor, Witness): H | DETAIL: Ensure Poles are plumb and within design tolerances | FREQUENCY: Per pole | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | RECORDS: Photos | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor. | [16 empty] | Kerb CHAR(AMP) Channel | [17 empty] | 3A - In-Situ Concrete Island
[8 empty] | 11 | As-builts CHAR(AMP) CCHAR(AMP)I Diagram | H | As-built as per ATOC requirements | At the completion of the Lot of work | Drawings | As-built as per ATOC requirements | Asbuilt Drawing | 11 - As-builts CHAR(AMP) CCHAR(AMP)I Diagram | ACTION (Hold, Monitor, Witness): H | DETAIL: As-built as per ATOC requirements | FREQUENCY: At the completion of the Lot of work | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings | CONFORMANCE CRITERIA: As-built as per ATOC requirements | RECORDS: Asbuilt Drawing | FREQUENCY: Prior to commencement | [16 empty] | VERIFICATION ACTIVITY: QA FORM | [17 empty] | VERIFICATION ACTIVITY: QA FORM
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey | [16 empty] | METHODS OR REFERENCE: TDM Technical Standards - KC0001 | [17 empty] | METHODS OR REFERENCE: TDM Technical Standards - IS0001
[23 empty] | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | [16 empty] | FREQUENCY: Every 10m for Clegg | [17 empty] | FREQUENCY: Each Site
[23 empty] | RECORDS: Survey Records | [16 empty] | ACCEPTANCE CRITERIA: Kerb CHAR(AMP) Channel to be laid using basalt kerb hand-laid on compacted GAP40. Thickness - 100mm on Footpath / 300mm on roads CVI > 25 | [17 empty] | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm CVI > 12
[23 empty] | 3 - Survey Setout (2) | [16 empty] | HOLD POINT: In process Inspection | [17 empty] | HOLD POINT: In process Inspection
[23 empty] | ACTION (Hold, Monitor, Witness): H | [16 empty] | RECORDS: Clegg Sheet Photos | [17 empty] | RECORDS: Photos
[23 empty] | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation. | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer | [17 empty] | ONSITE RESPONSIBILITY: Site Engineer
[23 empty] | FREQUENCY: Prior to commencement | [16 empty] | Kerb Setout | [17 empty] | 4 - Concrete Infill
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection | [16 empty] | VERIFICATION ACTIVITY: QA FORM | [17 empty] | VERIFICATION ACTIVITY: QA FORM
[23 empty] | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | [16 empty] | METHODS OR REFERENCE: TDM Technical Standards - KC0001 | [17 empty] | METHODS OR REFERENCE: TDM Technical Standards - IS0001 CHAR(AMP) IS0002
[23 empty] | RECORDS: Photos / Engineers approval documentation | [16 empty] | FREQUENCY: Every site | [17 empty] | FREQUENCY: Each Site
[23 empty] | 4 - Locate existing services by hand digging/ hydrovac | [16 empty] | ACCEPTANCE CRITERIA: Site Setout as per construction drawings and heights and falls verified | [17 empty] | ACCEPTANCE CRITERIA: 150/180mm depth of 20MPa Concrete Surface finish to confirm with Engineer's Rep Cross Fall of 2% or max rise in centre of 180mm
[23 empty] | ACTION (Hold, Monitor, Witness): W | [16 empty] | HOLD POINT: Mandatory HOLD POINT - | [17 empty] | HOLD POINT: In process Inspection
[23 empty] | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation | [16 empty] | RECORDS: KCHAR(AMP)C Pre-pour Checklist | [17 empty] | RECORDS: FH Concrete QA sheet. Concrete Delivery Dockets
[23 empty] | FREQUENCY: Prior to Installation | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer / MSQA | [17 empty] | ONSITE RESPONSIBILITY: Site Engineer
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing | [16 empty] | Channel Material | [17 empty] | 7 - As built information
[23 empty] | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded | [16 empty] | VERIFICATION ACTIVITY: QA FORM | [17 empty] | VERIFICATION ACTIVITY: Drawings
[23 empty] | RECORDS: Digging/Excavating Control Checklist | [16 empty] | METHODS OR REFERENCE: TDM Technical Standards - KC0001 | [17 empty] | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
[23 empty] | 5 - Material Compliance (1) | [16 empty] | FREQUENCY: Every site | [17 empty] | FREQUENCY: Every Site
[23 empty] | ACTION (Hold, Monitor, Witness): H | [16 empty] | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days | [17 empty] | ACCEPTANCE CRITERIA: As built drawings
[23 empty] | DETAIL: Ensure duct pipes and poles are as per drawings and specification | [16 empty] | HOLD POINT: In process Inspection | [17 empty] | HOLD POINT: In Process Inspection
[23 empty] | FREQUENCY: Upon delivery to site | [16 empty] | RECORDS: Concrete Docket | [17 empty] | RECORDS: As-built records
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer | [17 empty] | ONSITE RESPONSIBILITY: Supervisor and Engineer
[23 empty] | CONFORMANCE CRITERIA: | [16 empty] | Channel Level | [17 empty] | 7 - RAMM DATA
[23 empty] | RECORDS: Delivery Docket | [16 empty] | VERIFICATION ACTIVITY: QA FORM | [17 empty] | VERIFICATION ACTIVITY: RAMM DATA SHEET
[23 empty] | 5 - Material Compliance (2) | [16 empty] | METHODS OR REFERENCE: TDM Technical Standards - KC0001 | [17 empty] | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
[23 empty] | ACTION (Hold, Monitor, Witness): H | [16 empty] | FREQUENCY: Every site | [17 empty] | FREQUENCY: Every Site
[23 empty] | DETAIL: Ensure all concrete used is 20MPa mix | [16 empty] | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level | [17 empty] | ACCEPTANCE CRITERIA: RAMM SHEET
[23 empty] | FREQUENCY: Upon delivery to site | [16 empty] | HOLD POINT: In process Inspection | [17 empty] | HOLD POINT: In Process Inspection
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials | [16 empty] | RECORDS: Photos | [17 empty] | RECORDS: As-built records
[23 empty] | CONFORMANCE CRITERIA: | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer | [17 empty] | ONSITE RESPONSIBILITY: Supervisor and Engineer
[23 empty] | RECORDS: Delivery Docket | [16 empty] | Footpaths
[23 empty] | 6 - Trenching | [16 empty] | VERIFICATION ACTIVITY: QA FORM
[23 empty] | ACTION (Hold, Monitor, Witness): H | [16 empty] | METHODS OR REFERENCE: TDM Technical Standards - FP0001
[23 empty] | DETAIL: Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 1000mm cover to duct when under berm/footpath (1500mm cover when under road crossing - non motorway/expressway) | [16 empty] | FREQUENCY: 10m intervals
[23 empty] | FREQUENCY: 10m Intervals | [16 empty] | ACCEPTANCE CRITERIA: Subgrade CBR > 3
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection | [16 empty] | HOLD POINT: In process Inspection
[23 empty] | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | [16 empty] | RECORDS: Scalar Sheet
[23 empty] | RECORDS: Photos | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer
[23 empty] | 6.1 - Trenching | [16 empty] | Concrete Footpaths
[23 empty] | ACTION (Hold, Monitor, Witness): H | [16 empty] | VERIFICATION ACTIVITY: QA FORM
[23 empty] | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs | [16 empty] | METHODS OR REFERENCE: TDM Technical Standards - FP0001
[23 empty] | FREQUENCY: 10m Intervals | [16 empty] | FREQUENCY: 10m Intervals
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure | [16 empty] | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX) Concrete Strength 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing) Standard Footpath - 100mm thick Heavy Duty - 150mm thick
[23 empty] | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings | [16 empty] | HOLD POINT: Inprocess Inspection
[23 empty] | RECORDS: Dipsheet CHAR(AMP) Photos | [16 empty] | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
[23 empty] | 7 - Duct Installation | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer
[23 empty] | ACTION (Hold, Monitor, Witness): W | [16 empty] | AC Footpaths
[23 empty] | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct. | [16 empty] | VERIFICATION ACTIVITY: QA FORM
[23 empty] | FREQUENCY: Prior to Installation | [16 empty] | METHODS OR REFERENCE: TDM Technical Standards - FP0003
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | [16 empty] | FREQUENCY: 10m Intervals
[23 empty] | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | [16 empty] | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3) Basecourse - 150mm min. thickness GAP40 Clegg CIV > 27 DG10/Fine asphalt mix used
[23 empty] | RECORDS: Photos | [16 empty] | HOLD POINT: Inprocess Inspection
[23 empty] | 7.1 - Duct Installation | [16 empty] | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
[23 empty] | ACTION (Hold, Monitor, Witness): H | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer
[23 empty] | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables | [16 empty] | Pram Crossing
[23 empty] | FREQUENCY: 10m Intervals | [16 empty] | VERIFICATION ACTIVITY: Visual
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | [16 empty] | METHODS OR REFERENCE: TDM Technical Standards - FP006
[23 empty] | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | [16 empty] | FREQUENCY: Each Crossing
[23 empty] | RECORDS: Photos | [16 empty] | ACCEPTANCE CRITERIA: Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. Tactiles Directional CHAR(AMP) warning - 60mm; 600mm flares;width as per design; Slope no greater than 1:12 where practicably possible Clegg CIV > 12
[23 empty] | 7.2 - Duct Installation | [16 empty] | HOLD POINT: Mandatory HOLD POINT -
[23 empty] | ACTION (Hold, Monitor, Witness): H | [16 empty] | RECORDS: Photos
[23 empty] | DETAIL: Asbuilt Survey | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer
[23 empty] | FREQUENCY: 20m Intervals | [16 empty] | Service Covers and Street Furniture
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | [16 empty] | VERIFICATION ACTIVITY: Visual
[23 empty] | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | [16 empty] | METHODS OR REFERENCE: AT Contract Specification 14000
[23 empty] | RECORDS: Survey Records | [16 empty] | FREQUENCY: Everysite
[23 empty] | 8 - Bedding | [16 empty] | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
[23 empty] | ACTION (Hold, Monitor, Witness): H | [16 empty] | HOLD POINT: Inprocess Inspection
[23 empty] | DETAIL: Lay min. 100mm pit sand or finer for bedding and haunching | [16 empty] | RECORDS: Nil
[23 empty] | FREQUENCY: 10m Intervals | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | [16 empty] | As built information
[23 empty] | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | [16 empty] | VERIFICATION ACTIVITY: Drawings
[23 empty] | RECORDS: Photos | [16 empty] | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
[23 empty] | 9 - Warning Tape | [16 empty] | FREQUENCY: Every Site
[23 empty] | ACTION (Hold, Monitor, Witness): H | [16 empty] | ACCEPTANCE CRITERIA: As built drawings
[23 empty] | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines. | [16 empty] | HOLD POINT: In Process Inspection
[23 empty] | FREQUENCY: 10m Intervals | [16 empty] | RECORDS: Asbuilt records
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer CHAR(AMP) PM
[23 empty] | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions | [16 empty] | RAMM DATA
[23 empty] | RECORDS: Photos | [16 empty] | VERIFICATION ACTIVITY: RAMM DATA SHEET
[23 empty] | 10 - Traffic signal pole erection | [16 empty] | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
[23 empty] | ACTION (Hold, Monitor, Witness): H | [16 empty] | FREQUENCY: Every Site
[23 empty] | DETAIL: Ensure Design engineer as inspected pole locations prior to proceeding | [16 empty] | ACCEPTANCE CRITERIA: RAMM SHEET
[23 empty] | FREQUENCY: Per pole | [16 empty] | HOLD POINT: In Process Inspection
[23 empty] | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection | [16 empty] | RECORDS: RAMM Sheet
[23 empty] | CONFORMANCE CRITERIA: Sign off by design engineer | [16 empty] | ONSITE RESPONSIBILITY: Site Engineer CHAR(AMP) PM
RECORDS: Engineer sign off
10.1 - Traffic signal pole erection
ACTION (Hold, Monitor, Witness): H
DETAIL: Ensure Pot hole is as per design with required depths and widths
FREQUENCY: Per pole
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
RECORDS: Dipsheet CHAR(AMP) Photos
10.2 - Traffic signal pole erection
ACTION (Hold, Monitor, Witness): H
DETAIL: Ensure Poles are plumb and within design tolerances
FREQUENCY: Per pole
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
RECORDS: Photos
11 - As-builts CHAR(AMP) CCHAR(AMP)I Diagram
ACTION (Hold, Monitor, Witness): H
DETAIL: As-built as per ATOC requirements
FREQUENCY: At the completion of the Lot of work
INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
CONFORMANCE CRITERIA: As-built as per ATOC requirements
RECORDS: Asbuilt Drawing