## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | ITP-075-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0075 - Asphalt Placement | 9fb03d06-6160-4b7b-a83b-cfefade42822
checkpoint-group | Lot Information
checkpoint-status | 1.0 Lot Information
date | Lot Created On
date | Lot Opened On
date | Work Commenced On
select | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
text | From and To Chainage
select | Construction Element | PAVI - Paving
select | Activity | PAVI - Asphalt Placement
select | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
select | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
text | Engineer Responsible
text | comments
checkpoint-group | 1 - Preliminary Works
checkpoint-status | 1.1 Submission of Mix Design
label | Frequency: Prior to commencing paving
label | - - - - - - - - -
label | Acceptance Criteria: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.407.06
label | - - - - - - - - -
label | Inspection / Test Method: Correspondence of receipt of mix design
label | - - - - - - - - -
label | Record of Conformity: VR approval Completed ITP
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
text | Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent
holdpoint | HOLD POINT
checkpoint-status | 1.2 Ensure underlying lot conforms
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: All quality information received for lot (includes levels, area and volume) and NCRs (BIRs) approved.
label | - - - - - - - - -
label | Reference Documents: Relevant ITP for underlying lot
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of Conformity: Inspection and Test Plan
label | - - - - - - - - -
label | HP*
checkpoint-status | 1.3 Visual Inspection of underlying lot
label | Frequency: Prior to Commencing
label | - - - - - - - - -
label | Acceptance Criteria: If the execution of any part of the work under the Subcontract is dependent upon the quality and completeness of an existing surface or work performed by Separate Contractors, the subcontractors shall visually inspect the existing surface or Separate Contractor's work for matters including the following:
label | (i) Homogeneous surface and pavement material
label | (ii) Uniform in texture
label | (iii) Free from tearing and scabbing
label | (iv) Free from laminations
label | (v) Free from loose and foreign materials
label | and immediately notify the Contractors Representative of all matters discovered that a competent contractor who specialises in the type of works performed under Subcontract should have discussed by such inspection which in the Subcontractor's opinion render such work unsuitable for the proper execution of the work under the Subcontract.
label | - - - - - - - - -
label | Reference Documents: CTW-175S Special Condition 11 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
label | - - - - - - - - -
label | Inspection / Test Method: Visual Inspection
label | - - - - - - - - -
label | Record of Conformity: Inspection and Test Plan ITP Signed
label | - - - - - - - - -
label | WP
label | - - - - - - - - -
text | Responsibility: Site Engineer/ Asphalt Supervisor
checkpoint-status | 1.4 Ambient Conditions for Placing
label | Frequency: Prior to commencing paving
label | - - - - - - - - -
label | Acceptance Criteria: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | Base & Intermediate Courses: 5°C for conventional binders or
label | 10°C for PMBs & Class 600
label | Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | - - - - - - - - -
label | Reference Documents: 407.13
label | - - - - - - - - -
label | Inspection / Test Method: Verify
label | - - - - - - - - -
label | Record of Conformity: Thermometer / gauge
label | - - - - - - - - -
label | IP
label | - - - - - - - - -
text | Responsibility: Site Engineer/ Asphalt Supervisor
checkpoint-status | 1.5 Planning of Joints
label | Frequency: Prior to commencing paving
label | - - - - - - - - -
label | Acceptance Criteria: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client (MRPV):
label | (i) Transverse Joints Offset from layer to layer by at least 2m
label | (ii) Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. V
label | (iii) Wearing course shall be on lane lines.
label | - - - - - - - - -
label | Reference Documents: 407.17 (b) & (c) Pavement Drawings
label | - - - - - - - - -
label | Inspection / Test Method: Measure and mark out runs by tape measure or survey
label | - - - - - - - - -
label | Record of Conformity: Paving Plan
label | - - - - - - - - -
label | WP
label | - - - - - - - - -
text | Responsibility: Project Engineer/ Asphalt Supervisor Superintendent
checkpoint-status | 1.6 Longitudinal Joints with existing Pavement
label | Frequency: Prior to commencing paving
label | - - - - - - - - -
label | Acceptance Criteria: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each individual layer.
label | - - - - - - - - -
label | Reference Documents: 407.16 (c) Project Specs. Section 3040.06 (d)(vii)
label | - - - - - - - - -
label | Inspection / Test Method: Visual Inspection
label | - - - - - - - - -
label | Record of Conformity: ITP Signed
label | - - - - - - - - -
label | WP
label | - - - - - - - - -
text | Responsibility: Project Engineer/ Asphalt Supervisor
checkpoint-group | 2 - Asphalt Placement
checkpoint-status | 2.1 Commencement of placement
label | Frequency: Prior to commencing Paving
label | - - - - - - - - -
label | Acceptance Criteria: Approval to place asphalt on the sub-base or granular base for a new pavement or for an ordinary of an existing bituminous surfaced pavement.
label | - - - - - - - - -
label | Reference Documents: 404.13 405.07 407.18 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
label | - - - - - - - - -
label | Inspection / Test Method: Visual Inspection
label | - - - - - - - - -
label | Record of Conformity: Inspection and Test Plan
label | - - - - - - - - -
label | HP
label | - - - - - - - - -
text | Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent
holdpoint | HOLD POINT
checkpoint-status | 2.2 Cold Weather Placement Management Plan
label | Frequency: Prior to commencing Paving (Seasonal)
label | - - - - - - - - -
label | Acceptance Criteria: Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
label | - - - - - - - - -
label | Reference Documents: 407.17C
label | - - - - - - - - -
label | Inspection / Test Method: Document review
label | - - - - - - - - -
label | Record of Conformity: Inspection and Test Plan
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
text | Responsibility: Project Engineer/ Asphalt Project Manager or Engineer
checkpoint-status | 2.3 Mix Design Confirmation
label | Frequency: Each lot
label | - - - - - - - - -
label | Acceptance Criteria: Check correct mix design as per pavement design has been delivered prior to laying mix.
label | - - - - - - - - -
label | Reference Documents: VicRoads Spec. Cl.407.06
label | - - - - - - - - -
label | Inspection / Test Method: Visual Inspection & Delivery Docket
label | - - - - - - - - -
label | Record of Conformity: Delivery docket Completed ITP
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
text | Responsibility: Site Engineer/ Asphalt Supervisor
checkpoint-status | 2.4 Running traffic on Placed Asphalt
label | Frequency: During Construction
label | - - - - - - - - -
label | Acceptance Criteria: Traffic not to be placed on asphalt placed until Fulton Hogan agree the surface temperature is less than the required mix temp. (SMA 40°C) to receive traffic.
label | - - - - - - - - -
label | Reference Documents: 404.14 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
label | - - - - - - - - -
label | Inspection / Test Method: Verify
label | - - - - - - - - -
label | Record of Conformity: Inspection and Test Plan ITP Signed Thermometer / gauge
label | - - - - - - - - -
label | HP*
label | - - - - - - - - -
text | Responsibility: Site Engineer/ Asphalt Supervisor
checkpoint-group | 3 - Testing
checkpoint-status | 3.1 Placing Material
label | Frequency: Per Lot
label | - - - - - - - - -
label | Acceptance Criteria: 407.21 - DGA as per 407.22 405.08 - RGG - not less than 3 passes with steel wheeled roller. 3 passes to be made within time to compaction cessation substrate (pavement) temperature is between 7° and 10°C.
label | - - - - - - - - -
label | Reference Documents: 407.21 405.08 404.14 417.12 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
label | - - - - - - - - -
label | Inspection / Test Method: Material Sampling & testing
label | - - - - - - - - -
label | Record of Conformity: Visual Inspection/ Compaction test results Visual Inspection/ Visual Inspection/ Field Report/
label | - - - - - - - - -
label | WP
label | - - - - - - - - -
text | Responsibility: Site Engineer/ Asphalt Supervisor Superintendent
checkpoint-status | 3.2 Survey Level Conformance
label | Frequency: Per 4,000m2 at completion of work
label | - - - - - - - - -
label | Acceptance Criteria: 407.293 Surface Level Tolerances for Sub-base and Pavement Courses
label
label | Scale of Surface Level Measurement -
label | Granular or CT Subbase
label | Range (mm) Max S. (mm)
label | Scale A - +4 to -8 8
label | Scale B - +6 to -12 13
label
label | Asphalt Layers
label | Range (mm) Max S. (mm)
label | Scale A - +/- 5 8
label | Scale B - +/- 8 10
label | - - - - - - - - -
label | Reference Documents: VicRoads Sec 407.293 Surface Level Tolerances for Sub-base and Pavement Courses
label | - - - - - - - - -
label | Inspection / Test Method: Document Review/ Site Inspection
label | - - - - - - - - -
label | Record of Conformity: Survey Conformance Report
label | - - - - - - - - -
label | SCP
label | - - - - - - - - -
text | Responsibility: Site Engineer/ Surveyor / Survey Manager
checkpoint-status | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
date | Date:
date | Work Completed On
checkpoint-group | Lot Verification
checkpoint-status | Lot Verification.
select | Is the relevant RFI attached to the Lot? | YES, NO, N/A
select | Is the relevant NCR attached to the Lot? | YES, NO, N/A
select | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
select | Lot verified By | Babak Rudd-Project Quality Manager, Abid Hameed (Area 1 Manager), Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
text | Other:
select | Lot Status | OUTSTANDING, CLOSED
date | Lot Closed On
text | comments