## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-006-STR&CIV-Material Inspection-Precast Panel | itp |  |  |  |  | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0
checkpoint-no-status | CHK-006-STR-RSS Walls-Material Inspection-Precast Panel
note | Document Title: CHK-006-STR/CIV-Material Inspection-Precast
note | ITP Description: Material Inspection-Precast
note | Discipline (e.g. CIV/STR/RAIL): STR/CIV
note | Revision Number: 0
note | Revision Date: 10/01/2023
note | ITP created by: Ethan Caruana-Smith
note | ITP approved for use by: Pradeep Talasila
checkpoint | 1 - Delivery Details
note | Acceptance Criteria:
textbox | Enter: Delivery Docket Number:
textbox | Enter: Delivery Date:
textbox | Enter: Element ID (s):
note | Attach: Delivery Docket and packaging Slip
note | Method: Document Review, Visual
note | Frequency: Each Delivery
note | Category: IP
note | Responsibility: PE/SE
note | Verifying Documents: This Checklist
textbox | Date Completed:
checkpoint | 2 - Packaging Inspection-Quantity
note | Acceptance Criteria: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
note | Method: Visual
note | Frequency: Each Delivery
note | Category: IP
note | Responsibility: PE/SE
note | Verifying Documents: This Checklist
textbox | Date Completed:
checkpoint | 3 - Packaging Inspection-Delivery Contents
note | Acceptance Criteria: Do the contents of the delivery match the freight list/packaging slip?
note | Method: Document Review, Visual
note | Frequency: Each Delivery
note | Category: IP
note | Responsibility: PE/SE
note | Verifying Documents: This Checklist
textbox | Date Completed:
checkpoint | 4 - Packaging Inspection-Birth Certificate
note | Acceptance Criteria: Is the delivery accompanied by Precast items Birth Certificates?
note | ○ Precast components are to be marked on the birth certificate.
note | ○ Cast date and lot are to be marked on the birth certificate.
note | Method: Document Review
note | Frequency: Each Precast item
note | Category: IP
note | Responsibility: PE/SE
note | Verifying Documents: This Checklist
textbox | Date Completed:
checkpoint | 5 - Packaging Inspection-Transport
note | Acceptance Criteria: Is the condition of packaging acceptable.
note | ○ Precast items are protected from damage during the transport
note | Method: Visual
note | Frequency: Each Precast item
note | Category: IP
note | Responsibility: PE/SE
note | Verifying Documents: This Checklist
textbox | Date Completed:
checkpoint | 6 - Fault IDs:
note | Acceptance Criteria: For each precast type delivered, check for the following:
note | 1 - Identification markings match the element type
note | 2 - Element fabricated as per drawings
note | 3 - Cracks
note | 4 - Spalling/Damage to concrete surface
note | 5 - Exposed Reinforcement
note | 6 - Damage to Anti-Graffiti coating
note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
textbox | Date Completed:
checkpoint | 7 - Check for Faults - 1
note | Reference: Item 6 on this Checklist
note | Acceptance Criteria: For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
note | Method: Visual, Measure
note | Frequency: Each precast type delivered
note | Category: IP
note | Responsibility: PE/SE
note | Verifying Documents: This Checklist
textbox | Date Completed:
checkpoint | 7 - Check for Faults - 2
note | Reference: Item 6 on this Checklist
note | Acceptance Criteria: For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
note | Method: Visual, Measure
note | Frequency: Each precast type delivered
note | Category: IP
note | Responsibility: PE/SE
note | Verifying Documents: This Checklist
textbox | Date Completed:
checkpoint | 7 - Check for Faults - 3
note | Reference: Item 6 on this Checklist
note | Acceptance Criteria: For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
note | Method: Visual, Measure
note | Frequency: Each precast type delivered
note | Category: IP
note | Responsibility: PE/SE
note | Verifying Documents: This Checklist
textbox | Date Completed:
checkpoint | 7 - Check for Faults - 4
note | Reference: Item 6 on this Checklist
note | Acceptance Criteria: For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
note | Method: Visual, Measure
note | Frequency: Each precast type delivered
note | Category: IP
note | Responsibility: PE/SE
note | Verifying Documents: This Checklist
textbox | Date Completed:
checkpoint | 7 - Check for Faults - 5
note | Reference: Item 6 on this Checklist
note | Acceptance Criteria: For Each Precast type delivered:
textbox | Enter: Panel Identification:
textbox | Enter: Quantity:
textbox | Enter: Fault ID if any:
note | Method: Visual, Measure
note | Frequency: Each precast type delivered
note | Category: IP
note | Responsibility: PE/SE
note | Verifying Documents: This Checklist
textbox | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP