## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Enviro WB Primer + Enviro 200P Ultra |  |  |  |  | Yes | Enviro WB Primer + Enviro 200P Ultra 2 | 1400418b-abe9-4b78-a7d3-a436272335f4
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS
checkpoint-status |  |  | checkpoint | Enviro Shield
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex FC
checkpoint-status |  |  | checkpoint | Enviro 200P Ultra
checkpoint-group |  |  | section | PRE COMMENCEMENT
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | e8bf325a-221e-5169-ab66-1f19e6b1dc22 |  | note | Store materials in a dry, clean place away from direct sunlight.
checkpoint-status |  |  | checkpoint | Acceptance of Substrate
label | c79ead02-45b0-51a3-ba58-268b38cf2e69 |  | note | Obtain clearance for work initiation.
label | cf4640f8-4182-508e-930b-7f1459caa4e1 |  | note | Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes.
label | 98187acd-d6cf-5a84-976f-b766d77b7db9 |  | note | Patching products must be fully cured as per PDS before applying the membrane.
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges
label | 92dc835e-7f94-5ad7-af78-1450f503eba9 |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
checkpoint-status |  |  | checkpoint | Acceptance of wall
label | 487146e6-3145-5413-bb75-5b6ffe0f7b97 |  | note | FC sheeting to have max 6mm gap at floor/wall junction.
label | f015fe3a-d9c2-5bf5-a309-d8a80f6e093e |  | note | Sheets to be set with manufacturers base coat, including all nails, penetrations and corners.
label | 90e408e9-b7f0-5c3f-9870-ec323e754912 |  | note | Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
checkpoint-status |  |  | checkpoint | Falls in Substrate
label | a5b3c5ae-dd18-5faf-b9f1-20c9fcfc927f |  | note | Builder to confirm compliant falls; minimum 1-100 falls.
holdpoint |  |  | signoff | Foreman to confirm falls - Signature
checkpoint-status |  |  | checkpoint | Cracks in Substrate
label | 5a5b906c-13eb-5077-a355-f2dd1f8bdf38 |  | note | Ensure no substrate cracks greater than 1.6mm.
label | eeac5119-5ef1-57f3-9867-17ee4177038d |  | note | Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
checkpoint-group |  |  | section | SUBSTRATE PREPARATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Substrate Preparation: AS 4654.2-2012
label | fb93cb3b-a4cf-5675-8618-e291d1d21bd0 |  | note | Ensure Surface is prepared to receive primer application.
label | 7a84e907-2b3b-5a6f-856d-be34a706e9a3 |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 2a428091-e3fc-5648-abc7-635d4128cc92 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 9402f0ad-57c1-539d-894d-e1fc9adbe086 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 27554716-ba06-5711-a5a2-bd0ea2be02e5 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
checkpoint-group |  |  | section | ENVIRO SHIELD- PRIME COAT
checkpoint-status |  |  | checkpoint | Moisture Content
label | 512642b0-b502-56e1-974e-a50b1b0bf3a3 |  | note | Check Moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
checkpoint-status |  |  | checkpoint | Weather/RH
label | 71c9dfe4-64a7-5bdc-85ce-ceb6ecaf0a72 |  | note | Apply within 10-35°C
label | 2ceafb97-c637-5a37-809f-bda74ddcc0cc |  | note | RH must be 0-85%
checkpoint-status |  |  | checkpoint | Application
label | 195b15db-c2f1-5849-a4bc-f5bf08e94d23 |  | note | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base Thoroughly mix with a mechanical mixer at low speed (less than 400 RPM) prior to application.
label | f5a5bb5e-0ba5-5c25-8810-b33e4755a589 |  | note | Mix for 5 minutes or until uniform.
label | 5bc89dda-5d6c-5bed-b8fd-3ba151912462 |  | note | Allow to stand 5 minutes after mixing and then mix again for a minute.
checkpoint-group |  |  | section | BOND BREAKER
checkpoint-status |  |  | checkpoint | Bond Breaker
label | b7ee1a4e-d721-50f3-923b-85c45795a7df |  | note | • Apply Enviro Flex FC/compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | d81037ed-6735-5f98-920d-66cc0726f167 |  | note | • This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | aaa34591-6a4c-5445-8940-fb718269ba15 |  | note | • Allow to cure prior to over coating with membrane coats.
checkpoint-group |  |  | section | 200P Ultra
checkpoint-status |  |  | checkpoint | Weather/RH
label | f8cb57fc-ab84-5a41-b242-2fe7036ae9b6 |  | note | Apply within 10-35°C
label | a884830c-bb38-5f12-9882-36dd0c3fd6f6 |  | note | RH must be 0-85%
checkpoint-status |  |  | checkpoint | Mixing
label | c952e314-f0a0-52c1-b3aa-5e42445958c5 |  | note | • 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Application
label | bb7718e6-f5bb-5c80-9b65-c02f8905b32b |  | note | • 200P Ultra to be applied by roller Veritcally on substrate and cut in with brush on terminations.
label | 01cfd8fc-6301-57da-8041-fab021c13017 |  | note | • Allow membrane to dry for 24 Hours before proceeding to the second coat.
checkpoint-group |  |  | section | 200P Ultra - Second Coat
checkpoint-status |  |  | checkpoint | Weather/RH
label | 3ba7da83-f324-5318-80db-aaf353575721 |  | note | Apply within 10-35°C
label | d2d72042-de47-51f6-ad8f-64c1d7b10088 |  | note | RH must be 0-85%
checkpoint-status |  |  | checkpoint | Mixing
label | b63da3d6-27f2-56b9-be43-87dc37f733e0 |  | note | • 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Application
label | 7613a303-788a-5475-a015-1027e88d53b1 |  | note | • 200P Ultra to be applied by roller horizontally on substrate and cut in with brush on terminations.
label | 36674073-2af0-565a-a7e4-67e9d9d0bc97 |  | note | • Allow membrane to cure for 3 days prior to next steps
checkpoint-status |  |  | checkpoint | QA TESTING
label | 016ce142-8b99-56f3-8f7f-245cc1b223fc |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | 91b1a52f-7b52-542c-a21c-23db4dc3c746 |  | note | Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2)
label | 31a44ba6-0e19-5611-ad62-827a10a96c5e |  | note | 24 Hours flood testing to take place.
checkpoint-group |  |  | section | FINAL BUILDERS SIGN OFF
checkpoint-status |  |  | checkpoint | Final Builders Signoff
holdpoint |  |  | signoff | Final Sign off
checklist-sectioned |  |  | checklist | Enviro B-LV+700X+250NS |  |  |  |  | Yes | Enviro B-LV+700X+250NS | 7238ce4d-8046-4b7e-8304-84c3b3d056c9
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex Pro
checkpoint-status |  |  | checkpoint | Enviro B-LV
checkpoint-status |  |  | checkpoint | Enviro 700X
checkpoint-status |  |  | checkpoint | Enviro 250NS
checkpoint-group |  |  | section | PRE COMMENCEMENT
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | a90deebd-4b2c-56e7-a338-b4006bcbe483 |  | note | Store materials in a dry, clean place away from direct sunlight.
checkpoint-status |  |  | checkpoint | Acceptance of Substrate
label | d5a01907-59b7-56a2-b6fb-020f80f73ef8 |  | note | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per PDS before applying the membrane.
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges
label | 04e787f6-2bcd-5ad5-82af-30327f6b1d98 |  | note | All puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
checkpoint-status |  |  | checkpoint | Falls in Substrate
label | ecff1019-101d-565e-afb1-3c5d00c1a544 |  | note | Builder to confirm compliant falls; minimum 1-100 falls.
holdpoint |  |  | signoff | Foreman to confirm falls - Signature
checkpoint-status |  |  | checkpoint | Cracks in Substrate
label | b9caf4af-277f-5de7-ba94-e75625e802d7 |  | note | Ensure no substrate cracks greater than 1.6mm. Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Ensure Surface is prepared to receive primer application.
label | 251ed254-665d-5a49-aef0-57a386522de6 |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 4908694c-b736-5fa2-93d4-e3922ee625f6 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 0ed2c5ee-c328-52b4-b065-750ce22c2780 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | a0c2f061-01d7-5227-9304-7be222a285b0 |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
checkpoint-group |  |  | section | EPOXY B-LV - PRIME COAT
checkpoint-status |  |  | checkpoint | Moisture Content
label | bd6af807-1cd2-5764-8a67-8cf5ce10407b |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
checkpoint-status |  |  | checkpoint | Weather/RH
label | f147488c-b517-57f9-9d98-241af6ca4809 |  | note | Apply within 5-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Product Mixing
label | 2825ba0e-c11b-50c6-a852-4966b92bcbf7 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Primer Application
label | 0549ae29-3c82-545b-a49b-82d4597ea950 |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
checkpoint-group |  |  | section | BOND BREAKER
checkpoint-status |  |  | checkpoint | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 76ef8dce-12a0-52a9-962b-69005965eb16 |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | 78bd4520-a789-5e86-8998-e75e7e8f577a |  | note | Bond breaker to be tack free prior to coating.
checkpoint-group |  |  | section | ENVIRO 700X - FIRST COAT
checkpoint-status |  |  | checkpoint | Weather/RH
label | 0556dd77-a8c0-565c-a606-ad3d476b11e5 |  | note | Apply within 5-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Product Mixing
label | 48fe264a-68f5-50f3-922e-24cfe8fa3a72 |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | 700X Application
label | 7fb0d9f8-87db-55ec-8bac-87ed78332340 |  | note | • Enviro 700X to be applied by roller vertically on substrate and cut in with brush on terminations. • Allow membrane to dry for 24 Hours before proceeding to the second coat.
checkpoint-group |  |  | section | ENVIRO 700X - SECOND COAT
checkpoint-status |  |  | checkpoint | Weather/RH
label | 548958cf-75c1-5b84-a55a-0fcf6ab8ecfe |  | note | Apply within 5-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Product Mixing
label | 67623c44-a701-56bd-a391-cd2e78c3a747 |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | 700X Application
label | f3453705-ccf6-531a-86b2-f168f2e55f2a |  | note | • Enviro 700X to be applied by roller horizontally on substrate and cut in with brush on terminations. • Allow membrane to dry for 24 Hours before proceeding to the second coat.
checkpoint-status |  |  | checkpoint | QA TESTING
label | 18c4ebd0-4d43-5262-8257-6f2eb47dea4b |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.( 1 test per 10m2) Conduct Electronic Leak Testing ( ELT) and rectify as required.
checkpoint-group |  |  | section | 250NS
checkpoint-status |  |  | checkpoint | Weather/RH
label | 762e4368-3337-5bff-a331-dea5271f6283 |  | note | Apply within 10-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Mixing
label | 0c1d057b-a52c-55e2-92b4-9cc497d1c9b9 |  | note | • Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | 250NS Application
label | d81ab561-9d0e-56ba-8383-bc8bea78d7b5 |  | note | • Enviro 250NS to be applied by roller vertically on substrate and cut in with brush on terminations. • Allow membrane to dry for 24 Hours before proceeding to the second coat.
checkpoint-group |  |  | section | 250NS -SECOND COAT
checkpoint-status |  |  | checkpoint | Weather/RH
label | 3e0d3d99-0354-579a-b226-f574de877435 |  | note | Apply within 10-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Mixing
label | 60c8c6d4-2a6d-52e7-b1ba-deff8e10451a |  | note | • Enviro 250NS should be thoroughly mixed with a mechanical mixer at low speed (less that 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | 250NS Application
label | 790b3e0e-5b9f-5177-996c-815161f4ad42 |  | note | • Enviro 250NS to be applied by roller horizontally on substrate and cut in with brush on terminations. • Allow membrane to dry for 24 Hours before proceeding to the second coat.
checkpoint-group |  |  | section | DETAILING
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing
label | 191270a5-f8dc-511b-9397-140e7e5e5347 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
checkpoint-group |  |  | section | FINAL BUILDERS SIGN OFF
checkpoint-status |  |  | checkpoint | Final Sign off.
holdpoint |  |  | signoff | Final Sign off.
checklist-sectioned |  |  | checklist | Enviro B-LV+700X+250NS |  |  |  |  | Yes | Enviro B-LV+700X | c900cdbc-3f63-42a2-90f1-ed2363806f1e
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex Pro
checkpoint-status |  |  | checkpoint | Enviro B-LV
checkpoint-status |  |  | checkpoint | Enviro 700X
checkpoint-status |  |  | checkpoint | Enviro 250NS
checkpoint-group |  |  | section | PRE COMMENCEMENT
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | e333766d-16d5-504c-9510-2469b82ebe85 |  | note | Store materials in a dry, clean place away from direct sunlight.
checkpoint-status |  |  | checkpoint | Acceptance of Substrate
label | 107480fc-bd0a-5ace-81c6-4da862d80e2d |  | note | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per PDS before applying the membrane.
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges
label | e4d37a3e-1427-5235-ad7c-f76ee4b63644 |  | note | All puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
checkpoint-status |  |  | checkpoint | Falls in Substrate
label | 7d6d7e9e-46f1-5ba5-a2b7-d986476b67b6 |  | note | Builder to confirm compliant falls; minimum 1-100 falls.
holdpoint |  |  | signoff | Foreman to confirm falls - Signature
checkpoint-status |  |  | checkpoint | Cracks in Substrate
label | edafea83-ff64-5b84-9c8e-19f453497524 |  | note | Ensure no substrate cracks greater than 1.6mm. Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Ensure Surface is prepared to receive primer application.
label | 1224003f-6205-5831-8944-c0697f95170a |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 27e17b2c-9a2f-5d8d-8049-819108b750ef |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 0f485b77-35d8-5082-9f15-3eced1352bef |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | 100d0262-f942-5093-b06d-5fc92f9e341b |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
checkpoint-group |  |  | section | EPOXY B-LV - PRIME COAT
checkpoint-status |  |  | checkpoint | Moisture Content
label | b7f378b8-b436-580b-a6c4-c5a9f1d4675d |  | note | Check moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
checkpoint-status |  |  | checkpoint | Weather/RH
label | e892bc77-d1c6-5eaf-b196-5110cb522f4e |  | note | Apply within 5-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Product Mixing
label | fc052f84-a4ab-5ee2-874a-98a665fa8453 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Primer Application
label | 9ca4b01b-2567-50e1-a9d2-7ab863c53399 |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
checkpoint-group |  |  | section | BOND BREAKER
checkpoint-status |  |  | checkpoint | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 05b30fdc-949f-5beb-9f00-09d50fc57490 |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | 5f5db274-0042-5726-9354-5acd38313cf3 |  | note | Bond breaker to be tack free prior to coating.
checkpoint-group |  |  | section | ENVIRO 700X - FIRST COAT
checkpoint-status |  |  | checkpoint | Weather/RH
label | f73ca180-8f94-5588-ba77-30547af2cf4e |  | note | Apply within 5-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Product Mixing
label | a5e77088-3917-504e-8e7b-00a3d3b5e98b |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | 700X Application
label | 3a39935a-2a19-54f5-97e7-618a57ebe389 |  | note | • Enviro 700X to be applied by roller vertically on substrate and cut in with brush on terminations. • Allow membrane to dry for 24 Hours before proceeding to the second coat.
checkpoint-group |  |  | section | ENVIRO 700X - SECOND COAT
checkpoint-status |  |  | checkpoint | Weather/RH
label | 6df9f4db-691a-5ce4-b9d3-c9134460b959 |  | note | Apply within 5-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Product Mixing
label | bdd54a07-9a8d-5c54-90d2-429b3cd6d309 |  | note | • Product should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | 700X Application
label | 386e586c-af2f-51fc-b074-6f83f383f3f2 |  | note | • Enviro 700X to be applied by roller horizontally on substrate and cut in with brush on terminations. • Allow membrane to dry for 24 Hours before proceeding to the second coat.
checkpoint-status |  |  | checkpoint | QA TESTING
label | f302913a-6afd-5452-9323-ffaf79645166 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.( 1 test per 10m2) Conduct Electronic Leak Testing ( ELT) and rectify as required.
checkpoint-group |  |  | section | DETAILING
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing
label | b7f83ada-bf6b-5360-87ea-45bf83ba7d8d |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
checkpoint-group |  |  | section | FINAL BUILDERS SIGN OFF
checkpoint-status |  |  | checkpoint | Final Sign off.
holdpoint |  |  | signoff | Final Sign off.
checklist-sectioned |  |  | checklist | Enviro Systems - Epoxy BLV+HP1200+900PUR+800TC |  |  |  |  | Yes | Enviro Systems - Epoxy BLV+HP1200+900PUR+800TC | ef98b3a6-0554-42e1-9610-4e9267fa0936
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS
checkpoint-status |  |  | checkpoint | Enviro B-LV
checkpoint-status |  |  | checkpoint | Sika Flex FC/ Enviro Flex FC
checkpoint-status |  |  | checkpoint | Enviro HP1200
checkpoint-status |  |  | checkpoint | Enviro 900 PUR
checkpoint-status |  |  | checkpoint | Enviro 800TC
checkpoint-group |  |  | section | PRE COMMENCEMENT
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | b38d25b9-7098-5135-b24e-42f48a5dc509 |  | note | Store materials in a dry, clean place away from direct sunlight.
checkpoint-status |  |  | checkpoint | Acceptance of Substrate
label | 5026eb0c-7b1c-5ec3-9779-128182b22596 |  | note | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per PDS before applying the membrane.
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges
label | 5765f799-d413-51b3-b319-1a6409bd5c61 |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
checkpoint-status |  |  | checkpoint | Falls in Substrate
label | 9e326024-953c-5b84-8a23-b4265557dce3 |  | note | Builder to confirm compliant falls; minimum 1-100 falls.
holdpoint |  |  | signoff | Foreman to confirm falls - Signature
checkpoint-status |  |  | checkpoint | Cracks in Substrate
label | d3f06f6b-cd48-5792-93f1-089655c76a02 |  | note | Ensure no substrate cracks greater than 1.6mm. Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Ensure Surface is prepared to receive primer application.
label | 9a2cc920-9295-5f19-ab1c-a63401f2688b |  | note | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | 9065037b-d890-5fa0-968a-2144dfc47c78 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | 3d304199-45bc-51a7-a7e9-54faa2189ed2 |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | ed67cfb6-6d2d-5d23-8bb2-5ddf961b58bd |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
checkpoint-group |  |  | section | EPOXY B-LV - PRIME COAT
checkpoint-status |  |  | checkpoint | Moisture Content
label | 480d9bbe-74a9-5440-a1f1-ae517c9ba123 |  | note | Check Moisture content of substrate, not to exceed 6% ( Min.1 test per 10m2.)
checkpoint-status |  |  | checkpoint | Weather/RH
label | a8dfb98e-f56b-54e0-97b4-27e25a98ed17 |  | note | Apply within 5-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Product Mixing
label | 538e0d6d-d678-5807-939d-7348dc646813 |  | note | Mix Part A (12L) and Part B (6L) seperately add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Primer Application
label | 066e1ca0-4cc2-502d-8461-a1c97f42ccca |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface. Apply one coat of Enviro Epoxy B to achieve a minimum Dry Film Thickness (DFT) of 75 microns. Ensure Primer is dry and tack free (within 24 hours) prior to next coat.
checkpoint-group |  |  | section | BOND BREAKER
checkpoint-status |  |  | checkpoint | Apply compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | ac36b393-f794-5f20-b9de-29d35040e3ec |  | note | This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | 63f2ce22-031a-5667-9e2f-289b1ac58c8a |  | note | Bond breaker to be tack free prior to coating.
checkpoint-group |  |  | section | ENVIRO HP1200- BASE COAT
checkpoint-status |  |  | checkpoint | Weather/RH
label | b21758cd-36e0-59ba-a323-5525c49ba552 |  | note | Apply within 5-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Product mixing
label | b1d53ff9-4ab1-5501-8484-891f9ce58972 |  | note | Mixing by way of 1:1 mix ratio (by volume) in heated plural component.
checkpoint-status |  |  | checkpoint | HP1200 Application
label | b5f8c1e8-a016-5d38-aec3-189a36fac179 |  | note | HP1200 must be sprayed using high pressue plural component dispensing equipment - Drums of component must be pre-heated to at least 25C prior to mixing or dispensing. Mix Part B thoroughly with a mechanical power mixer before use.
checkpoint-status |  |  | checkpoint | QA TESTING
label | 92a06010-ad48-5881-9ea0-41bdfe75a247 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.( 1 test per 10m2) Conduct Electronic Leak Testing ( ELT) and rectify as required.
checkpoint-group |  |  | section | ENVIRO 900 PUR- WEAR COAT
checkpoint-status |  |  | checkpoint | Weather/RH
label | 62d23f86-e9c0-539b-a236-d5b9bdb92901 |  | note | Apply within 5-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Mixing of Product
label | c2a1855b-a876-58cb-8432-b54f55483f71 |  | note | Enviro 900 has a mix ratio of 2.2:1 (A:B). Mix Part A and Part B separately, before combining. Enviro 900 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for a minimum of thirty seconds prior to application.
checkpoint-status |  |  | checkpoint | Application
label | 9e807e4a-a755-5c74-b318-a321e5edd80f |  | note | Enviro 900 to be applied by squeegee, roller or brush to finished membrane. Aggregate should be uniformly broadcasted to the wet Enviro 900 within 10 minutes.
checkpoint-group |  |  | section | ENVIRO 800 TC
checkpoint-status |  |  | checkpoint | Weather/RH
label | a2ebd3c9-d609-59b3-b534-d3dd3793169f |  | note | Apply within 10-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Mixing of Product
label | 368ca3fa-17af-5c66-ba3d-7618f66f4fc1 |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume. Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | Application
label | 7656f645-2b2d-59ca-af40-784d9061547a |  | note | Enviro 800TC to be applied by roller or brush to finished membrane. Allow coat to sufficiently dry before proceeding to the next coat
checkpoint-group |  |  | section | ENVIRO 800 TC - 2ND COAT
checkpoint-status |  |  | checkpoint | Weather/RH
label | 88b3fe6c-0f21-52e0-b57c-9851da1c7c1d |  | note | Apply within 10-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Mixing of Product
label | 88ec5710-0b77-52bf-9cab-977bf3980681 |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume. Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Add Part B to Part A and mix to a uniform colour and consistency of a minimum 3 minutes - allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | Application
label | c801dd76-b34d-534a-9012-fd29b3195663 |  | note | Enviro 800TC to be applied by roller or brush to finished membrane. Allow coat to sufficiently dry before proceeding to the next coat.
checkpoint-group |  |  | section | DETAILING
checkpoint-status |  |  | checkpoint | Vertical Termination Detailing
label | 375ae17b-8fb2-5948-8334-572c5d6b6e96 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
checkpoint-group |  |  | section | FINAL BUILDERS SIGN OFF
checkpoint-status |  |  | checkpoint | Final Sign off.
holdpoint |  |  | signoff | Final Sign off.
checklist-sectioned |  |  | checklist | Enviro WB Primer + Enviro 200P Ultra |  |  |  |  | Yes | Enviro WB Primer + Enviro 200P Ultra | f8fc3edf-02ed-4321-94ad-635052207780
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS
checkpoint-status |  |  | checkpoint | Enviro Shield
checkpoint-status |  |  | checkpoint | Enviro Flex FC/ Sika Flex FC
checkpoint-status |  |  | checkpoint | Enviro 200P Ultra
checkpoint-group |  |  | section | PRE COMMENCEMENT
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | 9ca6a190-d8f3-5b2d-aa58-3db17fe364e2 |  | note | Store materials in a dry, clean place away from direct sunlight.
checkpoint-status |  |  | checkpoint | Acceptance of Substrate
label | afd9c8e5-17fb-539f-af2f-77adb6bbead3 |  | note | Obtain clearance for work initiation. Ensure a smooth substrate without protrusions, voids, or formwork distortions. The substrate should be free of honeycombing/bug holes. Patching products must be fully cured as per PDS before applying the membrane.
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges
label | 1194f4bd-1471-5dbb-a9ac-32bf95f9e1ba |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
checkpoint-status |  |  | checkpoint | Acceptance of wall
label | 670d53db-311a-5c6e-b9bd-7c129c56fafa |  | note | FC sheeting to have max 6mm gap at floor/wall junction. Sheets to be set with manufacturers base coat, including all nails, penetrations and corners. Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
checkpoint-status |  |  | checkpoint | Falls in Substrate
label | 7d40421d-f0d3-5927-81d8-9cd2bad09d75 |  | note | Builder to confirm compliant falls; minimum 1-100 falls.
holdpoint |  |  | signoff | Foreman to confirm falls - Signature
checkpoint-status |  |  | checkpoint | Cracks in Substrate
label | afe6354d-5f92-5eea-afb4-044fb39d5608 |  | note | Ensure no substrate cracks greater than 1.6mm. Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks are to be referred to engineers for treatment methodology.
checkpoint-group |  |  | section | SUBSTRATE PREPERATION: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Ensure Surface is prepared to receive primer application.
label | 51a7977e-2e77-5ccf-939b-5a6ea20da4db |  | note | Clean substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
label | adfcb16f-9484-58a9-b7fa-9a7a55913720 |  | note | Achieve CSP2 and CSP3 Concrete finish.
label | bccf8a4f-eeaf-5a01-ad69-c9fc5a02e8db |  | note | Remove all sharp edges including screws, nails and concrete/mortar projection.
label | d9753c22-63f5-59fb-a4ea-e3a2d603168a |  | note | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
checkpoint-group |  |  | section | ENVIRO SHIELD- PRIME COAT
checkpoint-status |  |  | checkpoint | Moisture Content
label | ed8d3fd9-64b5-5d11-a243-b966558520b3 |  | note | Check Moisture content of substrate, not to exceed 6% (Min.1 test per 10m2).
checkpoint-status |  |  | checkpoint | Weather/RH
label | fa7fa0c7-b313-5fc9-86e4-f08bee761205 |  | note | Apply within 10-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Application
label | fd8e14c7-33f6-5b18-af37-7ffc4db7375b |  | note | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base Thoroughly mix with a mechanical mixer at low speed (less than 400 RPM) prior to application. Mix for 5 minutes or until uniform. Allow to stand 5 minutes after mixing and then mix again for a minute.
checkpoint-group |  |  | section | BOND BREAKER
checkpoint-status |  |  | checkpoint | • Apply Enviro Flex FC/compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints.
label | 2becb364-1400-598b-a428-5a7efd5aeb5d |  | note | • This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas.
label | ccf2afad-49a9-517f-b05f-315e317661b6 |  | note | • Allow to cure prior to over coating with membrane coats.
checkpoint-group |  |  | section | 200P Ultra
checkpoint-status |  |  | checkpoint | Weather/RH
label | 7232c153-5b85-5a5c-92e1-a20fc4df8161 |  | note | Apply within 10-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Mixing
label | f586687f-772b-5b08-ba23-e48ac859e950 |  | note | • 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Application
label | 9c1fe8a7-a036-598f-904e-668afdfc5832 |  | note | • 200P Ultra to be applied by roller Veritcally on substrate and cut in with brush on terminations. • Allow membrane to dry for 24 Hours before proceeding to the second coat.
checkpoint-group |  |  | section | 200P Ultra - Second Coat
checkpoint-status |  |  | checkpoint | Weather/RH
label | a4e5ddc2-39fd-5813-bbc9-e1a37bfbe50d |  | note | Apply within 10-35°C RH must be 0-85%
checkpoint-status |  |  | checkpoint | Mixing
label | a6e436ad-aecc-5d75-beee-6d2a452f67ce |  | note | • 200P Ultra should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Application
label | 745781d6-a9b8-5b2c-92a4-89471de6196d |  | note | • 200P Ultra to be applied by roller horizontally on substrate and cut in with brush on terminations. • Allow membrane to cure for 3 days prior to next steps
checkpoint-status |  |  | checkpoint | QA TESTING
label | 731c5e15-b01c-5983-90df-639a84e32ca0 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.0mm to manufacturers instructions.( 1 test per 10m2) 24 Hours flood testing to take place.
checkpoint-group |  |  | section | FINAL BUILDERS SIGN OFF
checkpoint-status |  |  | checkpoint | Final Sign off.
holdpoint |  |  | signoff | Final Sign off.