## Structure
Tier 1 | Tier 2 | Tier 3 | Instruction to CONQA | Checklist Name
Job Details |  |  | prepopulate | Job Details Checklist
Panel QA
Panels
|  | PC-01 | prepopulate | Precast Panel QA (V1)
PC-02
PC-03
PC-04
PC-05
PC-06
PC-07
PC-08
PC-09
PC-10
PC-11
PC-12
PC-13
PC-14
PC-15
PC-16
PC-17
PC-18
PC-19
PC-20
PC-21
PC-22
PC-23

## Precast Panel QA (V1)
Type | Name | Values | Prefix | Postfix | Template Name
checklist | Precast Panel QA
section | Precast Element Details
checkpoint | Concrete Details Complete
text | Concrete Volume
text | Concrete Strength
text | Enter Drawing Revision Number
text | Cast Date
text | Admixture Required
section | Formwork Set Up Checks
checkpoint | Length/Width/Thickness/Cutouts/Diagonals
checkpoint | Edge Details & Rebates
checkpoint | Inserts on MF (Weld plates, RB's, TIM's, Penetrations, DB Bottoms)
checkpoint | MF roughening's
checkpoint | Sides Straight & Magnets Fastened
checkpoint | Mould Face Clean
section | Prepour Checks
checkpoint | Mould Cleaned & Oiled
checkpoint | Reinforcing details checked/highlighted off against shop drawing (Bar sizes, grades and spacings)
checkpoint | Check covers on all sides, MF and TF
checkpoint | There is sufficient cover to rebates around openings or weatherproofing details
checkpoint | Starters (Size, Grade, Setout and Length)
Checkpoint | Inserts on TF (Weld plates, RB's, TIM's, Penetrations, DB's, Rebates)
checkpoint | Lifters
checkpoint | Tie wire Trimmed
checkpoint | Panel fully clean
checkpoint | General Photos Attached
checkpoint | Shop Drawing Checked Off (attach photo)
section | Demould Inspection
checkpoint | Demould Inspection complete
section | Loading Out
checkpoint | Photo take of Panel on Truck
checkpoint | No remedial work required on site
section | Test Results, Certificates and Documentation
checkpoint | Upload reinforcing detail sheets
checkpoint | Concrete Docket Attached
checkpoint | Upload Concrete test results
checkpoint | Upload Photo of Reinforcing Cast # Tracking
checkpoint | Upload Lift Designs

## Precast Install QA
Type | Name | Values | Prefix | Postfix | Template Name
checklist | Precast Install QA
section | Details
checkpoint | Details Complete
text | Watpac supervisor
text | Precast Supplier
text | Rigging Company
text | Riggin Supervisor
text | Crane Supplier
section | Lifting and Quality Checks
checkpoint | Birth Cert (QA) Provided
checkpoint | Panel Visual inspection (any damage, check coulour and quality) take photo
checkpoint | Can the panel be lifted as per rigging details provided in shop drawing?
checkpoint | Do strongbacks, fall protection need to be installed prior to lift?
section | Post install check
checkpoint | Set out check - Grid / level / plumb
checkpoint | All Bracekts installed with correct number of fixings, washers, packing shims etc
checkpoint | Grouting
checkpoint | Propping signed off temp works engineer
checkpoint | Grouting
Checkpoint | Ready/OK to pour upper level

## Job Details Checklist
Type | Name | Values | Prefix | Postfix | Template Name
checklist-flat | Job Details Checklist
checkpoint | Project details entered below
textbox | Job File Number
textbox | Project Name
textbox | Site Address
textbox | Main Contractor
textbox | Main Contractor POC
textbox | Structural Engineer
textbox | Architect

## Draft Checklists
Type | Name | Values | Prefix | Postfix | Template Name
checklist | Panel Checklist
section | Pre-Manufacturing QA check
checkpoint | Information Complete
note | Unit Mark
section | Reo Cage Check (PMC1)
checkpoint | Correct size and type
checkpoint | Laps and splices correct
checkpoint | Cover checked
checkpoint | Spacing checked
checkpoint | Starter bars checked and correct
checkpoint | Reinforcing placed correctly, checked and approved
note | Attach Photos
note | Heat numbers Photo
section | Prepour Check -PC1
checkpoint | Table/Mould cleaned before setup
checkpoint | Length/Width/Thickness/Cutouts
checkpoint | Square
checkpoint | Edge Details & Rebates
checkpoint | Cast in items (Inserts, Weldplates)
checkpoint | Mould Cleaned & Oiled
checkpoint | Rugasol
checkpoint | Main Reinforcing
checkpoint | Starters
checkpoint | Lifters
checkpoint | Drawings & General Photos
section | Concrete
checkpoint | Concrete Docket Attached (photo)
textbox | Concrete Mix code
section | Manufacturing Check - Postpour Check -PC2
checkpoint | Information Complete
checkpoint | Details
textbox | Post pour Completion date
checkpoint | Does Unit Need any remedial work
checkpoint | MF/NF/sides photos
textbox | General comment
section | Monarc/ Archtectural finish Check (PC3)
checkpoint | Unit required Monarc/Archtectutal finish
note | Yes- Below question. No- next section
checkpoint | Monarc/Arch Drawing photos
textbox | Unit Checked/Proceessed by
checkpoint | MF Finishing photos
checkpoint | NF Finishing photos
checkpoint | Sides Finishing photos
checkpoint | Does Unit Washed after Monarc Processing
checkpoint | Does Unit Need any remedial work
textbox | General comment
checklist | Precast Concrete Pour & Installation Checklist
section | Pre-Pour
checkpoint | Pour to be completed and position confirmed
note | Pass when photo of the area/sketch of the pour AND gridline reference have been uploaded
checkpoint | Formwork has correct dimensions & heights
checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint | Temporary works completed/confirmed/signed off
checkpoint | Any/all cast in items checked/correct (location and size)
checkpoint | Penetrations correctly formed/located, checked and accurate
checkpoint | Bottom of concrete pour is clean and free of debris/roughened
checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
signoff | Request Sign Off
section | Pour & Post-Pour
checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
tickbox | All concrete dockets photographed/attached here
checkpoint | General photos/comments/observations during placement
checkpoint | Concrete surface finish to specifications
checkpoint | Concrete pour completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
note | FINAL: Pass when work(s) are completed, area clean & tidy (any issues please comment below)
signoff | Installation
section | Installation
checkpoint | Latest drawings available, checked and referenced
checkpoint | Set out checked and done
checkpoint | Starter Bars checked
checkpoint | Timber Blocks Installed
checkpoint | Packers installed on correct RL
checkpoint | Access to items
checkpoint | Check dimensions of panels - on delivery
checkpoint | Panel props installed with the correct fixings
checkpoint | Verticality checked
checkpoint | Panel placed in correct place
checkpoint | Panel aligned and secured
checkpoint | Final check - Panel installation complete and ready for sign off
note | Marked up drawing photographed if applicable
signoff | Request Review
checklist | Precast Panel Checklist
section | Info
checkpoint | Information Complete
textbox | Concrete Volume
textbox | Concrete Strength
section | Prepour
checkpoint | Length/Width/Thickness/Cutouts
checkpoint | Square
checkpoint | Edge Details & Rebates
checkpoint | Cast in items (Inserts, Weldplates)
checkpoint | Main Reinforcing
checkpoint | Starters
checkpoint | Stirrups
checkpoint | Lifters
checkpoint | Mould Cleaned & Oiled
checkpoint | Tie wire Trimmed
checkpoint | Rugasol
checkpoint | Drawings & General Photos
section | Concrete
checkpoint | Concrete results obtained
checkpoint | Concrete Docket Attached (photo)
textbox | Concrete Docket Number
section | Post Pour
checkpoint | Post pour Complete
textbox | Release Date
textbox | Release Strength
checkpoint | Remedial Required
checkpoint | Mould Face Finish
checkpoint | Near Face Finish
checkpoint | Cast -In/Inserts/Penetrations
checkpoint | Starter lengths/Positions
checkpoint | Approved
checkpoint | Mill certificate attached
checklist | Pre-Stressed Concrete Checklist
section | Unit Info
checkpoint | Unit information entered and correct
note | Attach photo/s of construction drawings
checkpoint | Attach photo of casting summary report
section | Pre Pour
checkpoint | Formwork
textbox | Overall Dimensions
textbox | Checkouts/Rebates to Edges
textbox | Face Surface Finish
checkpoint | Reinforcing / Strand
textbox | Strand / Bar Size Type & Spacing
tickbox | Security of Tying
tickbox | Cover to Face & Sides
textbox | No. of Strands
textbox | Heights of Strands
textbox | No. of Stirrups & Spacing
textbox | Initial Gauge Pressure
textbox | Final Gauge Pressure
textbox | Final Extension
textbox | Coil Number
note | Attach photo of Stressing Calculation Sheet
checkpoint | APPROVAL TO POUR
textbox | Name of Approver
signoff | CLICK HERE TO REQUEST APPROVAL
section | Pour
checkpoint | Visual check - specified finish achieved
tickbox | U2 (Near Face)
tickbox | U3 (Near Face)
tickbox | F4 (Mould Face)
tickbox | Broom
tickbox | Exposed
textbox | Other:
note | Attach photos of units
checkpoint | Concrete Delivery
textbox | Truck Arrival Time
note | Photo of Concrete Delivery Docket
checkpoint | Cast-In Items
textbox | Size, Type & Location of 'Fixings'
textbox | Lifting Point Rating & Anchorage
section | Post Pour
checkpoint | Release strength achieved
textbox | Strength:
button | Select type | Crush (destructive test), Schmidt (non-destructive test)
note | Upload printout OR import PDF of graph
checkpoint | Overall Dimensions Including Blockouts
tickbox | Dimensions checked
checkpoint | Visual Check
tickbox | Chip/damage free
tickbox | Excess Poly and Strand removed
tickbox | Surface finish achieved as per spec
button | Strand protection required? | Yes, No, NA
note | Attach photos of units
section | Post Pour Finishing Work
checkpoint | Post Pour Finishing Work required?
button | Post Pour Finishing Work required | Yes,No
textbox | Describe work to be undertaken
note | Attach photos
checkpoint | Post Pour Finishing Work completed
textbox | Product and technique/s used
note | Attach photos
section | Approval for Delivery
checkpoint | Pre-Delivery Inspection
textbox | Inspection Notes:
checkpoint | APPROVED FOR DELIVERY
signoff | CLICK TO INFORM PM OF DELIVERY
checklist | Precast QA Checklist
section | Precast Element Details
checkpoint | Concrete Details Complete
textbox | Concrete Volume
textbox | Concrete Strength
textbox | Enter Drawing Revision Number
textbox | Cast Date
section | Reinforcing Yard Checks (Reo QA)
checkpoint | Operative on the reinforcing cutting line has uploaded clear photo of open stock bundle boar
checkpoint | Cut and bent bars checked off against detail sheet
checkpoint | Perimeter bars and spacing marks confirmed
checkpoint | Cast in Items checked and marked on cage (Dross Ducts, Inserts Weld Plates)
checkpoint | Overall cage dimensions in plan checked and there will be sufficient concrete cover to edges
checkpoint | Overall cage thickness checked and there will be sufficient cover to MF and TF
checkpoint | There is sufficient cover to rebates around openings or along edge forms
checkpoint | Weld plates can be fitted to cage in correct locations?
checkpoint | Reinforcing details checked/highlighted off against shop drawing (upload photo)
section | Formwork Set Up Checks (Tables QA)
checkpoint | Sides Straight & Magnets Fastened
checkpoint | Mould Face Clean
checkpoint | Length/Width/Thickness/Cutouts
checkpoint | Edge Details & Rebates
checkpoint | MF Weld plates in correct location and siliconed to table
section | Prepour Checks (Tables QA)
checkpoint | Main Reinforcing
checkpoint | Starters
checkpoint | Stirrups
checkpoint | Lifters
checkpoint | Mould Cleaned & Oiled
checkpoint | Tie wire Trimmed
checkpoint | General Photos Attached
checkpoint | Concrete Docket Attached
checkpoint | Shop Drawing Checked Off (attach photo)
section | Loading Out (Yard QA)
checkpoint | Load Docket Given to Driver
checkpoint | Photo take of Panel on Truck
checkpoint | No remedial work required on site
section | Test Results, Certificates and Documentation (Reo & Yard QA)
checkpoint | Upload reinforcing detail sheets
checkpoint | Upload Photo of Reinforcing Stock Bundle Tags (Cast # Tracking)
checkpoint | Upload Concrete test results
checklist-flat | Job Details Checklist
checkpoint | Project details entered below
textbox | Job File Number
textbox | Project Name
textbox | Site Address
textbox | Main Contractor
textbox | Main Contractor POC
textbox | Structural Engineer
textbox | Architect