## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Instruction to CONQA | Checklist Name | Grouping
Site QA
Basebuild
Basement B5
Floor Based Work
[6 empty] | QA-Fire Rated Bulkhead for Steel penetration to Korok Wall/Promatect | Checklist Group 1
QA-Steel Stud Internal Wall framing and insulation
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
QA-Door Installation
QA-Promatect Framing and lining
Apt Lift Lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
East Stair
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Stair lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Basement B4
Floor Based Work
[6 empty] | QA-Fire Rated Bulkhead for Steel penetration to Korok Wall/Promatect | Checklist Group 1
QA-Steel Stud Internal Wall framing and insulation
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
QA-Door Installation
QA-Promatect Framing and lining
Apt Lift Lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
East Stair
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Stair lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Basement B3
Floor Based Work
[6 empty] | QA-Fire Rated Bulkhead for Steel penetration to Korok Wall/Promatect | Checklist Group 1
QA-Steel Stud Internal Wall framing and insulation
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
QA-Door Installation
QA-Promatect Framing and lining
Apt Lift Lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Podium Lift Lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
East Stair
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Stair lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Basement B2
Floor Based Work
[6 empty] | QA-Fire Rated Bulkhead for Steel penetration to Korok Wall/Promatect | Checklist Group 1
QA-Steel Stud Internal Wall framing and insulation
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
QA-Door Installation
QA-Promatect Framing and lining
Apt Lift Lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Podium Lift Lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
East Stair
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Stair lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Basement B1
Floor Based Work
[6 empty] | QA-Fire Rated Bulkhead for Steel penetration to Korok Wall/Promatect | Checklist Group 1
QA-Steel Stud Internal Wall framing and insulation
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
QA-Door Installation
QA-Promatect Framing and lining
Apt Lift Lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Podium Lift Lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
East Stair
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Stair lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Goods Lift lobby
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Fire Control Room
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Security/Comms RM
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Main Switch Board
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Rubbish Room
[6 empty] | QA-Fire Rated Timber Bulkhead Framing | Checklist Group 2
QA-Fire Rated Timber Bulkhead lining
Ground Floor
Floor Based Work
[6 empty] | QA-Fire Rated Bulkhead for Steel penetration to Korok Wall/Promatect | Checklist Group 3
QA-Fibrecement Board Wall Lining
QA-Promatect Framing and lining
QA-Fire Sealant Infill to Comflor Groove
QA-Door Installation
Grand Lobby
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Apt Lobby
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Apt Lift Lobby
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Mail RM
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Good Lift Lobby
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
BoH
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
VIP Car Lift Lobby
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
West Stair
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
East Stair
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Other Area
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Level 1
|  |  | Floor based Work |  |  |  | Checklist Group 3
|  |  | Podium Lobby |  |  |  | Checklist Group 4
|  |  | Management Facilities |  |  |  | Checklist Group 4
|  |  | Apt Lift Lobby |  |  |  | Checklist Group 4
|  |  | Toilet |  |  |  | Checklist Group 4
|  |  | Goods Lift Lobby |  |  |  | Checklist Group 4
|  |  | West Stair |  |  |  | Checklist Group 4
|  |  | East Stair |  |  |  | Checklist Group 4
|  |  | Other Area |  |  |  | Checklist Group 4
Level 2
|  |  | Floor based Work |  |  |  | Checklist Group 3
|  |  | Apt Lift Lobby |  |  |  | Checklist Group 4
|  |  | Goods Lift Lobby |  |  |  | Checklist Group 4
|  |  | VIP Storage |  |  |  | Checklist Group 4
|  |  | West Stair |  |  |  | Checklist Group 4
|  |  | East Stair |  |  |  | Checklist Group 4
|  |  | Other Area |  |  |  | Checklist Group 4
Level 3
|  |  | Floor based Work |  |  |  | Checklist Group 3
|  |  | Apt Lift Lobby |  |  |  | Checklist Group 4
|  |  | Goods Lift Lobby |  |  |  | Checklist Group 4
|  |  | VIP Storage |  |  |  | Checklist Group 4
|  |  | West Stair |  |  |  | Checklist Group 4
|  |  | East Stair |  |  |  | Checklist Group 4
|  |  | Other Area |  |  |  | Checklist Group 4
Level 5
|  |  | Floor based Work |  |  |  | Checklist Group 3
|  |  | Office Lobby |  |  |  | Checklist Group 4
|  |  | Goods Lift Lobby |  |  |  | Checklist Group 4
|  |  | Service Reticulation |  |  |  | Checklist Group 4
|  |  | Femail Toilet |  |  |  | Checklist Group 4
|  |  | Mail Toilet |  |  |  | Checklist Group 4
|  |  | West Stair |  |  |  | Checklist Group 4
|  |  | East Stair |  |  |  | Checklist Group 4
|  |  | Other Area |  |  |  | Checklist Group 4
Level 6
|  |  | Floor based Work |  |  |  | Checklist Group 3
|  |  | Office Lobby |  |  |  | Checklist Group 4
|  |  | Goods Lift Lobby |  |  |  | Checklist Group 4
|  |  | Service Reticulation |  |  |  | Checklist Group 4
|  |  | Femail Toilet |  |  |  | Checklist Group 4
|  |  | Mail Toilet |  |  |  | Checklist Group 4
|  |  | West Stair |  |  |  | Checklist Group 4
|  |  | East Stair |  |  |  | Checklist Group 4
|  |  | Other Area |  |  |  | Checklist Group 4
Level 7
|  |  | Floor based Work |  |  |  | Checklist Group 3
|  |  | Apt Lift Lobby |  |  |  | Checklist Group 4
|  |  | Pool Lobby |  |  |  | Checklist Group 4
|  |  | Goods Lift Lobby |  |  |  | Checklist Group 4
|  |  | Male WC |  |  |  | Checklist Group 4
|  |  | Femail WC |  |  |  | Checklist Group 4
|  |  | West Stair |  |  |  | Checklist Group 4
|  |  | East Stair |  |  |  | Checklist Group 4
|  |  | Pool Area |  |  |  | Checklist Group 4
|  |  | Other Area |  |  |  | Checklist Group 4
Level 7M
|  |  | Floor based Work |  |  |  | Checklist Group 3
|  |  | Plant Room |  |  |  | Checklist Group 4
Level 8
|  |  | North Balcony |  | Copy to Level 9-Level 40
[6 empty] | QA-Fire Separation PFP Infill to Façade | Checklist Group 5
QA-Steel Stud External Framing and Sliding Door Bulkhead
QA-Weathline Air Barrier
QA-Building Wrap
South Elevation
[6 empty] | QA-Fire Separation PFP Infill to Façade | Checklist Group 6
QA-Building Wrap
Floor Based Work
[6 empty] | QA-Fire Rated Steel Stud Bulkhead Framing | Checklist Group 7
QA-Fire Rated Steel Stud Bulkhead Lining
QA-Fire Sealant Infill to Comflor Groove
QA-Fire Rated Bulkhead for Steel penetration to Korok Wall/Promatect
QA-Promatect Framing and lining
QA-Door Installation
QA--FRR timber packing to steel plate
Apt Lift lobby
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
West Stair
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 8
QA-GIB Plasterboard Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
East Stair
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 8
QA-GIB Plasterboard Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Apt Corridor
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 8
QA-GIB Plasterboard Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Goods Lift Lobby
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 8
QA-GIB Plasterboard Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
|  |  | Unit 801 |  | Copy to Level 9-Level 40 with room no modified
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Unit 802
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Unit 803
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Unit 805
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Unit 806
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Unit 807
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Unit 808
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Unit 809
[6 empty] | QA-Steel Stud Internal Wall framing and insulation | Checklist Group 4
QA-GIB Plasterboard Wall Lining
QA-Fibrecement Board Wall Lining
QA-Ceiling Grid and insulation
QA-Ceiling Lining
Level 9
|  |  | Unit 901 |  |  |  | Checklist Group 4
|  |  | Unit 902 |  |  |  | Checklist Group 4
|  |  | Unit 903 |  |  |  | Checklist Group 4
|  |  | Unit 905 |  |  |  | Checklist Group 4
|  |  | Unit 906 |  |  |  | Checklist Group 4
|  |  | Unit 907 |  |  |  | Checklist Group 4
|  |  | Unit 909 |  |  |  | Checklist Group 4
|  |  | Unit 909 |  |  |  | Checklist Group 4
|  | Level 10 | Unit 1001
Unit 1002
Unit 1003
Unit 1005
Unit 1006
Unit 1007
Unit 1008
|  | Level 11 | Unit 1101
Unit 1102
Unit 1103
Unit 1105
Unit 1106
Unit 1107
Unit 1108
|  | Level 12 | Unit 1201
Unit 1202
Unit 1203
Unit 1205
Unit 1206
Unit 1207
Unit 1208
|  | Level 13 | Unit 1301
Unit 1302
Unit 1303
Unit 1305
Unit 1306
Unit 1307
Unit 1308
|  | Level 15 | Unit 1501
Unit 1502
Unit 1503
Unit 1505
Unit 1506
Unit 1507
Unit 1508
Unit 1509
|  | Level 16 | Unit 1601
Unit 1602
Unit 1603
Unit 1605
Unit 1606
Unit 1607
Unit 1608
Unit 1609
|  | Level 17 | Unit 1701
Unit 1702
Unit 1703
Unit 1705
Unit 1706
Unit 1707
Unit 1708
|  | Level 18 | Unit 1801
Unit 1802
Unit 1803
Unit 1805
Unit 1806
Unit 1807
Unit 1808
|  | Level 19 | Unit 1901
Unit 1902
Unit 1903
Unit 1905
Unit 1906
Unit 1907
Unit 1908
|  | Level 20 | Unit 2001
Unit 2002
Unit 2003
Unit 2005
Unit 2006
Unit 2007
Unit 2008
|  | Level 21 | Unit 2101
Unit 2102
Unit 2103
Unit 2105
Unit 2106
Unit 2107
Unit 2108
|  | Level 22 | Unit 2201
Unit 2202
Unit 2203
Unit 2205
Unit 2206
Unit 2207
Unit 2208
|  | Level 23 | Unit 2301
Unit 2302
Unit 2303
Unit 2305
Unit 2306
Unit 2307
Unit 2308
Unit 2309
|  | Level 25 | Unit 2501
Unit 2502
Unit 2503
Unit 2505
Unit 2506
Unit 2507
Unit 2508
Unit 2509
|  | Level 27 | Unit 2701
Unit 2702
Unit 2703
Unit 2705
Unit 2706
Unit 2707
Unit 2708
|  | Level 28 | Unit 2801
Unit 2802
Unit 2803
Unit 2805
Unit 2806
Unit 2807
Unit 2808
|  | Level 29 | Unit 2901
Unit 2902
Unit 2903
Unit 2905
Unit 2906
Unit 2907
Unit 2908
|  | Level 30 | Unit 3001
Unit 3002
Unit 3003
Unit 3005
Unit 3006
Unit 3007
Unit 3008
Unit 3009
|  | Level 31 | Unit 3101
Unit 3102
Unit 3103
Unit 3105
Unit 3106
Unit 3107
Unit 3108
Unit 3109
|  | Level 32 | Unit 3201
Unit 3202
Unit 3203
Unit 3205
Unit 3206
Unit 3207
Unit 3208
|  | Level 33 | Unit 3301
Unit 3302
Unit 3303
Unit 3305
Unit 3306
Unit 3307
Unit 3308
|  | Level 35 | Unit 3501
Unit 3502
Unit 3503
Unit 3505
Unit 3506
Unit 3507
Unit 3508
|  | Level 36 | Unit 3601
Unit 3602
Unit 3603
Unit 3605
Unit 3606
Unit 3607
Unit 3608
|  | Level 37 | Unit 3701
Unit 3702
Unit 3703
Unit 3705
Unit 3706
Unit 3707
Unit 3708
|  | Level 38 | Unit 3801
Unit 3802
Unit 3803
Unit 3805
Unit 3806
Unit 3807
Unit 3808
|  | Level 39 | Unit 3901
Unit 3902
Unit 3903
Unit 3905
Unit 3906
Unit 3907
Unit 3908
|  | Level 40 | Unit 4001
Unit 4002
Unit 4003
Unit 4005
Unit 4006
Unit 4007
Unit 4008

## Checklists
Type | Name | Values | Prefix | Postfix
checklist | QA-Fire Rated Timber Bulkhead Framing
section | Details
checkpoint | Job details
textbox | Level of Timber Bulkhead:
textbox | Location of Timber Bulkhead:
checkpoint | Handover from main contractor
tickbox | Area accessible
tickbox | Structure ready
tickbox | Intunescent painting ready
date | Handover date:
checkpoint | Fire Resistant requirement
button | Select requirement | 60 min, 90 min, 120 min
checkpoint | GIB system
tickbox | GBUC 120
section | Bulkhead Framing Installation
checkpoint | Apply Two Layers 19mm on RIB infill timber flooring junction
checkpoint | Min 200mm Extension of Gib or Nearest Plank
checkpoint | Hilti CP606 Fire Seal
checkpoint | Gib Board Screw 1st Layer 41mm 2nd Layer 57mm. @200mm centers,12mm min edge distance
checkpoint | Timber framing as per NZS 3604
checkpoint | Council preline inspection
date | Inspection date:
section | Any additional photos, comments and observations
checkpoint | additional photos
section | Handover to Lining Installation
checkpoint | Handover to lining installation
date | Handover date:
checklist | QA-Fire Rated Timber Bulkhead lining
section | Details
checkpoint | Job details
textbox | Level of Timber Bulkhead:
textbox | Location of Timber Bulkhead:
checkpoint | Handover
note | Area handed over from the below
tickbox | CCNZL
tickbox | LBY
tickbox | DFS
date | Handover date:
checkpoint | Fire Resistant requirement
button | Select requirement | 60 min, 90 min, 120 min
checkpoint | GIB system
tickbox | GBUC 120
section | GIB Lining Installation
checkpoint | Installation details
date | Date of First Layer installation:
date | Date of Second Layer installation:
checkpoint | GIB Lining Correctly Installed as per GIB manual
tickbox | The joints of the second layer are offset 600mm from those in the first layer.
tickbox | All sheet end butt joints must occur over solid framing.
tickbox | 41mm GIB Screws for Inner Layer ;57mm GIB Screws for Outer layer
tickbox | 12mm screw sheet edge,200mm centers to perimeter/framing/sheet ends.
tickbox | GIB fire and sound seal applied where required.
checkpoint | Council postline inspection
date | Inspection date:
section | Villaboard Lining Installation
checkpoint | Is Villaboard lining required?
button | Select requirement | YES, NO, N/A
checkpoint | Villaboard Lining Installation as per James Hardie Villaboard Installation manual
tickbox | Fixed with Exposed SS CSK @ 200mm Centers to edge,300mm centers to framing.
tickbox | Fixing Edge distance 50mm
tickbox | Expressed joint with Inseal 3259 sealing tape, 10mm max joint width
tickbox | No Villaboard to fire compressive material side
section | Any additional photos, comments and observations
checkpoint | additional photos
section | Handover
checkpoint | Handover accepted by main contractor
date | Handover date:
holdpoint | Request main contractor signoff
checklist | QA-Fire Rated Steel Stud Bulkhead Framing
section | Details
checkpoint | Job details
textbox | Level of Timber Bulkhead:
textbox | Location of Timber Bulkhead:
checkpoint | Handover from main contractor
tickbox | Area accessible
tickbox | Structure ready
tickbox | Intumescent painting ready
date | Handover date:
checkpoint | Fire Resistant requirement
button | Select requirement | 60 min, 90 min, 120 min
checkpoint | GIB system
button | Select requirement | GBSA 60c, GBSA 90c
section | Framing Installation
checkpoint | Framing installed as per design
tickbox | Timber Plaste Fix: with Hilti MX57mm steel nails @600mm centers staggered
tickbox | Top Track Fix: Hilti H6 anchors@600mm centers;100mm max.to end of track.
tickbox | Bottom Track Fix:Hilti H6 anchors@600mm centers or Rondo Junner Fixed with 12G Type 17 Wood Screws @600mm center
tickbox | Stud fixed to tracks at centers as per Rondo Design.(600mm nominal)
tickbox | Bracing stud/angle fixed to stud as per Rondo Design(600mm nominal)
checkpoint | Insulation installed to bulkhead framing as per design (R1.8 Pink Batt BIB 75mm glass wool Insulation )
checkpoint | Third party inspection (optional)
button | Engineer | PASS, FAIL, N/A
button | Architect | PASS, FAIL, N/A
button | Main Contractor | PASS, FAIL, N/A
checkpoint | Council preline inspection
date | Inspection date:
section | Any additional photos, comments and observations
checkpoint | additional photos
section | Handover for Lining
checkpoint | Handover to lining complete
date | Handover date:
checklist | QA-Fire Rated Steel Stud Bulkhead Lining
section | Details
checkpoint | Job details
textbox | Level of Timber Bulkhead:
textbox | Location of Timber Bulkhead:
checkpoint | Handover
note | Area handed over from the below
tickbox | CCNZL
tickbox | LBY
tickbox | DFS
date | Handover date:
checkpoint | Fire resistant requirement
button | Select requirement | 60 min, 90 min, 120 min
checkpoint | Fire Rated system
button | Select requirement | GBSA 60c, GBSA 90c
section | GIB Lining Installation
checkpoint | GIB Lining Correctly Installed as per GIB manual
tickbox | GBSA 90c double layer of 13mm fyreline each side;GBSA 60c upgraded with double layer of 13mm aqualine each side.
tickbox | Fastener: Inner and single layer: 25mm screw,Outer layer: 41mm screws. 300mm centers up each stud,12mm from sheet edge and 50mm sheet end.
tickbox | A bead of GIB Soundseal® acoustic sealant is required around the perimeter of the inner lining. The outer lining is then bedded onto the bead.
date | Date of First Layer installation:
date | Date of Second Layer installation:
date | Inspection date:
checkpoint | Level 3 stopping applied as per GIB manual
section | Any additional photos, comments and observations
checkpoint | additional photos
section | Handover to main contractor
checkpoint | Handover to main contractor complete
date | Handover date:
holdpoint | Request main contractor signoff
checklist | QA-Steel Stud Internal Wall framing and insulation
section | Details
checkpoint | Handover from main contractor
tickbox | Area accessible
tickbox | Structure ready
tickbox | Intumescent painting ready
date | Handover date:
section | Setting out
checkpoint | Setting out
button | Grid Line/ Datum Line Handed over from Main Contractor | YES, NO, N/A
button | Setting out as per latest architectural lay out plan, marked and checked | YES, NO, N/A
checkpoint | Type A Shower Tray Size Check: A1：1399mm A2：1339mm
checkpoint | Type B Shower Tray Size Check: B：1519mm
checkpoint | Type C Shower Tray Size Check: C：1393mm
checkpoint | Type D Shower Tray Size Check: D1：1521mm D2:1184mm D3:1169mm
section | Stud Framing Installation
checkpoint | Top Track Fix: Hilti H6 anchors@600mm centers;Top Track Size as per Rondo Design. Hilti TTS Fire Seal installed as per design.
checkpoint | Bottom Track Fix: Hilti H6 anchors@600mm centers;Top Track Size as per Rondo Design.
checkpoint | Stud type and fixing as per Rondo Design table,Nominal 20mm deflection gap on top
checkpoint | Nogging Type/No as per Rondo Design Table, Addtional Track 100 below head track when required in Rondo Design
checkpoint | Full Height Single Lined Wall: Addtional tied back connection with Rondo 562 brackets as per Rondo Designed
checkpoint | Furring Channel Direct Fix Partition with Betagrip-Stud Centers as per Rondo Design Table, Direct Fix Clip Span 1000mm Maximum
section | Door Opening Installation
checkpoint | Door Lintel/Jamb Stud Installed as per Rondo Design SK09/10/11,HUS6 anchor fixed between Track and Jamb Stud as per detail
checkpoint | Additional Timber Infill to Door Jamb
section | Quality Check
checkpoint | General framing on plan: 5mm; Shower area wall on plan:2mm
checkpoint | Tolerances:Deviation from vertical: 5mm per 2.4m
checkpoint | Wall Framing at mid-height under 3m long horizontal straight edge:6mm gradual bow; under 1.3m long horizontal straight edge 1.5mm out of line.
checkpoint | Wall Corners:5mm deviation from 500mm sqaure
section | Nogging
checkpoint | All service nogging marked and installed
checkpoint | Joinery nogging and any special nogging installed
section | Handover
checkpoint | Framing ready and handover to main contractor for first fix
date | Handover date:
checkpoint | Main Contractor Handover: Service 1st fix complete, ready for insulation and lining
date | Handover date:
holdpoint | Request main contractor signoff
section | Insulation
checkpoint | Insulation installed (R1.8 Pink Batt BIB 75mm glass wool Insulation to internal walls )
checkpoint | Insulation installed (R2.2 Polyester wall insulation to balcony sliding door bulkhead )
checkpoint | Any additional photos, comments and observations
checkpoint | additional photos
section | Council Preline Inspection and Handover
checkpoint | Council preline inspection
date | Inspection date:
checkpoint | Handover to GIB Contractor for lining
date | Handover Date
checklist | QA-Fire Rated Bulkhead for Steel penetration to Korok Wall/Promatect
section | Details
checkpoint | Job details
textbox | Level:
textbox | Location:
section | Install Timber/Steel Framing
checkpoint | Install substrate-fixed with Hilti MX Universal Nail, washer required when using steel framing
checkpoint | Edge distance requirement for ryanbatt installation: 90min 100mm;60min 50mm
checkpoint | Pre-lined framing required and installed
checkpoint | Insulation installed , match STC rating
checkpoint | 2 layers of 13mm fyreline installed as per GIB manual
checkpoint | Stopping and fire seal
tickbox | Lining stopping completed
tickbox | Fire sealant to perimeter completed
section | Any additional photos, comments and observations
checkpoint | additional photos
section | Handover
checkpoint | Handover to Maincontractor
date | Handover date:
checklist | QA-Fire Sealant Infill to Comflor Groove
section | Details
checkpoint | Job details
textbox | Level of comfloor groove:
textbox | Location of comfloor groove:
section | Infill Installation
checkpoint | Large groove infill with 100kg/m3 mineral wool then applied with Hilti CP606
checkpoint | Small groove applied with Hilti CP606
section | Any additional photos, comments and observations
checkpoint | additional photos
section | Handover
checkpoint | Area complete and handed over
date | Handover date:
checklist | QA-Fire Separation PFP Infill to Façade
section | Details
checkpoint | Job details
textbox | Elevation:
textbox | Level:
textbox | Grid Line:
section | Install Timber/Steel Substrate
checkpoint | Install substrate-fixed with Hilti MX Universal Nail
Button | Select framing type | Timber,Steel
checkpoint | Edge distance requirement for ryanbatt installation: 90min 100mm;60min 50mm
checkpoint | Pre-lined framing required and installed
section | Install Weatherline
checkpoint | 1st Layer Plaster board with 41mm x 6g Ceramic Coated High Thread Screws @200mm centers
checkpoint | 2nd Layer Plaster board with 63mm x 8g Ceramic Coated High Thread Screws @200mm centers
checkpoint | Apply Gib Fire Sound Seal
checkpoint | Handover for Passive fire material installation
section | Vaproshield revealshield install
checkpoint | Install Vaproshield Revealshield over rayn batt and weathline, seal with vapro bond
section | Any additional photos, comments and observations
checkpoint | additional photos
section | Inspection - third party
checkpoint | CCNZL
checkpoint | Fire Engineer
checkpoint | Architect
checklist | QA-Building Wrap
section | Building Wrap Installation
checkpoint | Fire Rated Wall Completed and Ready for Building Wrap
checkpoint | Material Correct-Vaproshield Reveal Shield / Vaprobond/ Liquidflash / Vaprosilicone Transition Sheet
checkpoint | Install Building Wraps,including Revealshield SA flashing/ Vapro liquid flash around window opening/penetrations as per Vaproshield Speciication.
tickbox | Flash around opening with and apply vaproLiquid flash as per architect requirement
tickbox | Minimum Overlap between sheet-80mm
tickbox | Revealshield adhered and sealed to soffit air barrier coating with liquidflash to seal trough of comflor
tickbox | All penetration-tool vaproLiquiflash evenly at least 5 cm onto the face and at least 2.5cm out along all sides of penetration
tickbox | Backing rod used to Wall DHT
checkpoint | Vaprosilicone transition strip installed with vaprobond between wall and facade / wall and PFC
checkpoint | Council postline inspection
date | Inspection date:
section | Any additional photos, comments and observations
checkpoint | additional photos
section | Handover
checkpoint | Handed over the area to main contractor
date | Handover date:
checklist | QA-Steel Stud External Framing and Sliding Door Bulkhead
section | Details
checkpoint | Handover from main contractor
tickbox | Area accessible
tickbox | Structure ready
tickbox | Intumescent painting ready
date | Handover date:
section | Setting out
checkpoint | Setting out
button | Grid Line/ Datum Line Handed over from Main Contractor | YES, NO, N/A
button | Setting out as per latest architectural lay out plan, marked and checked | YES, NO, N/A
checkpoint | Any additional photos, comments and observations
section | Stud Framing Installation
checkpoint | Top Track Fix:S683 Slotted DHT Hilti H6 anchors@400mm centers;Hilti TTS Fire Seal installed as per design.Top Track Size as per Rondo Design.
checkpoint | Bottom Track Fix: Hilti H6 anchors@400mm centers;Top Track Size as per Rondo Design.
checkpoint | Stud type and fixing as per Rondo Design table,Nominal 20mm deflection gap on top
checkpoint | Nogging Type/No as per Rondo Design Table, Addtional Track 100 below head track when required in Rondo Design
checkpoint | Alternative top track Normal DHT fix stud with slotted bracket 203 to slab.
checkpoint | Penetration Detail as per Rondo design 7166-19-003-F-92EO
section | Sliding door Bulkhead Installation
checkpoint | Height clearance check : 2740mm height
checkpoint | 92 Stud framing installed as per Rondo design SK01-3
checkpoint | Top Track Fix:Bracket 201 fix between dropper and top track with Hilti H8*75 @600mm centers;
checkpoint | Stud type and fixing as per Rondo Design table,Nominal 20mm deflection gap on top
section | Any additional photos, comments and observations
checkpoint | additional photos
section | Handover
checkpoint | Main Contractor Handover: Service 1st fix complete, ready for lining
date | Handover date:
holdpoint | Request main contractor signoff
section | Council Preline Inspection and Handover
checkpoint | Council preline inspection
date | Inspection date:
checkpoint | Handover to GIB Contractor for lining
date | Handover Date
checklist | QA-FRR timber packing to steel plate
section | Details
checkpoint | Handover from main contractor
tickbox | Area accessible
tickbox | Structure ready
tickbox | Intumescent painting ready
date | Handover date:
section | FRR Timber Packing Installation
checkpoint | H1.2 SG8 timber nail to steel plate with Hilti X-U 16 @600mm max center
checkpoint | DPC seperation between timber and structure
checkpoint | 2 layers of 13mm fyreline installed as per GIB manual
checkpoint | Edge distance requirement for ryanbatt installation: 90min 100mm;60min 50mm
checkpoint | Stopping applied, fire sealant (Hilti CP606）applied to perimeter of GIB.
Section | Any additional photos, comments and observations
checkpoint | additional photos
section | Handover
checkpoint | Handed over the area to main contractor
date | Handover date:

## INDEX
Seascape_LBY_Basebuild_QA Check List
QA Item Breakdown | Checklist No. | Note
QA-Fire Rated Timber Bulkhead Framing | Checklist-01
QA-Fire Rated Timber Bulkhead lining | Checklist-02
QA-Fire Rated Steel Stud Bulkhead Framing | Checklist-03
QA-Fire Rated Steel Stud Bulkhead Lining | Checklist-04
QA-Steel Stud Internal Wall framing and insulation | Checklist-05
QA-Fire Rated Bulkhead for Steel penetration to Korok Wall/Promatect | Checklist-06
QA-Fire Sealant Infill to Comflor Groove | Checklist-07
QA-Fire Separation PFP Infill to Façade | Checklist-08
QA-GIB Plasterboard Wall Lining | Checklist-09
QA-Fibrecement Board Wall Lining | Checklist-10
QA-Ceiling Grid and insulation | Checklist-11
QA-Ceiling Lining | Checklist-12
QA-Building Wrap | Checklist-13
QA-Promatect Framing and lining | Checklist-14
QA-Steel Stud External Framing and bulkhead | Checklist-15
QA-FRR timber packing to steel plate | Checklist-16