## ITP Test Sheet
Inspection & Test Plan Pukekohe Train Station Upgrade |  |  |  | PROJECT: | Pukekohe Train Station Upgrade |  |  |  | DISCIPLINE |  | Security
|  |  |  | PROJECT LOCATION: | Pukekohe |  |  |  | SUB-CONTRACTOR |  | CSLI
|  |  |  | JOB NO# | 401987
|  |  | ACTION | SIGNATORY |  | ROLE |  |  | PERSON(S) RESPONSIBLE
|  | W | WITNESS | Requiring Main Contractor Representative |  | Project Engineer |  |  | Downer
|  | H | HOLD POINT | Requiring Sub-contractor Representative |  | Sub-Contractor Representative |  |  | Cabling Contractor
|  | M | MONITOR | Requiring Auckland Transport Representative |  | Sub-Contractor Representative |  |  | AT Rep
|  |  |  | Requiring CSLI On-Site Representative |  | Sub-Contractor Representative |  |  | Cristiano Silveira
|  |  |  | Requiring CSLI Project Manager Representative |  | CSLI Project Manager |  |  | Wiremu Thompson
NO: | INSPECTION / TEST POINT | ACTION (W, M, H) | CONFORMANCE CRITERIA (WHATS REQUIRED) | FREQUENCY | INSPECTION / TEST METHOD | VERIFICATION RECORDS | AS/NZS STANDARD | SIGNATORY | DATE(S) | SIGNATURE
PRE-INSTALLATION
1 | Device Product Data Sheets | W | Recommended CCTV Data Sheets as Per Provided Drawings | As Required | Visual Inspection | Manufacturers Data Sheet | 3000
2 | Provided Security Drawings | M | As Per Provided Construction Drawings By Downer Construction | As Required | Visual Inspection | Design drawings
3 | Device FAT Testing - Off Site | W | Device Testing and Pre-Setup | As Required | Visual Inspection | CSLI-CCTV-FAT CSLI-EHP-FAT CSLI-PID-FAT
CABLE INSTALLATION
1 | Sub-Contractor Installed Cabling | H | Point to Point testing completed by cabling contractor confirmimg cabling is sufficient to use. | Always | Cable Testing | Design drawings | 3000, 3008, 3017, 1660
CCTV INSTALLATION
1 | Completed Asset data sheets | W | Complete asset data sheets for each camera and send through to the networks team for IP Address assignment | Pre-Commissioning | Visual Inspection | AT Asset data sheet
2 | Network switch port allocation | H | Confirm with networks team on which device has been assigned to each network port | Pre-Commissioning | Visual Inspection
3 | Installation of cameras at provided locations | M | Correct camera models are installed in the locations as per provided design drawings | Always | Visual Inspection FAT reported viewed | Design drawings | 3000, 3008, 3017, 62676
4 | Allignment of camera FOV as per coordination with AT rep | H | Field Of Views to be coordinated with both AT/AOR to capture required images | Always | Visual Inspection Network connection testing
5 | Installation Verification | W | Onsite SAT Test to be completed and signed | Post Commissioning | Visual Inspection | CSLI-CCTV-SAT
EMERGENCY HELP POINT INSTALLATION
1 | Completed Asset data sheets | W | Complete asset data sheets for each EHP and send through to the networks team for IP Address assignment | Pre-Commissioning | Visual Inspection | AT Asset data sheet
2 | Network switch port allocation | H | Confirm with networks team on which device has been assigned to each network port | Pre-Commissioning | Visual Inspection
3 | Installation of EHPs in provided locations | M | Installation as per provided design drawings EHP is installed using correct concrete fixtures and is sturdy | Always | Visual Inspection FAT Report Sighted | Design drawings | 3000, 3008 & 3017
4 | VOIP between Service desk and onsite unit | H | Confirm with Service desk operator that both Mic and Speaker are operating correctly | Always | Communication Testing Network connection testing
5 | Installation Verification | W | Onsite SAT Test to be completed and signed | Post Commissioning | Visual Inspection | CSLI-EHP-SAT
PUBLIC INFORMATION DISPLAY INSTALLATION
1 | Completed Asset data sheets | W | Complete asset data sheets for each PID and send through to the networks team for IP Address assignment | Pre-Commissioning | Visual Inspection | AT Asset data sheet
2 | Network switch port allocation | H | Confirm with networks team on which device has been assigned to each network port | Pre-Commissioning | Visual Inspection
3 | Installation of PIDs in provided locations | M | Installation as per provided design drawings PID is installed using correct fixtures and is sturdy | Always | Visual Inspection Electrical Testing FAT Report Sighted | Design drawings | 3000, 3008 & 3017
4 | Test connection to Playlist system | H | Playlist is able to send communications to PID PC Time clock and schedule updates with current state | Always | Communication Testing Network connection testing
5 | Installation Verification | W | Onsite SAT Test to be completed and signed | Post Commissioning | Visual Inspection | CSLI-PID-SAT
COMMISSIONING
1 | CCTV System | W | Wittness completed for camera location and operation | Post Commissioning | Visual Inspections | CSLI-CCTV-FAT CSLI-CCTV-SAT | 3000, 3017
2 | EHP System | W | Wittness completed for camera location and operation | Post Commissioning | Visual Inspections | CSLI-EHP-FAT CSLI-EHP-SAT | 3000, 3017
3 | PID System | W | Wittness completed for camera location and operation | Post Commissioning | Visual Inspections Electrical Tests | CSLI-PID-FAT CSLI-PID-SAT | 3000, 3017
HANDOVER
1 | QA and checksheet documentation | M | Complete and submit the following documents - Commissioning and testing Checksheets - Compliance certificates and producer statements - Schedule of Test Results for the installation - Assets updated in AT Device management System | Post Commissioning | Visual inspection | Checksheets, ITPs, electrical test certificates are complete and filed within the O&M manual
2 | Final inspection with Client | M | Client to review installation is completed as per other sections of this ITP | Post Commissioning | Visual Inspection | ITP | N/A
Comments:
Accepted By :_____________________________________________ |  |  | Sub-contractor | Accepted By :_____________________________________________ | Project Manager |  | Accepted By :_____________________________________________ |  |  |  | Quality Manager
Signature:_____________________________ |  |  |  | Signature:________________________________________________ |  |  | Signature:________________________________________________