## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
276b743e-f2a1-4ba1-a5e3-e95412e91c86 | checklist | Civil / Electrical Construction |  | Civil / Electrical Construction
e4c2d24c-0938-45b2-add4-999b1f58cac2 | section | Site Works
099b4265-b0d5-4827-96a6-30ea1caa1cc7 | checkpoint | High-Vis PPE worn on site at all times
5c13b5a8-5561-4d8c-894c-a57da984efed | checkpoint | Pre-works photos
4923eaca-86e1-439a-9c4a-0c3f92c37b77 | checkpoint | Underground Service location
9bea0ce4-304b-50bf-aac1-fdd9bb99242d | note | Completed prior to breaking ground
93051b5b-d199-4b2b-ab97-05867342b62d | checkpoint | Location and orientation confirmed for: ( PID/SVL/VMS/Help phone/Beacon)– EVA, Free Standing Display (FSD), Charger and MSB/s
3c923ff1-e1df-5979-b0d6-7e20aa35d862 | dropdown | select | PID, SVL, VMS, Help Phone, Beacon
131aa7b7-fd27-4f1e-a725-fffacc32f53b | checkpoint | Foundation dimensions confirmed based on Site Design and PS1
0632798e-dbb8-5c47-bd5a-3f1c2a308254 | note | Please ensure concrete footing is level with curb/grade and square edge
6cb90e5d-69f8-50c0-8ace-35b311a6ae05 | note | Attach PS1 design showing installation depths etc
e1a37814-3f30-5f0e-bd19-fb11ecc79269 | note | Foot dimensions and depth/thickness:
0e47b002-776a-425e-bd6a-abdff0d97ee1 | checkpoint | Traffic management in place
545d2513-d4fd-4d0a-9a10-9d3c942ab7a0 | checkpoint | Sediment control in place
0053927a-8220-4cf8-b92b-21e4bc28d772 | checkpoint | Excavation Completion / Subgrade Condition photos and soil strengths
57fb732f-4ca1-4bfb-bb63-a500bca465ca | checkpoint | Shear vane required to comply with confirmation of soil bearing capacity (150kPa), as per PS1 design documentation
126dcf12-1479-4d59-9b84-6d295886378b | checkpoint | Hardfill Condition photos
c4d1b553-c3bb-4c28-bd39-1b929c930b20 | signoff | HOLD POINT
9b4c70a2-673e-411e-828e-f8f7d01426ed | checkpoint | Concrete boxing area and level suitable for pedestrians?
0652c3bc-115b-5c0a-85a0-e9a9ec9694e4 | textbox | Earth electrode -
627116b5-ab2d-5b28-8bbc-529ba1e0ac1c | note | Concrete to be poured only once checked against site design from Project Manager
225c3a16-2239-4bb7-954c-381625d34b92 | signoff | Send to Project Manager
8bf68b6c-ec2d-4f06-bda6-e767ad18b363 | checkpoint | Meter/switchboard/MEN and equipment checked prior to livening?
a4e7335a-8347-5e2f-9108-77d4b26b697d | note | MSB circuit breakers and tails checked prior to meter installation. MSB code locks equipped (Code: )
7041a112-3101-40cb-9f64-a7a6fc0ac96c | checkpoint | Book in VIPID for delivery and install of equipment
8e3d1d98-d96a-5897-8401-fdc95e6467a6 | note | Ensure the Hiab has all the necessary lifting equipment, and that hardware is wrapped prior to delivery. Return wrapping and mounting pallets.
7d2718dc-e840-4b10-b7b2-eabd85f2a000 | checkpoint | EVA / Free Standing Display (FSD) installed, and verticality confirmed
b72cf385-b5cc-4bf8-b33e-867ff80ac387 | checkpoint | Parking bay paint marking completed
993f3e6d-e5ff-42b5-8b27-717a041f3e28 | checkpoint | Reinstatement, clean up and post-works completion photos.
1d2dcceb-5e85-57c1-81f4-aab0abe992b0 | note | Please ensure site is free from concrete in footpath/Berm/parking bay
da99e2f0-e22f-47c5-a971-77d29e0edd74 | section | Post Construction (Electrical) Notes Sign-off Initials
9df94eac-b954-4b85-ad3c-e5285a4b9f1a | checkpoint | Electrical Certificate of Compliance / Electrical Safety Certificate
d92b2bb5-b7d3-5edd-a0af-cb18c33d2f2e | note | Rev 1.0 ¦ 10.08.2023
9d3c0afd-8a39-49e6-8c7c-bea6af99d0f4 | checkpoint | Livening Agent Electrical Safety Certificate & ROI
068ef00a-f0a1-4b8c-9e68-f8d2503f1731 | checkpoint | Final Site Walkover
45748a11-17a6-46f6-81eb-c20a209b2a2f | checkpoint | Application for Final Completion
497b265f-16a3-47a2-a964-65daa43625e9 | checkpoint-no-value | Site Details
78f739ff-e012-51fc-b7a0-e54903a4e60a | textbox | Site
ac71085e-c394-56ab-914f-c409ca2114e1 | textbox | Product installed/commissioned
703550e7-f957-5480-acae-f2783831e0e4 | textbox | Commissioning Date
c2a0015d-f7a3-46b8-96fd-66ea6ad7be10 | checkpoint | Signoff - For and on behalf of the Contractor
efac0c2e-fd9a-4610-bd7f-64ccf0190424 | signoff | Signoff
8c1cf5ae-9e01-44bd-8978-1d466d62f697 | checkpoint | Signoff - For and on behalf of CSLI
80e183dc-49d7-49cf-bd67-ea0e24cd9710 | signoff | Signoff
4ed76444-fa5a-45e3-ba5d-9a3b8f03b49d | checklist | Pre-Construction Requirement |  | Pre-Construction Requirement
de16aeac-dbf3-441d-aa1a-15981c887b5d | section | Pre-site work items Notes Sign-off Initials
ca7722b4-835d-4fbb-a65e-ebbcf8f5f6e1 | checkpoint | Dial Before You Dig (DBYD) and On Site-Service location
97d4f264-7c32-5c76-974e-2611ee1b359b | note | Notification to necessary stakeholders/service owners as necessary), On-site service clearance, review of archaeological site info (NZ Archaeological Association), review of site contamination history and notification to Auckland council as necessary. Note this process should be completed immediately following project confirmation so that we have enough lead in time to ensure
04137d05-3a0f-4abb-8ff0-08fe9a16ad7e | checkpoint | EDB (Vector – Auckland Specific) Contractor site meeting
0837acc1-a7d5-598a-a2b4-9b0a59ea879b | note | Meeting on-site to discuss EDB contractors’ requirements for civil enabling works and traffic management. Apply for close approach consent with Vector (if required).
3936d673-7fc7-49e4-8c44-289427fbb012 | checkpoint | Site Layout Design
124bce63-7b5a-58d4-9593-8f10166e4992 | note | Draft of CAD design for site layout with respect to the ( PID/SVL/VMS/Help phone/Beacon)– installation PS1 foundation design document
a0015373-bef5-5419-af88-40995930123a | dropdown | Select (if neededd) | PID, SVL, VMS, Help Phone, Beacon
dd420d6d-0c69-4411-bca2-4464d177afa3 | checkpoint | Book in Livening agent
24c14fa6-a4e9-5bb7-b5ee-8c4cca02c055 | note | Correspond with livening agent on livening date (post Vector works completion) and book inspection prior to works.
946ea92e-f262-4c40-8b8f-6c90970de4e6 | checkpoint | Site Specific Safety Plan
7ce648ec-9c93-55d7-8098-366b807886ca | textbox | Details of Plan (if required)
c94c9f66-db52-4094-8648-917f0108672e | checkpoint | Site Work Method Statement - Electrical Work
403a894c-2e4a-56aa-bb0c-7ec29f1256b0 | note | Electrical Work, Excavation, ( PID/SVL/VMS/Help phone/Beacon)– Installation / Lifting Plan, as necessary
9d1506a7-0fb9-44ad-bb59-edd31c5c2a5c | section | Assembly / Pre-Commissioning
fae8b4f1-40ce-455a-a50c-0618afc2fc37 | checkpoint | Assembly Complete
caf5a6fd-7158-5b25-ad09-ec3d26bb73b4 | note | Please inform CSLI operations team of assembly dates prior /
818dd3cc-3c12-4ff5-adf1-a7fe92fa9a0c | checkpoint | Completion and Submission of Commissioning Documentation
3db48893-d664-5287-82ca-c4f277886e13 | note | Pre-Commissioning Checklist, Data required for commissioning, Commissioning Checklist
60d38b56-78e6-42db-bf9e-1619eafe649d | checkpoint | Pre-commissioning Complete
a3098335-8fc0-528d-9202-d9f1a03e1001 | note | Take good site photos- Pre – during - completion. : Ensure Photos have Road Markings/Key markers. : Photos of Trench depth- ducting and Earth Rod
3aa6bb22-afbc-4203-9112-8216c2e58b8e | checkpoint | Please prepare the following: Fill in commissioning steps
7d36be45-8b17-5892-b8fa-ccc4d8df3d86 | button | As-builts-drawing s+ dimensions, to include ICP# for Electrical supply. | Yes, No
0c5665b6-3027-5671-a876-1bfb2c346f68 | button | Ramm etc- to include ASSET Data Sheet | Yes, No
3d7108e4-d6e6-5c2e-a9ae-3b2764189205 | button | Electrical Testing to complete COC | Yes, No
3ec2e177-f13e-5051-aa68-1741c23fa9dc | button | Earth Electrode site review | Yes, No
4efdd9cc-a82d-5dfe-95c8-092a308e18bc | button | Arrange Electrical Inspector for livening site. | Yes, No
ee81d957-840b-5248-923d-7e37068400a1 | button | Check PID information is correctly Identified at Stop | Yes, No
be16ff01-2fdc-5728-b561-a7669aa4f1e3 | button | Check PID Push Button and Speaker operate. | Yes, No
86d748f8-cce1-55a0-a157-4c70468e63a5 | button | Confirm PID button is 1m from FL ( finished level) | Yes, No
120c16f6-27db-4214-b6b2-44203d26f70b | checklist | QA - PID Poles CSLI W810 |  | QA - PID Poles CSLI W810
3ce89cf7-5a5d-4432-b6b1-9f24abe6a413 | section | Service Location and Pole Installation Position
5f7ec1c9-fdcd-48b3-b45e-ad76fd8cc52b | checkpoint | 5 working days (min) prior to civil installation, complete service location/Before-U Digs on site. Take photos of the mark-outs and site.
51230721-96ae-4935-9940-9f60df18202f | checkpoint | Based on mark-outs sub-contractor/CSLi civil crew to confirm that pole can be installed in the proposed location.
2e27408c-1fdf-5d94-a467-d31f0472e639 | note | If proposed pole location is not achievable, PM must be notified, and an alternative pole location provided by the team that was on site. PM will engage AT and seek approval for the revised pole location prior to civil installation.
d0f24f25-20a0-4dcc-b106-dfa9aae20116 | section | Site
80378e99-2209-4303-bf3b-6bbb8d060326 | checkpoint | Photos of the site before works commence.
dc1aa390-3816-46c6-b0d0-c633d3686b69 | checkpoint | Photos of the existing sign prior to being removed.
0d5a4fed-a319-47b1-9bda-8ef602502fc6 | checkpoint | Photos of the power connection point
7e8ac0ab-39e0-5cf1-81ba-48b6c59273e3 | note | Include asset number if possible
bb5961c1-a3bd-44bf-9ef6-118e479352a7 | section | Pole installation
cbbd53df-1080-4586-92bc-4e2917d12b2d | checkpoint | Full depth of pole foundation (with measuring tape) – 900mm
15f5fc2e-1c4c-40fd-8321-27986e4abca5 | checkpoint | Full depth of pole embedment (with measuring tape) – 650mm
cd315083-5fe4-49cc-8aa4-c82a3536cbcf | checkpoint | Width of foundation – 400mm
431b4247-c693-4b1f-b081-5760467ef70f | checkpoint | Pole centred in the foundation (front to back and side to side)
73e61faf-6e9d-4a12-920b-e9d5a10f6664 | checkpoint | Full depth of concrete filled in foundation (800mm, 100mm from ground level)
42e2823d-e24e-4633-b968-8d5e437ead20 | checkpoint | Height of push button (with measuring tape) – 900-1000mm
7d73fae4-41ec-4d52-a67e-8be943fd96bd | checkpoint | Pole vertical (with level)
de9e6a08-f444-44ad-b5a3-7f5c345d96d1 | checkpoint | Power Pillar vertical (with level)
335d62f4-a3c9-4c26-8262-8b07d3d183cc | checkpoint | Earth-rod position
552b7254-ac20-4649-be49-c83ba0580a31 | section | Trench/Thrust
a997aaf3-e2f2-429c-ac60-1339686c6783 | checkpoint-no-value | Details
a0f55fc7-42e2-5132-b014-220fc3bd2974 | textbox | Trench depth
e73c532a-abec-4d3b-a104-bdadb6a2d9b7 | checkpoint | Trench fill including danger tape
471d4fe1-6ba8-4aca-862e-7728ea05bfd8 | checkpoint | Duct exiting PID pole
4c93ad51-6d0e-4d96-8270-a6ea67d0664a | checkpoint | Duct entering Power Pillar (either side if applicable)
6d4eb76f-c29a-46c2-91d9-e4e3ba9e2ecd | checkpoint | Duct at SL or TUD
60699e8b-0aad-406d-83f0-fe38c7635950 | checkpoint | Any joint in the ducting
7749c071-eec2-4c7a-a26e-5b7423181ea8 | checkpoint | Draw wires
c027693a-d262-4f76-94b6-31088c378c67 | section | As-build Drawing
1e5413af-d5b5-4a50-b0c5-b76a95113273 | checkpoint | Location of pole
4d347b18-8139-53c8-93c0-df1fe636db79 | note | With dimensions off at least 2 reference points, e.g.: face-of-curb, bus shelter, streetlight…
fac23581-646d-53a0-a0f7-5eb2a7bdb377 | dropdown | Pole flag direction | North, South, East, West
39224ced-27b8-4323-8492-19dd9777a889 | checkpoint | Power pillar and earth rod
ab0f8339-6747-4991-8f76-11fbd9e726f4 | checkpoint | Concrete apron with dimensions
e9189dde-4358-4e65-b116-393520ffa543 | checkpoint | Trench path (dimensions off reference points, 2 points preferred at a change in direction)
ff578b37-c572-5896-813e-26085dc02c7c | textbox | Depth of trench/thrust
27da641a-efcf-541b-b5d4-009f983863bd | textbox | Total length of trench/thrust
5a1de6b8-22e4-4b75-b90b-87549d6ce7b6 | section | Variations Photos
660b2d5d-8a4b-44d9-8c5c-75be33454d62 | checkpoint | Photos of anything that has caused delays
492d9928-f839-42bc-8340-1bd180f02a7a | checkpoint | Photos of anything that has caused additional material
e8ba1d6f-61ed-41ef-8d79-e5001ded3144 | checkpoint | Photos of anything that has caused a change in plan