## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Pukekohe Train Station Upgrade - Security | itp |  |  |  |  | ITP - Pukekohe Train Station Upgrade - Security
section | PRE-INSTALLATION
checkpoint | 1 - Device Product Data Sheets
label | ACTION (W, M, H) - W
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Recommended CCTV Data Sheets as Per Provided Drawings
label | FREQUENCY - As Required
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS - Manufacturers Data Sheet
label | AS/NZS STANDARD - 3000
checkpoint | 2 - Provided Security Drawings
label | ACTION (W, M, H) - M
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - As Per Provided Construction Drawings By Downer Construction
label | FREQUENCY - As Required
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS - Design drawings
label | AS/NZS STANDARD -
checkpoint | 3 - Device FAT Testing - Off Site
label | ACTION (W, M, H) - W
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Device Testing and Pre-Setup
label | FREQUENCY - As Required
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS - CSLI-CCTV-FAT, CSLI-EHP-FAT, CSLI-PID-FAT
label | AS/NZS STANDARD -
section | CABLE INSTALLATION
checkpoint | 1 - Sub-Contractor Installed Cabling
label | ACTION (W, M, H) - H
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Point to Point testing completed by cabling contractor confirmimg cabling is sufficient to use.
label | FREQUENCY - Always
label | INSPECTION / TEST METHOD - Cable Testing
label | VERIFICATION RECORDS - Design drawings
label | AS/NZS STANDARD - 3000, 3008, 3017, 1660
holdpoint | HOLD POINT
section | CCTV INSTALLATION
checkpoint | 1 - Completed Asset data sheets
label | ACTION (W, M, H) - W
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete asset data sheets for each camera and send through to the networks team for IP Address assignment
label | FREQUENCY - Pre-Commissioning
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS - AT Asset data sheet
label | AS/NZS STANDARD -
checkpoint | 2 - Network switch port allocation
label | ACTION (W, M, H) - H
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with networks team on which device has been assigned to each network port
label | FREQUENCY - Pre-Commissioning
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS -
label | AS/NZS STANDARD -
holdpoint | HOLD POINT
checkpoint | 3 - Installation of cameras at provided locations
label | ACTION (W, M, H) - M
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Correct camera models are installed in the locations as per provided design drawings
label | FREQUENCY - Always
label | INSPECTION / TEST METHOD - Visual Inspection, FAT reported viewed
label | VERIFICATION RECORDS - Design drawings
label | AS/NZS STANDARD - 3000, 3008, 3017, 62676
checkpoint | 4 - Allignment of camera FOV as per coordination with AT rep
label | ACTION (W, M, H) - H
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Field Of Views to be coordinated with both AT/AOR to capture required images
label | FREQUENCY - Always
label | INSPECTION / TEST METHOD - Visual Inspection, Network connection testing
label | VERIFICATION RECORDS -
label | AS/NZS STANDARD -
holdpoint | HOLD POINT
checkpoint | 5 - Installation Verification
label | ACTION (W, M, H) - W
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Onsite SAT Test to be completed and signed
label | FREQUENCY - Post Commissioning
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS - CSLI-CCTV-SAT
label | AS/NZS STANDARD -
section | EMERGENCY HELP POINT INSTALLATION
checkpoint | 1 - Completed Asset data sheets
label | ACTION (W, M, H) - W
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete asset data sheets for each EHP and send through to the networks team for IP Address assignment
label | FREQUENCY - Pre-Commissioning
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS - AT Asset data sheet
label | AS/NZS STANDARD -
checkpoint | 2 - Network switch port allocation
label | ACTION (W, M, H) - H
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with networks team on which device has been assigned to each network port
label | FREQUENCY - Pre-Commissioning
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS -
label | AS/NZS STANDARD -
holdpoint | HOLD POINT
checkpoint | 3 - Installation of EHPs in provided locations
label | ACTION (W, M, H) - M
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Installation as per provided design drawings. EHP is installed using correct concrete fixtures and is sturdy.
label | FREQUENCY - Always
label | INSPECTION / TEST METHOD - Visual Inspection, FAT Report Sighted
label | VERIFICATION RECORDS - Design drawings
label | AS/NZS STANDARD - 3000, 3008 & 3017
checkpoint | 4 - VOIP between Service desk and onsite unit
label | ACTION (W, M, H) - H
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with Service desk operator that both Mic and Speaker are operating correctly
label | FREQUENCY - Always
label | INSPECTION / TEST METHOD - Communication Testing, Network connection testing
label | VERIFICATION RECORDS -
label | AS/NZS STANDARD -
holdpoint | HOLD POINT
checkpoint | 5 - Installation Verification
label | ACTION (W, M, H) - W
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Onsite SAT Test to be completed and signed
label | FREQUENCY - Post Commissioning
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS - CSLI-EHP-SAT
label | AS/NZS STANDARD -
section | PUBLIC INFORMATION DISPLAY INSTALLATION
checkpoint | 1 - Completed Asset data sheets
label | ACTION (W, M, H) - W
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete asset data sheets for each PID and send through to the networks team for IP Address assignment
label | FREQUENCY - Pre-Commissioning
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS - AT Asset data sheet
label | AS/NZS STANDARD -
checkpoint | 2 - Network switch port allocation
label | ACTION (W, M, H) - H
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with networks team on which device has been assigned to each network port
label | FREQUENCY - Pre-Commissioning
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS -
label | AS/NZS STANDARD -
holdpoint | HOLD POINT
checkpoint | 3 - Installation of PIDs in provided locations
label | ACTION (W, M, H) - M
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Installation as per provided design drawings. PID is installed using correct fixtures and is sturdy.
label | FREQUENCY - Always
label | INSPECTION / TEST METHOD - Visual Inspection, Electrical Testing, FAT Report Sighted
label | VERIFICATION RECORDS - Design drawings
label | AS/NZS STANDARD - 3000, 3008 & 3017
checkpoint | 4 - Test connection to Playlist system
label | ACTION (W, M, H) - H
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Playlist is able to send communications to PID PC. Time clock and schedule updates with current state.
label | FREQUENCY - Always
label | INSPECTION / TEST METHOD - Communication Testing, Network connection testing
label | VERIFICATION RECORDS -
label | AS/NZS STANDARD -
holdpoint | HOLD POINT
checkpoint | 5 - Installation Verification
label | ACTION (W, M, H) - W
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Onsite SAT Test to be completed and signed
label | FREQUENCY - Post Commissioning
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS - CSLI-PID-SAT
label | AS/NZS STANDARD -
section | COMMISSIONING
checkpoint | 1 - CCTV System
label | ACTION (W, M, H) - W
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Wittness completed for camera location and operation
label | FREQUENCY - Post Commissioning
label | INSPECTION / TEST METHOD - Visual Inspections
label | VERIFICATION RECORDS - CSLI-CCTV-FAT, CSLI-CCTV-SAT
label | AS/NZS STANDARD - 3000, 3017
checkpoint | 2 - EHP System
label | ACTION (W, M, H) - W
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Wittness completed for camera location and operation
label | FREQUENCY - Post Commissioning
label | INSPECTION / TEST METHOD - Visual Inspections
label | VERIFICATION RECORDS - CSLI-EHP-FAT, CSLI-EHP-SAT
label | AS/NZS STANDARD - 3000, 3017
checkpoint | 3 - PID System
label | ACTION (W, M, H) - W
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Wittness completed for camera location and operation
label | FREQUENCY - Post Commissioning
label | INSPECTION / TEST METHOD - Visual Inspections, Electrical Tests
label | VERIFICATION RECORDS - CSLI-PID-FAT, CSLI-PID-SAT
label | AS/NZS STANDARD - 3000, 3017
section | HANDOVER
checkpoint | 1 - QA and checksheet documentation
label | ACTION (W, M, H) - M
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete and submit the following documents
label | ○ Commissioning and testing Checksheets
label | ○ Compliance certificates and producer statements
label | ○ Schedule of Test Results for the installation
label | ○ Assets updated in AT Device management System
label | FREQUENCY - Post Commissioning
label | INSPECTION / TEST METHOD - Visual inspection
label | VERIFICATION RECORDS - Checksheets, ITPs, electrical test certificates are complete and filed within the O&M manual
label | AS/NZS STANDARD -
checkpoint | 2 - Final inspection with Client
label | ACTION (W, M, H) - M
label | CONFORMANCE CRITERIA (WHATS REQUIRED) - Client to review installation is completed as per other sections of this ITP
label | FREQUENCY - Post Commissioning
label | INSPECTION / TEST METHOD - Visual Inspection
label | VERIFICATION RECORDS - ITP
label | AS/NZS STANDARD - N/A