## Shoulder Construction
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Tirau to Waiouru Rehabilitation Acceleration Programe (TWRAP) Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA M/03, M4 S |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Designer | Eng. Rep / NZTA | Contractor | Date
1.0. AGGREGATE ACCEPTANCE TESTING
1.01 | AP65 | Crushing Resistance | H | 1 Test per material per source | NZS4407:3.10 | > 100KN | IANZ report | Contractor |  | A | I | R | dd/mm/yy
1.02 |  | Particle size distribution | H | 1 Test per material per source | NZS4407:3.8.1 | As per NZTA M03 Specfication | IANZ report | Contractor |  | A | I | R | dd/mm/yy
1.03 | NZTA M04 | Crushing Resistance |  | 1 Test per material per source | NZS4407:2.4.7 | > 130KN | IANZ report | Contractor |  | A | I | R | dd/mm/yy
1.04 |  | Particle size distribution | H | 1 Test per material per source | NZS4407:2.4.7 | As per NZTA M04 Specfication | IANZ report | Contractor |  | A | I | R | dd/mm/yy
2.0. CONSTUCTION
2.01 | Earthworks | Cut to Waste Insitu Shoulder | M | As per design drawings | Visual / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.02 | AP65 Placement | Gap 65 Placed in Accordance with Design and Survey | M | As per design drawings | Visual / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.03 | AP65 Compaction | Compact in Layers no greater than 200mm. | H | 1 MDD Test per 50m | Nuclear Densometer MDD Test | 95% MDD Achieved | IANZ report | Contractor |  | I | A | R | dd/mm/yy
2.04 | M4 Placement | M4 Placed in Accordance with Design Drawing and Survey | M | As per design drawings | Visual / Photo | Minimum Width 300mm. | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.05 | M4 Compaction | Compact in Layers no greater than 150mm. | H | 1MDD Test per 50m | Nuclear Densometer MDD Test | 98% MDD Achieved | IANZ report | Contractor |  | I | A | R | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.