## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Kerb and Channel | itp |  |  |  |  | ITP - Kerb and Channel Rev 0
section | 1.0. AGGREGATE AND CONCRETE TESTING
checkpoint | 1.01 - Concrete
label | Detail of Activity / Test - Concrete Supply
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 Test per material per source
label | Inspection / Test method - NZS4407:3.10
label | Acceptance Criteria - 20Mpa Minmum Strength after 28 Day
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - NZTA M04
label | Detail of Activity / Test - Crushing Resistance
label | Minimum Test Frequency - 1 Test per material per source
label | Inspection / Test method - NZS4407:2.4.7
label | Acceptance Criteria - > 130KN
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.03 - NZTA M04
label | Detail of Activity / Test - Particle size distribution
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 Test per material per source
label | Inspection / Test method - NZS4407:2.4.7
label | Acceptance Criteria - As per NZTA M04 Specfication
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. CONSTUCTION
checkpoint | 2.01 - Earthworks
label | Detail of Activity / Test - Cut to Waste Existing Kerb and Channel
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - As per IFC drawings
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - Prepare Subgrade
label | Detail of Activity / Test - Subgrade further compacted or excavate the unsuitable material and replace
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Test Every 10m
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Clegg Result >15
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - M4 Palcement
label | Detail of Activity / Test - Compacted layer of GAP40 as required to adjust height of new K&C shall be placed over subgrade. (75mm Min)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Test Every 10m
label | Inspection / Test method - Clegg Test
label | Acceptance Criteria - Clegg Result >30
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Kerb and Channel Placement, Line and Level
label | Detail of Activity / Test - Construction of Kerb as per profile setout in IFC drawing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Throughout the activity
label | Inspection / Test method - Meausre off Survey Pegs
label | Acceptance Criteria - Check Sheet of Survey Pegs Versus Actual
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.05 - Contraction/Expansion Joints
label | Detail of Activity / Test - Maximum spacing of 3m and minimum 50mm deep
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Once
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Measure Cut Spacings
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.06 - Curing of Concrete
label | Detail of Activity / Test - Curing period shall not be less than 1 day OR 36 hours
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Throughout the activity
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Visual Inspection
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature