## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
ITP 0001 - Clearing & Grubbing
| Scope |  |  | ITP 0001 - Clearing & Grubbing
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0001 - Clearing & Grubbing
|  | Area 2 | dynamic | Area 2 | ITP 0001 - Clearing & Grubbing
Columns
|  | 1.1 Induction |  | 1.1 Induction
|  | 1.2 Safety measures are in place, SWMS undertaken |  | 1.2 Safety measures are in place, SWMS undertaken
|  | 1.3 Check that current revision drawings are being used |  | 1.3 Check that current revision drawings are being used
|  | 1.4 Confirm understanding of current EMP related to the work area & that all prescribed environmental controls are in place |  | 1.4 Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
|  | 1.5 Excavation Permit issued |  | 1.5 Excavation Permit issued
|  | 1.6 Traffic Management (When required) |  | 1.6 Traffic Management (When required)
|  | 1.7 Vegetation Removal Permit (if required) |  | 1.7 Vegetation Removal Permit (if required)
|  | 1.8 Extent of Clearing & Grubbing |  | 1.8 Extent of Clearing and Grubbing
|  | 2.1 Identification of Cultural Heritage sites & areas of Cultural Significance |  | 2.1 Identification of Cultural Heritage sites and areas of Cultural Significance
|  | 2.2 Stockpiling |  | 2.2 Stockpiling
|  | 2.3 Stripping of topsoil |  | 2.3 Stripping of topsoil
|  | 2.4 Removal of abandoned services |  | 2.4 Removal of abandoned services
|  | 2.5 Clearing of Trees & Vegetation |  | 2.5 Clearing of Trees and Vegetation
|  | 2.6 Clearing Process |  | 2.6 Clearing Process
|  | 2.7 Grubbing of vegetation |  | 2.7 Grubbing of vegetation
|  | 3.1 Disposal of vegetation |  | 3.1 Disposal of vegetation
|  | 3.2 Topsoil Placement |  | 3.2 Topsoil Placement
|  | Final Inspection |  | Final Inspection
ITP 0006 - Excavation, Fill With Type B & Subgrade Prep
| Scope |  |  | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep
|  | Area 2 | dynamic | Area 2 | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used
|  | 1.2 - Excavation Permit issued |  | 1.2 - Excavation Permit issued
|  | 1.3 - Re-Use of insitu material |  | 1.3 - Re-Use of insitu material
|  | 1.4 - Type B Material Approval |  | 1.4 - Type B Material Approval
|  | 1.4 - Type B Material Approval - Teambinder Approval number | Teambinder Approval number | 1.4 - Type B Material Approval
|  | 2.1 - Survey set-out |  | 2.1 - Survey set-out
|  | 2.2 - Ground water |  | 2.2 - Ground water
|  | 2.3 - Acceptance of Rock Subgrade (when applicable) |  | 2.3 - Acceptance of Rock Subgrade (when applicable)
|  | 2.4 - Proof Roll - Cut Floor |  | 2.4 - Proof Roll - Cut Floor
|  | 2.5 - Compaction Testing |  | 2.5 - Compaction Testing
|  | 2.6 - Survey Pickup |  | 2.6 - Survey Pickup
|  | 3.1 - Placement of Fill |  | 3.1 - Placement of Fill
|  | 3.2 - Preparation of final surface - Subgrade |  | 3.2 - Preparation of final surface - Subgrade
|  | 3.3 - Trimming & level conformity |  | 3.3 - Trimming and level conformity
|  | 3.4 - Proof Roll - Top of fill layer |  | 3.4 - Proof Roll - Top of fill layer
|  | 3.5 - Post-compaction Testing |  | 3.5 - Post-compaction Testing
|  | 3.6 - Survey Pickup - Top of subgrade |  | 3.6 - Survey Pickup - Top of subgrade
|  | 4.1 - Survey As-Built |  | 4.1 - Survey As-Built
|  | 4.2 - Non-conformance Closure |  | 4.2 - Non-conformance Closure
|  | 4.2 - Non-conformance Closure - CAMS Case Number(s) | CAMS Case Number(s) | 4.2 - Non-conformance Closure
|  | 4.3 - Red Line Markups |  | 4.3 - Red Line Markups
|  | 4.3 - Red Line Markups - RFI References | RFI References | 4.3 - Red Line Markups
|  | 4.4 - Final Inspection |  | 4.4 - Final Inspection
|  | Final Inspection |  | Final Inspection
ITP 0007 - Fill With Material Type A
| Scope |  |  | ITP 0007 - Fill With Material Type A
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0007 - Fill With Material Type A
|  | Area 2 | dynamic | Area 2 | ITP 0007 - Fill With Material Type A
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used
|  | 1.2 - Excavation Permit issued |  | 1.2 - Excavation Permit issued
|  | 1.3 - Type A Material Approval |  | 1.3 - Type A Material Approval
|  | 1.3 - Type A Material Approval - Teambinder Approval number: | Teambinder Approval number: | 1.3 - Type A Material Approval
|  | 1.4 - Review of Subgrade Test Roll |  | 1.4 - Review of Subgrade Test Roll
|  | Subgrade ITP Number: |  | Subgrade ITP Number:
|  | 2.1 - Survey set-out |  | 2.1 - Survey set-out
|  | 2.2 - Placement of Fill |  | 2.2 - Placement of Fill
|  | 2.2 - Placement of Fill - RFI Number: | RFI Number: | 2.2 - Placement of Fill
|  | 2.5 - Preparation of final surface |  | 2.5 - Preparation of final surface
|  | 2.7 - Proof Roll - Top of placed layer |  | 2.7 - Proof Roll - Top of placed layer
|  | 2.8 - Post-compaction Testing |  | 2.8 - Post-compaction Testing
|  | 3.1 - Survey As-Built |  | 3.1 - Survey As-Built
|  | 3.2 - Non-conformance Closure |  | 3.2 - Non-conformance Closure
|  | 3.2 - Non-conformance Closure - CAMS Case Number(s): | CAMS Case Number(s): | 3.2 - Non-conformance Closure
|  | 3.3 - Red Line Markups |  | 3.3 - Red Line Markups
|  | 3.4 - Final Inspection |  | 3.4 - Final Inspection
|  | Final Inspection |  | Final Inspection
ITP 0009 - Unbound Pavements
| Scope |  |  | ITP 0009 - Unbound Pavements
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0009 - Unbound Pavements
|  | Area 2 | dynamic | Area 2 | ITP 0009 - Unbound Pavements
Columns
|  | 1.1 - Induction |  | 1.1 - Induction
|  | 1.2 - Check that current revision drawings are being used |  | 1.2 - Check that current revision drawings are being used
|  | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area & that all prescribed environmental controls are in place |  | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
|  | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken |  | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
|  | 1.5 - Crushed Rock Mix design |  | 1.5 - Crushed Rock Mix design
|  | 1.6 - Excavation Permit issued |  | 1.6 - Excavation Permit issued
|  | 1.7 - Traffic Management (When required) |  | 1.7 - Traffic Management (When required)
|  | 2.1 - Transverse Joints |  | 2.1 - Transverse Joints
|  | 2.2 - Longitudinal Joints |  | 2.2 - Longitudinal Joints
|  | 2.3 - Lot Size |  | 2.3 - Lot Size
|  | 2.4 - Proof Roll |  | 2.4 - Proof Roll
|  | 3.1 - Determine Testing Scale & Initial testing frequency |  | 3.1 - Determine Testing Scale & Initial testing frequency
|  | 3.2 - Modified Compactive Effort |  | 3.2 - Modified Compactive Effort
|  | 3.3 - Permeability Testing |  | 3.3 - Permeability Testing
|  | 3.4 - Post-compaction Plasticity Index |  | 3.4 - Post-compaction Plasticity Index
|  | 3.5 - Post-compaction Grading |  | 3.5 - Post- compaction Grading
|  | 3.6 - Test Requisition |  | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - Test Requested on | Test Requested on | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - Location | Location | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - Material Type | Material Type | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - Material Source | Material Source | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - Compaction Test (Standard) | Compaction Test (Standard) | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - Compaction Test (Modified) | Compaction Test (Modified) | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - Maximum Particle Test | Maximum Particle Test | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - CBR/Swell Test | CBR/Swell Test | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - PI Test | PI Test | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - Permeability Test | Permeability Test | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - Grading | Grading | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - Moisture | Moisture | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - See comments | See comments | 3.6 - Test Requisition
|  | 3.6 - Test Requisition - Test Level/Layer | Test Level/ Layer | 3.6 - Test Requisition
|  | 3.7 - Survey Level |  | 3.7 - Survey Level
|  | Final Inspection |  | Final Inspection
ITP 0010 - Subsoil Drainage
| Scope |  |  | ITP 0010 - Subsoil Drainage
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0010 - Subsoil Drainage
|  | Area 2 | dynamic | Area 2 | ITP 0010 - Subsoil Drainage
Columns
|  | 1.1 - Subsurface Drainage Pipes |  | 1.1 - Subsurface Drainage Pipes
|  | 1.1 - Subsurface Drainage Pipes - Teambinder Material Approval Number: | Enter Teambinder Material Approval Number: | 1.1 - Subsurface Drainage Pipes
|  | 1.2 - Drainage Geotextile |  | 1.2 - Drainage Geotextile
|  | 1.2 - Subsurface Drainage Pipes - Teambinder Material Approval Number: | Enter Teambinder Material Approval Number: | 1.2 - Drainage Geotextile
|  | 1.3 - SSD Backfill Material |  | 1.3 - SSD Backfill Material
|  | 1.3 - Subsurface Drainage Pipes - Teambinder Material Approval Number: | Enter Teambinder Material Approval Number: | 1.3 - SSD Backfill Material
|  | 1.4 - Terminals & Pits |  | 1.4 - Terminals & Pits
|  | 1.4 - Terminals & Pits - Teambinder Material Approval Number: | Enter Teambinder Material Approval Number: | 1.4 - Terminals & Pits
|  | 1.5 - Compaction Methodology |  | 1.5 - Compaction Methodology
|  | 1.5 - Compaction Methodology - Teambinder Material Approval Number: | Enter Teambinder Material Approval Number: | 1.5 - Compaction Methodology
|  | 2.1 - Check current revision drawings are being used |  | 2.1 - Check current revision drawings are being used
|  | 2.2 - Excavation Permit issued |  | 2.2 - Excavation Permit issued
|  | 3.1 - Suitability of Materials |  | 3.1 - Suitability of Materials
|  | 3.2 - Managing Existing Drainage |  | 3.2 - Managing Existing Drainage
|  | 3.3 - Excavation of Trench |  | 3.3 - Excavation of Trench
|  | 3.4 - Use of Geotextile |  | 3.4 - Use of Geotextile
|  | 3.5 - Installation of Subsoil Drainage |  | 3.5 - Installation of Subsoil Drainage
|  | 3.6 - Placing of Granular Filter Material |  | 3.6 - Placing of Granular Filter Material
|  | 3.7 - Installation of Subsurface Outlet marker posts (If required) |  | 3.7 - Installation of Subsurface Outlet marker posts (If required)
|  | 3.8 - Flushing Test |  | 3.8 - Flushing Test
|  | 3.9 - Inspection & Completion |  | 3.9 - Inspection and Completion
|  | Final Inspection |  | Final Inspection
ITP 0011 - Cement Treated Crushed Rock
| Scope |  |  | ITP 0011 - Cement Treated Crushed Rock
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0011 - Cement Treated Crushed Rock
|  | Area 2 | dynamic | Area 2 | ITP 0011 - Cement Treated Crushed Rock
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used
|  | 1.2 - Submit Mix Design - Cement treated crushed rock (CTCR) mix |  | 1.2 - Submit Mix Design - Cement treated crushed rock (CTCR) mix
|  | 1.2 - Submit Mix Design - Cement treated crushed rock (CTCR) mix - Team Binder Approval Number: | Team Binder Approval Number: | 1.2 - Submit Mix Design - Cement treated crushed rock (CTCR) mix
|  | 1.3 - Survey Set-out |  | 1.3 - Survey Set-out
|  | 1.4 - Previous Layer Level Conformance |  | 1.4 - Previous Layer Level Conformance
|  | 2.1 - Lot Size |  | 2.1 - Lot Size
|  | 2.2 - Hold Point - Alternate Binder |  | 2.2 - Hold Point - Alternate Binder
|  | 2.3 - Transverse Joints |  | 2.3 - Transverse Joints
|  | 2.4 - Longitudinal Joints |  | 2.4 - Longitudinal Joints
|  | 2.5 - Layer Thickness |  | 2.5 - Layer Thickness
|  | 2.6 - Delivery, Placement & Working Time |  | 2.6 - Delivery, Placement and Working Time
|  | 2.7 - Water |  | 2.7 - Water
|  | 3.1 - Determine Testing Scale |  | 3.1 - Determine Testing Scale
|  | 3.2 - Compaction - Modified Compactive Effort & Moisture content |  | 3.2 - Compaction - Modified Compactive Effort & Moisture content
|  | 3.3 - Surface Shape |  | 3.3 - Surface Shape
|  | 3.4 - Surface Level |  | 3.4 - Surface Level
|  | Final Inspection |  | Final Inspection
ITP 0012 - Kerb and Channel
| Scope |  |  | ITP 0012 - Kerb and Channel
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0012 - Kerb and Channel
|  | Area 2 | dynamic | Area 2 | ITP 0012 - Kerb and Channel
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used
|  | 1.2 - Mix design |  | 1.2 - Mix design
|  | 1.3 - Bedding Material |  | 1.3 - Bedding Material
|  | 1.4 - Curing Compound |  | 1.4 - Curing Compound
|  | 1.5 - Temporary drainage provisions |  | 1.5 - Temporary drainage provisions
|  | 2.1 - Setting out |  | 2.1 - Setting out
|  | 2.2 - Bedding |  | 2.2 - Bedding
|  | 2.3 - Formwork |  | 2.3 - Formwork
|  | 2.4 - Pre Pour Check |  | 2.4 - Pre Pour Check
|  | 2.5 - Concrete placement |  | 2.5 - Concrete placement
|  | 2.6 - Transitions |  | 2.6 - Transitions
|  | 2.7 - Surface Finish |  | 2.7 - Surface Finish
|  | 2.8 - Formwork Stripping |  | 2.8 - Formwork Stripping
|  | 2.9 - Tolerance |  | 2.9 - Tolerance
|  | 2.10 - Curing |  | 2.10 - Curing
|  | 2.11 - Joints |  | 2.11 - Joints
|  | 2.12 - Backfilling |  | 2.12 - Backfilling
|  | 2.13 - Protection of Concrete |  | 2.13 - Protection of Concrete
|  | 2.14 - Cracking of Concrete |  | 2.14 - Cracking of Concrete
|  | 3.1 - Survey Conformance |  | 3.1 - Survey Conformance
|  | 3.2 - Non-conformance Report (NCR) Closure |  | 3.2 - Non-conformance Report (NCR) Closure
|  | 3.3 - Red lines |  | 3.3 - Red lines
|  | Final Inspection |  | Final Inspection
ITP 0013 - Structural Concrete
| Scope |  |  | ITP 0013 - Structural Concrete
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0013 - Structural Concrete
|  | Area 2 | dynamic | Area 2 | ITP 0013 - Structural Concrete
Columns
|  | Referenced Documentation |  | Referenced Documentation
|  | 2.1 - Concrete mix design |  | 2.1 - Concrete mix design
|  | 2.1 - Concrete mix design - Teambinder Material Approval number | Teambinder Material Approval number | 2.1 - Concrete mix design
|  | 2.2 - Reinforcement Certification |  | 2.2 - Reinforcement Certification
|  | 2.2 - Reinforcement Certification - Teambinder Material Approval number | Teambinder Material Approval number | 2.2 - Reinforcement Certification
|  | 2.3 - Bar Chairs/Aspros Certification |  | 2.3 - Bar Chairs/Aspros Certification
|  | 2.3 - Bar Chairs/Aspros Certification - Teambinder Material Approval number | Teambinder Material Approval number | 2.3 - Bar Chairs/Aspros Certification
|  | 2.4 - Evaporative Retardant |  | 2.4 - Evaporative Retardant
|  | 2.4 - Evaporative Retardant - Teambinder Material Approval number | Teambinder Material Approval number | 2.4 - Evaporative Retardant
|  | 2.5 - Curing Compound |  | 2.5 - Curing Compound
|  | 3.1 - Concrete Placement & Compaction Work Method Statements |  | 3.1 - Concrete Placement and Compaction Work Method Statements
|  | 3.1 - Concrete Placement & Compaction Work Method Statements - Teambinder Approval number | Teambinder Approval number | 3.1 - Concrete Placement and Compaction Work Method Statements
|  | 3.2 - Concrete Sampling & Testing Procedure |  | 3.2 - Concrete Sampling and Testing Procedure
|  | 3.2 - Concrete Sampling & Testing Procedure - Teambinder Approval number | Teambinder Approval number | 3.2 - Concrete Sampling and Testing Procedure
|  | 3.3 - Concrete Placement & Compaction Toolbox Meeting |  | 3.3 - Concrete Placement and Compaction Toolbox Meeting
|  | 3.3 - Concrete Placement & Compaction Toolbox Meeting - Teambinder Approval number | Teambinder Approval number | 3.3 - Concrete Placement and Compaction Toolbox Meeting
|  | 3.4 - Hot and/or Cold Weather Concreting Procedure |  | 3.4 - Hot and/or Cold Weather Concreting Procedure
|  | 3.4 - Hot and/or Cold Weather Concreting Procedure - Teambinder Approval number | Teambinder Approval number | 3.4 - Hot and/or Cold Weather Concreting Procedure
|  | 3.5 - Curing Methodology (for Concrete & Grout) |  | 3.5 - Curing Methodology (for Concrete and Grout)
|  | 3.5 - Curing Methodology (for Concrete & Grout) - Teambinder Approval number | Teambinder Approval number | 3.5 - Curing Methodology (for Concrete and Grout)
|  | 3.6 - Concrete Drilling Procedure |  | 3.6 - Concrete Drilling Procedure
|  | 3.6 - Concrete Drilling Procedure - Teambinder Approval number | Teambinder Approval number | 3.6 - Concrete Drilling Procedure
|  | 4.1 - Check that IFC drawings are being used |  | 4.1 - Check that IFC drawings are being used
|  | 4.2 - Survey set out works |  | 4.2 - Survey set out works
|  | 4.3 - Excavation Permit issued |  | 4.3 - Excavation Permit issued
|  | 4.4 - Excavation Inspection |  | 4.4 - Excavation Inspection
|  | 5.1 - Formwork Design & Construction |  | 5.1 - Formwork Design and Construction
|  | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m) |  | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
|  | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m) |  | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
|  | 5.4 - Reinforcement Placement |  | 5.4 - Reinforcement Placement
|  | 5.5 - Pre-pour Survey |  | 5.5 - Pre-pour Survey
|  | 6.1 - Construction Joint Preparation |  | 6.1 - Construction Joint Preparation
|  | 6.2 - Cast-in Items |  | 6.2 - Cast-in Items
|  | 6.3 - Pre-pour Inspection |  | 6.3 - Pre-pour Inspection
|  | 6.4 - Weather Conditions & Evaporation Limits |  | 6.4 - Weather Conditions & Evaporation Limits
|  | 6.5 - Concrete Testing - Sampling Frequency |  | 6.5 - Concrete Testing - Sampling Frequency
|  | 6.6 - Concrete Testing - Slump |  | 6.6 - Concrete Testing - Slump
|  | 6.7 - Concrete Testing - Spread, Passability & Viscosity |  | 6.7 - Concrete Testing - Spread, Passability & Viscosity
|  | 6.8 - Concrete Testing - Compressive Strength Cylinders |  | 6.8 - Concrete Testing - Compressive Strength Cylinders
|  | 6.9 - Supply & Discharge Rates |  | 6.9 - Supply & Discharge Rates
|  | 6.10 - Surface Finishes |  | 6.10 - Surface Finishes
|  | 7.1 - Thermal Differential Monitoring |  | 7.1 - Thermal Differential Monitoring
|  | 7.2 - Early Age Compressive Strength Test Results - Removal of Formwork |  | 7.2 - Early Age Compressive Strength Test Results - Removal of Formwork
|  | 7.3 - Surface Inspection - Cracks |  | 7.3 - Surface Inspection - Cracks
|  | 7.4 - Early Age Compressive Strength Test Results - Placement of Fill Against Concrete |  | 7.4 - Early Age Compressive Strength Test Results - Placement of Fill Against Concrete
|  | 7.5 - Compressive Strength Result |  | 7.5 - Compressive Strength Result
|  | 7.6 - Post Pour Concrete Cover |  | 7.6 - Post Pour Concrete Cover
|  | 7.7 - Prepare As Built Drawings |  | 7.7 - Prepare As Built Drawings
|  | Final Inspection |  | Final Inspection
ITP 0015 - Structural Grout
| Scope |  |  | ITP 0015 - Structural Grout
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0015 - Structural Grout
|  | Area 2 | dynamic | Area 2 | ITP 0015 - Structural Grout
Columns
|  | 1.1 - Product Selection |  | 1.1 - Product Selection
|  | 1.1 - Product Selection - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.1 - Product Selection
|  | 1.2 - Curing Compound |  | 1.2 - Curing Compound
|  | 1.2 - Curing Compound - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.2 - Curing Compound
|  | 2.1 - Curing Methodology (for Concrete, Grout & Mortar) |  | 2.1 - Curing Methodology (for Concrete, Grout and Mortar)
|  | 2.1 - Curing Methodology (for Concrete, Grout & Mortar) - Teambinder Correspondence Approval number | Enter: Teambinder Correspondence Approval number | 2.1 - Curing Methodology (for Concrete, Grout and Mortar)
|  | 3.1 - IFC Drawings |  | 3.1 - IFC Drawings
|  | 3.2 - Survey Set-out |  | 3.2 - Survey Set-out
|  | 3.3 - Construction Joint |  | 3.3 - Construction Joint
|  | 4.1 - Formwork Construction & Placement |  | 4.1 - Formwork Construction & Placement
|  | 4.2 - Pre-pour Inspection |  | 4.2 - Pre-pour Inspection
|  | 4.3 - Weather Conditions |  | 4.3 - Weather Conditions
|  | 4.4 - Mixing Product |  | 4.4 - Mixing Product
|  | 4.5 - Product Testing - Compressive Strength Cubes |  | 4.5 - Product Testing - Compressive Strength Cubes
|  | 4.6 - Placement & Compaction |  | 4.6 - Placement & Compaction
|  | 4.7 - Surface Finishes |  | 4.7 - Surface Finishes
|  | 4.8 - Curing |  | 4.8 - Curing
|  | 5.1 - Compressive Strength Test Results |  | 5.1 - Compressive Strength Test Results
|  | 5.2 - As-built Survey |  | 5.2 - As-built Survey
|  | 5.3 - Non-conformance Report (NCR) Closure |  | 5.3 - Non-conformance Report (NCR) Closure
|  | Final Inspection |  | Final Inspection
ITP 0016 - Bored Piles
| Scope |  |  | ITP 0016 - Bored Piles
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0016 - Bored Piles
|  | Area 2 | dynamic | Area 2 | ITP 0016 - Bored Piles
Columns
|  | 1.1 - Induction |  | 1.1 - Induction
|  | 1.2 - Work pack briefing |  | 1.2 - Work pack briefing
|  | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken |  | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
|  | 1.4 - Check that current revision drawings are being used |  | 1.4 - Check that current revision drawings are being used
|  | 1.5 - Confirm understanding of current Environment Management Plan (CEMP) related to the work area & that all prescribed environmental controls are in place |  | 1.5 - Confirm understanding of current Environment Management Plan (CEMP) related to the work area and that all prescribed environmental controls are in place
|  | 1.6 - Excavation Permit issued |  | 1.6 - Excavation Permit issued
|  | 1.7 - Traffic Management (When required) |  | 1.7 - Traffic Management (When required)
|  | 1.8 - Mix design |  | 1.8 - Mix design
|  | 1.9 - Steel Reinforcement |  | 1.9 - Steel Reinforcement
|  | 1.10 - Quality Procedure for pile construction |  | 1.10 - Quality Procedure for pile construction
|  | 2.1 - Survey set-out |  | 2.1 - Survey set-out
|  | 2.2 - Protection of Adjacent Piles |  | 2.2 - Protection of Adjacent Piles
|  | 2.3 - Excavation levels |  | 2.3 - Excavation levels
|  | 2.4 - Inspection of Pile Excavation |  | 2.4 - Inspection of Pile Excavation
|  | 2.5 - Check reinforcement cages |  | 2.5 - Check reinforcement cages
|  | 2.6 - Pre – pour checklist |  | 2.6 - Pre – pour checklist
|  | 3.1 - Carry out sampling of concrete |  | 3.1 - Carry out sampling of concrete
|  | 3.2 - Place Concrete |  | 3.2 - Place Concrete
|  | 4.1 - Pile Testing |  | 4.1 - Pile Testing
|  | 4.2 - Concrete Test Results |  | 4.2 - Concrete Test Results
|  | 4.3 - Tolerance Check & As Built survey |  | 4.3 - Tolerance Check & As Built survey
|  | Final Inspection |  | Final Inspection
ITP 0017 - Underground Stormwater Drainage
| Scope |  |  | ITP 0017 - Underground Stormwater Drainage
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0017 - Underground Stormwater Drainage
|  | Area 2 | dynamic | Area 2 | ITP 0017 - Underground Stormwater Drainage
Columns
|  | 1.1 - Work pack briefing |  | 1.1 - Work pack briefing
|  | 1.1 - Work pack briefing - Work Pack (WP) | ○ Work Pack (WP) | 1.1 - Work pack briefing
|  | 1.2 - Lot Map |  | 1.2 - Lot Map
|  | 1.2 - Check that current revision drawings are being used |  | 1.2 - Check that current revision drawings are being used
|  | 1.2 - Check that current revision drawings are being used - Design Drawings | ○ Design Drawings | 1.2 - Check that current revision drawings are being used
|  | 1.2 - Check that current revision drawings are being used - RFI Approval Number | ○ RFI Approval Number | 1.2 - Check that current revision drawings are being used
|  | 1.3 - Ground Penetration Permit (GPP) issued by GPP Coordinator |  | 1.3 - Ground Penetration Permit (GPP) issued by GPP Coordinator
|  | 1.3 - Ground Penetration Permit (GPP) issued by GPP Coordinator - GPP No | ○ GPP No | 1.3 - Ground Penetration Permit (GPP) issued by GPP Coordinator
|  | 1.4 - Extension/ Modification of exissting drainage pits |  | 1.4 - Extension/ Modification of exissting drainage pits
|  | 2.1 - Drainage Pipes (RCP) |  | 2.1 - Drainage Pipes (RCP)
|  | 2.1 - Drainage Pipes (RCP) - Pipe Supply & Box Culverts | Pipe Supply & Box Culverts | 2.1 - Drainage Pipes (RCP)
|  | 2.1 - Drainage Pipes (RCP) - Other: | Other: | 2.1 - Drainage Pipes (RCP)
|  | 2.11 - Drainage Pipes (StormPro) |  | 2.11 - Drainage Pipes (StormPro)
|  | 2.11 - Drainage Pipes (StormPro) - Pipe Supply | Pipe Supply | 2.11 - Drainage Pipes (StormPro)
|  | 2.11 - Drainage Pipes (StormPro) - Other: | Other: | 2.11 - Drainage Pipes (StormPro)
|  | 2.12 - Drainage Pits |  | 2.12 - Drainage Pits
|  | 2.12 - Drainage Pits - Pit Supply | Pit Supply | 2.12 - Drainage Pits
|  | 2.12 - Drainage Pits - Other: | Other: | 2.12 - Drainage Pits
|  | 2.2 - Drainage Bedding Material Supply Source / Approval Project Wide |  | 2.2 - Drainage Bedding Material Supply Source / Approval Project Wide
|  | 2.2 - Drainage Bedding Material Supply Source / Approval Project Wide - Bedding & Haunch Material | Bedding & Haunch Material | 2.2 - Drainage Bedding Material Supply Source / Approval Project Wide
|  | 2.2 - Drainage Bedding Material Supply Source / Approval Project Wide - Other: | Other: | 2.2 - Drainage Bedding Material Supply Source / Approval Project Wide
|  | 2.21 - Drainage Bedding Material Supply Source Testing |  | 2.21 - Drainage Bedding Material Supply Source Testing
|  | 2.3 - Drainage Backfill Material |  | 2.3 - Drainage Backfill Material
|  | 2.3 - Drainage Backfill Material - Select Backfill; | Select Backfill; | 2.3 - Drainage Backfill Material
|  | 2.3 - Drainage Backfill Material - Other: | Other: | 2.3 - Drainage Backfill Material
|  | 2.31 - Backfill Material Testing |  | 2.31 - Backfill Material Testing
|  | 2.4 - Material Inspection (Upon Delivery) |  | 2.4 - Material Inspection (Upon Delivery)
|  | 2.5 - Pit Access covers |  | 2.5 - Pit Access covers
|  | 2.5 - Pit Access covers - Pit Access Cover (s) | Pit Access Cover (s) | 2.5 - Pit Access covers
|  | 2.5 - Pit Access covers - Other: | Other: | 2.5 - Pit Access covers
|  | 3.1 - Drainage Pipes & Pits |  | 3.1 - Drainage Pipes & Pits
|  | 3.2 - Survey Set Out / Position of pipe/culvert/pits |  | 3.2 - Survey Set Out / Position of pipe/culvert/pits
|  | 3.3 - Excavation |  | 3.3 - Excavation
|  | 3.3 - Bedding |  | 3.3 - Bedding
|  | 3.4 - Laying - Circular Pipe |  | 3.4 - Laying - Circular Pipe
|  | 3.5 - Laying - Box Culverts |  | 3.5 - Laying - Box Culverts
|  | 3.6 - Laying - Cutting of RCP/Culverts (If applicable) |  | 3.6 - Laying - Cutting of RCP/Culverts (If applicable)
|  | 3.7 - Jointing Circular Pipe |  | 3.7 - Jointing Circular Pipe
|  | 3.8 - Survey |  | 3.8 - Survey
|  | 3.9 - Backfilling |  | 3.9 - Backfilling
|  | 3.10 - Backfilling with cement stabilised sand (If required) |  | 3.10 - Backfilling with cement stabilised sand (If required)
|  | 4.1 - Bedding Compaction Requirements |  | 4.1 - Bedding Compaction Requirements
|  | 4.2 - Backfill Compaction & Moisture requirements |  | 4.2 - Backfill Compaction and Moisture requirements
|  | 4.3 - Flushing System |  | 4.3 - Flushing System
|  | 4.4 - Inspection of drainage lines |  | 4.4 - Inspection of drainage lines
|  | 4.5 - Repairs to Steel reinforced concrete pipes |  | 4.5 - Repairs to Steel reinforced concrete pipes
|  | 4.6 - Flushing System |  | 4.6 - Flushing System
|  | 5.1 - Lot Map |  | 5.1 - Lot Map
|  | 5.2 - As build/ Redline |  | 5.2 - As build/ Redline
|  | Final Inspection |  | Final Inspection
ITP 0018 - Protective and / or Decorative Concrete Coatings
| Scope |  |  | ITP 0018 - Protective and / or Decorative Concrete Coatings
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0018 - Protective and / or Decorative Concrete Coatings
|  | Area 2 | dynamic | Area 2 | ITP 0018 - Protective and / or Decorative Concrete Coatings
Columns
|  | 1.1 - Anti-graffiti System Selection |  | 1.1 - Anti-graffiti System Selection
|  | 1.2 - Decorative & Anti-carbonation System Selection |  | 1.2 - Decorative & Anti-carbonation System Selection
|  | 1.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection |  | 1.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
|  | 1.4 - Atmospheric & Splash Zone (Dual Protective) System Selection |  | 1.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
|  | 1.5 - Work Procedures |  | 1.5 - Work Procedures
|  | 1.6 - Coating Personnel & Equipment |  | 1.6 - Coating Personnel & Equipment
|  | 1.7 - Protection of Adjacent Works & Property |  | 1.7 - Protection of Adjacent Works & Property
|  | 1.8 - Minimum Concrete Curing Period |  | 1.8 - Minimum Concrete Curing Period
|  | 1.9 - Trial Application (or Past Performance) Inspection |  | 1.9 - Trial Application (or Past Performance) Inspection
|  | 2.1 - Material Records |  | 2.1 - Material Records
|  | 2.2 - Weather Conditions |  | 2.2 - Weather Conditions
|  | 2.3 - Surface Preparation |  | 2.3 - Surface Preparation
|  | 2.4 - Surface Moisture Testing |  | 2.4 - Surface Moisture Testing
|  | 3.1 - Method of Application |  | 3.1 - Method of Application
|  | 3.2 - Wet Film Thickness (WFT) Testing |  | 3.2 - Wet Film Thickness (WFT) Testing
|  | 3.3 - Inspection & Defect Identification |  | 3.3 - Inspection & Defect Identification
|  | 3.4 - Drying & Curing |  | 3.4 - Drying and Curing
|  | 4.1 - Clean-up & Waste Disposal |  | 4.1 - Clean-up & Waste Disposal
|  | 4.2 - Dry Film Thickness (DFT) Testing |  | 4.2 - Dry Film Thickness (DFT) Testing
|  | 4.3 - Adhesion Bond Strength Testing |  | 4.3 - Adhesion Bond Strength Testing
|  | 4.4 - Penetration Depth Testing |  | 4.4 - Penetration Depth Testing
|  | 4.5 - Non-conforming Coatings |  | 4.5 - Non-conforming Coatings
|  | 4.6 - Coating Application Guarantee |  | 4.6 - Coating Application Guarantee
|  | 4.7 - Repair to Damaged Coating |  | 4.7 - Repair to Damaged Coating
|  | 4.8 - Non-conformance Report (NCR) Closure |  | 4.8 - Non-conformance Report (NCR) Closure
|  | Final Inspection |  | Final Inspection
ITP 0019 - Bonded Anchors (100 Year Design Life)
| Scope |  |  | ITP 0019 - Bonded Anchors (100 Year Design Life)
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0019 - Bonded Anchors (100 Year Design Life)
|  | Area 2 | dynamic | Area 2 | ITP 0019 - Bonded Anchors (100 Year Design Life)
Columns
|  | 1.1 - Bonded Anchor System - Chemical Adhesive |  | 1.1 - Bonded Anchor System - Chemical Adhesive
|  | 1.1 - Bonded Anchor System - Chemical Adhesive - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.1 - Bonded Anchor System - Chemical Adhesive
|  | 1.2 - Bonded Anchor System - Reinforcement |  | 1.2 - Bonded Anchor System - Reinforcement
|  | 1.2 - Bonded Anchor System - Reinforcement - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.2 - Bonded Anchor System - Reinforcement
|  | 1.3 - Bonded Anchor System - Stainless Steel Anchors |  | 1.3 - Bonded Anchor System - Stainless Steel Anchors
|  | 1.3 - Bonded Anchor System - Stainless Steel Anchors - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.3 - Bonded Anchor System - Stainless Steel Anchors
|  | 1.4 - Bonded Anchor System - Proprietary Threaded Anchor Rods & Metallic Bolts |  | 1.4 - Bonded Anchor System - Proprietary Threaded Anchor Rods & Metallic Bolts
|  | 1.4 - Bonded Anchor System - Proprietary Threaded Anchor Rods & Metallic Bolts - Teambinder Material Approval Number | Enter: Teambinder Material Approval Number | 1.4 - Bonded Anchor System - Proprietary Threaded Anchor Rods & Metallic Bolts
|  | 1.5 - Ultimate Load Testing (for Alternate Product or Changes to Existing Product) |  | 1.5 - Ultimate Load Testing (for Alternate Product or Changes to Existing Product)
|  | 1.5 - Ultimate Load Testing (for Alternate Product or Changes to Existing Product) - Teambinder Approval number | Enter: Teambinder Approval number | 1.5 - Ultimate Load Testing (for Alternate Product or Changes to Existing Product)
|  | 2.1 - Design of Bonded Anchors Subject to Tensile Forces |  | 2.1 - Design of Bonded Anchors Subject to Tensile Forces
|  | 2.1 - Design of Bonded Anchors Subject to Tensile Forces - Teambinder Approval number | Enter: Teambinder Approval number | 2.1 - Design of Bonded Anchors Subject to Tensile Forces
|  | 2.2 - Bonded Anchor Work Method Statement |  | 2.2 - Bonded Anchor Work Method Statement
|  | 2.2 - Bonded Anchor Work Method Statement - Teambinder Approval number | Enter: Teambinder Approval number | 2.2 - Bonded Anchor Work Method Statement
|  | 2.3 - Load Testing Work Method Statement |  | 2.3 - Load Testing Work Method Statement
|  | 2.3 - Load Testing Work Method Statement - Teambinder Approval number | Enter: Teambinder Approval number | 2.3 - Load Testing Work Method Statement
|  | 2.4 - Competency & Training of Personnel |  | 2.4 - Competency & Training of Personnel
|  | 2.4 - Competency & Training of Personnel - Teambinder Approval number | Enter: Teambinder Approval number | 2.4 - Competency & Training of Personnel
|  | 3.1 - Installation Equipment |  | 3.1 - Installation Equipment
|  | 3.2 - Setting Out |  | 3.2 - Setting Out
|  | 4.1 - Hole Drilling/Coring |  | 4.1 - Hole Drilling/Coring
|  | 4.2 - Hole Cleaning |  | 4.2 - Hole Cleaning
|  | 4.3 - Substrate Temperature |  | 4.3 - Substrate Temperature
|  | 4.4 - Anchor Surface Condition |  | 4.4 - Anchor Surface Condition
|  | 4.5 - Adhesive Injection |  | 4.5 - Adhesive Injection
|  | 4.6 - Anchor Insertion |  | 4.6 - Anchor Insertion
|  | 4.7 - Adhesive Curing |  | 4.7 - Adhesive Curing
|  | 5.1 - Proof Load Testing |  | 5.1 - Proof Load Testing
|  | 5.2 - Failure of Load Testing |  | 5.2 - Failure of Load Testing
|  | 5.2 - Failure of Load Testing - Teambinder Approval Number | Enter: Teambinder Approval Number | 5.2 - Failure of Load Testing
|  | 5.3 - Surface Inspection - Cracks |  | 5.3 - Surface Inspection - Cracks
|  | 5.4 - Surface Inspection - Abandoned Holes & Post-testing Spalling |  | 5.4 - Surface Inspection - Abandoned Holes & Post-testing Spalling
|  | 5.5 - Non-conformance Report (NCR) Closure |  | 5.5 - Non-conformance Report (NCR) Closure
|  | Final Inspection |  | Final Inspection
ITP 0020 - Cycle Railing (Supply & Installation)
| Scope |  |  | ITP 0020 - Cycle Railing (Supply & Installation)
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0020 - Cycle Railing (Supply & Installation)
|  | Area 2 | dynamic | Area 2 | ITP 0020 - Cycle Railing (Supply & Installation)
Columns
|  | 1.1 - Railing Components |  | 1.1 - Railing Components
|  | 1.1 - Railing Components - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.1 - Railing Components
|  | 1.2 - Fixing Detail |  | 1.2 - Fixing Detail
|  | 1.2 - Fixing Detail - Teambinder Approval number | Enter: Teambinder Approval number | 1.2 - Fixing Detail
|  | 1.3 - Base Plate Bedding (non-structural) Grout or Mortar |  | 1.3 - Base Plate Bedding (non-structural) Grout or Mortar
|  | 1.3 - Base Plate Bedding (non-structural) Grout or Mortar - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.3 - Base Plate Bedding (non-structural) Grout or Mortar
|  | 2.1 - Certification of Installers |  | 2.1 - Certification of Installers
|  | 2.1 - Certification of Installers - Teambinder Approval number | Enter: Teambinder Approval number | 2.1 - Certification of Installers
|  | 3.1 - IFC Drawings |  | 3.1 - IFC Drawings
|  | 3.2 - Materials Inspection Checklist |  | 3.2 - Materials Inspection Checklist
|  | 4.1 - Bearing / Mounting Surface Preparation |  | 4.1 - Bearing / Mounting Surface Preparation
|  | 4.2 - Railing Handling |  | 4.2 - Railing Handling
|  | 4.3 - Railing Erection |  | 4.3 - Railing Erection
|  | 4.4 - Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S) |  | 4.4 - Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
|  | 5.1 - Inspection of Coating |  | 5.1 - Inspection of Coating
|  | 5.2 - As-built Survey |  | 5.2 - As-built Survey
|  | 5.3 - Non-conformance Report (NCR) Closure |  | 5.3 - Non-conformance Report (NCR) Closure
|  | Final Inspection |  | Final Inspection
ITP 0026 - Guardrail Installation
| Scope |  |  | ITP 0026 - Guardrail Installation
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0026 - Guardrail Installation
|  | Area 2 | dynamic | Area 2 | ITP 0026 - Guardrail Installation
Columns
|  | 1.1 - Work pack briefing |  | 1.1 - Work pack briefing
|  | 1.2 - Check that current revision drawings are being used |  | 1.2 - Check that current revision drawings are being used
|  | 2.1 - Steel Test Certificates |  | 2.1 - Steel Test Certificates
|  | 2.2 - Steel Material Properties & Protection |  | 2.2 - Steel Material Properties & Protection
|  | 2.2 - Steel Material Properties & Protection - Teambinder Approval: | Teambinder Approval: | 2.2 - Steel Material Properties & Protection
|  | 2.3 - Identification of guard fence components |  | 2.3 - Identification of guard fence components
|  | 2.4 - W-Beam Barrier with non standard requirements or other special measures |  | 2.4 - W-Beam Barrier with non standard requirements or other special measures
|  | 2.5 - Concrete mix design (As Applicable) |  | 2.5 - Concrete mix design (As Applicable)
|  | 2.5 - Concrete mix design (As Applicable) - Teambinder Approval: | Teambinder Approval: | 2.5 - Concrete mix design (As Applicable)
|  | 3.1 - Approval of location & length |  | 3.1 - Approval of location and length
|  | 3.2 - Survey set-out |  | 3.2 - Survey set-out
|  | 3.3 - Post Installation |  | 3.3 - Post Installation
|  | 3.4 - W-Beams |  | 3.4 - W-Beams
|  | 3.5 - Guard Fence Tolerances |  | 3.5 - Guard Fence Tolerances
|  | 4.1 - Dimensions & set-out |  | 4.1 - Dimensions and set-out
|  | 4.2 - Bedding & concrete |  | 4.2 - Bedding and concrete
|  | 4.3 - Separation from Kerb |  | 4.3 - Separation from Kerb
|  | 5.1 - Compliance Audit of Barrier System Installation |  | 5.1 - Compliance Audit of Barrier System Installation
|  | 6.1 - Delineators |  | 6.1 - Delineators
|  | 6.2 - Grassing of disturbed areas |  | 6.2 - Grassing of disturbed areas
|  | 6.3 - Quality Assurance |  | 6.3 - Quality Assurance
|  | Final Inspection |  | Final Inspection
ITP 0040 - Gas Protection Works
| Scope |  |  | ITP 0040 - Gas Protection Works
Rows
|  | Utilities | dynamic | Utilities | ITP 0040 - Gas Protection Works
Columns
|  | 1.1 - Induction |  | 1.1 - Induction
|  | 1.2 - Safety measures are in place, SWMS undertaken |  | 1.2 - Safety measures are in place, SWMS undertaken
|  | 1.3 - Check that current revision drawings are being used |  | 1.3 - Check that current revision drawings are being used
|  | 1.4 - Confirm understanding of current EMP related to the work area & that all prescribed environmental controls are in place |  | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
|  | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider |  | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
|  | 2.1 - Approved materials ordered. |  | 2.1 - Approved materials ordered.
|  | 2.2 - Receival & Inspection of products. |  | 2.2 - Receival and Inspection of products.
|  | 3A.1 - Survey set-out |  | 3A.1 - Survey set-out
|  | 3A.2 - Excavate & expose Pipeline |  | 3A.2 - Excavate and expose Pipeline
|  | 3A.3 - Survey pick up |  | 3A.3 - Survey pick up
|  | 3A.4 - Place pipe protection material |  | 3A.4 - Place pipe protection material
|  | 3A.5 - Survey pick up - Encasement of Asset |  | 3A.5 - Survey pick up - Encasement of Asset
|  | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement) |  | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
|  | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement) |  | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
|  | 3A.8 - Backfill Trench (where material forms part of permanent works) |  | 3A.8 - Backfill Trench (where material forms part of permanent works)
|  | Test Requisition |  | Test Requisition
|  | Test Requisition - Test Requested on | Test Requested on | Test Requisition
|  | Test Requisition - Location | Location | Test Requisition
|  | Test Requisition - Material Type | Material Type | Test Requisition
|  | Test Requisition - Material Source | Material Source | Test Requisition
|  | Test Requisition - Compaction Test (Standard) | Compaction Test (Standard) | Test Requisition
|  | Test Requisition - Compaction Test (Modified) | Compaction Test (Modified) | Test Requisition
|  | Test Requisition - Maximum Particle Test | Maximum Particle Test | Test Requisition
|  | Test Requisition - CBR/Swell Test | CBR/Swell Test | Test Requisition
|  | Test Requisition - PI Test | PI Test | Test Requisition
|  | Test Requisition - Permeability Test | Permeability Test | Test Requisition
|  | Test Requisition - Grading | Grading | Test Requisition
|  | Test Requisition - Moisture | Moisture | Test Requisition
|  | Test Requisition - See comments | See comments | Test Requisition
|  | Test Requisition - Test Level/ Layer | Test Level/ Layer | Test Requisition
|  | 4.1 - Surface Reinstatement |  | 4.1 - Surface Reinstatement
|  | 4.2 - Survey data captured for as-built purposes |  | 4.2 - Survey data captured for as-built purposes
|  | Final Inspection |  | Final Inspection
ITP 0041 - Water Protection Works
| Scope |  |  | ITP 0041 - Water Protection Works
Rows
|  | Utilities | dynamic | Utilities | ITP 0041 - Water Protection Works
Columns
|  | 1.1 - Induction |  | 1.1 - Induction
|  | 1.2 - Safety measures are in place, SWMS undertaken |  | 1.2 - Safety measures are in place, SWMS undertaken
|  | 1.3 - Check that current revision drawings are being used |  | 1.3 - Check that current revision drawings are being used
|  | 1.4 - Confirm understanding of current EMP related to the work area & that all prescribed environmental controls are in place |  | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
|  | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider |  | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
|  | 2.1 - Approved materials ordered. |  | 2.1 - Approved materials ordered.
|  | 2.2 - Receival & Inspection of products. |  | 2.2 - Receival and Inspection of products.
|  | 3A.1 - Survey set-out |  | 3A.1 - Survey set-out
|  | 3A.2 - Excavate & expose Pipeline |  | 3A.2 - Excavate and expose Pipeline
|  | 3A.3 - Survey Pick up |  | 3A.3 - Survey Pick up
|  | 3A.4 - Place pipe protection material |  | 3A.4 - Place pipe protection material
|  | 3A.5 - Survey pick up- Encasement of Asset |  | 3A.5 - Survey pick up- Encasement of Asset
|  | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement) |  | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
|  | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement) |  | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
|  | 3A.8 - Backfill Trench (where material forms part of permanent works) |  | 3A.8 - Backfill Trench (where material forms part of permanent works)
|  | Test Requisition |  | Test Requisition
|  | Test Requisition - Test Requested on | Test Requested on | Test Requisition
|  | Test Requisition - Location | Location | Test Requisition
|  | Test Requisition - Material Type | Material Type | Test Requisition
|  | Test Requisition - Material Source | Material Source | Test Requisition
|  | Test Requisition - Compaction Test (Standard) | Compaction Test (Standard) | Test Requisition
|  | Test Requisition - Compaction Test (Modified) | Compaction Test (Modified) | Test Requisition
|  | Test Requisition - Maximum Particle Test | Maximum Particle Test | Test Requisition
|  | Test Requisition - CBR/Swell Test | CBR/Swell Test | Test Requisition
|  | Test Requisition - PI Test | PI Test | Test Requisition
|  | Test Requisition - Permeability Test | Permeability Test | Test Requisition
|  | Test Requisition - Grading | Grading | Test Requisition
|  | Test Requisition - Moisture | Moisture | Test Requisition
|  | Test Requisition - See comments | See comments | Test Requisition
|  | Test Requisition - Test Level/ Layer | Test Level/ Layer | Test Requisition
|  | 4.1 - Surface Reinstatement |  | 4.1 - Surface Reinstatement
|  | 4.2 - Survey data captured for as-built purposes |  | 4.2 - Survey data captured for as-built purposes
|  | Final Inspection |  | Final Inspection
ITP 0042 - Comms Protection Works
| Scope |  |  | ITP 0042 - Comms Protection Works
Rows
|  | Utilities | dynamic | Utilities | ITP 0042 - Comms Protection Works
Columns
|  | 1.1 - Induction |  | 1.1 - Induction
|  | 1.2 - Safety measures are in place, SWMS undertaken |  | 1.2 - Safety measures are in place, SWMS undertaken
|  | 1.3 - Check that current revision drawings are being used |  | 1.3 - Check that current revision drawings are being used
|  | 1.4 - Confirm understanding of current EMP related to the work area & that all prescribed environmental controls are in place |  | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
|  | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider |  | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
|  | 2.1 - Approved materials ordered. |  | 2.1 - Approved materials ordered.
|  | 2.2 - Receival & Inspection of products. |  | 2.2 - Receival and Inspection of products.
|  | 3A.1 - Survey set-out |  | 3A.1 - Survey set-out
|  | 3A.2 - Excavate & expose Pipeline |  | 3A.2 - Excavate and expose Pipeline
|  | 3A.3 - Survey pick up |  | 3A.3 - Survey pick up
|  | 3A.4 - Place pipe protection material |  | 3A.4 - Place pipe protection material
|  | 3A.5 - Survey Pick up - Encasement of Asset |  | 3A.5 - Survey Pick up - Encasement of Asset
|  | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement) |  | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
|  | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement) |  | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
|  | 3A.8 - Backfill Trench (where material forms part of permanent works) |  | 3A.8 - Backfill Trench (where material forms part of permanent works)
|  | Test Requisition |  | Test Requisition
|  | Test Requisition - Test Requested on | Test Requested on | Test Requisition
|  | Test Requisition - Location | Location | Test Requisition
|  | Test Requisition - Material Type | Material Type | Test Requisition
|  | Test Requisition - Material Source | Material Source | Test Requisition
|  | Test Requisition - Compaction Test (Standard) | Compaction Test (Standard) | Test Requisition
|  | Test Requisition - Compaction Test (Modified) | Compaction Test (Modified) | Test Requisition
|  | Test Requisition - Maximum Particle Test | Maximum Particle Test | Test Requisition
|  | Test Requisition - CBR/Swell Test | CBR/Swell Test | Test Requisition
|  | Test Requisition - PI Test | PI Test | Test Requisition
|  | Test Requisition - Permeability Test | Permeability Test | Test Requisition
|  | Test Requisition - Grading | Grading | Test Requisition
|  | Test Requisition - Moisture | Moisture | Test Requisition
|  | Test Requisition - See comments | See comments | Test Requisition
|  | Test Requisition - Test Level/ Layer | Test Level/ Layer | Test Requisition
|  | 4.1 - Surface Reinstatement |  | 4.1 - Surface Reinstatement
|  | 4.2 - Survey data captured for as-built purposes |  | 4.2 - Survey data captured for as-built purposes
|  | Final Inspection |  | Final Inspection
ITP 0043 - Electrical Protection Works
| Scope |  |  | ITP 0043 - Electrical Protection Works
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0043 - Electrical Protection Works
|  | Area 2 | dynamic | Area 2 | ITP 0043 - Electrical Protection Works
Columns
|  | 1.1 - Induction |  | 1.1 - Induction
|  | 1.2 - Safety measures are in place, SWMS undertaken |  | 1.2 - Safety measures are in place, SWMS undertaken
|  | 1.3 - Check that current revision drawings are being used |  | 1.3 - Check that current revision drawings are being used
|  | 1.4 - Confirm understanding of current EMP related to the work area & that all prescribed environmental controls are in place |  | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
|  | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider |  | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
|  | 2.1 - Approved materials ordered. |  | 2.1 - Approved materials ordered.
|  | 2.2 - Receival & Inspection of products. |  | 2.2 - Receival and Inspection of products.
|  | 3A.1 - Survey set-out |  | 3A.1 - Survey set-out
|  | 3A.2 - Excavate & expose Pipeline |  | 3A.2 - Excavate and expose Pipeline
|  | 3A.3 - Survey pick up |  | 3A.3 - Survey pick up
|  | 3A.4 - Place pipe protection material |  | 3A.4 - Place pipe protection material
|  | 3A.5 - Survey pick up- Encasement of Asset |  | 3A.5 - Survey pick up- Encasement of Asset
|  | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement) |  | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
|  | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement) |  | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
|  | 3A.8 - Backfill Trench (where material forms part of permanent works) |  | 3A.8 - Backfill Trench (where material forms part of permanent works)
|  | Test Requisition |  | Test Requisition
|  | Test Requisition - Test Requested on |  | Test Requested on
|  | Test Requisition - Location |  | Location
|  | Test Requisition - Material Type |  | Material Type
|  | Test Requisition - Material Source |  | Material Source
|  | Test Requisition - Compaction Test (Standard) |  | Compaction Test (Standard)
|  | Test Requisition - Compaction Test (Modified) |  | Compaction Test (Modified)
|  | Test Requisition - Maximum Particle Test |  | Maximum Particle Test
|  | Test Requisition - CBR/Swell Test |  | CBR/Swell Test
|  | Test Requisition - PI Test |  | PI Test
|  | Test Requisition - Permeability Test |  | Permeability Test
|  | Test Requisition - Grading |  | Grading
|  | Test Requisition - Moisture |  | Moisture
|  | Test Requisition - See comments |  | See comments
|  | Test Requisition - Test Level/ Layer |  | Test Level/ Layer
|  | 4.1 - Surface Reinstatement |  | 4.1 - Surface Reinstatement
|  | 4.2 - Survey data captured for as-built purposes |  | 4.2 - Survey data captured for as-built purposes
|  | Final Inspection |  | Final Inspection
ITP 0045 - Installation of Traffic Signals
| Scope |  |  | ITP 0045 - Installation of Traffic Signals
Rows
|  | Utilities | dynamic | Utilities | ITP 0045 - Installation of Traffic Signals
Columns
|  | 1.1 - Induction |  | 1.1 - Induction
|  | 1.2 - Check that current revision drawings are being used |  | 1.2 - Check that current revision drawings are being used
|  | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area & that all prescribed environmental controls are in place |  | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
|  | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken |  | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
|  | 1.5 - Ground Penetration Permit issued |  | 1.5 - Ground Penetration Permit issued
|  | 2.1 - Civil Works |  | 2.1 - Civil Works
|  | 2.2 - Electrical Works |  | 2.2 - Electrical Works
|  | 3.1 - Completion of Traffic Signal Works |  | 3.1 - Completion of Traffic Signal Works
|  | Final Inspection |  | Final Inspection
ITP 0049 - TOPSOIL PLACEMENT AND LANDSCAPING
| Scope |  |  | ITP 0049 - TOPSOIL PLACEMENT AND LANDSCAPING
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0049 - TOPSOIL PLACEMENT AND LANDSCAPING
|  | Area 2 | dynamic | Area 2 | ITP 0049 - TOPSOIL PLACEMENT AND LANDSCAPING
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used
|  | 1.2 - Submissions & records |  | 1.2 - Submissions and records
|  | 1.2 - Submissions & records - Teambinder Approval #: | Enter Teambinder Approval #: | 1.2 - Submissions and records
|  | 1.3 - Supply of mulch |  | 1.3 - Supply of mulch
|  | 1.4 - Supply of topsoil |  | 1.4 - Supply of topsoil
|  | 2.1 - Setting out planting areas |  | 2.1 - Setting out planting areas
|  | 2.2 - Site Preparation |  | 2.2 - Site Preparation
|  | 2.3 - Ripping of subsoil |  | 2.3 - Ripping of subsoil
|  | 2.4 - Topsoil Placement |  | 2.4 - Topsoil Placement
|  | 2.5 - Cultivation |  | 2.5 - Cultivation
|  | 2.6 - Bulk density of soils for planting & grassing |  | 2.6 - Bulk density of soils for planting and grassing
|  | 2.7 - Topsoil finished surface levels |  | 2.7 - Topsoil finished surface levels
|  | 2.8 - Planting |  | 2.8 - Planting
|  | 2.9 - Mulching |  | 2.9 - Mulching
|  | 2.10 - Grassing of disturbed areas |  | 2.10 - Grassing of disturbed areas
|  | 2.11 - Grassing |  | 2.11 - Grassing
|  | Final Inspection |  | Final Inspection
ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS
| Scope |  |  | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS
|  | Area 2 | dynamic | Area 2 | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used
|  | 1.2 - Bedding Material / Base Layer |  | 1.2 - Bedding Material / Base Layer
|  | 1.2 - Bedding Material / Base Layer - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.2 - Bedding Material / Base Layer
|  | 1.3 - Concrete Mix |  | 1.3 - Concrete Mix
|  | 1.3 - Concrete Mix - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.3 - Concrete Mix
|  | 1.4 - Evaporative Retardant |  | 1.4 - Evaporative Retardant
|  | 1.4 - Evaporative Retardant - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.4 - Evaporative Retardant
|  | 1.5 - Curing Compound |  | 1.5 - Curing Compound
|  | 1.5 - Curing Compound - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.5 - Curing Compound
|  | 2.1 - Setting Out |  | 2.1 - Setting Out
|  | 2.2 - Temporary Drainage Provisions (if required) |  | 2.2 - Temporary Drainage Provisions (if required)
|  | 2.3 - Pavement Thickness Increases for Crossings |  | 2.3 - Pavement Thickness Increases for Crossings
|  | 2.4 - Bedding Preparation |  | 2.4 - Bedding Preparation
|  | 2.5 - Formwork |  | 2.5 - Formwork
|  | 2.6 - Steel Reinforcement |  | 2.6 - Steel Reinforcement
|  | 2.7 - Pre-pour inspection |  | 2.7 - Pre-pour inspection
|  | 2.8 - Concrete Testing |  | 2.8 - Concrete Testing
|  | 2.12 - Curing |  | 2.12 - Curing
|  | 2.13 - Tolerances |  | 2.13 - Tolerances
|  | 2.16 - Joints |  | 2.16 - Joints
|  | 2.17 - Stripping Formwork |  | 2.17 - Stripping Formwork
|  | 2.18 - Protection of Newly Poured Concrete |  | 2.18 - Protection of Newly Poured Concrete
|  | 3.1 - Survey data captured for as-built purposes |  | 3.1 - Survey data captured for as-built purposes
|  | 3.2 - Cracking of Concrete |  | 3.2 - Cracking of Concrete
|  | 3.2 - Compressive Strength Test Results |  | 3.2 - Compressive Strength Test Results
|  | 3.3 - Backfilling |  | 3.3 - Backfilling
|  | 4.1 - As-built Survey |  | 4.1 - As-built Survey
|  | 4.2 - Red-Line Markup |  | 4.2 - Red-Line Markup
|  | 4.3 - Non-conformance Report (NCR) Closure |  | 4.3 - Non-conformance Report (NCR) Closure
|  | Final Inspection |  | Final Inspection
ITP 0060 - Installation of Unmetered VESI Public Lighting
| Scope |  |  | ITP 0060 - Installation of Unmetered VESI Public Lighting
Rows
|  | Utilities | dynamic | Utilities | ITP 0060 - Installation of Unmetered VESI Public Lighting
Columns
|  | 1.1 Authority to commence contestable construction (ACCC) issued by Jemena |  | 1.1 Authority to commence contestable construction (ACCC) issued by Jemena
|  | 1.1 Authority to commence contestable construction (ACCC) issued by Jemena - Responsibility: Project Engineer /PM2 | Responsibility: Project Engineer /PM2 | 1.1 Authority to commence contestable construction (ACCC) issued by Jemena
|  | 1.2 Induction |  | 1.2 Induction
|  | 1.2 Induction - Responsibility: Site Engineer / Site Foreman | Responsibility: Site Engineer / Site Foreman | 1.2 Induction
|  | 1.3 Check that current revision drawings are being used |  | 1.3 Check that current revision drawings are being used
|  | 1.3 Check that current revision drawings are being used - Responsibility: Site Engineer / Site Foreman | Responsibility: Site Engineer / Site Foreman | 1.3 Check that current revision drawings are being used
|  | 1.4 Confirm understanding of current Environment Management Plan (EMP) related to the work area & that all prescribed environmental controls are in place |  | 1.4 Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
|  | 1.4 Confirm understanding of current Environment Management Plan (EMP) related to the work area & that all prescribed environmental controls are in place - Responsibility: Site Engineer | Responsibility: Site Engineer | 1.4 Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
|  | 1.5 Safety measures are in place, Safe Work Method Statement (SWMS) undertaken |  | 1.5 Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
|  | 1.5 Safety measures are in place, Safe Work Method Statement (SWMS) undertaken - Responsibility: Site Engineer & /Site Foreman Superintendent | Responsibility: Site Engineer & /Site Foreman Superintendent | 1.5 Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
|  | 1.6 Ground Penetration Permit issued |  | 1.6 Ground Penetration Permit issued
|  | 1.6 Ground Penetration Permit issued - Responsibility: Site Engineer | Responsibility: Site Engineer | 1.6 Ground Penetration Permit issued
|  | 2.1 Staged Construction Audit - Civil Works |  | 2.1 Staged Construction Audit - Civil Works
|  | 2.1 Staged Construction Audit - Civil Works - Responsibility: Sub-Contractor | Responsibility: Sub-Contractor | 2.1 Staged Construction Audit - Civil Works
|  | 2.2 Staged Construction Audit – Cable Works |  | 2.2 Staged Construction Audit – Cable Works
|  | 2.2 Staged Construction Audit – Cable Works - Responsibility: Sub-Contractor | Responsibility: Sub-Contractor | 2.2 Staged Construction Audit – Cable Works
|  | 2.3 Staged Construction Audit – Handover |  | 2.3 Staged Construction Audit – Handover
|  | 2.3 Staged Construction Audit – Handover - Responsibility: Sub-Contractor | Responsibility: Sub-Contractor | 2.3 Staged Construction Audit – Handover
|  | 2.3 As-Built submission to Jemena |  | 2.3 As-Built submission to Jemena
|  | 2.3 As-Built submission to Jemena - Responsibility: Fulton Hogan / Powerplant | Responsibility: Fulton Hogan / Powerplant | 2.3 As-Built submission to Jemena
|  | 3.1 Pre Commissioning Audit |  | 3.1 Pre Commissioning Audit
|  | 3.1 Pre Commissioning Audit - Responsibility: PM2 (Powerplant) | Responsibility: PM2 (Powerplant) | 3.1 Pre Commissioning Audit
|  | 3.2 Commissioning |  | 3.2 Commissioning
|  | 3.2 Commissioning - Responsibility: Sub-Contractor | Responsibility: Sub-Contractor | 3.2 Commissioning
|  | 4.1 Final Audit |  | 4.1 Final Audit
|  | 4.1 Final Audit - Responsibility: PM2 (Powerplant) | Responsibility: PM2 (Powerplant) | 4.1 Final Audit
|  | Final Inspection |  | Final Inspection
ITP 0063 - PERMANENT LINE MARKING
| Scope |  |  | ITP 0063 - PERMANENT LINE MARKING
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0063 - PERMANENT LINE MARKING
|  | Area 2 | dynamic | Area 2 | ITP 0063 - PERMANENT LINE MARKING
Columns
|  | 1.1 Inductions |  | 1.1 Inductions
|  | 1.2 Safety measures are in place, SWMS undertaken |  | 1.2 Safety measures are in place, SWMS undertaken
|  | 1.3 Check that current revision drawings are being used |  | 1.3 Check that current revision drawings are being used
|  | 1.4 Confirm understanding of current EMP related to the work area & that all prescribed environmental controls are in place |  | 1.4 Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
|  | 1.5 Traffic Management (When required) |  | 1.5 Traffic Management (When required)
|  | 2.1 Verification of line marking material |  | 2.1 Verification of line marking material
|  | 2.2 Site preparation |  | 2.2 Site preparation
|  | 2.3 Removal of unsuitable/redundant markings (If required) |  | 2.3 Removal of unsuitable/redundant markings (If required)
|  | 2.4 Set out of line markings; dimensions & spacings |  | 2.4 Set out of line markings; dimensions and spacings
|  | 2.5 Painted pavement marking application (if required) |  | 2.5 Painted pavement marking application (if required)
|  | 2.6 Long life pavement marking application |  | 2.6 Long life pavement marking application
|  | 2.7 Protection of works |  | 2.7 Protection of works
|  | 3.1 Acceptance of retroflectivity |  | 3.1 Acceptance of retroflectivity
|  | 3.2 Acceptance of colour |  | 3.2 Acceptance of colour
|  | 3.3 Acceptance of tolerances |  | 3.3 Acceptance of tolerances
|  | 3.4 Acceptance of work |  | 3.4 Acceptance of work
|  | 3.5 Records & reporting |  | 3.5 Records & reporting
|  | Final Inspection |  | Final Inspection
ITP 0065 - Wire Rope Safety Barrier (WRSB)
| Scope |  |  | ITP 0065 - Wire Rope Safety Barrier (WRSB)
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0065 - Wire Rope Safety Barrier (WRSB)
|  | Area 2 | dynamic | Area 2 | ITP 0065 - Wire Rope Safety Barrier (WRSB)
Columns
|  | Referenced Documentation |  | Referenced Documentation
|  | 2.1 - Material Test Certificates |  | 2.1 - Material Test Certificates
|  | 2.2 - WRSB Material Properties & Protection |  | 2.2 - WRSB Material Properties & Protection
|  | 2.3 - Concrete mix design |  | 2.3 - Concrete mix design
|  | 3.1 - IFC Drawings |  | 3.1 - IFC Drawings
|  | 3.2 - Survey Set-out |  | 3.2 - Survey Set-out
|  | 4.1 - Post Foundations & Anchor Blocks |  | 4.1 - Post Foundations and Anchor Blocks
|  | 4.2 - Tensioning of the Wire Rope |  | 4.2 - Tensioning of the Wire Rope
|  | 4.3 - Construction Tolerances |  | 4.3 - Construction Tolerances
|  | 4.4 - Concrete Maintenance Strip |  | 4.4 - Concrete Maintenance Strip
|  | 4.5 - Pre-Pour inspection |  | 4.5 - Pre-Pour inspection
|  | 4.6 - Concrete testing |  | 4.6 - Concrete testing
|  | 4.7 - Curing of concrete maintenance strip |  | 4.7 - Curing of concrete maintenance strip
|  | Test Requisition |  | Test Requisition
|  | Test Requisition - Test Requested on | Test Requested on | Test Requisition
|  | Test Requisition - Location | Location | Test Requisition
|  | Test Requisition - Material Type | Material Type | Test Requisition
|  | Test Requisition - Material Source | Material Source | Test Requisition
|  | Test Requisition - Compaction Test (Standard) | Compaction Test (Standard) | Test Requisition
|  | Test Requisition - Compaction Test (Modified) | Compaction Test (Modified) | Test Requisition
|  | Test Requisition - Maximum Particle Test | Maximum Particle Test | Test Requisition
|  | Test Requisition - CBR/Swell Test | CBR/Swell Test | Test Requisition
|  | Test Requisition - PI Test | PI Test | Test Requisition
|  | Test Requisition - Permeability Test | Permeability Test | Test Requisition
|  | Test Requisition - Grading | Grading | Test Requisition
|  | Test Requisition - Moisture | Moisture | Test Requisition
|  | Test Requisition - See comments | See comments | Test Requisition
|  | Test Requisition - Test Level/ Layer | Test Level/ Layer | Test Requisition
|  | 5.1 - Compliance Audit of Barrier System Installation |  | 5.1 - Compliance Audit of Barrier System Installation
|  | 5.2 - Delineators |  | 5.2 - Delineators
|  | 5.3 - Compressive Strength Test Results |  | 5.3 - Compressive Strength Test Results
|  | 5.4 - As-built Survey |  | 5.4 - As-built Survey
|  | 5.5 - Non-conformance Report (NCR) Closure |  | 5.5 - Non-conformance Report (NCR) Closure
|  | 5.6 - Inspection of Grassed Areas |  | 5.6 - Inspection of Grassed Areas
|  | 5.7 - MRPV Quality Final Inspection |  | 5.7 - MRPV Quality Final Inspection
|  | Final Inspection |  | Final Inspection
ITP 0066 - Directional Drilling
| Scope |  |  | ITP 0066 - Directional Drilling
Rows
|  | Utilities | dynamic | Utilities | ITP 0066 - Directional Drilling
Columns
|  | 1.1 - IFC / Shop Drawings Submission & Approval. |  | 1.1 - IFC / Shop Drawings Submission & Approval.
|  | 1.2 - Survey Set-Out |  | 1.2 - Survey Set-Out
|  | 1.3 - Excavation Permit/ Service Location |  | 1.3 - Excavation Permit/ Service Location
|  | 1.4 - Superintendent Notification |  | 1.4 - Superintendent Notification
|  | 2.1 - Conduit Sizing |  | 2.1 - Conduit Sizing
|  | 2.2 - HDPE Pipe Inspection |  | 2.2 - HDPE Pipe Inspection
|  | 3.1 - Entry/ Exit Points |  | 3.1 - Entry/ Exit Points
|  | 3.2 - Minimum Cover |  | 3.2 - Minimum Cover
|  | 3.3 - Survey pick up / Bore Mark Out |  | 3.3 - Survey pick up / Bore Mark Out
|  | 4.1 - Entry/ Exit Points |  | 4.1 - Entry/ Exit Points
|  | 4.2 - Grouting |  | 4.2 - Grouting
|  | 4.3 - Backfilling |  | 4.3 - Backfilling
|  | 4.4 - Draw Cord |  | 4.4 - Draw Cord
|  | 4.5 - Site clean up |  | 4.5 - Site clean up
|  | 4.6 - Records |  | 4.6 - Records
|  | Final Inspection |  | Final Inspection
ITP 0074 - Installation of Fencing
| Scope |  |  | ITP 0074 - Installation of Fencing
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0074 - Installation of Fencing
|  | Area 2 | dynamic | Area 2 | ITP 0074 - Installation of Fencing
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used
|  | 1.2 - Confirm understanding of current Environment Management Plan (EMP) related to the work area & that all prescribed environmental controls are in place |  | 1.2 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
|  | 1.3 - Excavation Permit Issued |  | 1.3 - Excavation Permit Issued
|  | 1.4 - Traffic Management (When required) |  | 1.4 - Traffic Management (When required)
|  | 1.5 - Material Conformance |  | 1.5 - Material Conformance
|  | 2.1 - Site preparation |  | 2.1 - Site preparation
|  | 2.2 - Fencing Set Out |  | 2.2 - Fencing Set Out
|  | 2.3 - Install Fence |  | 2.3 - Install Fence
|  | 3.1 - Asbuilt Survey |  | 3.1 - Asbuilt Survey
|  | Final Inspection |  | Final Inspection
ITP 0075 - Asphalt Placement
| Scope |  |  | ITP 0075 - Asphalt Placement
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0075 - Asphalt Placement
|  | Area 2 | dynamic | Area 2 | ITP 0075 - Asphalt Placement
Columns
|  | 1.1 Submission of Mix Design |  | 1.1 Submission of Mix Design
|  | 1.1 Submission of Mix Design - Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent | Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent | 1.1 Submission of Mix Design
|  | 1.2 Ensure underlying lot conforms |  | 1.2 Ensure underlying lot conforms
|  | 1.3 Visual Inspection of underlying lot |  | 1.3 Visual Inspection of underlying lot
|  | 1.3 Visual Inspection of underlying lot - Responsibility: Site Engineer/ Asphalt Supervisor | Responsibility: Site Engineer/ Asphalt Supervisor | 1.3 Visual Inspection of underlying lot
|  | 1.4 Ambient Conditions for Placing |  | 1.4 Ambient Conditions for Placing
|  | 1.4 Ambient Conditions for Placing - Responsibility: Site Engineer/ Asphalt Supervisor | Responsibility: Site Engineer/ Asphalt Supervisor | 1.4 Ambient Conditions for Placing
|  | 1.5 Planning of Joints |  | 1.5 Planning of Joints
|  | 1.5 Planning of Joints - Responsibility: Project Engineer/ Asphalt Supervisor Superintendent | Responsibility: Project Engineer/ Asphalt Supervisor Superintendent | 1.5 Planning of Joints
|  | 1.6 Longitudinal Joints with existing Pavement |  | 1.6 Longitudinal Joints with existing Pavement
|  | 1.6 Longitudinal Joints with existing Pavement - Responsibility: Project Engineer/ Asphalt Supervisor | Responsibility: Project Engineer/ Asphalt Supervisor | 1.6 Longitudinal Joints with existing Pavement
|  | 2.1 Commencement of placement |  | 2.1 Commencement of placement
|  | 2.1 Commencement of placement - Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent | Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent | 2.1 Commencement of placement
|  | 2.2 Cold Weather Placement Management Plan |  | 2.2 Cold Weather Placement Management Plan
|  | 2.2 Cold Weather Placement Management Plan - Responsibility: Project Engineer/ Asphalt Project Manager or Engineer | Responsibility: Project Engineer/ Asphalt Project Manager or Engineer | 2.2 Cold Weather Placement Management Plan
|  | 2.3 Mix Design Confirmation |  | 2.3 Mix Design Confirmation
|  | 2.3 Mix Design Confirmation - Responsibility: Site Engineer/ Asphalt Supervisor | Responsibility: Site Engineer/ Asphalt Supervisor | 2.3 Mix Design Confirmation
|  | 2.4 Running traffic on Placed Asphalt |  | 2.4 Running traffic on Placed Asphalt
|  | 2.4 Running traffic on Placed Asphalt - Responsibility: Site Engineer/ Asphalt Supervisor | Responsibility: Site Engineer/ Asphalt Supervisor | 2.4 Running traffic on Placed Asphalt
|  | 3.1 Placing Material |  | 3.1 Placing Material
|  | 3.1 Placing Material - Responsibility: Site Engineer/ Asphalt Supervisor Superintendent | Responsibility: Site Engineer/ Asphalt Supervisor Superintendent | 3.1 Placing Material
|  | 3.2 Survey Level Conformance |  | 3.2 Survey Level Conformance
|  | 3.2 Survey Level Conformance - Responsibility: Site Engineer/ Surveyor / Survey Manager | Responsibility: Site Engineer/ Surveyor / Survey Manager | 3.2 Survey Level Conformance
|  | Final Inspection |  | Final Inspection
ITP 0076 - Permanent Roadside Signage
| Scope |  |  | ITP 0076 - Permanent Roadside Signage
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0076 - Permanent Roadside Signage
|  | Area 2 | dynamic | Area 2 | ITP 0076 - Permanent Roadside Signage
Columns
|  | 1.1 - Inductions |  | 1.1 - Inductions
|  | 1.2 - Safety measures are in place, SWMS undertaken |  | 1.2 - Safety measures are in place, SWMS undertaken
|  | 1.3 - Check that current revision drawings are being used |  | 1.3 - Check that current revision drawings are being used
|  | 1.4 - Confirm understanding of current EMP related to the work area & that all prescribed environmental controls are in place |  | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
|  | 1.5 - Traffic Management (When required) |  | 1.5 - Traffic Management (When required)
|  | 2.1 - Set out posts & foundations |  | 2.1 - Set out posts and foundations
|  | 2.2 - Material compliance |  | 2.2 - Material compliance
|  | 2.3 - Installation method |  | 2.3 - Installation method
|  | 2.4 - Installation tolerances |  | 2.4 - Installation tolerances
|  | Final Inspection |  | Final Inspection
ITP 0077 - Electrical and Communications Conduit Installation
| Scope |  |  | ITP 0077 - Electrical and Communications Conduit Installation
Rows
|  | Utilities | dynamic | Utilities | ITP 0077 - Electrical and Communications Conduit Installation
Columns
|  | 1.1 - IFC / Shop Drawings Submission & Approval. |  | 1.1 - IFC / Shop Drawings Submission & Approval.
|  | 1.2 - Survey Set-Out |  | 1.2 - Survey Set-Out
|  | 1.3 - Excavation Permit/ Service Location |  | 1.3 - Excavation Permit/ Service Location
|  | 2.1 - Conduit Sizing |  | 2.1 - Conduit Sizing
|  | 2.2 - Material Backfill |  | 2.2 - Material Backfill
|  | 3.1 - Entry/ Exit Points |  | 3.1 - Entry/ Exit Points
|  | 3.2 - Minimum Cover |  | 3.2 - Minimum Cover
|  | 3.3 - Backfilling |  | 3.3 - Backfilling
|  | 3.4 - Compaction Requirements |  | 3.4 - Compaction Requirements
|  | 3.5 - Survey pick up / Bore Mark Out |  | 3.5 - Survey pick up / Bore Mark Out
|  | 4.1 - Entry/ Exit Points |  | 4.1 - Entry/ Exit Points
|  | 4.2 - Conduit Layout |  | 4.2 - Conduit Layout
|  | 4.3 - Draw Cord |  | 4.3 - Draw Cord
|  | 4.4 - Site clean up |  | 4.4 - Site clean up
|  | 4.5 - Maintenance of Pavement |  | 4.5 - Maintenance of Pavement
|  | 4.6 - Records |  | 4.6 - Records
|  | Final Inspection |  | Final Inspection
ITP 0078 - Insitu Pit Construction
| Scope |  |  | ITP 0078 - Insitu Pit Construction
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0078 - Insitu Pit Construction
|  | Area 2 | dynamic | Area 2 | ITP 0078 - Insitu Pit Construction
Columns
|  | 1.1 Check for correct documentation |  | 1.1 Check for correct documentation
|  | 1.1 Check for correct documentation - Responsibility: Site Engineer/ Supervisor | Responsibility: Site Engineer/ Supervisor | 1.1 Check for correct documentation
|  | 1.2 Implementation of all measures & controls |  | 1.2 Implementation of all measures and controls
|  | 1.2 Implementation of all measures & controls - Responsibility: Site Engineer/ Supervisor | Responsibility: Site Engineer/ Supervisor | 1.2 Implementation of all measures and controls
|  | 1.3 Use of approved mix design |  | 1.3 Use of approved mix design
|  | 1.3 Use of approved mix design - Responsibility: Site Engineer | Responsibility: Site Engineer | 1.3 Use of approved mix design
|  | 1.4 Correct materials are being used |  | 1.4 Correct materials are being used
|  | 1.4 Correct materials are being used - Responsibility: Site Engineer | Responsibility: Site Engineer | 1.4 Correct materials are being used
|  | 1.5 Excavation Permit |  | 1.5 Excavation Permit
|  | 1.5 Excavation Permit - Responsibility: Site Engineer | Responsibility: Site Engineer | 1.5 Excavation Permit
|  | 2.1 Excavation |  | 2.1 Excavation
|  | 2.1 Excavation - Responsibility: Site Engineer/ Site Supervisor | Responsibility: Site Engineer/ Site Supervisor | 2.1 Excavation
|  | 2.2 Construction Methodology |  | 2.2 Construction Methodology
|  | 2.2 Construction Methodology - Responsibility: Site Engineer/ Site Supervisor | Responsibility: Site Engineer/ Site Supervisor | 2.2 Construction Methodology
|  | 2.3 Formwork levels & position |  | 2.3 Formwork levels and position
|  | 2.3 Formwork levels & position - Responsibility: Site Engineer/ Surveyor | Responsibility: Site Engineer/ Surveyor | 2.3 Formwork levels and position
|  | 3.1 Placement methodology |  | 3.1 Placement methodology
|  | 3.1 Placement methodology - Responsibility: Site Engineer/ Site Supervisor | Responsibility: Site Engineer/ Site Supervisor | 3.1 Placement methodology
|  | 3.2 Minimum Cover |  | 3.2 Minimum Cover
|  | 3.2 Minimum Cover - Responsibility: Site Engineer/ Site Supervisor | Responsibility: Site Engineer/ Site Supervisor | 3.2 Minimum Cover
|  | 4.1 Pre-pour Checklist |  | 4.1 Pre-pour Checklist
|  | 4.1 Pre-pour Checklist - Responsibility: Site Engineer | Responsibility: Site Engineer | 4.1 Pre-pour Checklist
|  | 4.2 Pre-pour inspection |  | 4.2 Pre-pour inspection
|  | 4.2 Pre-pour inspection - Responsibility: Site Engineer/ Superintendent | Responsibility: Site Engineer/ Superintendent | 4.2 Pre-pour inspection
|  | 4.3 Temperature |  | 4.3 Temperature
|  | 4.3 Temperature - Responsibility: Site Engineer/ Site Supervisor | Responsibility: Site Engineer/ Site Supervisor | 4.3 Temperature
|  | 5.1 Carry out sampling of concrete |  | 5.1 Carry out sampling of concrete
|  | 5.1 Carry out sampling of concrete - Responsibility: Site Engineer | Responsibility: Site Engineer | 5.1 Carry out sampling of concrete
|  | 5.2 Slump Testing |  | 5.2 Slump Testing
|  | 5.2 Slump Testing - Responsibility: Site Engineer | Responsibility: Site Engineer | 5.2 Slump Testing
|  | 5.3 Compressive testing |  | 5.3 Compressive testing
|  | 5.3 Compressive testing - Responsibility: Site Engineer | Responsibility: Site Engineer | 5.3 Compressive testing
|  | 5.4 Cleaning formwork |  | 5.4 Cleaning formwork
|  | 5.4 Cleaning formwork - Responsibility: Site Engineer/ Superintendent | Responsibility: Site Engineer/ Superintendent | 5.4 Cleaning formwork
|  | 5.5 Discharge time |  | 5.5 Discharge time
|  | 5.5 Discharge time - Responsibility: Site Engineer | Responsibility: Site Engineer | 5.5 Discharge time
|  | 5.6 Placement methodology |  | 5.6 Placement methodology
|  | 5.6 Placement methodology - Responsibility: Site Engineer/ Site Supervisor | Responsibility: Site Engineer/ Site Supervisor | 5.6 Placement methodology
|  | 5.7 Load Spacing |  | 5.7 Load Spacing
|  | 5.7 Load Spacing - Responsibility: Site Engineer/ Site Supervisor | Responsibility: Site Engineer/ Site Supervisor | 5.7 Load Spacing
|  | 5.8 Compaction |  | 5.8 Compaction
|  | 5.8 Compaction - Responsibility: Site Engineer/ Site Supervisor | Responsibility: Site Engineer/ Site Supervisor | 5.8 Compaction
|  | 5.9 Construction Joints |  | 5.9 Construction Joints
|  | 5.9 Construction Joints - Responsibility: Site Engineer/ Site Supervisor | Responsibility: Site Engineer/ Site Supervisor | 5.9 Construction Joints
|  | 6.1 Formwork removal |  | 6.1 Formwork removal
|  | 6.1 Formwork removal - Responsibility: Site Engineer | Responsibility: Site Engineer | 6.1 Formwork removal
|  | 6.2 Post-pour Checklist |  | 6.2 Post-pour Checklist
|  | 6.2 Post-pour Checklist - Responsibility: Site Engineer | Responsibility: Site Engineer | 6.2 Post-pour Checklist
|  | Final Inspection |  | Final Inspection
ITP 0079 - Watermain Construction
| Scope |  |  | ITP 0079 - Watermain Construction
Rows
|  | Utilities | dynamic | Utilities | ITP 0079 - Watermain Construction
Columns
|  | 1 Issued for construction drawings |  | 1 Issued for construction drawings
|  | 2 Permits with relevant authorities |  | 2 Permits with relevant authorities
|  | 3 Survey set-out |  | 3 Survey set-out
|  | 4 Service location |  | 4 Service location
|  | 4.1 Installation of property service conduits |  | 4.1 Installation of property service conduits
|  | 5 Correct pipe & fittings onsite |  | 5 Correct pipe and fittings onsite
|  | 6 Correct embedment / backfill materials onsite |  | 6 Correct embedment / backfill materials onsite
|  | 7 Environmental controls |  | 7 Environmental controls
|  | 8 Safety controls |  | 8 Safety controls
|  | 9 Trenching |  | 9 Trenching
|  | 10 Trenching |  | 10 Trenching
|  | 11 Placement of embedment material |  | 11 Placement of embedment material
|  | 12 Pipe laying |  | 12 Pipe laying
|  | 13 Property services |  | 13 Property services
|  | 14 Dual water property services |  | 14 Dual water property services
|  | 15 Valve installation |  | 15 Valve installation
|  | 16 Hydrant installation |  | 16 Hydrant installation
|  | 17 Washout installation |  | 17 Washout installation
|  | 18 Acceptance of concrete delivery |  | 18 Acceptance of concrete delivery
|  | 19 Installation of anchor blocks & thrust restraints |  | 19 Installation of anchor blocks and thrust restraints
|  | 19.1 Correct steel reinforcement used in restraint |  | 19.1 Correct steel reinforcement used in restraint
|  | 20 Placement of embedment overlay |  | 20 Placement of embedment overlay
|  | 21 Installation of detectable marker tape |  | 21 Installation of detectable marker tape
|  | 22 Placement of compactable material in trafficable areas |  | 22 Placement of compactable material in trafficable areas
|  | 23 Monitoring of WC1 works |  | 23 Monitoring of WC1 works
|  | 24 Monitoring of WC2 works |  | 24 Monitoring of WC2 works
|  | 25 Swabbing & flushing, Pressure test & Chlorination works |  | 25 Swabbing and flushing, Pressure test and Chlorination works
|  | 26 Water quality testing. |  | 26 Water quality testing.
|  | Final Inspection |  | Final Inspection
ITP 0081 - Structural Crack Repair
| Scope |  |  | ITP 0081 - Structural Crack Repair
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0081 - Structural Crack Repair
|  | Area 2 | dynamic | Area 2 | ITP 0081 - Structural Crack Repair
Columns
|  | Referenced Documentation |  | Referenced Documentation
|  | 2.1 - Assessment of Crack |  | 2.1 - Assessment of Crack
|  | 2.1 - Assessment of Crack - Teambinder Correspondence Approval number: | Teambinder Correspondence Approval number: | 2.1 - Assessment of Crack
|  | 2.2 - Work Procedure |  | 2.2 - Work Procedure
|  | 2.2 - Work Procedure - Teambinder Material Approval number: | Teambinder Material Approval number: | 2.2 - Work Procedure
|  | 3.1 - Resin Injection/Gravity Feed (Inactive): Epoxy or Polyurethane Resin Selection |  | 3.1 - Resin Injection/Gravity Feed (Inactive): Epoxy or Polyurethane Resin Selection
|  | 3.1 - Resin Injection/Gravity Feed (Inactive): Epoxy or Polyurethane Resin Selection - Teambinder Material Approval number: | Teambinder Material Approval number: | 3.1 - Resin Injection/Gravity Feed (Inactive): Epoxy or Polyurethane Resin Selection
|  | 3.2 - Routing & Sealing (Active): Flexible Sealant Selection |  | 3.2 - Routing and Sealing (Active): Flexible Sealant Selection
|  | 3.2 - Routing & Sealing (Active): Flexible Sealant Selection - Teambinder Material Approval number | Teambinder Material Approval number | 3.2 - Routing and Sealing (Active): Flexible Sealant Selection
|  | 3.3 - Routing & Sealing (Inactive): Epoxy Mortar or Paste Selection |  | 3.3 - Routing and Sealing (Inactive): Epoxy Mortar or Paste Selection
|  | 3.3 - Routing & Sealing (Inactive): Epoxy Mortar or Paste Selection - Teambinder Material Approval number | Teambinder Material Approval number | 3.3 - Routing and Sealing (Inactive): Epoxy Mortar or Paste Selection
|  | 3.4 - Protective Coating: Silane Selection - Inactive Cracks <0.2mm Width |  | 3.4 - Protective Coating: Silane Selection - Inactive Cracks <0.2mm Width
|  | 3.4 - Protective Coating: Silane Selection - Inactive Cracks <0.2mm Width - Teambinder Material Approval number: | Teambinder Material Approval number: | 3.4 - Protective Coating: Silane Selection - Inactive Cracks <0.2mm Width
|  | 4.1 - Contractor Competency |  | 4.1 - Contractor Competency
|  | 4.2 - Injection Equipment |  | 4.2 - Injection Equipment
|  | 4.3 - Weather Conditions |  | 4.3 - Weather Conditions
|  | 5.1 - Surface Preparation |  | 5.1 - Surface Preparation
|  | 5.2 - Resin Injection: Inactive Crack Repairs |  | 5.2 - Resin Injection: Inactive Crack Repairs
|  | 5.2 - Routing & Sealing: Active Crack Repairs |  | 5.2 - Routing & Sealing: Active Crack Repairs
|  | 5.3 - Routing & Sealing: Inactive Crack Repairs |  | 5.3 - Routing and Sealing: Inactive Crack Repairs
|  | 5.4 - Gravity Feed: Inactive Crack Repairs |  | 5.4 - Gravity Feed: Inactive Crack Repairs
|  | 5.6 - Penetrant Coating Method: Inactive Cracks <0.2mm Width Repairs |  | 5.6 - Penetrant Coating Method: Inactive Cracks <0.2mm Width Repairs
|  | 6.1 - Curing & Finishing |  | 6.1 - Curing & Finishing
|  | 6.2 - Repair Verification |  | 6.2 - Repair Verification
|  | 6.3 - Non-conformance Report (NCR) Closure |  | 6.3 - Non-conformance Report (NCR) Closure
|  | Final Inspection |  | Final Inspection
ITP 0082 - Structural Patch Repair
| Scope |  |  | ITP 0082 - Structural Patch Repair
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0082 - Structural Patch Repair
|  | Area 2 | dynamic | Area 2 | ITP 0082 - Structural Patch Repair
Columns
|  | Referenced Documentation |  | Referenced Documentation
|  | 2.1 - Assessment of Affected Concrete |  | 2.1 - Assessment of Affected Concrete
|  | 2.2 - Deviations from Manufacturer's TDS and/or Specification |  | 2.2 - Deviations from Manufacturer's TDS and/or Specification
|  | 2.3 - Work Method Statement & Inspection & Test Plans |  | 2.3 - Work Method Statement and Inspection and Test Plans
|  | 3.1 - Material approval & Reference |  | 3.1 - Material approval and Reference
|  | 3.1 - Material approval & Reference - TeamBinder Material Approval Number: | TeamBinder Material Approval Number: | 3.1 - Material approval and Reference
|  | 4.1 - Surface Preparation |  | 4.1 - Surface Preparation
|  | 4.2 - Pre Application of Repair Mortar |  | 4.2 - Pre Application of Repair Mortar
|  | 4.3 - Application of Repair Mortar |  | 4.3 - Application of Repair Mortar
|  | 4.4 - Measuring Tolerances |  | 4.4 - Measuring Tolerances
|  | 4.5 - Cementitious Repair Mortar Test Cubes |  | 4.5 - Cementitious Repair Mortar Test Cubes
|  | Final Inspection |  | Final Inspection
ITP 0083 - Precast Barriers (Supply & Installation)
| Scope |  |  | ITP 0083 - Precast Barriers (Supply & Installation)
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0083 - Precast Barriers (Supply & Installation)
|  | Area 2 | dynamic | Area 2 | ITP 0083 - Precast Barriers (Supply & Installation)
Columns
|  | Referenced Documentation |  | Referenced Documentation
|  | 2.1 - Precast Elements |  | 2.1 - Precast Elements
|  | 2.2 - Joint Sealant |  | 2.2 - Joint Sealant
|  | 2.2 - Joint Sealant - Teambinder Material Approval number: | Teambinder Material Approval number: | 2.2 - Joint Sealant
|  | 3.1 - Survey Set-out of Precast Elements |  | 3.1 - Survey Set-out of Precast Elements
|  | 3.2 - Sealing Strips, Backing Rod & Bitumen Board |  | 3.2 - Sealing Strips, Backing Rod & Bitumen Board
|  | 3.3 - Materials Inspection Checklist |  | 3.3 - Materials Inspection Checklist
|  | 4.1 - Precast Handling |  | 4.1 - Precast Handling
|  | 4.2 - Precast Placement |  | 4.2 - Precast Placement
|  | 4.3 - Draw-string in Service Ducts |  | 4.3 - Draw-string in Service Ducts
|  | 4.4 - Precast Traceability |  | 4.4 - Precast Traceability
|  | 5.1 - Joint Sealant Application |  | 5.1 - Joint Sealant Application
|  | 5.2 - Flowable Grout Pour |  | 5.2 - Flowable Grout Pour
|  | 5.3 - Barrier fencing |  | 5.3 - Barrier fencing
|  | 5.4 - As-built Survey |  | 5.4 - As-built Survey
|  | 5.5 - Non-conformance Report (NCR) Closure |  | 5.5 - Non-conformance Report (NCR) Closure
|  | Final Inspection |  | Final Inspection
ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS
| Scope |  |  | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS
|  | Area 2 | dynamic | Area 2 | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS
Columns
|  | 1.1 - Induction |  | 1.1 - Induction
|  | 1.2 - Check that current revision drawings are being used |  | 1.2 - Check that current revision drawings are being used
|  | 1.3 - Confirm understanding of current Construction Environment Management Plan (CEMP) & Environmental Control Plan (ECP) related to the work area & that all prescribed environmental controls are in place |  | 1.3 - Confirm understanding of current Construction Environment Management Plan (CEMP) and Environmental Control Plan (ECP) related to the work area and that all prescribed environmental controls are in place
|  | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken |  | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
|  | 1.5 - Excavation Permit issued (if required) |  | 1.5 - Excavation Permit issued (if required)
|  | 2.1 - Stabilised Subgrade |  | 2.1 - Stabilised Subgrade
|  | 2.2 - Investigation & determination of design lime spreading rate |  | 2.2 - Investigation and determination of design lime spreading rate
|  | 2.3 - Material Selection |  | 2.3 - Material Selection
|  | 2.4 - Preliminary trial |  | 2.4 - Preliminary trial
|  | 3.2 - Preparation of Subgrade |  | 3.2 - Preparation of Subgrade
|  | 3.3 - Proof Roll |  | 3.3 - Proof Roll
|  | 3.4 - Pre-treatment of earthworks |  | 3.4 - Pre-treatment of earthworks
|  | 3.5 - Spreading of Lime |  | 3.5 - Spreading of Lime
|  | 3.6 - Slaking of Quicklime |  | 3.6 - Slaking of Quicklime
|  | 3.7 - Mixing |  | 3.7 - Mixing
|  | 3.8 - Compaction |  | 3.8 - Compaction
|  | 3.9 - Trimming |  | 3.9 - Trimming
|  | 3.10 - Curing & protection of compacted layers |  | 3.10 - Curing and protection of compacted layers
|  | 4.1 - Requirements & Acceptance of Lime Spreading Rate |  | 4.1 - Requirements and Acceptance of Lime Spreading Rate
|  | 4.2 - Subgrade Testing |  | 4.2 - Subgrade Testing
|  | Test Requisition |  | Test Requisition
|  | Test Requisition - Test Requested on | Test Requested on | Test Requisition
|  | Test Requisition - Location | Location | Test Requisition
|  | Test Requisition - Material Type | Material Type | Test Requisition
|  | Test Requisition - Material Source | Material Source | Test Requisition
|  | Test Requisition - Compaction Test (Standard) | Compaction Test (Standard) | Test Requisition
|  | Test Requisition - Compaction Test (Modified) | Compaction Test (Modified) | Test Requisition
|  | Test Requisition - Maximum Particle Test | Maximum Particle Test | Test Requisition
|  | Test Requisition - CBR/Swell Test | CBR/Swell Test | Test Requisition
|  | Test Requisition - PI Test | PI Test | Test Requisition
|  | Test Requisition - Permeability Test | Permeability Test | Test Requisition
|  | Test Requisition - Grading | Grading | Test Requisition
|  | Test Requisition - Moisture | Moisture | Test Requisition
|  | Test Requisition - See comments | See comments | Test Requisition
|  | Test Requisition - Test Level/ Layer | Test Level/ Layer | Test Requisition
|  | Final Inspection |  | Final Inspection
ITP 0085 - SUP INSTALLATION (HCC)
| Scope |  |  | ITP 0085 - SUP INSTALLATION (HCC)
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0085 - SUP INSTALLATION (HCC)
|  | Area 2 | dynamic | Area 2 | ITP 0085 - SUP INSTALLATION (HCC)
Columns
|  | 1.1 - Check that current revision drawings are being used |  | 1.1 - Check that current revision drawings are being used
|  | 1.2 - Bedding Material / Base Layer |  | 1.2 - Bedding Material / Base Layer
|  | 1.2 - Bedding Material / Base Layer - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.2 - Bedding Material / Base Layer
|  | 1.3 - Concrete Mix |  | 1.3 - Concrete Mix
|  | 1.3 - Concrete Mix - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.3 - Concrete Mix
|  | 1.4 - Evaporative Retardant |  | 1.4 - Evaporative Retardant
|  | 1.4 - Evaporative Retardant - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.4 - Evaporative Retardant
|  | 1.5 - Curing Compound |  | 1.5 - Curing Compound
|  | 1.5 - Curing Compound - Teambinder Material Approval number | Enter: Teambinder Material Approval number | 1.5 - Curing Compound
|  | 2.1 - Temporary Drainage Provisions (if required) |  | 2.1 - Temporary Drainage Provisions (if required)
|  | 2.2 - Pavement Thickness Increases for Crossings |  | 2.2 - Pavement Thickness Increases for Crossings
|  | 2.3 - Bedding Preparation |  | 2.3 - Bedding Preparation
|  | 2.4 - Formwork |  | 2.4 - Formwork
|  | 2.5 - Steel Reinforcement |  | 2.5 - Steel Reinforcement
|  | 2.6 - Pre-pour inspection |  | 2.6 - Pre-pour inspection
|  | 2.7 - Concrete Testing |  | 2.7 - Concrete Testing
|  | 2.8 - Curing |  | 2.8 - Curing
|  | 2.9 - Tolerances |  | 2.9 - Tolerances
|  | 2.10 - Joints |  | 2.10 - Joints
|  | 2.11 - Stripping Formwork |  | 2.11 - Stripping Formwork
|  | 2.12 - Protection of Newly Poured Concrete |  | 2.12 - Protection of Newly Poured Concrete
|  | 3.1 - Survey data captured for as-built purposes |  | 3.1 - Survey data captured for as-built purposes
|  | 3.2 - Cracking of Concrete |  | 3.2 - Cracking of Concrete
|  | 3.2 - Compressive Strength Test Results |  | 3.2 - Compressive Strength Test Results
|  | 3.3 - Backfilling |  | 3.3 - Backfilling
|  | 4.1 - As-built Survey |  | 4.1 - As-built Survey
|  | 4.2 - Red-Line Markup |  | 4.2 - Red-Line Markup
|  | 4.3 - Non-conformance Report (NCR) Closure |  | 4.3 - Non-conformance Report (NCR) Closure
|  | Final Inspection |  | Final Inspection
ITP 0086 - Welding Carbon Reinforcement
| Scope |  |  | ITP 0086 - Welding Carbon Reinforcement
Rows
|  | Area 1 | dynamic | Area 1 | ITP 0086 - Welding Carbon Reinforcement
|  | Area 2 | dynamic | Area 2 | ITP 0086 - Welding Carbon Reinforcement
Columns
|  | 1.1 - Induction |  | 1.1 - Induction
|  | 1.2 - Check that current revision drawings are being used |  | 1.2 - Check that current revision drawings are being used
|  | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken |  | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
|  | 2.1 - Welding Procedure Qualification |  | 2.1 - Welding Procedure Qualification
|  | 3.1 - Surface Preparation |  | 3.1 - Surface Preparation
|  | 3.2 - Assembly |  | 3.2 - Assembly
|  | 3.3 - Preheating |  | 3.3 - Preheating
|  | 3.4 - Weather Conditions |  | 3.4 - Weather Conditions
|  | 4.1 - Inspection & Quality of Welds |  | 4.1 - Inspection and Quality of Welds
|  | Final Inspection |  | Final Inspection