## Table 1
LOCATION | SIGNAGE TYPE | ITP CHECKLIST ITEMS
Parish Hall
| P.1 – Digital Totem Sign |  Manufacture sign as per Approved brief and shop drawings.  Install base plate onto footing (Footing by RCC). Core drill holes for M10 bolets in slab.  Install Signage as per approved locations – ref MAAT-GEN-MPN-001 & 3  Connect Digital Signage through Electrical provisions. Power supplied in conduit by others. Conduit inserted through base into centre section and connected to monito  Testing and Commissioning to occur using generic software on external tablet via wi-fi..
| D.2.1 – Precinct Directional Sign |  Manufacture sign as per Approved Documentation.  Install base plate onto footing (Footing by RCC). Core drill holes for M10 bolets in slab.  Install Signage as per approved locations – ref MAAT-GEN-MPN-001 & 3  Connect Power. Power supplied in conduit by others. Conduit inserted through base.  Testing that lighting is operational
| I.6.2 – Laser cut street numbers |  Manufacture letters as per approved artwork, 316 marine grade stainless steel  Set out drilling template on wall as per brief, being height AFFL and in from left hand edge.  Drill 4mm holes for pins, locating through template.  Inject Chemset into holes, Insert letters, space off wall to ensure uniformity off wall.
School
| I.2 – School Building ID |  Manufacture letters as per approved artwork.  Set out drilling template on wall as per brief, being height AFFL and in from left hand edge.  Drill 6mm holes for pins, locating through template.  Inject Chemset into holes, Insert letters, space off wall to ensure uniformity off wall.
| I.6.2 – Laser cut street numbers |  Manufacture letters as per approved artwork.  Set out drilling template on wall as per brief, being height AFFL and in from left hand edge.  Drill 4mm holes for pins, locating through template.  Inject Chemset into holes, Insert letters, space off wall to ensure uniformity off wall.
Cambridge St
| I.6.2 – Laser cut street numbers |  Manufacture letters as per approved artwork.  Set out drilling template on wall as per brief, being height AFFL and in from left hand edge.  Drill 4mm holes for pins, locating through template.  Inject Chemset into holes, Insert letters, space off wall to ensure uniformity off wall.
| I.9.1 – Illuminated Under Awning Sign (Retail Space) |  Manufacture according to approved shop drawing.  Measure and drill fixing holes in awning, location as per brief.  PSU located inside sign. Connect to powere (Power provided to location by others)  Test lighting is operational.