## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | P.1 - Digital Totem Sign
section | Digital Totem Sign
checkpoint | Manufacture sign as per Approved brief and shop drawings.
checkpoint | Install base plate onto footing (Footing by RCC). Core drill holes for M10 bolets in slab.
checkpoint | Install Signage as per approved locations – ref MAAT-GEN-MPN-001 & 3.
checkpoint | Connect Digital Signage through Electrical provisions. Power supplied in conduit by others. Conduit inserted through base into centre section and connected to monitor.
checkpoint | Testing and Commissioning to occur using generic software on external tablet via wi-fi.
checklist | D.2.1 - Precinct Directional Sign
section | Precinct Directional Sign
checkpoint | Manufacture sign as per Approved Documentation.
checkpoint | Install base plate onto footing (Footing by RCC). Core drill holes for M10 bolets in slab.
checkpoint | Install Signage as per approved locations – ref MAAT-GEN-MPN-001 & 3
checkpoint | Connect Power. Power supplied in conduit by others. Conduit inserted through base.
checkpoint | Testing that lighting is operational.
checklist | I.6.2 - Laser Cut Street Numbers
section | Laser Cut Street Numbers
checkpoint | Manufacture letters as per approved artwork, 316 marine grade stainless steel.
checkpoint | Set out drilling template on wall as per brief, being height AFFL and in from left hand edge.
checkpoint | Drill 4mm holes for pins, locating through template.
checkpoint | Inject Chemset into holes, Insert letters, space off wall to ensure uniformity off wall.
checklist | I.2 - School Building ID
section | School Building ID
checkpoint | Manufacture letters as per approved artwork.
checkpoint | Set out drilling template on wall as per brief, being height AFFL and in from left hand edge.
checkpoint | Drill 6mm holes for pins, locating through template.
checkpoint | Inject Chemset into holes, Insert letters, space off wall to ensure uniformity off wall.
checklist | I.9.1 - Illuminated Under Awning Sign (Retail Space)
section | Illuminated Under Awning Sign (Retail Space)
checkpoint | Manufacture according to approved shop drawing.
checkpoint | Measure and drill fixing holes in awning, location as per brief.
checkpoint | PSU located inside sign. Connect to power (Power provided to location by others).
checkpoint | Test lighting is operational.