## Sheet1
1 | Device Product Data Sheets | W | Recommended CCTV Data Sheets as Per Provided Drawings | As Required | Visual Inspection | Manufacturers Data Sheet | 3000 | 1 - Device Product Data Sheets | ACTION (W, M, H) - W | CONFORMANCE CRITERIA (WHATS REQUIRED) - Recommended CCTV Data Sheets as Per Provided Drawings | FREQUENCY - As Required | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - Manufacturers Data Sheet | AS/NZS STANDARD - 3000 | 1 - Device Product Data Sheets
2 | Provided Security Drawings | M | As Per Provided Construction Drawings By Downer Construction | As Required | Visual Inspection | Design drawings |  | 2 - Provided Security Drawings | ACTION (W, M, H) - M | CONFORMANCE CRITERIA (WHATS REQUIRED) - As Per Provided Construction Drawings By Downer Construction | FREQUENCY - As Required | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - Design drawings | AS/NZS STANDARD - | ACTION (W, M, H) - W
3 | Device FAT Testing - Off Site | W | Device Testing and Pre-Setup | As Required | Visual Inspection | CSLI-CCTV-FAT CSLI-EHP-FAT CSLI-PID-FAT |  | 3 - Device FAT Testing - Off Site | ACTION (W, M, H) - W | CONFORMANCE CRITERIA (WHATS REQUIRED) - Device Testing and Pre-Setup | FREQUENCY - As Required | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - CSLI-CCTV-FAT CSLI-EHP-FAT CSLI-PID-FAT | AS/NZS STANDARD - | CONFORMANCE CRITERIA (WHATS REQUIRED) - Recommended CCTV Data Sheets as Per Provided Drawings
1 | Sub-Contractor Installed Cabling | H | Point to Point testing completed by cabling contractor confirmimg cabling is sufficient to use. | Always | Cable Testing | Design drawings | 3000, 3008, 3017, 1660 | 1 - Sub-Contractor Installed Cabling | ACTION (W, M, H) - H | CONFORMANCE CRITERIA (WHATS REQUIRED) - Point to Point testing completed by cabling contractor confirmimg cabling is sufficient to use. | FREQUENCY - Always | INSPECTION / TEST METHOD - Cable Testing | VERIFICATION RECORDS - Design drawings | AS/NZS STANDARD - 3000, 3008, 3017, 1660 | FREQUENCY - As Required
1 | Completed Asset data sheets | W | Complete asset data sheets for each camera and send through to the networks team for IP Address assignment | Pre-Commissioning | Visual Inspection | AT Asset data sheet |  | 1 - Completed Asset data sheets | ACTION (W, M, H) - W | CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete asset data sheets for each camera and send through to the networks team for IP Address assignment | FREQUENCY - Pre-Commissioning | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - AT Asset data sheet | AS/NZS STANDARD - | INSPECTION / TEST METHOD - Visual Inspection
2 | Network switch port allocation | H | Confirm with networks team on which device has been assigned to each network port | Pre-Commissioning | Visual Inspection |  |  | 2 - Network switch port allocation | ACTION (W, M, H) - H | CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with networks team on which device has been assigned to each network port | FREQUENCY - Pre-Commissioning | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - | AS/NZS STANDARD - | VERIFICATION RECORDS - Manufacturers Data Sheet
3 | Installation of cameras at provided locations | M | Correct camera models are installed in the locations as per provided design drawings | Always | Visual Inspection FAT reported viewed | Design drawings | 3000, 3008, 3017, 62676 | 3 - Installation of cameras at provided locations | ACTION (W, M, H) - M | CONFORMANCE CRITERIA (WHATS REQUIRED) - Correct camera models are installed in the locations as per provided design drawings | FREQUENCY - Always | INSPECTION / TEST METHOD - Visual Inspection FAT reported viewed | VERIFICATION RECORDS - Design drawings | AS/NZS STANDARD - 3000, 3008, 3017, 62676 | AS/NZS STANDARD - 3000
4 | Allignment of camera FOV as per coordination with AT rep | H | Field Of Views to be coordinated with both AT/AOR to capture required images | Always | Visual Inspection Network connection testing |  |  | 4 - Allignment of camera FOV as per coordination with AT rep | ACTION (W, M, H) - H | CONFORMANCE CRITERIA (WHATS REQUIRED) - Field Of Views to be coordinated with both AT/AOR to capture required images | FREQUENCY - Always | INSPECTION / TEST METHOD - Visual Inspection Network connection testing | VERIFICATION RECORDS - | AS/NZS STANDARD - | 2 - Provided Security Drawings
5 | Installation Verification | W | Onsite SAT Test to be completed and signed | Post Commissioning | Visual Inspection | CSLI-CCTV-SAT |  | 5 - Installation Verification | ACTION (W, M, H) - W | CONFORMANCE CRITERIA (WHATS REQUIRED) - Onsite SAT Test to be completed and signed | FREQUENCY - Post Commissioning | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - CSLI-CCTV-SAT | AS/NZS STANDARD - | ACTION (W, M, H) - M
1 | Completed Asset data sheets | W | Complete asset data sheets for each EHP and send through to the networks team for IP Address assignment | Pre-Commissioning | Visual Inspection | AT Asset data sheet |  | 1 - Completed Asset data sheets | ACTION (W, M, H) - W | CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete asset data sheets for each EHP and send through to the networks team for IP Address assignment | FREQUENCY - Pre-Commissioning | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - AT Asset data sheet | AS/NZS STANDARD - | CONFORMANCE CRITERIA (WHATS REQUIRED) - As Per Provided Construction Drawings By Downer Construction
2 | Network switch port allocation | H | Confirm with networks team on which device has been assigned to each network port | Pre-Commissioning | Visual Inspection |  |  | 2 - Network switch port allocation | ACTION (W, M, H) - H | CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with networks team on which device has been assigned to each network port | FREQUENCY - Pre-Commissioning | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - | AS/NZS STANDARD - | FREQUENCY - As Required
3 | Installation of EHPs in provided locations | M | Installation as per provided design drawings EHP is installed using correct concrete fixtures and is sturdy | Always | Visual Inspection FAT Report Sighted | Design drawings | 3000, 3008 CHAR(AMP) 3017 | 3 - Installation of EHPs in provided locations | ACTION (W, M, H) - M | CONFORMANCE CRITERIA (WHATS REQUIRED) - Installation as per provided design drawings EHP is installed using correct concrete fixtures and is sturdy | FREQUENCY - Always | INSPECTION / TEST METHOD - Visual Inspection FAT Report Sighted | VERIFICATION RECORDS - Design drawings | AS/NZS STANDARD - 3000, 3008 CHAR(AMP) 3017 | INSPECTION / TEST METHOD - Visual Inspection
4 | VOIP between Service desk and onsite unit | H | Confirm with Service desk operator that both Mic and Speaker are operating correctly | Always | Communication Testing Network connection testing |  |  | 4 - VOIP between Service desk and onsite unit | ACTION (W, M, H) - H | CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with Service desk operator that both Mic and Speaker are operating correctly | FREQUENCY - Always | INSPECTION / TEST METHOD - Communication Testing Network connection testing | VERIFICATION RECORDS - | AS/NZS STANDARD - | VERIFICATION RECORDS - Design drawings
5 | Installation Verification | W | Onsite SAT Test to be completed and signed | Post Commissioning | Visual Inspection | CSLI-EHP-SAT |  | 5 - Installation Verification | ACTION (W, M, H) - W | CONFORMANCE CRITERIA (WHATS REQUIRED) - Onsite SAT Test to be completed and signed | FREQUENCY - Post Commissioning | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - CSLI-EHP-SAT | AS/NZS STANDARD - | AS/NZS STANDARD -
1 | Completed Asset data sheets | W | Complete asset data sheets for each PID and send through to the networks team for IP Address assignment | Pre-Commissioning | Visual Inspection | AT Asset data sheet |  | 1 - Completed Asset data sheets | ACTION (W, M, H) - W | CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete asset data sheets for each PID and send through to the networks team for IP Address assignment | FREQUENCY - Pre-Commissioning | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - AT Asset data sheet | AS/NZS STANDARD - | 3 - Device FAT Testing - Off Site
2 | Network switch port allocation | H | Confirm with networks team on which device has been assigned to each network port | Pre-Commissioning | Visual Inspection |  |  | 2 - Network switch port allocation | ACTION (W, M, H) - H | CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with networks team on which device has been assigned to each network port | FREQUENCY - Pre-Commissioning | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - | AS/NZS STANDARD - | ACTION (W, M, H) - W
3 | Installation of PIDs in provided locations | M | Installation as per provided design drawings PID is installed using correct fixtures and is sturdy | Always | Visual Inspection Electrical Testing FAT Report Sighted | Design drawings | 3000, 3008 CHAR(AMP) 3017 | 3 - Installation of PIDs in provided locations | ACTION (W, M, H) - M | CONFORMANCE CRITERIA (WHATS REQUIRED) - Installation as per provided design drawings PID is installed using correct fixtures and is sturdy | FREQUENCY - Always | INSPECTION / TEST METHOD - Visual Inspection Electrical Testing FAT Report Sighted | VERIFICATION RECORDS - Design drawings | AS/NZS STANDARD - 3000, 3008 CHAR(AMP) 3017 | CONFORMANCE CRITERIA (WHATS REQUIRED) - Device Testing and Pre-Setup
4 | Test connection to Playlist system | H | Playlist is able to send communications to PID PC Time clock and schedule updates with current state | Always | Communication Testing Network connection testing |  |  | 4 - Test connection to Playlist system | ACTION (W, M, H) - H | CONFORMANCE CRITERIA (WHATS REQUIRED) - Playlist is able to send communications to PID PC Time clock and schedule updates with current state | FREQUENCY - Always | INSPECTION / TEST METHOD - Communication Testing Network connection testing | VERIFICATION RECORDS - | AS/NZS STANDARD - | FREQUENCY - As Required
5 | Installation Verification | W | Onsite SAT Test to be completed and signed | Post Commissioning | Visual Inspection | CSLI-PID-SAT |  | 5 - Installation Verification | ACTION (W, M, H) - W | CONFORMANCE CRITERIA (WHATS REQUIRED) - Onsite SAT Test to be completed and signed | FREQUENCY - Post Commissioning | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - CSLI-PID-SAT | AS/NZS STANDARD - | INSPECTION / TEST METHOD - Visual Inspection
1 | CCTV System | W | Wittness completed for camera location and operation | Post Commissioning | Visual Inspections | CSLI-CCTV-FAT CSLI-CCTV-SAT | 3000, 3017 | 1 - CCTV System | ACTION (W, M, H) - W | CONFORMANCE CRITERIA (WHATS REQUIRED) - Wittness completed for camera location and operation | FREQUENCY - Post Commissioning | INSPECTION / TEST METHOD - Visual Inspections | VERIFICATION RECORDS - CSLI-CCTV-FAT CSLI-CCTV-SAT | AS/NZS STANDARD - 3000, 3017 | VERIFICATION RECORDS - CSLI-CCTV-FAT CSLI-EHP-FAT CSLI-PID-FAT
2 | EHP System | W | Wittness completed for camera location and operation | Post Commissioning | Visual Inspections | CSLI-EHP-FAT CSLI-EHP-SAT | 3000, 3017 | 2 - EHP System | ACTION (W, M, H) - W | CONFORMANCE CRITERIA (WHATS REQUIRED) - Wittness completed for camera location and operation | FREQUENCY - Post Commissioning | INSPECTION / TEST METHOD - Visual Inspections | VERIFICATION RECORDS - CSLI-EHP-FAT CSLI-EHP-SAT | AS/NZS STANDARD - 3000, 3017 | AS/NZS STANDARD -
3 | PID System | W | Wittness completed for camera location and operation | Post Commissioning | Visual Inspections Electrical Tests | CSLI-PID-FAT CSLI-PID-SAT | 3000, 3017 | 3 - PID System | ACTION (W, M, H) - W | CONFORMANCE CRITERIA (WHATS REQUIRED) - Wittness completed for camera location and operation | FREQUENCY - Post Commissioning | INSPECTION / TEST METHOD - Visual Inspections Electrical Tests | VERIFICATION RECORDS - CSLI-PID-FAT CSLI-PID-SAT | AS/NZS STANDARD - 3000, 3017 | 1 - Sub-Contractor Installed Cabling
1 | QA and checksheet documentation | M | Complete and submit the following documents - Commissioning and testing Checksheets - Compliance certificates and producer statements - Schedule of Test Results for the installation - Assets updated in AT Device management System | Post Commissioning | Visual inspection | Checksheets, ITPs, electrical test certificates are complete and filed within the OCHAR(AMP)M manual |  | 1 - QA and checksheet documentation | ACTION (W, M, H) - M | CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete and submit the following documents - Commissioning and testing Checksheets - Compliance certificates and producer statements - Schedule of Test Results for the installation - Assets updated in AT Device management System | FREQUENCY - Post Commissioning | INSPECTION / TEST METHOD - Visual inspection | VERIFICATION RECORDS - Checksheets, ITPs, electrical test certificates are complete and filed within the OCHAR(AMP)M manual | AS/NZS STANDARD - | ACTION (W, M, H) - H
2 | Final inspection with Client | M | Client to review installation is completed as per other sections of this ITP | Post Commissioning | Visual Inspection | ITP | N/A | 2 - Final inspection with Client | ACTION (W, M, H) - M | CONFORMANCE CRITERIA (WHATS REQUIRED) - Client to review installation is completed as per other sections of this ITP | FREQUENCY - Post Commissioning | INSPECTION / TEST METHOD - Visual Inspection | VERIFICATION RECORDS - ITP | AS/NZS STANDARD - N/A | CONFORMANCE CRITERIA (WHATS REQUIRED) - Point to Point testing completed by cabling contractor confirmimg cabling is sufficient to use.
FREQUENCY - Always
INSPECTION / TEST METHOD - Cable Testing
VERIFICATION RECORDS - Design drawings
AS/NZS STANDARD - 3000, 3008, 3017, 1660
1 - Completed Asset data sheets
ACTION (W, M, H) - W
CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete asset data sheets for each camera and send through to the networks team for IP Address assignment
FREQUENCY - Pre-Commissioning
INSPECTION / TEST METHOD - Visual Inspection
VERIFICATION RECORDS - AT Asset data sheet
AS/NZS STANDARD -
2 - Network switch port allocation
ACTION (W, M, H) - H
CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with networks team on which device has been assigned to each network port
FREQUENCY - Pre-Commissioning
INSPECTION / TEST METHOD - Visual Inspection
VERIFICATION RECORDS -
AS/NZS STANDARD -
3 - Installation of cameras at provided locations
ACTION (W, M, H) - M
CONFORMANCE CRITERIA (WHATS REQUIRED) - Correct camera models are installed in the locations as per provided design drawings
FREQUENCY - Always
INSPECTION / TEST METHOD - Visual Inspection FAT reported viewed
VERIFICATION RECORDS - Design drawings
AS/NZS STANDARD - 3000, 3008, 3017, 62676
4 - Allignment of camera FOV as per coordination with AT rep
ACTION (W, M, H) - H
CONFORMANCE CRITERIA (WHATS REQUIRED) - Field Of Views to be coordinated with both AT/AOR to capture required images
FREQUENCY - Always
INSPECTION / TEST METHOD - Visual Inspection Network connection testing
VERIFICATION RECORDS -
AS/NZS STANDARD -
5 - Installation Verification
ACTION (W, M, H) - W
CONFORMANCE CRITERIA (WHATS REQUIRED) - Onsite SAT Test to be completed and signed
FREQUENCY - Post Commissioning
INSPECTION / TEST METHOD - Visual Inspection
VERIFICATION RECORDS - CSLI-CCTV-SAT
AS/NZS STANDARD -
1 - Completed Asset data sheets
ACTION (W, M, H) - W
CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete asset data sheets for each EHP and send through to the networks team for IP Address assignment
FREQUENCY - Pre-Commissioning
INSPECTION / TEST METHOD - Visual Inspection
VERIFICATION RECORDS - AT Asset data sheet
AS/NZS STANDARD -
2 - Network switch port allocation
ACTION (W, M, H) - H
CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with networks team on which device has been assigned to each network port
FREQUENCY - Pre-Commissioning
INSPECTION / TEST METHOD - Visual Inspection
VERIFICATION RECORDS -
AS/NZS STANDARD -
3 - Installation of EHPs in provided locations
ACTION (W, M, H) - M
CONFORMANCE CRITERIA (WHATS REQUIRED) - Installation as per provided design drawings EHP is installed using correct concrete fixtures and is sturdy
FREQUENCY - Always
INSPECTION / TEST METHOD - Visual Inspection FAT Report Sighted
VERIFICATION RECORDS - Design drawings
AS/NZS STANDARD - 3000, 3008 CHAR(AMP) 3017
4 - VOIP between Service desk and onsite unit
ACTION (W, M, H) - H
CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with Service desk operator that both Mic and Speaker are operating correctly
FREQUENCY - Always
INSPECTION / TEST METHOD - Communication Testing Network connection testing
VERIFICATION RECORDS -
AS/NZS STANDARD -
5 - Installation Verification
ACTION (W, M, H) - W
CONFORMANCE CRITERIA (WHATS REQUIRED) - Onsite SAT Test to be completed and signed
FREQUENCY - Post Commissioning
INSPECTION / TEST METHOD - Visual Inspection
VERIFICATION RECORDS - CSLI-EHP-SAT
AS/NZS STANDARD -
1 - Completed Asset data sheets
ACTION (W, M, H) - W
CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete asset data sheets for each PID and send through to the networks team for IP Address assignment
FREQUENCY - Pre-Commissioning
INSPECTION / TEST METHOD - Visual Inspection
VERIFICATION RECORDS - AT Asset data sheet
AS/NZS STANDARD -
2 - Network switch port allocation
ACTION (W, M, H) - H
CONFORMANCE CRITERIA (WHATS REQUIRED) - Confirm with networks team on which device has been assigned to each network port
FREQUENCY - Pre-Commissioning
INSPECTION / TEST METHOD - Visual Inspection
VERIFICATION RECORDS -
AS/NZS STANDARD -
3 - Installation of PIDs in provided locations
ACTION (W, M, H) - M
CONFORMANCE CRITERIA (WHATS REQUIRED) - Installation as per provided design drawings PID is installed using correct fixtures and is sturdy
FREQUENCY - Always
INSPECTION / TEST METHOD - Visual Inspection Electrical Testing FAT Report Sighted
VERIFICATION RECORDS - Design drawings
AS/NZS STANDARD - 3000, 3008 CHAR(AMP) 3017
4 - Test connection to Playlist system
ACTION (W, M, H) - H
CONFORMANCE CRITERIA (WHATS REQUIRED) - Playlist is able to send communications to PID PC Time clock and schedule updates with current state
FREQUENCY - Always
INSPECTION / TEST METHOD - Communication Testing Network connection testing
VERIFICATION RECORDS -
AS/NZS STANDARD -
5 - Installation Verification
ACTION (W, M, H) - W
CONFORMANCE CRITERIA (WHATS REQUIRED) - Onsite SAT Test to be completed and signed
FREQUENCY - Post Commissioning
INSPECTION / TEST METHOD - Visual Inspection
VERIFICATION RECORDS - CSLI-PID-SAT
AS/NZS STANDARD -
1 - CCTV System
ACTION (W, M, H) - W
CONFORMANCE CRITERIA (WHATS REQUIRED) - Wittness completed for camera location and operation
FREQUENCY - Post Commissioning
INSPECTION / TEST METHOD - Visual Inspections
VERIFICATION RECORDS - CSLI-CCTV-FAT CSLI-CCTV-SAT
AS/NZS STANDARD - 3000, 3017
2 - EHP System
ACTION (W, M, H) - W
CONFORMANCE CRITERIA (WHATS REQUIRED) - Wittness completed for camera location and operation
FREQUENCY - Post Commissioning
INSPECTION / TEST METHOD - Visual Inspections
VERIFICATION RECORDS - CSLI-EHP-FAT CSLI-EHP-SAT
AS/NZS STANDARD - 3000, 3017
3 - PID System
ACTION (W, M, H) - W
CONFORMANCE CRITERIA (WHATS REQUIRED) - Wittness completed for camera location and operation
FREQUENCY - Post Commissioning
INSPECTION / TEST METHOD - Visual Inspections Electrical Tests
VERIFICATION RECORDS - CSLI-PID-FAT CSLI-PID-SAT
AS/NZS STANDARD - 3000, 3017
1 - QA and checksheet documentation
ACTION (W, M, H) - M
CONFORMANCE CRITERIA (WHATS REQUIRED) - Complete and submit the following documents - Commissioning and testing Checksheets - Compliance certificates and producer statements - Schedule of Test Results for the installation - Assets updated in AT Device management System
FREQUENCY - Post Commissioning
INSPECTION / TEST METHOD - Visual inspection
VERIFICATION RECORDS - Checksheets, ITPs, electrical test certificates are complete and filed within the OCHAR(AMP)M manual
AS/NZS STANDARD -
2 - Final inspection with Client
ACTION (W, M, H) - M
CONFORMANCE CRITERIA (WHATS REQUIRED) - Client to review installation is completed as per other sections of this ITP
FREQUENCY - Post Commissioning
INSPECTION / TEST METHOD - Visual Inspection
VERIFICATION RECORDS - ITP
AS/NZS STANDARD - N/A