## Sheet1
Inspection and Test Plan Te Ara o Te Ata Earthworks Cut - ITP - 004
This ITP has been prepared by |  |  |  | Reviewed by [as applicable] |  |  |  | Reviewed by DSR | [5 empty] | Approved by [as applicable]
Rev Number |  | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date |  | Name |  | Signature |  | Date
Rev 01 |  | Isaac Dunn | I.D | 2022-08-24 | TeAmorangi Simeon | T.S | 2022-08-29 | Danny Beasant |  | D.B |  | 2022-11-17
Rev 02
Rev 03
Rev 04
ITP NO: CONQA # |  |  | Project: Te Ara o Te Ata | [8 empty] | Rev.A
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [8 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity/Specification: Earthworks Cut
Item | Titles | Description |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Method (H,I,W,R) |  |  | Verifying Records |  | Site Engineer approved | DSR Engineer verification | Certified Complete (Date, relevant checklist title/lab report number etc)
Responsible [tick]
[6 empty] | Method/Description | Test frequency |  | Conformance Criteria | Constructor | Designer
1.0 Pre-Construction
1.01 | Approved CWP | CWP |  | Health and safety management plan |  | Document Review | Prior to personal starting |  | Ensure all crew members are briefed on the CWP | H |  |  | signed off CWP
1.02 | IFC issued | Design |  | Consent conditions |  | Document Review | Prior to starting |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB | H |  |  | IFC drawings or written approval from PAB
1.03 | Approved SCWMP | SCWMP |  | Consent conditions |  | Document Review | Once prior to works commencing |  | TRC review and approval | H |  |  | Approved SCWMP
2.0 During Construction
2.01 | Set out extents | Set out extents of cut and check against design |  | IFC drawings |  | Survey/visual | Prior to Commencement |  | Consistent with latest IFC drawings and marked out within specification tolerances | H |  |  | Earthworks Cut Checklist dsr reports
2.02 | Verify Machine Control | Ensure GPS plant have the correct model set up in machine and that a datum is available for checking |  | IFC drawings |  | Survey/visual | Daily |  | Consistency with datums | W |  |  | Plant Pre Starts
2.03 | Assess Crest detail | Confirm stabilsation requirements |  | IFC drawings |  | Hand augers/ slope assess | Prior to Excavation |  | Consistency with latest IFC Construction Drawings | H | H |  | Earthworks Cut Checklist dsr reports
2.04 | Install crest detail - Soil Nailing | Soil Nailing |  | IFC drawings |  | Visual Inspection | Prior to cutting rock slope |  | Designer to confirm extents of soil nailing | H | H |  | Sub Contractor QA Records
| Install crest detail - Erosion Matting | Erosion Matting |  | IFC drawings |  | Visual Inspection | Prior to cutting rock slope |  | Desgner to confirm extents of erosion matting | H | W |  | Sub Contractor QA Records
2.05 | Cut Face inspection | Cut Face inspection |  | MMA-DES-GEO-E1-SPC-3859 And latest IFC drawings |  | Survey check by construction team, visual inspection by designer. | 100m2 or maximum 5m vertical cut |  | Surveyor to confirm cut slope profile is within specification tolerances. | H |  |  | Earthworks Cut Checklist, Survey record, As-built
2.06 |  | Cut face material verification - Geo mapping |  | MMA-DES-GEO-E1-SPC-3859 And latest IFC drawings |  | Geo inspection and face mapping | At soil-rock interface, each Each 100m2 or maximum 5m vertical cut |  | Designer to confim ground conditions are in accordance with design. If not confirm remedial works required. | H | H |  | Earthworks Cut Checklist dsr reports, And face map from geotechnical engineer/geologist
2.07 | Install Rock Drape | Set out drape anchorages |  | MMA-DES-GEO-E1-SPC-9349 And latest IFC drawings |  | Geo walk over | Prior to drilling |  | All cuts greater than 20m in height, where detailed on latest IFC drawings or as instructed by Geotechnical Engineer / Geologist | H | H |  | Sub Contractor QA Records
2.08 |  | Install anchors |  | MMA-DES-GEO-E1-SPC-9349 And latest IFC drawings |  | Drill and grout records. Stressing records. | During construction and at end |  | Undertake one investigation test at each cut site. Acceptance test 20% of production anchorages. | H | H |  | Sub Contractor QA Records. Calibration certificates for stressing equipment.
2.09 |  | Install Drapes |  | MMA-DES-GEO-E1-SPC-9349 And latest IFC drawings |  | Visual inspection | During construction and at end |  | Geobrugg TECCO Product manual | H | H |  | Sub Contractor QA Records
2.1 | Install Rock Bolts | Install Rock Bolts |  | MMA-DES-GEO-E1-SPC-9349 And latest IFC drawings |  | Drill and grout records. Stressing records. | During construction and at end |  | Undertake one investigation test at each cut site. Acceptance test 20% of production anchorages. | H | H |  | Sub Contractor QA Records. Calibration certificates for stressing equipment.
2.11 | Catch Ditch Inspection | Construction of catch ditch |  | MMA-DES-GEO-E1-SPC-3859 And latest IFC drawings |  | Visual inspection | During construction and at end |  | Catch ditch to be consitent with IFC drawings | W | H |  | EarthworksCut Checklist
3.0 Post Construction
3.01 | Rock Fall Test | Rock fall trial and ARL assessment of draped and undraped rock cuts to confirm the design intent has been achieved |  | MMA-DES-GEO-E1-MEM-10095 |  | Visual inspection | After catch ditch is formed at each rock cutting site |  | ARL 4 to 5 should be achieved | H | H |  | Designer assessment Memo
3.02 | Survey As-builts | Survey As-builts |  | MMA-DES-GEO-E1-SPC-3859 |  | Survey As-built | During construction and at end |  | Ensure all features and buried items are captured. | H |  |  | Digital file
3.03 | Monitoring Data | Ensure all monitoring data has been collected and reviewed |  | MMA-DES-GEO-E1-SPC-3859 MMA-DES-GEO-E1-SPC-9349 |  | Visual inspection and review of monitoring data review. | End of construction |  | Monitoring data confirms satisfactory performance of cutting and drape system. | H | H |  | Digital file
3.04 | Red Line Mark Ups | As-builts |  | MMA-DES-GEO-E1-SPC-3859 |  | Red Pen Mark up | End of construction |  | All variances captured | H | W |  | Red Pen mark ups