## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-029
[11 empty] | Revision : 001 | Date : 21/04/2022
Client: |  | MRPA |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Fencing |  | Name: Martin Syawish |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Job No: |  |  |  | Specifications:
|  |  |  | Structure / Component: Fencing |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : 20/04/2022 |  | Date : 20/04/2022 |  |  | Date : 20/04/2022
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | •Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Check Materials |  | Prior to commencing any activity | •Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of this specification 707 and drawings. | Fencing Plan | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Confirm Footings position |  | Prior to commencing any activity | •Confirm footings are set out to locations specified on design drawings | Fencing Plan | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.2 | Post Installation |  | Each Lot | •Timber and concrete posts shall be set in dug or drilled holes •Posts shall be set solidly and any space left around the posts shall be backfilled and the backfilling compacted. • Concrete Shall be 20MPA strength grade complying with the requirements of AS 1379/1991 | 704.04 (a) AS1379 SD3161 Fencing Plan | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Strainer Assembelies |  | Each Lot | •Strainer assemblies shall be provided at all ends, angles, abrupt changes of grade, and intersections of cross fences as shown on the drawings. Intermediate strainer assemblies shall be provided on straights at intervals not exceeding 200 m, and spaced to the best advantage in the circumstances. | 704.04 (a) | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.5 | Strainer Assembelies |  | Each Lot | •Plain wires shall be reeved through holes drilled in the posts except that where treated round posts are used wires may be attached with staples after straining. The length of staples shall be 50 mm for pine posts and 40 mm for hardwood posts. Barbed wire shall be secured with galvanized tie wire of not less than 2.5 mm diameter passed through holes bored in the posts, and twisted to the barbed wire on each side of the post, or shall be stapled to treated posts with staples. | 704.04 (a) | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
3 | Completion
3.1 | Clean up |  | Post Completion | •Personnel to ensure all chainwire is tied off and that work areas are clean and free of excess materials | Fencing Plan | Verify | This ITP signed off | SCP | Project Engineer /Surveyor | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.