## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-01-028 - Chainwire Fence Installation | [5 empty] | ITP-01-028 - Chainwire Fence Installation
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is:
label | • PSP, EMP, TMP, JSEA, SWMS & WP
label | – – – – – – – – –
label | REFERENCE DOCUMENTS:
label | • PSP
label | • EMP
label | • TMP
label | • JSEA
label | • SWMS
label | • WP
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual Inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.3 Check Materials
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Unless specified otherwise, all fencing materials and products shall be supplied by the Contractor and shall be of the dimensions, manufacture, quality and structural grade in accordance with the requirements of this specification 707 and drawings.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Fencing Plan
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 1.4 Confirm Footings position
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Confirm footings are set out to locations specified on design drawings
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Fencing Plan
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Footing Installation
label | FREQUENCY: Prior to post installation
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Concrete shall be of minimum strength N20
label | • Concrete footing shall be 600mm x 300mm for intermediate posts
label | • Concrete footing shall be 900mm x 300mm for end panel posts
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Fencing Plan SD3131
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.2 Post Installation
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Posts shall be set in concrete footings of the dimensions shown on the drawings
label | • Posts shall be Installed to concrete surface in culvert area with baseplate and bolt assembly
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 704.04 (d) AS1554 Fencing Plan
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.3 Grout Installation
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Footing surface shall be cleaned and roughened before application
label | • Non shrink dry pack grout shall be placed under base plate where applicable in culvert area and footpath areas
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: AS1554
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
checkpoint | 2.4 Chainwire mesh fence
label | FREQUENCY: Each Lot
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • End, corner and gate posts shall be braced as shown on the drawings.
label | • Line posts shall be braced as shown on the drawings at not more than 120 m intervals.
label | • Chain wire shall comply with the requirements of AS 1725.
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: 704.04 (d) AS1725
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Visual inspection
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | HP*
label | – – – – – – – – –
label | RESPONSIBILITY: Fulton Hogan Engineer
label | – – – – – – – – –
text | DATE:
section | 3 - Completion
checkpoint | 3.1 Clean up
label | FREQUENCY: Post Completion
label | – – – – – – – – –
label | ACCEPTANCE CRITERIA: Personnel to ensure all chainwire is tied off and that work areas are clean and free of excess materials
label | – – – – – – – – –
label | REFERENCE DOCUMENTS: Fencing Plan
label | – – – – – – – – –
label | INSPECTION/TEST METHOD: Verify
label | – – – – – – – – –
label | RECORD OF CONFORMITY: This ITP signed off
label | – – – – – – – – –
label | SCP
label | – – – – – – – – –
label | RESPONSIBILITY: Project Engineer/Surveyor
label | – – – – – – – – –
text | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: