## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | 4 - DEMOLITION |  |  |  |  | Yes | 4 - DEMOLITION | 12abe88a-656d-4740-8f56-214b7054966a
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | works completed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Rubbish removed
checklist-flat |  |  | checklist | 8 - FORMWORK |  |  |  |  | Yes | 8 - FORMWORK | 15e55c23-953b-4e18-b7b8-4ab640f166dc
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | works completed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 26 - TILING |  |  |  |  | Yes | 26 - TILING | 17b1a840-168f-4dcd-a36d-652a6f121e70
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | Area waterproofed as per specifications
checkpoint-status |  |  | checkpoint | Tiles laid with correct glue and grout specified
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 38 - PRELIMINARIES |  |  |  |  | Yes | 38 - PRELIMINARIES | 193bd288-b458-47c6-bb71-6ce3afb3e35d
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 29 - PAINTING |  |  |  |  | Yes | 29 - PAINTING | 1c255772-39b0-45f5-b257-b0d81b87ecc6
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 25 - APPLIANCES |  |  |  |  | Yes | 25 - APPLIANCES | 1d10bed5-92fb-4347-bca1-6aed55039148
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 19 - EXTERNAL CLADDING |  |  |  |  | Yes | 19 - EXTERNAL CLADDING | 29f842d9-b501-4374-8fe5-d20ea52a1cec
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | Weather Sarking Installed as Per Specifications
checkpoint-status |  |  | checkpoint | Cladding installed as per specification
checkpoint-status |  |  | checkpoint | Correct fixings utilised
checklist-flat |  |  | checklist | 11 - MASONRY |  |  |  |  | Yes | 11 - MASONRY | 36af30fa-f69d-47cd-9c2e-04cc79348211
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | works completed as per as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 24 - FIXTURES AND FITTINGS |  |  |  |  | Yes | 24 - FIXTURES AND FITTINGS | 37c6d967-ed11-4eb4-a8d9-58df8a44b2a2
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | Overall quality of finish |  |  |  |  | Yes | Overall quality of finish | 39be068b-9f1a-4fec-930b-987423fa0e9f
checklist-flat |  |  | checklist | 21 - DOORS AND DOOR FRAMES |  |  |  |  | Yes | 21 - DOORS AND DOOR FRAMES | 41de3ac6-f70d-4c09-8daf-a54a1156e43c
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | Hardware & Fixtures installed as per FFE schedule
checkpoint-status |  |  | checkpoint | All Hardware & Fixtures installed correctly
checkpoint-status |  |  | checkpoint | Correct Fixings Used & Applied
checklist-flat |  |  | checklist | 10 - STRUCTURAL STEEL |  |  |  |  | Yes | 10 - STRUCTURAL STEEL | 486495bd-00e0-4f14-ab12-634f789252c1
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | works completed as per specification
checkpoint-status |  |  | checkpoint | Weld joins primed with selected primer paint
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 6 - TERMITE CONTROL |  |  |  |  | Yes | 6 - TERMITE CONTROL | 4916320c-4448-482b-a846-80e468ffeb7e
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | works completed per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 35 - EXTERNAL WORKS |  |  |  |  | Yes | 35 - EXTERNAL WORKS | 531e9fc6-c633-4430-98f8-ac114f1f26d5
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 15 - FRAMING AND CARPENTRY |  |  |  |  | Yes | 15 - FRAMING AND CARPENTRY | 56e47875-daef-48ca-923b-fabfe85a7ff4
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | Timber Floor/Ceiling Joists Installation completed
checkpoint-status |  |  | checkpoint | Correct fixings used as per specifications
checkpoint-status |  |  | checkpoint | correct stud spacing incorporated as per specifications (Steel Stud)
checkpoint-status |  |  | checkpoint | correct stud spacing incorporated as per specifications (Timber frame)
checkpoint-status |  |  | checkpoint | Frames installed straight and plumb
checkpoint-status |  |  | checkpoint | Subfloor installed as per specifications
checkpoint-status |  |  | checkpoint | Correct fixings used as per specifications
checkpoint-status |  |  | checkpoint | fix (skirting and/or arches) completed as per specifications
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 13 - METALWORK |  |  |  |  | Yes | 13 - METALWORK | 5ba9ab1f-848d-446d-9d94-b13cbd6b8926
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | works completed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 7 - CONCRETE |  |  |  |  | Yes | 7 - CONCRETE | 61bece9a-5594-4121-894f-510c49fb4c8d
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | works completed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 14 - INTERNAL GLAZING |  |  |  |  | Yes | 14 - INTERNAL GLAZING | 67bf6db6-0909-4531-b69f-1c1b6a9ac9ac
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | works completed as per Australian Standards
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 9 - REINFORCING |  |  |  |  | Yes | 9 - REINFORCING | 6a174c30-6b8e-4116-8891-3a5c3f70ab0e
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | works completed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 31 - FENCE AND SCREENS |  |  |  |  | Yes | 31 - FENCE AND SCREENS | 88335215-1788-4cc4-b2e8-d092fab4acb9
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | Glazing installed as per Aus Standards |  |  |  |  | Yes | Glazing installed as per Aus Standards | a5089748-4cdd-4e8c-a7f0-8f53bd76c1fb
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | Door Fitting |  |  |  |  | Yes | Door Fitting | a71bb38f-dfd5-4f5c-bb98-87d1e561e3c6
checkpoint-status |  |  | checkpoint | Frames installed straight and Plumb
checkpoint-status |  |  | checkpoint | All Reveals Installed Correctly as Designed
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 27 - TIMBER FLOORING |  |  |  |  | Yes | 27 - TIMBER FLOORING | aac4f1ab-9558-4a1b-991e-3261da84e075
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 23 - JOINERY |  |  |  |  | Yes | 23 - JOINERY | b5fc6f4c-8b7b-4af7-ae65-8f137b12a776
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 34 - MECHANICAL SERVICES |  |  |  |  | Yes | 34 - MECHANICAL SERVICES | b6f40c47-ecf2-435b-9664-39cc2ac830b5
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 22 - RENDER |  |  |  |  | Yes | 22 - RENDER | ba09d631-afdb-43ff-9320-277875e0bbf7
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 0 - MISCELLANEOUS |  |  |  |  | Yes | 0 - MISCELLANEOUS | bfd71268-aa0b-4aa5-9adc-b8984671e40e
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 33 - ELECTRICAL SERVICES |  |  |  |  | Yes | 33 - ELECTRICAL SERVICES | caff63db-a02a-4e58-ba6b-1fff96a699aa
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 18 - ROOF AND ROOF PLUMBING |  |  |  |  | Yes | 18 - ROOF AND ROOF PLUMBING | cba4997b-6ee5-4526-b6d8-9877e52dd4d3
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | works completed as per Australian Standards
checkpoint-status |  |  | checkpoint | Cappings installed as per Specifications
checkpoint-status |  |  | checkpoint | Correct Flashings utilised as per specifications
checkpoint-status |  |  | checkpoint | Correct fixings utilised
checkpoint-status |  |  | checkpoint | Roof installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 36 - SITE MANAGEMENT |  |  |  |  | Yes | 36 - SITE MANAGEMENT | cc9916b1-bd0e-481c-8914-8935727b072e
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 32 - HYDRAULIC SERVICES |  |  |  |  | Yes | 32 - HYDRAULIC SERVICES | db34b4c6-6f7b-4a19-8623-267c3b07d5e5
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 30 - LANDSCAPING |  |  |  |  | Yes | 30 - LANDSCAPING | e18242cd-1e8d-4474-91e4-761543956aee
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 17 - CEILING LINING |  |  |  |  | Yes | 17 - CEILING LINING | e6894547-8803-43b0-b507-533a64cde158
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | tiled Ceiling grid installed as per specification
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | correct stud spacings utilised
checkpoint-status |  |  | checkpoint | Plaster Ceilings installed as per specifications
checkpoint-status |  |  | checkpoint | Ceiling frame installed as per specifications
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 16 - WALL PARTITIONS AND LININGS |  |  |  |  | Yes | 16 - WALL PARTITIONS AND LININGS | e8976b65-5824-42c5-aae0-9a8bacb73546
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | Plaster Walls installed as per specifications
checkpoint-status |  |  | checkpoint | Fire rating caulk applied to areas where required
checkpoint-status |  |  | checkpoint | insulation installed (if required) as per specifications
checkpoint-status |  |  | checkpoint | Correct fire rating caulk utilised
checkpoint-status |  |  | checkpoint | Stopping & Sanding completed
checkpoint-status |  |  | checkpoint | Plaster Walls - Overall Quality of Finish
checkpoint-status |  |  | checkpoint | Plaster Ceilings installed as per specifications
checkpoint-status |  |  | checkpoint | Set Out, Marking Stud layout & Opening etc
checkpoint-status |  |  | checkpoint | Stopping & Sanding completed
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 12 - STAIRS |  |  |  |  | Yes | 12 - STAIRS | e97bfc2a-506c-4e2b-898c-dd841e426323
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | works completed as per Australian Standards
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 28 - CARPETS |  |  |  |  | Yes | 28 - CARPETS | e9a96a45-2362-4e65-9193-c88188c761bc
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 5 - GROUNDWORKS |  |  |  |  | Yes | 5 - GROUNDWORKS | eb26991b-195a-4a75-a27f-c49d903fd322
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | Check for power lines, pipes and other hazards
checkpoint-status |  |  | checkpoint | works completed per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 37 - SCAFFOLDS AND HIRE ITEMS |  |  |  |  | Yes | 37 - SCAFFOLDS AND HIRE ITEMS | f44e4ad9-cb30-44d0-8b41-091aef439fb4
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | Correct Flashings utilised as per specifications |  |  |  |  | Yes | Correct Flashings utilised as per specifications | f8c0ca12-1cb2-4a7f-887d-a41cb3cf2482
checkpoint-status |  |  | checkpoint | Area left tidy & accessible
checkpoint-status |  |  | checkpoint | Overall quality of finish
checklist-flat |  |  | checklist | 20 - ALUMINIUM DOORS AND WINDOWS |  |  |  |  | Yes | 20 - ALUMINIUM DOORS AND WINDOWS | f8d6c70b-2acb-431c-a660-1a8fa25f035a
checkpoint-status |  |  | checkpoint | For all latest consented drawings, checked & referenced
checkpoint-status |  |  | checkpoint | installed as per specification
checkpoint-status |  |  | checkpoint | Frames installed Straight and Plumb
checkpoint-status |  |  | checkpoint | Correct fixings utilised